__export__.project_task_3440_77673cd4 | Ensure automated actions are running fine | 2021-05-31 | 2021-06-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | FALSE | 0 | 0 | 0 | 0 | 2021-06-06 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-07-19 19:00 | TRUE | Zuma Sales LLC | 57.625 | 35.5625 | 461.1646 | 284.5718 | 2021-05-31 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-04-23 21:51 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-06-17 18:25 | 4346 | 0 | 0 | 0 | 0 | Normal | Sprint 2123
__export__.project_task_3306_342d2769 | Job Position: Interview Survey | 2021-04-12 | 2021-04-18 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 1.92 | 1.92 | 0.08 | 96 |  | 1 | Complete | TRUE | Muhammad Saqlain Alam | 2021-04-07 01:57 | TRUE | EquityTeam | 0 | 8 | 0 | 64 | 2021-04-12 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2021-04-07 01:57 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>What do we do with "Stage/Survey" table that is on the main section? Maybe a "Tab" called interviews?</p><p><br></p><p>Create a tab on Job Position form called "Interviews"</p><p>move the "Interview Survey Dictionary" to the created "Interviews" tab from the main section</p><p>move the "Interview Form" under the "Recruitment" tab to the created "Interviews" tab.</p> | 2021-04-18 00:39 | 4750 | 2 | 0 | 0 | 0 | Normal | Sprint 2116
__export__.project_task_2136_d8561483 | FW: You have been assigned to Edits to Recruitment Module (#45): Recruiter Signature | 2021-01-25 | 2021-01-31 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 5.17 | 5.17 | -3.17 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-06 01:49 | TRUE | EquityTeam | 0 | 40.75 | 0 | 326.0492 | 2021-01-25 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2021-01-06 01:49 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>Request Recruiters Signature - named recruiter- show at the bottom of all email templates that are sent out to a candidate. </span><br></p> | 2021-03-03 20:03 | 6934 | 2 | 0 | 0 | 0 | Normal | Sprint 2105
__export__.project_task_2100_4ab7af62 | Security Audits:For all team in pakistan office | 2021-01-04 | 2021-01-10 | Configuration | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 1.33 | 1.33 | -1.33 | 0 |  | FALSE | Complete | TRUE | FALSE | 2021-01-04 18:20 | FALSE | Silverdale Technology LLC | 0 | 7.8125 | 0 | 62.6035 | 2021-01-04 | Complete | Muhammad Zubair | InProgress | FALSE |  | Kaleem Khan | 2021-01-04 18:20 | Silverdale Technology LLC, Nick Foy | Executive / Mechanisms | Silverdale Technology LLC | <p>For the security audits, everyone in this task is requested to follow the steps after each 90 days .</p><p><br></p><p>1.Change the GitHub account password.</p><p>2.Change odoo passwords.</p><p>3.Change Email passwords.</p><p>4.Change Last Pass passwords.</p> | 2021-01-14 15:56 | 6966 | 0 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_2031_a5932fef | invoice template for line items with no prices | 2020-12-28 | 2021-01-03 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Muzher Siddique | 2.17 | 2.17 | 0.83 | 72.33 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-23 06:41 | TRUE | Mid-America Gardens, LLC | 0 | 15.5 | 0 | 124 | 2020-12-28 | Complete | Naseeb Razaq | Done | FALSE |  | Levi Barnes | 2020-12-23 06:41 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>create an invoice template that doesn't have prices on lined items.</p> | 2021-01-13 17:51 | 7265 | 3 | 0 | 0 | 0 | Normal | Sprint 2053
__export__.project_task_2007_5129259a | Review 3rd Party Apps: scheduled activity |  |  | Development | PWX: Help (P23) | Levi Barnes | FALSE | 0.67 | 0.67 | -0.17 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-21 20:49 | TRUE | EquityTeam | 0 | 7.125 | 0 | 57.1905 |  | Complete | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2020-12-21 20:49 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | FALSE | <p>Please review this module and estimate how much time it would take to develop this module: <span style="color: rgb(0, 0, 0); font-family: inherit; font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;">https://apps.odoo.com/apps/modules/14.0/schedule_activity_app/</span></p> | 2020-12-30 22:19 | 7299 | 0.5 | 0 | 0 | 0 | Normal
__export__.project_task_1239_1b58e67c | Import of Product Master List | 2020-09-21 | 2020-09-27 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-18 00:54 | FALSE | Continuant | 0 | 13 | 0 | 104 | 2020-09-21 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-09-18 00:54 | Continuant | FALSE | FALSE | <p>Test and provide instructions on how to import the product master list GFK provided in order to populate the manufacturer part number for all of the matching Continuant Products. </p> | 2020-10-07 03:08 | 9575 | 0 | 0 | 0 | 0 | Normal | Sprint 32
__export__.project_task_1185_3fe676d8 | Distributor API: Order Confirmation | 2020-09-07 | 2020-09-13 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-08 21:55 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-09-07 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-09-08 21:55 | Continuant | FALSE | FALSE | <p>This task was created at the request of Anusha to track distributor API issues we run into during testing, especially regarding order confirmation. </p> |  | 9794 | 0 | 0 | 0 | 0 | Normal | Sprint 30
__export__.project_task_1148_14c17300 | GFK Integration: Create GFK Manufacturer Name and Manufacturer ID table | 2020-08-31 | 2020-09-06 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-27 03:02 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-31 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-27 03:02 | Continuant | FALSE | FALSE | <p>In Odoo there needs to be a table that has a list of GFK manufacturer names and its corresponding manufacturer ID. This will be used along with the manufacturer part number to get the GFK product ID. </p> |  | 10101 | 0 | 0 | 0 | 0 | Normal | Sprint 29
__export__.project_task_823_bf4026fb | Select city iOS-Implementation | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_243_16d0c493 | Email for APP Maven | 2020-08-24 | 2020-08-30 | Development | Silverdale: Help (P12) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-07 21:13 | FALSE | Silverdale Technology LLC | 0 | 0 | 0 | 0 | 2020-08-24 | Complete | Muhammad Zubair | InProgress | FALSE |  | Muhammad Afzaal | 2020-07-07 21:13 | Silverdale Technology LLC | FALSE | FALSE | <p><br></p> |  | 11307 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_4624_2de3e011 | UEDF Activation Validation Error Message | 2021-08-16 | 2021-08-22 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 1.5 | 1.5 | 0 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-17 03:17 | TRUE | Cellpoint Corporation | 0 | 8.875 | 0 | 71.146 | 2021-08-16 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Muhammad Zubair | 2021-08-17 03:17 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Current:</p><p><br></p><p>If the UEDF Activation cannot be done, it doesn't generate a file</p><p><br></p><p><br></p><p>Required: </p><p><br></p><p>If the UEDF Activation cannot be done, it shows an error that "UEDF cannot be done for some of the IMEIs since they are not in the state that required UEDF Activation."<br></p> | 2021-08-31 02:25 | 1581 | 1.5 | 0 | 0 | 0 | Normal | Sprint 2134
__export__.project_task_4606_d7a65294 | All products need to be dropship | 2021-08-23 | 2021-08-29 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 | 0.5 | 0 | 2021-08-27 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-16 23:33 | TRUE | Zuma Sales LLC | 0 | 2.625 | 0 | 21.0186 | 2021-08-23 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-16 23:33 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p> <br></p> | 2021-08-20 20:34 | 1584 | 0.5 | 0 | 0 | 0 | Normal | Sprint 2135
__export__.project_task_3439_7c355316 | Ensure backups are running correctly | 2021-05-31 | 2021-06-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | FALSE | 0 | 0 | 0 | 0 | 2021-06-06 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-07-19 19:00 | TRUE | Zuma Sales LLC | 57.625 | 35.5625 | 461.1699 | 284.6832 | 2021-05-31 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-04-23 21:50 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-06-17 18:31 | 4346 | 0 | 0 | 0 | 0 | Normal | Sprint 2123
__export__.project_task_3305_062317bf | applicant email template | 2021-04-12 | 2021-04-18 | Configuration | PWX: Help (P23) | Levi Barnes | Danish Hassan | 2.2 | 2.2 | -0.2 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-04-07 01:52 | TRUE | EquityTeam | 0 | 8 | 0 | 64 | 2021-04-12 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2021-04-07 01:52 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>modify the "Applicant: Completing App and Survey" to hyperlink to the survey specified on the "Interview Form" field under the "Recruitment" tab of the Job Position form instead of the 3rd party survey that is currently hyperlinked.</p> | 2021-04-18 00:39 | 4750 | 2 | 0 | 0 | 0 | Normal | Sprint 2116
__export__.project_task_2400_6268f29d | Brand Customer Portal | 2021-02-08 | 2021-02-14 | Development | Continuant: Quotation Management / Automation (P31) | Nick Foy | Fahad Hassan | 3.78 | 3.78 | -1.4467 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2021-02-02 04:15 | FALSE | Continuant | 7 | 28.8125 | 56 | 230.3906 | 2021-02-08 | Complete | Muhammad Zubair | Done | FALSE | External - Client | Kaesi Lee | 2021-01-22 04:05 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Triple the size of the logo on the website. (see attachment for Logo). <br></p> | 2021-03-03 20:23 | 6548 | 2.3333 | 0 | 0 | 0 | Normal | Sprint 2108
__export__.project_task_2102_68c96422 | Security Audits:For all server related credentials | 2021-01-04 | 2021-01-10 | Configuration | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 0.5 | 0.5 | -0.5 | 0 |  | FALSE | Complete | TRUE | FALSE | 2021-01-04 18:21 | FALSE | Silverdale Technology LLC | 0 | 6.9375 | 0 | 55.6425 | 2021-01-04 | Complete | Muhammad Zubair | InProgress | FALSE |  | Kaleem Khan | 2021-01-04 18:21 | Silverdale Technology LLC, Nick Foy | Executive / Mechanisms | Silverdale Technology LLC | <p><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>For the security audits, everyone in this task is requested to follow the steps after each 90 days.</span><br><br></p><p>1.Change or Remove all ssh keys from GitHub.</p><p>2.Change all server passwords,(silverdale AWS password).</p><p>3.Change password for each client , like propertyworx@silverdaletech.com.</p><p>4.Change github security key.</p> | 2021-01-13 17:01 | 6966 | 0 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_1843_a917a5c2 | create survey buttons for meeting | 2020-12-28 | 2021-01-03 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 16 | 16 | 0 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-09 06:23 | TRUE | EquityTeam | 0 | 25.5 | 0 | 204 | 2020-12-28 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2020-12-09 06:23 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | The content of this cell is too long for an XLSX file (more than 32767 characters). Please use the CSV format for this export. | 2021-01-13 17:51 | 7602 | 16 | 0 | 0 | 0 | Normal | Sprint 2053
__export__.project_task_1797_4ea75634 | New Field for Lost Opportunity | 2021-01-25 | 2021-01-31 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 4.25 | 4.25 | -1.25 | 100 |  | FALSE | Complete | TRUE | FALSE | 2020-12-05 06:05 | FALSE | Cellpoint Corporation | 0 | 62.75 | 0 | 502.0425 | 2021-01-25 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Nick Foy | 2020-12-05 06:05 | Cellpoint Corporation | FALSE | FALSE | <p><font style="background-color: rgb(0, 255, 255);">On Auctions, create a new field for "Lost Opportunity" (calculation is Bid limit - Current Bid).</font></p><p><font style="background-color: rgb(0, 255, 255);"><br></font></p><p><font style="background-color: rgb(206, 231, 247);">The requirements were not clear. Its max-bid - current bid.<br></font><br></p> | 2021-03-03 20:03 | 7698 | 3 | 0 | 0 | 0 | Normal | Sprint 2105
__export__.project_task_1689_8fd1e984 | Set-Up Odoo Instance | 2020-11-30 | 2020-12-06 | Configuration | Mid-America: Odoo Implementation (P37) | Muhammad Afzaal | Muzher Siddique | 0.67 | 0.67 | 0.83 | 44.67 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-01 22:16 | TRUE | Mid-America Gardens, LLC | 0 | 1 | 0 | 8 | 2020-11-30 | Complete | Naseeb Razaq | Done | FALSE |  | Nick Foy | 2020-12-01 22:16 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <ol start="1" type="1"> <li class="gmail-m-1562986806393967776gmail-m5106383716250064975gmail-m-5940481973993785613msolistparagraph">Website<p></p></li> <li class="gmail-m-1562986806393967776gmail-m5106383716250064975gmail-m-5940481973993785613msolistparagraph">Email Marketing<p></p></li> <li class="gmail-m-1562986806393967776gmail-m5106383716250064975gmail-m-5940481973993785613msolistparagraph">eCommerce<p></p></li> <li class="gmail-m-1562986806393967776gmail-m5106383716250064975gmail-m-5940481973993785613msolistparagraph">Sales<p></p></li> <li class="gmail-m-1562986806393967776gmail-m5106383716250064975gmail-m-5940481973993785613msolistparagraph">Invoicing<p></p></li> <li class="gmail-m-1562986806393967776gmail-m5106383716250064975gmail-m-5940481973993785613msolistparagraph">Inventory<p></p></li> <li class="gmail-m-1562986806393967776gmail-m5106383716250064975gmail-m-5940481973993785613msolistparagraph">Studio<p></p></li> </ol> | 2020-12-02 22:41 | 7778 | 1.5 | 0 | 0 | 0 | Normal | Sprint 2049
__export__.project_task_1209_34e7a0bd | Update Order Successfully Placed Page | 2020-09-14 | 2020-09-20 | Bug Fix | Continuant: eCommerce (P9) | Gadha Continuant | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-14 21:37 | FALSE | Continuant | 0 | 7 | 0 | 55.9475 | 2020-09-14 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-09-14 21:37 | Continuant | FALSE | FALSE | <p>At the end of the checkout process, after the user has clicked send quotation, the splash page displays "Order Succesfuly Placed. Thank You." Please change this text to Quotation sent successfully. Thank you." (See attached image for further info). </p> | 2020-09-23 21:34 | 9650 | 0 | 0 | 0 | 0 | Normal | Sprint 31
__export__.project_task_1142_badb4364 | Loading Graphic for Get Availability | 2020-09-07 | 2020-09-13 | Development | Continuant: eCommerce (P9) | Gadha Continuant | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-27 01:39 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-09-07 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-27 01:39 | Continuant | FALSE | FALSE | <p>After pressing "Get Availability" on the product details page, there should be a loading graphic that indicates the site is working. </p><p>Also, if you click the get availability button twice, it displays duplicate tables, it should not display two duplicate tables. </p> |  | 10102 | 0 | 0 | 0 | 0 | Normal | Sprint 30
__export__.project_task_837_7ae427b6 | Forcefully update iOS-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_169_c20ab084 | Error when creating a new User | 2020-08-17 | 2020-08-23 | Bug Fix | Heronswood: Events (P3) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 | 2020-05-27 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-05-26 05:44 | FALSE | Port Gamble S’Klallam Foundation | 0 | 0 | 0 | 0 | 2020-08-17 | Complete | Naseeb Razaq | Done | FALSE |  | Nick Foy | 2020-05-26 05:44 | Port Gamble S’Klallam Foundation, Ross Bayton | Executive / Delivery / Alpha | FALSE | <p>When trying to create a new User</p><p><br></p><p>Error:</p><p><br></p><p>Error:</p><p>Odoo Server Error</p><p><br></p><p>Traceback (most recent call last):</p><p> File "/home/odoo/src/odoo/13.0/odoo/http.py", line 624, in _handle_exception</p><p> return super(JsonRequest, self)._handle_exception(exception)</p><p> File "/home/odoo/src/odoo/13.0/odoo/http.py", line 310, in _handle_exception</p><p> raise pycompat.reraise(type(exception), exception, sys.exc_info()[2])</p><p> File "/home/odoo/src/odoo/13.0/odoo/tools/pycompat.py", line 14, in reraise</p><p> raise value</p><p> File "/home/odoo/src/odoo/13.0/odoo/http.py", line 669, in dispatch</p><p> result = self._call_function(**self.params)</p><p> File "/home/odoo/src/odoo/13.0/odoo/http.py", line 350, in _call_function</p><p> return checked_call(self.db, *args, **kwargs)</p><p> File "/home/odoo/src/odoo/13.0/odoo/service/model.py", line 94, in wrapper</p><p> return f(dbname, *args, **kwargs)</p><p> File "/home/odoo/src/odoo/13.0/odoo/http.py", line 339, in checked_call</p><p> result = self.endpoint(*a, **kw)</p><p> File "/home/odoo/src/odoo/13.0/odoo/http.py", line 915, in __call__</p><p> return self.method(*args, **kw)</p><p> File "/home/odoo/src/odoo/13.0/odoo/http.py", line 515, in response_wrap</p><p> response = f(*args, **kw)</p><p> File "/home/odoo/src/odoo/13.0/addons/web/controllers/main.py", line 1322, in call_kw</p><p> return self._call_kw(model, method, args, kwargs)</p><p> File "/home/odoo/src/odoo/13.0/addons/web/controllers/main.py", line 1314, in _call_kw</p><p> return call_kw(request.env[model], method, args, kwargs)</p><p> File "/home/odoo/src/odoo/13.0/odoo/api.py", line 383, in call_kw</p><p> result = _call_kw_model(method, model, args, kwargs)</p><p> File "/home/odoo/src/odoo/13.0/odoo/api.py", line 356, in _call_kw_model</p><p> result = method(recs, *args, **kwargs)</p><p> File "/home/odoo/src/odoo/13.0/addons/auth_signup/models/res_users.py", line 228, in web_create_users</p><p> res = super(ResUsers, self).web_create_users(list(new_emails))</p><p> File "/home/odoo/src/odoo/13.0/addons/base_setup/models/res_users.py", line 23, in web_create_users</p><p> user = self.with_context(signup_valid=True).create(default_values)</p><p> File "&lt;decorator-gen-133&gt;", line 2, in create</p><p> File "/home/odoo/src/odoo/13.0/odoo/api.py", line 314, in _model_create_single</p><p> return create(self, arg)</p><p> File "/home/odoo/src/custom/trial/saas_trial/models/res_users.py", line 97, in create</p><p> res = super(ResUsers, self).create(values)</p><p> File "&lt;decorator-gen-93&gt;", line 2, in create</p><p> File "/home/odoo/src/odoo/13.0/odoo/api.py", line 314, in _model_create_single</p><p> return create(self, arg)</p><p> File "/home/odoo/src/odoo/13.0/addons/auth_signup/models/res_users.py", line 236, in create</p><p> user = super(ResUsers, self).create(values)</p><p> File "&lt;decorator-gen-109&gt;", line 2, in create</p><p> File "/home/odoo/src/odoo/13.0/odoo/api.py", line 314, in _model_create_single</p><p> return create(self, arg)</p><p> File "/home/odoo/src/odoo/13.0/addons/mail/models/res_users.py", line 89, in create</p><p> user = super(Users, self).create(values)</p><p> File "&lt;decorator-gen-90&gt;", line 2, in create</p><p> File "/home/odoo/src/odoo/13.0/odoo/api.py", line 314, in _model_create_single</p><p> return create(self, arg)</p><p> File "/home/odoo/src/odoo/13.0/odoo/addons/base/models/res_users.py", line 1219, in create</p><p> user = super(UsersView, self).create(values)</p><p> File "&lt;decorator-gen-88&gt;", line 2, in create</p><p> File "/home/odoo/src/odoo/13.0/odoo/api.py", line 335, in _model_create_multi</p><p> return create(self, [arg])</p><p> File "/home/odoo/src/odoo/13.0/odoo/addons/base/models/res_users.py", line 996, in create</p><p> return super(UsersImplied, self).create(vals_list)</p><p> File "&lt;decorator-gen-83&gt;", line 2, in create</p><p> File "/home/odoo/src/odoo/13.0/odoo/api.py", line 336, in _model_create_multi</p><p> return create(self, arg)</p><p> File "/home/odoo/src/odoo/13.0/odoo/addons/base/models/res_users.py", line 474, in create</p><p> users = super(Users, self).create(vals_list)</p><p> File "&lt;decorator-gen-3&gt;", line 2, in create</p><p> File "/home/odoo/src/odoo/13.0/odoo/api.py", line 336, in _model_create_multi</p><p> return create(self, arg)</p><p> File "/home/odoo/src/odoo/13.0/odoo/models.py", line 3686, in create</p><p> vals = self._add_missing_default_values(vals)</p><p> File "/home/odoo/src/odoo/13.0/odoo/models.py", line 1747, in _add_missing_default_values</p><p> defaults = self.default_get(list(missing_defaults))</p><p> File "/home/odoo/src/odoo/13.0/odoo/addons/base/models/res_users.py", line 1280, in default_get</p><p> values = super(UsersView, self).default_get(fields1)</p><p> File "/home/odoo/src/odoo/13.0/odoo/models.py", line 1196, in default_get</p><p> ir_defaults = self.env['ir.default'].get_model_defaults(self._name)</p><p> File "&lt;decorator-gen-42&gt;", line 2, in get_model_defaults</p><p> File "/home/odoo/src/odoo/13.0/odoo/tools/cache.py", line 90, in lookup</p><p> value = d[key] = self.method(*args, **kwargs)</p><p> File "/home/odoo/src/odoo/13.0/odoo/addons/base/models/ir_default.py", line 150, in get_model_defaults</p><p> result[row[0]] = json.loads(row[1])</p><p> File "/usr/lib/python3.6/json/__init__.py", line 354, in loads</p><p> return _default_decoder.decode(s)</p><p> File "/usr/lib/python3.6/json/decoder.py", line 339, in decode</p><p> obj, end = self.raw_decode(s, idx=_w(s, 0).end())</p><p> File "/usr/lib/python3.6/json/decoder.py", line 357, in raw_decode</p><p> raise JSONDecodeError("Expecting value", s, err.value) from None</p><p>json.decoder.JSONDecodeError: Expecting value: line 1 column 1 (char 0)</p> |  | 12330 | 0 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_4622_eba52a19 | Phone Check Import Issue | 2021-08-23 | 2021-08-29 | Bug Fix | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 18.08 | 18.08 | 3.92 | 82.18 |  | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-17 03:09 | TRUE | Cellpoint Corporation | 0 | 9.9375 | 0 | 79.2784 | 2021-08-23 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Muhammad Zubair | 2021-08-17 03:09 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Current: </p><p><br></p><ol><li><p>We tried importing Phone Check file with an IMEI that was on the list but the combination data for <span style="color: rgb(0, 0, 0); font-family: inherit; font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;">Model, Reg Model, Memory, Color, Sim Technology did not match with any existing product. It imported the file but did not add the done quantity in stock.move.line. Also marked the IMEI as received.</span><br></p></li><li><p>When importing with proper combination of <span style="color: rgb(0, 0, 0); font-family: inherit; font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;">Model, Reg Model, Memory, Color, Sim Technology that was for an IMEI that wasn't created: System threw an error that values do not match.</span></p></li><li><p>When importing with proper combination of <span style="color: rgb(0, 0, 0); font-family: inherit; font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;">Model, Reg Model, Memory, Color, Sim Technology that was for an IMEI that was created but different product was matching with the combination: the IMEI did not update to the product that matched the combo of </span><span style="color: rgb(0, 0, 0); font-family: inherit; font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;">Model, Reg Model, Memory, Color, Sim Technology</span></p></li></ol><p><br></p><p>Required:</p><p><br></p><ol><li><p>Importing Phone Check file with invalid info such as if the combination of Model, Reg Model, Memory, Color, Sim Technology does not match in the system, it should show an error and not import the file.</p></li><li><p>Show proper reference of values that do not match with the combination of the phone check data for <span style="color: rgb(0, 0, 0); font-family: inherit; font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;">Model, Reg Model, Memory, Color, Sim Technology. Error should show which values do not match.</span><br></p></li><li><p>When doing the import for Phone Check, if the IMEI doesn't exist and the values for <span style="color: rgb(0, 0, 0); font-family: inherit; font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;">Model, Reg Model, Memory, Color, Sim Technology match with a Product then</span> create the IMEI with that product and add it on the Stock Move, Stock Move Line. Add IMEI Exception State as Overage and update the PO with that product with Quantity based on the number of IMEIs for that product</p></li><li><p>When doing the import for Phone Check, if the IMEI exists and the values for <span style="font-family: inherit; font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit; color: rgb(0, 0, 0);">Model, Reg Model, Memory, Color, Sim Technology match with a different Product then update the Product on IMEI and update the stock move, Stock Move Line with that product.</span><br></p></li></ol> | 2021-09-01 02:25 | 1581 | 22 | 0 | 0 | 0 | Normal | Sprint 2135
__export__.project_task_4605_e1040bd1 | Training for quotation template | 2021-08-23 | 2021-08-29 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0.5 | 0.5 | 0 | 100 | 2021-08-27 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-16 23:32 | TRUE | Zuma Sales LLC | 0 | 5.5625 | 0 | 44.4623 | 2021-08-23 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-16 23:32 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p> <br></p> | 2021-08-25 17:43 | 1585 | 0.5 | 0 | 0 | 0 | Normal | Sprint 2135
__export__.project_task_3438_6e18e39e | Backup the production environment | 2021-05-31 | 2021-06-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | FALSE | 0 | 0 | 0 | 0 | 2021-06-06 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-07-19 19:00 | TRUE | Zuma Sales LLC | 57.625 | 35.5625 | 461.1779 | 284.7026 | 2021-05-31 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-04-23 21:50 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-06-17 18:32 | 4346 | 0 | 0 | 0 | 0 | Normal | Sprint 2123
__export__.project_task_3304_a8aa7baa | Deployment 06/04/2021 | 2021-04-12 | 2021-04-18 | Configuration | Heronswood: Help (P54) OLD DO NOT USE | Jeff Gross | Wajahat Ali | 0.5 | 0.5 | -0.5 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-04-06 22:50 | TRUE | Port Gamble S’Klallam Foundation | 0 | 8 | 0 | 64 | 2021-04-12 | Complete | Naseeb Razaq | In Warranty | TRUE |  | Wajahat Ali | 2021-04-06 22:50 | Port Gamble S’Klallam Foundation, Ross Bayton | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>Tasks:<br>3238</p> | 2021-04-18 00:39 | 4753 | 0 | 0 | 0 | 0 | Normal | Sprint 2116
__export__.project_task_2610_586b67f7 | General 2104 | 2021-01-25 | 2021-01-31 | Configuration | Mid-America: Odoo Implementation (P37) | Levi Barnes | Levi Barnes | 3 | 3 | -3 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-28 05:11 | TRUE | Mid-America Gardens, LLC | 0 | 2.875 | 0 | 23.1286 | 2021-01-25 | Complete | Naseeb Razaq | Done | FALSE |  | Levi Barnes | 2021-01-28 05:11 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><br></p> | 2021-02-01 21:08 | 6403 | 0 | 0 | 0 | 0 | Normal | Sprint 2105
__export__.project_task_2425_36c8b697 | customer_payment_option unit testing | 2021-02-01 | 2021-02-07 | Development | Continuant: Unit Testing (P51) | Nick Foy | Danish Hassan | 4.92 | 4.92 | -0.92 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2021-02-02 04:15 | FALSE | Continuant | 5 | 26.8125 | 40 | 214.3303 | 2021-02-01 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2021-01-26 04:38 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><br></p> | 2021-03-03 20:20 | 6451 | 4 | 0 | 0 | 0 | Normal | Sprint 2107
__export__.project_task_2367_5698c61b | Internal: Project UX Review: product categories | 2021-01-25 | 2021-01-31 | Development | Dialed Supply: Help (P21) | Levi Barnes | Raheel Aslam | 1.75 | 1.75 | 0.083333 | 95.45 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-19 00:36 | FALSE | Dialed Supply | 0 | 31.75 | 0 | 254.0403 | 2021-01-25 | Complete | Muhammad Zubair | Done | FALSE |  | Levi Barnes | 2021-01-19 00:36 | Dialed Supply, Michael Isaac | FALSE | Silverdale Technology LLC | The content of this cell is too long for an XLSX file (more than 32767 characters). Please use the CSV format for this export. | 2021-03-03 20:02 | 6623 | 1.8333 | 0 | 0 | 0 | Normal | Sprint 2105
__export__.project_task_2101_a68a0b61 | Security Audits:For the USA team | 2021-01-04 | 2021-01-10 | Configuration | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2021-01-04 18:21 | FALSE | Silverdale Technology LLC | 0 | 6.9375 | 0 | 55.595 | 2021-01-04 | Complete | Muhammad Zubair | InProgress | FALSE |  | Kaleem Khan | 2021-01-04 18:21 | Silverdale Technology LLC, Nick Foy | Executive / Mechanisms | Silverdale Technology LLC | <p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>For the security audits, everyone in this task is requested to follow the steps after each 90 days .</p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><br></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>1.Change the GitHub account password.</p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>2.Change odoo passwords.</p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>3.Change Email passwords.</p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>4.Change Last Pass passwords.</p> | 2021-01-13 16:57 | 6966 | 0 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_1784_6fc9c50f | Make Column Headers Sticky in Lot Views | 2020-12-07 | 2020-12-13 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Fahad Hassan | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-12-05 05:45 | FALSE | Cellpoint Corporation | 0 | 12.8125 | 0 | 102.5861 | 2020-12-07 | Complete | Farman Ahmad Cheema | InProgress | FALSE | Internal | Nick Foy | 2020-12-05 05:45 | Cellpoint Corporation | FALSE | Silverdale Technology LLC | <p>On admin portal, sticky column headers?</p><p><br></p><p>See 1795</p> | 2020-12-23 20:35 | 7698 | 0 | 0 | 0 | 0 | Normal | Sprint 2050
__export__.project_task_1646_4237863e | web editor error | 2020-12-07 | 2020-12-13 | Development | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 2.58 | 2.58 | 1.42 | 64.5 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-11-24 21:47 | TRUE | EquityTeam | 0 | 20.8125 | 0 | 166.7977 | 2020-12-07 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2020-11-24 21:47 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p class="MsoNormal"><span style="font-size:12.0pt">Uncaught TypeError: Cannot read property 'recordUndo' of undefined<br> <br> <a href="https://pwxusa.odoo.com/web/content/8541-9fa7e57/5/web_editor.assets_wysiwyg.js:456">https://pwxusa.odoo.com/web/content/8541-9fa7e57/5/web_editor.assets_wysiwyg.js:456</a><br> Traceback:<br> TypeError: Cannot read property 'recordUndo' of undefined<br> at LinkDialog.eventHandler.modules.linkDialog.showLinkDialog (<a href="https://pwxusa.odoo.com/web/content/8541-9fa7e57/5/web_editor.assets_wysiwyg.js:456:1121">https://pwxusa.odoo.com/web/content/8541-9fa7e57/5/web_editor.assets_wysiwyg.js:456:1121</a>)<br> at LinkDialog.show (<a href="https://pwxusa.odoo.com/web/content/5160-9b91b05/5/web_editor.assets_summernote.js:302:1023">https://pwxusa.odoo.com/web/content/5160-9b91b05/5/web_editor.assets_summernote.js:302:1023</a>)<br> at HTMLDivElement.showLinkDialog (<a href="https://pwxusa.odoo.com/web/content/5160-9b91b05/5/web_editor.assets_summernote.js:384:918">https://pwxusa.odoo.com/web/content/5160-9b91b05/5/web_editor.assets_summernote.js:384:918</a>)<br> at HTMLDivElement.hToolbarAndPopoverClick (<a href="https://pwxusa.odoo.com/web/content/5160-9b91b05/5/web_editor.assets_summernote.js:392:346">https://pwxusa.odoo.com/web/content/5160-9b91b05/5/web_editor.assets_summernote.js:392:346</a>)<br> at HTMLDivElement.dispatch (<a href="https://pwxusa.odoo.com/web/content/8537-022be46/5/web.assets_common_lazy.js:1613:447">https://pwxusa.odoo.com/web/content/8537-022be46/5/web.assets_common_lazy.js:1613:447</a>)<br> at HTMLDivElement.elemData.handle (<a href="https://pwxusa.odoo.com/web/content/8537-022be46/5/web.assets_common_lazy.js:1599:166">https://pwxusa.odoo.com/web/content/8537-022be46/5/web.assets_common_lazy.js:1599:166</a>)</span><br><br></p><p class="MsoNormal">------------------------------------------------</p><p class="MsoNormal"><br></p><p>Hello,<br> <br> The issue should be solved on your database.<br> <br> The issue was caused by one of the snippet (or "Custom Block") called "Equity Team Badges". For some reasons that I wasn't able to determine yet, it was containing a part of code that was confusing the code that was read when creating links. <br> <br> If you have any information that you think can be useful as of how this snippet was created, please let me know. There is probably a bug somewhere in the code which did introduced the "wrong code" and I would like to prevent the issue to happen in the long term.<br> <br> Sorry for the inconvenience,<br> Kind regards,<p></p></p><p><span style="font-size:10.0pt">____<p></p></span></p><p><span style="font-size:10.0pt">Loan<p></p></span></p><p class="MsoNormal"> </p><p><i><span style="font-size:10.0pt">Investigation Developer (Technical Support)</span></i><span style="font-size:10.0pt"><p></p></span></p><p></p><p></p> | 2020-12-23 20:35 | 7946 | 4 | 0 | 0 | 0 | Normal | Sprint 2050
__export__.project_task_1606_c54cb3e5 | Create an AV Project Pick List | 2020-11-16 | 2020-11-22 | Development | Continuant: AV Warehouse (P34) | Kaesi Lee | Danish Hassan | 12.08 | 12.08 | -4.08 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-11-17 02:55 | FALSE | Continuant | 1 | 13.625 | 8 | 108.8033 | 2020-11-16 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-11-14 04:46 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Each AV Project can have multiple Rooms where Items need to be installed. It's important that the right Items are picked for the right Project but also that they are packed into a identifiable cartons so they can be placed in the right room on the Customer premises.</p><p><br></p><p>Requirements:</p><p><br></p><ol><li><p>In AV Tracker, create a new table for "Pick Lists" - pick lists will be specific for a Project and Room</p><ol><li><p>Fields:</p><ol><li><p>Pick List ID (Number sequence starting "AVP10000001" and increment by 1</p></li><li><p>Project (Many2One from AV Tracker Projects</p></li><li><p>Room (list of Rooms in the AV Tracker: Rooms table, restricted to show only those from the Project selected in #2)</p></li><li><p>Items (list of Items in the AV Tracker: Items table, restricted to show only those from the Project selected in #2)</p><ol><li><p><font style="background-color: rgb(255, 255, 0);">When creating a pick list, the client needs to be able to select multiple items and these items should display as a list with the product name and the item ID. The visible items should be restricted to the items that are assigned to that project. Next to each item should be a check box so the client can select multiple items to add to a pick list at once. </font><br></p></li></ol></li><li><p>Pick Date Time (default to Today but User selectable to another date time)</p></li><li><p>Pick List State: <span style="text-align: inherit;"><font style="background-color: rgb(255, 255, 0);">Stages of Picklist should be the stages of the out delivery order (as a related field).</font></span></p></li><li><p>Outbound Delivery Order (the order created in #2 below)</p></li></ol></li><li><p>Create an Action Button for "Send to Pick"</p><ol><li><p>This will create an Outbound Delivery Order</p></li><li><p>The items will be populated in the Delivery Order from 1.4 above</p></li><li><p>Pick date time will be populated from 1.5 above</p></li><li><p>Populate the field in 1.7 above</p></li><li><p>Move the status of the Pick List to "Planned"</p></li><li><p><font style="background-color: rgb(255, 255, 0);">Default warehouse on the pick list to the warehouse in the product location</font></p></li><li><p><font style="background-color: rgb(255, 255, 0);">Partner ID should be populated by the parter in the related project</font></p></li></ol></li></ol></li></ol> | 2020-12-03 18:48 | 8203 | 8 | 0 | 0 | 0 | Normal | Sprint 2047
__export__.project_task_1139_e10d0769 | Billing And Shipping: Select Client Delivery Address | 2020-08-24 | 2020-08-30 | Development | Continuant: eCommerce (P9) | Gadha Continuant | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-26 19:59 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-24 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-26 19:59 | Continuant | FALSE | FALSE | <p>When you are in the shopping cart and you click process checkout, on the confirm order page it will display two addresses, the billing and the shipping. The shipping address defaults to the address of the person logged in when it should default to the contact's shipping address. See attached for an image of the correct info displayed. </p> |  | 10108 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_822_484c359b | Select state iOS-Implementation | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_4604_1593ace4 | Customer reference show in top fields in SO | 2021-08-23 | 2021-08-29 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Aleem khan | 2.75 | 2.75 | 0.25 | 91.67 | 2021-08-27 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-16 23:31 | TRUE | Zuma Sales LLC | 0 | 13.25 | 0 | 105.8988 | 2021-08-23 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-16 23:31 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p> Customer reference show in top fields in Sales Order<br></p> | 2021-09-04 02:25 | 1585 | 3 | 0 | 0 | 0 | Normal | Sprint 2135
__export__.project_task_4451_945ae340 | FW: rearrange job web page paragraphs | 2021-08-16 | 2021-08-22 | Development | PWX: Help (P23) | Farman Ahmad Cheema | Danish Hassan | 0 | 0 | 0 | 0 | 2021-08-24 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-06 17:16 | TRUE | EquityTeam | 0 | 15.6875 | 0 | 125.4244 | 2021-08-16 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Naseeb Razaq | 2021-08-06 17:16 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-08-31 02:25 | 1831 | 0 | 0 | 0 | 0 | Normal | Sprint 2134
__export__.project_task_3302_a144f87b | Stop to proceed negative quantity in POS | 2021-04-12 | 2021-04-18 | Development | DO NOT USE (old MMH: Help (P83)) | Jeff Gross | Muhammad Bilal | 8.08 | 8.08 | -1.08 | 100 |  | 4 | Complete | TRUE | Muhammad Saqlain Alam | 2021-04-06 19:18 | TRUE | Mountain Meadow Herbs | 0 | 8.3125 | 7.8014e-06 | 66.692 | 2021-04-12 | Complete | Naseeb Razaq | Done | FALSE |  | Naseeb Razaq | 2021-04-06 19:18 | Mountain Meadow Herbs, Gerry Carton | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; white-space: pre-wrap;'>In Point of sales there is already a feature for restriction of negative quantities, but in a new scenario its not useful. Find the attached video for clarification, its showing multiple orders for a single item, its getting done with negative quantities, while it should stop when proceeding further order when the quantity gets negative.</span><br></p><p><br></p><p>-------------Ticket#1172---------</p><p><br></p> | 2021-04-18 00:39 | 4757 | 7 | 0 | 0 | 0 | Normal | Sprint 2116
__export__.project_task_2373_e7101177 | Deployment 2102 Mid America Gardens | 2021-01-18 | 2021-01-24 | Configuration | Mid-America: Odoo Implementation (P37) | Levi Barnes | Muzher Siddique | 0.67 | 0.67 | 1.33 | 33.5 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-19 16:38 | TRUE | Mid-America Gardens, LLC | 0 | 0.875 | 0 | 6.8116 | 2021-01-18 | Complete | Naseeb Razaq | Done | FALSE |  | Muzher Siddique | 2021-01-19 16:38 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Deployed 1957, 2104</p> | 2021-01-20 15:27 | 6607 | 2 | 0 | 0 | 0 | Normal | Sprint 2104
__export__.project_task_2362_5650870c | Internal: Project UX Review: Add corn job to update products | 2021-01-25 | 2021-01-31 | Development | Dialed Supply: Help (P21) | Levi Barnes | Danish Hassan | 4.17 | 4.17 | -1.17 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-19 00:30 | FALSE | Dialed Supply | 0 | 31.75 | 0 | 254.0386 | 2021-01-25 | Complete | Muhammad Zubair | Done | FALSE |  | Levi Barnes | 2021-01-19 00:30 | Dialed Supply, Michael Isaac | FALSE | Silverdale Technology LLC | The content of this cell is too long for an XLSX file (more than 32767 characters). Please use the CSV format for this export. | 2021-03-03 20:02 | 6624 | 3 | 0 | 0 | 0 | Normal | Sprint 2105
__export__.project_task_1665_5d21dd95 | Quality | 2021-01-04 | 2021-01-10 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Nick Foy | 0.5 | 0.5 | 0.5 | 50 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-11-26 02:03 | TRUE | Wild Leaf Beverage | 0 | 28 | 0 | 224 | 2021-01-04 | Complete | Abdul Hameed | In Warranty | FALSE |  | Kaesi Lee | 2020-11-26 02:03 | Wild Leaf Beverage, Thomas Walker_ | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>Configure Quality Odoo Module on Wild Leaf. </p> | 2021-01-04 22:50 | 7918 | 1 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_1611_ccdcd202 | Mybids: Not showing time remaining order | 2020-11-23 | 2020-11-29 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 2.5 | 2.5 | -2.5 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-11-17 21:09 | FALSE | Cellpoint Corporation | 0 | 14.125 | 0 | 112.8577 | 2020-11-23 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Nick Foy | 2020-11-17 21:09 | Cellpoint Corporation | FALSE | Apps Maven | <p><br></p> | 2020-12-08 05:42 | 8115 | 0 | 0 | 0 | 0 | Normal | Sprint 2048
__export__.project_task_1601_3fc4712f | Google Calendar sync | 2020-11-30 | 2020-12-06 | Configuration | PWX: Help (P23) | Levi Barnes | Danish Hassan | 6.5 | 3.5 | -3.5 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-11-13 20:30 | TRUE | EquityTeam | 0 | 17.1875 | 0 | 137.3903 | 2020-11-30 | Complete | Farman Ahmad Cheema | Done | FALSE | Internal | Nick Foy | 2020-11-13 20:30 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | FALSE | <p><br></p> | 2020-12-08 21:53 | 8212 | 3 | 0 | 0 | 0 | Normal | Sprint 2049
__export__.project_task_1522_c9e2c6e5 | Import Parts List to Product Master |  |  | Development | Continuant: Quotation Management / Automation (P31) | Kaesi Lee | FALSE | 35.25 | 0 | -35.25 | 0 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-10-31 03:42 | FALSE | Continuant | 0 | 27 | 0 | 215.9039 |  | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-10-31 03:42 | Continuant, Allison Beers | Executive / Delivery / Bravo | FALSE | <p><br></p> | 2020-12-08 21:54 | 8540 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_1212_a3a6f6d7 | Sales Order Form View: Button Linking PO | 2020-09-14 | 2020-09-20 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-15 00:06 | FALSE | Continuant | 0 | 6.9375 | 0 | 55.5678 | 2020-09-14 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-09-15 00:06 | Continuant | FALSE | FALSE | <p>On the Sales Order form view add a button that links the matching purchase order. (see attached). </p> | 2020-09-23 21:34 | 9648 | 0 | 0 | 0 | 0 | Normal | Sprint 31
__export__.project_task_1162_57add2b8 | Product Form Page: Make Description for Vendors Read Only | 2020-08-31 | 2020-09-06 | Development | Continuant: eCommerce (P9) | Gadha Continuant | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-29 01:54 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-31 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-29 01:54 | Continuant | FALSE | FALSE | <p>When description for vendors has been populated by GFK it should be read only. </p> |  | 10054 | 0 | 0 | 0 | 0 | Normal | Sprint 29
__export__.project_task_542_7c31f09f | API:Select City | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:45 | FALSE | Cellpoint Corporation | 1.375 | 0 | 10.7572 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p>method: GET</p><p>Description: User has to send city in type parameter in to get city list, and in the value, parameter user has to send the state id</p><p>parameter: Type, value </p><p>API will Fetch the city data from the database table (res.city) with the condition (state_id=value)</p><p>append city.id, city.name,city.state_id.id into json </p><p>Retrive the Json Data</p><p><br></p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_4603_ca201244 | Delivery address should be visible in footer of page | 2021-08-23 | 2021-08-29 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Aleem khan | 3.42 | 3.42 | 0.08 | 97.71 | 2021-08-27 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-16 23:30 | TRUE | Zuma Sales LLC | 0 | 13.25 | 0 | 105.9118 | 2021-08-23 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-16 23:30 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p> <br></p> | 2021-09-04 02:25 | 1585 | 3.5 | 0 | 0 | 0 | Normal | Sprint 2135
__export__.project_task_4363_90b927d9 | Scan each item in Odoo Receiving and Phone Check Option | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Kaleem Khan | 10.67 | 10.67 | -0.0033333 | 100 | 2021-08-12 | 2 | Complete | TRUE | Fahad Hassan | 2021-07-27 01:28 | TRUE | Cellpoint Corporation | 0 | 24.5625 | 0 | 196.5684 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-07-27 01:28 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><font style="color: rgb(0, 0, 0);">1. There should be a dropdown option on the Transfer form 'Scan Serial' or 'Import Phone Check' </font></p><p><font style="color: rgb(0, 0, 0);">2. When Scan Serial is selected, the scanning screen should appear (</font><span style="color: rgb(0, 0, 0); font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;">Note: A screenshot is attached for reference for Scan screen)</span></p><p><font style="color: rgb(0, 0, 0);">3. Then the IMEI's of each Serial will be scanned.</font></p><p><font style="color: rgb(0, 0, 0);">4. The system should check if the record of that IMEI is there or not, </font></p><p><font style="color: rgb(0, 0, 0);">5. After verification of Each Serial scan, the status of those particular serials should be changed from Inbound to Received. </font></p><p><font style="color: rgb(0, 0, 0);">6. If the Serial (IMEI) does not exist in system then generate an exception.</font></p><p><font style="color: rgb(0, 0, 0);">7. If Import Phone Check is selected in step 1</font></p><p><font style="color: rgb(0, 0, 0);">8. Import Phone Check button should be displayed (</font><a href="/web#id=4360&amp;model=project.task&amp;view_type=form&amp;cids=1&amp;menu_id=295">Task for Functionality of Import Phone Check Button</a><font style="color: rgb(0, 0, 0);">)</font></p><p><br></p><p><br></p> | 2021-08-31 21:03 | 2087 | 10.6667 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3300_c42c75f3 | Deployment Wildleaf (06-04-21) | 2021-04-12 | 2021-04-18 | Other | Wild Leaf: Labeling (P60) | Jeff Gross | Wajahat Ali | 7.35 | 7.35 | -7.35 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-04-06 16:41 | FALSE | Wild Leaf Beverage | 0 | 8.5625 | 0 | 68.313 | 2021-04-12 | Complete | Muhammad Zubair | Done | FALSE |  | Muzher Siddique | 2021-04-06 16:41 | Wild Leaf Beverage, Matt Gladd | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>T3285(TH1055)</p><p>T3279</p><p>3280</p><p>3281</p><p>3282</p><p><span style='color: rgb(5, 38, 76); font-family: -apple-system, BlinkMacSystemFont, "Segoe UI", Helvetica, Arial, sans-serif, "Apple Color Emoji", "Segoe UI Emoji"; font-size: 18px; font-weight: 600; background-color: rgb(241, 248, 255);'>T3283</span><br><span style='color: rgb(5, 38, 76); font-family: -apple-system, BlinkMacSystemFont, "Segoe UI", Helvetica, Arial, sans-serif, "Apple Color Emoji", "Segoe UI Emoji"; font-size: 18px; font-weight: 600; background-color: rgb(241, 248, 255);'>3282</span><br></p> | 2021-04-18 00:39 | 4759 | 0 | 0 | 0 | 0 | Normal | Sprint 2116
__export__.project_task_2433_503de673 | invoice_portal_details unit testing | 2021-02-01 | 2021-02-07 | Development | Continuant: Unit Testing (P51) | Nick Foy | Kaleem Khan | 4.08 | 4.08 | -1.08 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2021-02-02 04:15 | FALSE | Continuant | 5 | 26.8125 | 40 | 214.3292 | 2021-02-01 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2021-01-26 04:43 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><br></p> | 2021-03-03 20:20 | 6451 | 3 | 0 | 0 | 0 | Normal | Sprint 2107
__export__.project_task_2363_e15e443d | Internal: Project UX Review: add related product id to api output | 2021-01-25 | 2021-01-31 | Development | Dialed Supply: Help (P21) | Levi Barnes | Raheel Aslam | 1.92 | 1.92 | -0.42 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-19 00:32 | FALSE | Dialed Supply | 0 | 31.75 | 0 | 254.0367 | 2021-01-25 | Complete | Muhammad Zubair | Done | FALSE |  | Levi Barnes | 2021-01-19 00:32 | Dialed Supply, Michael Isaac | FALSE | Silverdale Technology LLC | The content of this cell is too long for an XLSX file (more than 32767 characters). Please use the CSV format for this export. | 2021-03-03 20:02 | 6624 | 1.5 | 0 | 0 | 0 | Normal | Sprint 2105
__export__.project_task_2320_18282377 | shipping receive by | 2021-02-01 | 2021-02-07 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Kaleem Khan | 13.42 | 9.92 | -6.92 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-14 21:25 | TRUE | Mid-America Gardens, LLC | 0 | 33.875 | 0 | 270.9027 | 2021-02-01 | Complete | Naseeb Razaq | Done | FALSE |  | Levi Barnes | 2021-01-14 21:25 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | The content of this cell is too long for an XLSX file (more than 32767 characters). Please use the CSV format for this export. | 2021-03-03 20:19 | 6723 | 6.5 | 0 | 0 | 0 | Normal | Sprint 2107
__export__.project_task_2221_9b6aa25e | P1: cpbids.com/marketplace for Belmont not loading | 2021-01-04 | 2021-01-10 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 9.33 | 9.33 | -9.33 | 0 |  | FALSE | Complete | TRUE | FALSE | 2021-01-09 05:55 | FALSE | Cellpoint Corporation | 0 | 5 | 0 | 40 | 2021-01-04 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Nick Foy | 2021-01-09 05:55 | Cellpoint Corporation | FALSE | Silverdale Technology LLC | The content of this cell is too long for an XLSX file (more than 32767 characters). Please use the CSV format for this export. | 2021-01-17 01:08 | 6858 | 0 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_1510_1717a1f2 | User Roles Module | 2020-11-02 | 2020-11-08 | Configuration | PWX: Help (P23) | Levi Barnes | FALSE | 0.25 | 0.25 | -0.25 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-11-03 21:25 | TRUE | EquityTeam | 1.9375 | 6 | 15.4203 | 48 | 2020-11-02 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Nick Foy | 2020-10-30 22:45 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | FALSE | <p>As an odoo admin, PropertyWorx wants to set up the 3rd party module User Roles (<a href="https://apps.odoo.com/apps/modules/13.0/base_user_role/">link</a>) to extend the standard functionality regarding users and groups management. </p><p><br></p><p>Research the features of User Roles 3rd Party Module to support PropertyWorx on using User Roles' new features when setting up their users and groups in Odoo. </p><p><br></p><p><br></p><p><br></p><p><br></p> | 2020-11-09 22:44 | 8545 | 0 | 0 | 0 | 0 | Normal | Sprint 2045
__export__.project_task_1395_19044382 | Auto Update for iOS | 2020-10-12 | 2020-10-18 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-10-09 22:08 | FALSE | Cellpoint Corporation | 0 | 2 | 0 | 16 | 2020-10-12 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Muhammad Afzaal | 2020-10-09 22:08 | Cellpoint Corporation | FALSE | Deerom Technologies Pvt. Ltd. | <p><br></p> | 2020-10-13 23:11 | 9050 | 0 | 0 | 0 | 0 | Normal | Sprint 2042
__export__.project_task_1163_36f544dc | Sales Quotation: Order Type and Quote Type | 2020-08-31 | 2020-09-06 | Development | Continuant: eCommerce (P9) | Gadha Continuant | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-29 04:08 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-31 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-29 04:08 | Continuant | FALSE | FALSE | <p>A sales quotation that was created through the eCommerce module should have a default order type of Website Sale and a quote type of New</p> |  | 10052 | 0 | 0 | 0 | 0 | Normal | Sprint 29
__export__.project_task_1121_2e4eba3c | Synnex: Order Shipment and Tracking | 2020-09-14 | 2020-09-20 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-17 00:58 | FALSE | Continuant | 22 | 26 | 176 | 208 | 2020-09-14 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-18 01:45 | Continuant | FALSE | FALSE | <p>Use the distributor API to order shipment and obtain tracking information. </p> | 2020-09-23 01:23 | 10318 | 0 | 0 | 0 | 0 | Normal | Sprint 31
__export__.project_task_1035_919ef66b | Match Column fields with Completed Auctions | 2020-08-24 | 2020-08-30 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-28 13:51 | FALSE | Cellpoint Corporation | 11.125 | 0 | 88.8483 | 0 | 2020-08-24 | Complete | Muhammad Afzaal | Done | FALSE |  | Kaesi Lee | 2020-08-13 02:56 | Cellpoint Corporation | FALSE | FALSE | <p>View All Auctions, Match Columns with Completed Auctions</p> |  | 10437 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_4602_e4e2bf3f | Expiration date default to 7 days | 2021-08-23 | 2021-08-29 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 1.33 | 1.33 | 0.67 | 66.5 | 2021-08-27 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-16 23:30 | TRUE | Zuma Sales LLC | 0 | 10.25 | 0 | 81.9254 | 2021-08-23 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-16 23:30 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>Expiration date default to 7 days in Purchase<br></p> | 2021-09-01 02:25 | 1585 | 2 | 0 | 0 | 0 | Normal | Sprint 2135
__export__.project_task_4455_ad6c3b83 | Pallet Scanning on Delivery Order | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 5.92 | 5.92 | 1.08 | 84.57 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-06 18:36 | TRUE | Cellpoint Corporation | 0 | 15.6875 | 0 | 125.4244 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Muhammad Zubair | 2021-08-06 18:36 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Pallet Scanning will be dependent on Operation Type</p><p><br></p><p>On (Pallet), only package for package type without parent can be scanned on the first field</p><p><br></p><p>on field (package scanning), only packages for parent type with parent assigned that is (true) </p><p>..</p><p>as the pallet package will be scanned. </p><p><br></p><p>Only allow package scanning for packages that have the same product as the delivery order</p><p><br></p><p>Only allow package scanning upto the point where combined package quantity is not greater than the Delivery Order Demand</p><p><br></p><p>Only Allow number of packages that are allowed in First Field Package &gt; Package Type</p><p><br></p><p>When scanning done, assign parent package on sub-packages form.</p> | 2021-08-31 02:25 | 1829 | 7 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3289_99fabaeb | If the product is having zero price, then the substitute column automatically fills with a gift in the sales quotation. | 2021-04-05 | 2021-04-11 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Danish Hassan | 3.18 | 3.18 | -0.68 | 100 |  | 1 | Complete | TRUE | Muhammad Saqlain Alam | 2021-04-01 19:24 | TRUE | Mid-America Gardens, LLC | 0 | 11.3125 | 2.0976e-05 | 90.5992 | 2021-04-05 | Complete | Naseeb Razaq | Done | FALSE |  | Fahad Hussain Malik | 2021-04-01 19:24 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><font><span style="white-space: pre-wrap;">If the product is having zero price, then the substitute column automatically fills with a gift in the sales quotation.</span></font><br></p> | 2021-04-18 00:35 | 4877 | 2.5 | 0 | 0 | 0 | Normal | Sprint 2115
__export__.project_task_2360_703e6095 | Internal: Project UX Review:api security group | 2021-01-25 | 2021-01-31 | Development | Dialed Supply: Help (P21) | Levi Barnes | Danish Hassan | 2.92 | 2.92 | -0.42 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-19 00:14 | FALSE | Dialed Supply | 0 | 31.75 | 0 | 254.0364 | 2021-01-25 | Complete | Muhammad Zubair | Done | FALSE |  | Levi Barnes | 2021-01-19 00:14 | Dialed Supply, Michael Isaac | FALSE | Silverdale Technology LLC | <p>Add "Products Api" security group and restrict access to api products configuration and importing to this group.</p><p><br></p><p><br></p> | 2021-03-03 20:02 | 6624 | 2.5 | 0 | 0 | 0 | Normal | Sprint 2105
__export__.project_task_2009_10381c79 | Review 3rd Party Apps:oi base |  |  | Development | PWX: Help (P23) | Levi Barnes | FALSE | 0.67 | 0.67 | -0.17 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-21 20:52 | TRUE | EquityTeam | 0 | 7.125 | 0 | 57.1321 |  | Complete | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2020-12-21 20:52 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | FALSE | <p>Please review this module and estimate how much time it would take to develop this module:<br></p><p><br></p><p>https://apps.odoo.com/apps/modules/14.0/oi_base/</p> | 2020-12-30 22:19 | 7299 | 0.5 | 0 | 0 | 0 | Normal
__export__.project_task_1690_77ee14d7 | Set-Up Github | 2020-11-30 | 2020-12-06 | Configuration | Mid-America: Odoo Implementation (P37) | Muhammad Afzaal | Muzher Siddique | 0.17 | 0.17 | 0.83 | 17 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-01 22:16 | TRUE | Mid-America Gardens, LLC | 0 | 1 | 0 | 8 | 2020-11-30 | Complete | Naseeb Razaq | Done | FALSE |  | Nick Foy | 2020-12-01 22:16 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><br></p> | 2020-12-02 22:51 | 7778 | 1 | 0 | 0 | 0 | Normal | Sprint 2049
__export__.project_task_1562_d8caec4c | Procurement | 2021-01-04 | 2021-01-10 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | FALSE | 7 | 7 | 0 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-11-07 00:14 | TRUE | Wild Leaf Beverage | 0 | 41 | 0 | 328 | 2021-01-04 | Complete | Abdul Hameed | In Warranty | FALSE |  | Kaesi Lee | 2020-11-07 00:14 | Wild Leaf Beverage, Thomas Walker_ | Executive / Delivery / Alpha | FALSE | <p><br></p> | 2021-01-04 22:51 | 8376 | 7 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_1545_18eee67c | Customer Invoice Portal: Set Up Customer Access | 2020-11-23 | 2020-11-29 | Development | Continuant: Customer Portal AR (P32) | Kaesi Lee | Fahad Hassan | 13.92 | 13.92 | -3.0033 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-11-05 02:53 | FALSE | Continuant | 0 | 23 | 0 | 184 | 2020-11-23 | Complete | Muhammad Zubair | Done | FALSE | Internal | Kaesi Lee | 2020-11-05 02:53 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Create a process for providing a customer access to the customer invoice portal. </p><p><br></p><p>This should be done using standard Odoo, creating a user by granting portal access to a contact. This contact will create their own password and they'll be able to log in and view their invoices. </p><p><br><font style="background-color: rgb(255, 255, 0);">Remove the accept and accept and pay email template, no longer required. </font></p> | 2020-12-08 05:42 | 8421 | 10.9167 | 0 | 0 | 0 | Normal | Sprint 2048
__export__.project_task_1293_7a525aac | Only accept lower case email addresses | 2020-11-02 | 2020-11-08 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-10-08 10:48 | FALSE | Cellpoint Corporation | 8 | 36 | 64 | 288 | 2020-11-02 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Nick Foy | 2020-09-27 21:33 | Cellpoint Corporation | FALSE | Deerom Technologies Pvt. Ltd. | <p>When a new user is self-registering or when being created by an admin, only accept email addresses with lowercase letters.</p> | 2020-11-17 05:03 | 9338 | 0 | 0 | 0 | 0 | Normal | Sprint 2045
__export__.project_task_1140_0cb11cb4 | GFK Integration: Use Correct Vendors for Catalog Data | 2020-08-31 | 2020-09-06 | Development | Continuant: eCommerce (P9) | Gadha Continuant | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-26 20:09 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-31 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-26 20:09 | Continuant | FALSE | FALSE | <p>Import Tech data vendor SKU from GFK into the vendor "Tech Data"</p><p>Import Synnex vendor SKU from GFK into vendor "<span style="color: rgb(33, 37, 41); font-family: Roboto, Noto; font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;">Synnex Corporation" </span><br>Import Ingram vendor SKU from GFK into vendor "<span style="color: rgb(33, 37, 41); font-family: Roboto, Noto; font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;">Ingram Micro Inc"</span><br><br></p><p>These vendors should already exist in Odoo. </p> |  | 10108 | 0 | 0 | 0 | 0 | Normal | Sprint 29
__export__.project_task_927_03c63d15 | API:Auction detail:Postman | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-29 12:27 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-29 12:27 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10788 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_350_c8db2160 | Production Release #7 | 2020-09-07 | 2020-09-13 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0 | 0 | 0.00032117 | 0 | 2020-09-07 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE |  |  | 11092 | 0 | 0 | 0 | 0 | Normal | Sprint 30
__export__.project_task_4600_9b5a819b | Default Immediate Payment in Sales | 2021-08-23 | 2021-08-29 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Raheel Aslam | 0.42 | 0.42 | -0.17 | 100 | 2021-08-27 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-16 23:29 | TRUE | Zuma Sales LLC | 0 | 3.5625 | 0.012978 | 28.5246 | 2021-08-23 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-16 23:29 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-08-23 14:03 | 1585 | 0.25 | 0 | 0 | 0 | Normal | Sprint 2135
__export__.project_task_4449_98b08d73 | Remove Fields | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 2.5 | 2.5 | 0 | 100 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-06 16:56 | TRUE | Cellpoint Corporation | 0 | 11.6875 | 0 | 93.4233 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Muhammad Zubair | 2021-08-06 16:56 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>On Product: </p><p><br></p><p>SW Version</p><p>HW Version</p><p>Variant</p><p><br></p> | 2021-08-25 02:25 | 1831 | 2.5 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3434_f860a636 | Import Customer/Vendors data | 2021-06-21 | 2021-06-27 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | FALSE | 0 | 0 | 0 | 0 | 2021-07-06 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-07-19 18:59 | TRUE | Zuma Sales LLC | 57.6875 | 42.0625 | 461.2565 | 336.2654 | 2021-06-21 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-04-23 21:44 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-06-26 00:59 | 4346 | 0 | 0 | 0 | 0 | Normal | Sprint 2126
__export__.project_task_3280_fb765de4 | Under the pallet build menu, make all the fields non-mandatory. | 2021-04-05 | 2021-04-11 | Development | Wild Leaf: Help (P22) | Jeff Gross | Fahad Hassan | 1.25 | 1.25 | -0.41667 | 100 |  | 1 | Complete | TRUE | Muhammad Saqlain Alam | 2021-04-01 15:18 | TRUE | Wild Leaf Beverage | 0 | 11.6875 | 0 | 93.6945 | 2021-04-05 | Complete | Abdul Hameed | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-04-01 15:18 | Wild Leaf Beverage, Thomas Walker_ | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>In the partner form, under the pallet build menu, make all the fields non-mandatory. <br></p> | 2021-04-18 00:35 | 4881 | 0.83333 | 0 | 0 | 0 | Normal | Sprint 2115
__export__.project_task_2298_9c03e872 | Client walkthrough and feedback session | 2021-01-18 | 2021-01-24 | Configuration | Mid-America: Odoo Implementation (P37) | Levi Barnes | Levi Barnes | 3.25 | 3.25 | 0 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-13 18:56 | TRUE | Mid-America Gardens, LLC | 0 | 8.375 | 0 | 67.0708 | 2021-01-18 | Complete | Naseeb Razaq | Done | FALSE |  | Nick Foy | 2021-01-13 18:56 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Agenda:</p><p><br></p><ul><li><p>Customer journey (website, browse, view, pictures, details, prices, add to cart, log-in, check-out, /my)</p></li></ul><ul><li><p>View, adding, edit products</p></li><li><p>View, add, edit customers</p></li><li><p>View, add, edit sales orders</p></li><li><p>View and process deliveries</p></li></ul><p><span style="text-align: inherit;"><br></span><span style="color: rgb(0, 0, 0); font-family: inherit; font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;"><br></span></p> | 2021-01-25 22:39 | 6749 | 3.25 | 0 | 0 | 0 | Normal | Sprint 2104
__export__.project_task_2125_816e591c | Microsoft account | 2021-01-04 | 2021-01-10 | Configuration | Silverdale: Help (P12) | Muhammad Afzaal | Nick Foy | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2021-01-05 23:51 | FALSE | Silverdale Technology LLC | 0 | 2.625 | 0 | 21.195 | 2021-01-04 | Complete | Muhammad Zubair | InProgress | FALSE |  | Muhammad Afzaal | 2021-01-05 23:50 | Silverdale Technology LLC, Nick Foy | Executive / Mechanisms | Silverdale Technology LLC | <p>We need 2 Microsoft accounts for MS Team meetings </p><p>Email names could go with following names</p><p><br></p><p>HQ-PAK </p><p>NOC-PAK</p><p><br></p> | 2021-01-08 19:12 | 6936 | 0 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_1868_27481932 | Review 3rd Party Apps | 2020-12-21 | 2020-12-27 | Configuration | PWX: Help (P23) | Levi Barnes | FALSE | 5.51 | 0 | -5.51 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-15 04:41 | TRUE | EquityTeam | 0.0625 | 16.6875 | 0.26423 | 133.082 | 2020-12-21 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Nick Foy | 2020-12-14 21:44 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><span style="color: rgb(0, 0, 0); font-family: inherit; font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;"><br></span></p> | 2021-01-06 18:49 | 7466 | 0 | 0 | 0 | 0 | Normal | Sprint 2052
__export__.project_task_1213_66dec83b | Bug: Synnex: Obtaining Order Confirmation | 2020-09-14 | 2020-09-20 | Bug Fix | Continuant: eCommerce (P9) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-17 00:58 | FALSE | Continuant | 2 | 0 | 16 | 0 | 2020-09-14 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-09-15 00:11 | Continuant | FALSE | FALSE | <p>In Continuant's dev environment, they are seeing an issue obtaining an order confirmation from Synnex. Vendor reference is blank and distributor status is not confirmed.</p> |  | 9648 | 0 | 0 | 0 | 0 | Normal | Sprint 31
__export__.project_task_1208_446299a6 | Tech Data: Order Shipment and Tracking | 2020-09-21 | 2020-09-27 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-17 00:58 | FALSE | Continuant | 2.3125 | 15 | 18.473 | 119.7636 | 2020-09-21 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-09-14 19:32 | Continuant | FALSE | FALSE | <p><br></p> | 2020-10-05 19:17 | 9653 | 0 | 0 | 0 | 0 | Normal | Sprint 32
__export__.project_task_1149_4ce870d6 | OEM field: a search field with drop down menu | 2020-08-24 | 2020-08-30 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-27 03:07 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-24 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-27 03:07 | Continuant | FALSE | FALSE | <p>The OEM field should be a search field with a drop down menu to select the manufacturer name. This list should be identical to the list of manufacturers from GFK (you can get a list of manufacturers using the getmanufacturer request). </p><p><br></p><p> </p> |  | 10101 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_1123_2e802f8a | Ingram Micro: Order Shipment and Tracking | 2020-09-14 | 2020-09-20 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-17 00:58 | FALSE | Continuant | 22 | 27 | 176 | 216 | 2020-09-14 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-18 01:47 | Continuant | FALSE | FALSE | <div class="o_form_sheet_bg"><div class="clearfix position-relative o_form_sheet" style="width: 720px;"><div class="o_notebook"><div class="tab-content"><div class="tab-pane active" id="notebook_page_7144"><div class="oe_form_field oe_form_field_html o_field_widget" name="description" style="margin-bottom: 5px;"><div class="o_readonly"><p>Use the distributor API to order shipment and obtain tracking information. </p></div></div><div class="oe_clear"></div></div></div></div></div></div><aside class="o_chatter oe_chatter" style="-webkit-box-flex: 0; flex: 1000 0 auto; width: 720px; margin-right: auto; margin-left: auto; padding: 8px 0px; max-width: 720px; height: auto;"><div class="o_chatter_topbar" style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><div class="o_topbar_right_area"><div class="o_followers btn-group o_field_widget" name="message_follower_ids" style="margin-bottom: initial;"><div class="o_followers_title_box btn-group"></div><div class="o_followers_actions btn-group"></div></div><div><span class="o_chatter_attachment_button_count"><br></span></div></div></div><div class="o_mail_activity o_field_widget" name="activity_ids" style='text-align: left; margin-bottom: 5px; font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'></div><div class="o_mail_thread" style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><div class="o_mail_thread_content"></div></div></aside> | 2020-09-24 00:42 | 10318 | 0 | 0 | 0 | 0 | Normal | Sprint 31
__export__.project_task_885_77c9f680 | Place a bid Android-Implementation | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 2 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_4588_897bb90d | Share the data format | 2021-08-30 | 2021-09-05 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 2.5 | 2.5 | -1 | 100 | 2021-09-03 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-13 19:12 | TRUE | Zuma Sales LLC | 0 | 13.1875 | 0 | 105.3956 | 2021-08-30 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-13 19:12 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-09-02 21:24 | 1661 | 1.5 | 0 | 0 | 0 | Normal | Sprint 2136
__export__.project_task_4394_6a2da223 | Add validation that device is ready to be shipped | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 4.67 | 4.67 | 3.33 | 58.38 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-07-29 23:48 | TRUE | Cellpoint Corporation | 0 | 21.1875 | 0 | 169.6167 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-07-29 23:48 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><font class="text-black">Validations to add: </font></p><p><font class="text-black"><br></font></p><p><font class="text-black">1. On IMEI Print label</font></p><p><font class="text-black"> a) Check NMS Status (Value of status to add) </font></p><p><font class="text-black"> b) Check UEDF Status </font><br></p><p><font class="text-black">2. In Package when adding IMEI in package, check for following validations: </font></p><ol><li><p><font class="text-black">Serial NMS Status should be 0, if not, UEDF Processing Status should be processed</font></p></li><li><p><font class="text-black" color="#000000">Financial Eligibility Date should not be in the future</font></p></li><li><p><font class="text-black" color="#000000">Serial State should be Received </font></p></li></ol><p><br></p><p><br></p> | 2021-08-31 02:25 | 2016 | 8 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3272_ebd58e74 | Purchases on Item not showing the details | 2021-04-05 | 2021-04-11 | Development | DO NOT USE (old MMH: Help (P83)) | Jeff Gross | Raheel Aslam | 2.5 | 2.5 | 1 | 71.43 | 2021-04-02 | 1 | Complete | TRUE | Muhammad Saqlain Alam | 2021-03-30 22:22 | TRUE | Mountain Meadow Herbs | 0 | 13 | 0 | 104 | 2021-04-05 | Complete | Naseeb Razaq | Done | FALSE |  | Naseeb Razaq | 2021-03-30 22:22 | Mountain Meadow Herbs, Gerry Carton | Executive / Delivery / Alpha | Silverdale Technology LLC | <div>H1110<br>2) Purchases lines would click through to the PO. Now they do not open anything.</div><div><br></div><div><img src="https://www.silverdaletech.com/web/image/20330?access_token=1ca4b5ed-91f4-4764-9f2d-9fd003a6ca20" style="max-width: 100%; height: auto; width: 600px;"></div><div><br></div><div><img src="https://www.silverdaletech.com/web/image/20331?access_token=91fdf405-edf9-42fe-a235-6edb625cb158" style="max-width: 100%; height: auto; width: 600px;"></div><div><br></div><div>Looking at the Toggle, you would think it would have to open, because "Disable opening" is not checked.</div><div><img src="https://www.silverdaletech.com/web/image/20332?access_token=4fc70e06-eb1a-497a-8d4a-8df291049b62" style="max-width: 100%; height: auto; width: 600px;"></div><div><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'></div> | 2021-04-18 00:35 | 4922 | 3.5 | 0 | 0 | 0 | Normal | Sprint 2115
__export__.project_task_2319_71c78bcb | SO line item substitute note(and checkbox) | 2021-01-25 | 2021-01-31 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Raheel Aslam | 9.83 | 9.83 | -1.83 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-14 21:24 | TRUE | Mid-America Gardens, LLC | 0 | 33.8125 | 0 | 270.7034 | 2021-01-25 | Complete | Naseeb Razaq | Done | FALSE |  | Levi Barnes | 2021-01-14 21:24 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | The content of this cell is too long for an XLSX file (more than 32767 characters). Please use the CSV format for this export. | 2021-03-03 20:06 | 6723 | 8 | 0 | 0 | 0 | Normal | Sprint 2105
__export__.project_task_1700_84ce7af3 | Delete "Core Focus" and make fields HTML | 2020-12-07 | 2020-12-13 | Development | PWX: Help (P23) | Levi Barnes | Fahad Hassan | 5.67 | 4.42 | -2.67 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-02 12:53 | TRUE | EquityTeam | 0 | 15.8125 | 0 | 126.5861 | 2020-12-07 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2020-12-02 12:53 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | The content of this cell is too long for an XLSX file (more than 32767 characters). Please use the CSV format for this export. | 2020-12-23 20:35 | 7763 | 3 | 0 | 0 | 0 | Normal | Sprint 2050
__export__.project_task_1574_e8109b01 | Make Price Editable for Account Executives | 2020-11-23 | 2020-11-29 | Development | Continuant: Quotation Management / Automation (P31) | Kaesi Lee | Raheel Aslam | 10.08 | 10.08 | -3.08 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-11-10 01:20 | FALSE | Continuant | 0 | 59 | 0 | 472 | 2020-11-23 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-11-10 01:20 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><font style="background-color: rgb(255, 255, 0);">As an Odoo admin I would like to provide account executives the ability to edit the sales price of products in a quotation. </font></p><p><br></p><p class="MsoNormal">I would like them to edit the sale price of a product on the sales order line only for that specific quote.</p><p></p><p></p> | 2021-01-30 03:45 | 8303 | 7 | 0 | 0 | 0 | Normal | Sprint 2048
__export__.project_task_1141_5d582eb6 | Conditional Dropship Order | 2020-09-07 | 2020-09-13 | Development | Continuant: eCommerce (P9) | Deepak Krishnan | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-27 01:02 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-09-07 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-27 01:02 | Continuant | FALSE | FALSE | <p>The Continuant eCommerce generated orders should have their default route set to dropship. Orders created through the sales order module directly, not through eCommerce, should work as per the existing method. </p> |  | 10103 | 0 | 0 | 0 | 0 | Normal | Sprint 30
__export__.project_task_1137_4cb96f53 | Carrier Code for UPS and FedEx Ground | 2020-08-24 | 2020-08-30 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-26 19:35 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-24 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-26 19:35 | Continuant | FALSE | FALSE | <p>Ingram is requesting the carrier code for the distributor API. </p> |  | 10108 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_224_6502ca5c | Server Disconnected | 2020-07-06 | 2020-07-12 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-14 19:15 | FALSE | Cellpoint Corporation | 10.875 | 0 | 86.9805 | 0 | 2020-07-06 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Muhammad Afzaal | 2020-06-29 20:16 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 11500 | 0 | 0 | 0 | 0 | Normal | Sprint 21
__export__.project_task_206_a875557e | Sorting and Search Web | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan | FALSE | 0 | 0 | 8 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-10 12:12 | FALSE | Cellpoint Corporation | 12.3125 | 0 | 98.4621 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-06-23 19:32 | Cellpoint Corporation | FALSE | FALSE | <p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">We allow our buyers to search an auction using search, tags and other filters options </span></p><p><b id="docs-internal-guid-660f918d-7fff-2890-f5f1-ce6a5d679d3f" style="caret-color: rgb(0, 0, 0); color: rgb(0, 0, 0); font-family: -webkit-standard; font-style: normal; font-variant-caps: normal; letter-spacing: normal; orphans: auto; text-align: start; text-indent: 0px; text-transform: none; white-space: normal; widows: auto; word-spacing: 0px; -webkit-text-size-adjust: auto; -webkit-text-stroke-width: 0px; text-decoration: none; font-weight: normal;"><br><br></b></p><p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">Filters include, location, Seller, Category, Reserve price, current price.</span></p><p><span style="caret-color: rgb(0, 0, 0); color: rgb(0, 0, 0); font-family: -webkit-standard;"><br></span></p> |  | 11645 | 8 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_4587_186abc73 | All business processes in place |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 3.5 | 3.5 | -0.5 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-13 19:11 | TRUE | Zuma Sales LLC | 0 | 5 | 0 | 40 |  | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-13 19:11 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-08-23 13:59 | 1661 | 3 | 0 | 0 | 0 | Normal
__export__.project_task_4454_b185c82c | User Validation Error on Vendor ASN Import, Phone Check Import, UEDF Response | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Kaleem Khan | 14.92 | 14.92 | -6.92 | 100 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-06 18:30 | TRUE | Cellpoint Corporation | 0 | 11.6875 | 0 | 93.4233 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Muhammad Zubair | 2021-08-06 18:30 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>If the file loaded has any error based on the following description: <br><br>Format doesn't match</p><p>Specific Column Values do not match </p><p><br></p><p><br></p><p>Please show user validation error pointing to problems in the file. </p><p><br></p><p>Incase if the Column arrangement is not per the selected format, user error "File doesn't match with the format" <br>incase columns have wrong values, user error "Columns X Row X has wrong value" </p><p><br></p><p>Stop on first error and show validation to user in case 2.</p> | 2021-08-25 02:25 | 1830 | 8 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3271_7b419dfa | Editing field not allowing | 2021-04-05 | 2021-04-11 | Development | DO NOT USE (old MMH: Help (P83)) | Jeff Gross | Raheel Aslam | 2.5 | 2.5 | -0.5 | 100 | 2021-04-01 | 1 | Complete | TRUE | Muhammad Saqlain Alam | 2021-03-30 22:18 | TRUE | Mountain Meadow Herbs | 0 | 13 | 0 | 104 | 2021-04-05 | Complete | Naseeb Razaq | Done | FALSE |  | Naseeb Razaq | 2021-03-30 22:18 | Mountain Meadow Herbs, Gerry Carton | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>Ticket # 1063, H1111</p><p><br></p><p><br></p><div style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>1) Please make the Display Name field editable.</div><div style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>It can't be set as editable in Toggle and pulling up the field through MORE does not make it changeable eiother, instead I get the message below.</div><div><br></div><p><br></p><p><br></p><p><img src="https://www.silverdaletech.com/web/image/20328?access_token=03c169c8-1d59-46af-b6cc-9d08d091ac78" style='max-width: 100%; height: auto; font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; width: 600px;'><br></p> | 2021-04-18 00:35 | 4922 | 2 | 0 | 0 | 0 | Normal | Sprint 2115
__export__.project_task_2330_dacbde80 | wishlist install | 2021-01-18 | 2021-01-24 | Configuration | Mid-America: Odoo Implementation (P37) | Levi Barnes | Levi Barnes | 0.25 | 0.25 | -0.25 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-15 05:31 | TRUE | Mid-America Gardens, LLC | 0 | 11 | 0 | 88 | 2021-01-18 | Complete | Naseeb Razaq | Done | FALSE |  | Levi Barnes | 2021-01-15 05:31 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>install wishlist</p> | 2021-01-30 20:41 | 6715 | 0 | 0 | 0 | 0 | Normal | Sprint 2104
__export__.project_task_1827_422512d1 | Continuant Quotation Response Deployment 2049 | 2020-11-30 | 2020-12-06 | Configuration | Continuant: Quotation Management / Automation (P31) | Muzher Siddique | FALSE | 0.67 | 0.67 | 0.33 | 67 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-12-08 19:02 | FALSE | Continuant | 0 | 0.1875 | 0 | 1.3913 | 2020-11-30 | Complete | Muhammad Zubair | Done | FALSE |  | Muzher Siddique | 2020-12-08 19:02 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><br></p> | 2020-12-08 20:26 | 7613 | 1 | 0 | 0 | 0 | Normal | Sprint 2049
__export__.project_task_1693_7c9b8ae3 | appraisals core evaluation | 2020-12-14 | 2020-12-20 | Development | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 13 | 12.67 | -1 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-01 22:56 | TRUE | EquityTeam | 0 | 19.5 | 0 | 156 | 2020-12-14 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2020-12-01 22:56 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | FALSE | The content of this cell is too long for an XLSX file (more than 32767 characters). Please use the CSV format for this export. | 2020-12-29 17:10 | 7777 | 12 | 0 | 0 | 0 | Normal | Sprint 2051
__export__.project_task_1206_f85e2e44 | Back End Fixes | 2020-09-07 | 2020-09-13 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-14 17:27 | FALSE | Cellpoint Corporation | 0 | 6.5 | 0 | 52 | 2020-09-07 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-09-14 17:27 | Cellpoint Corporation | FALSE | FALSE | <div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">8.state import in production</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">9.import city in production</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">10.import country in production</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">11.sign up flow</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">12.hide invitation buttom</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">13.change odoobot name to cpbids</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">14.change status message verfication token mismatch to logged in another device</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">15.address issue (api fix)</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">16. change reply email odoo bot to noreply@cpbids.com</div> | 2020-09-23 12:26 | 9655 | 0 | 0 | 0 | 0 | Normal | Sprint 30
__export__.project_task_1169_d8a77030 | Check Distributors for Shipping Notification Policy | 2020-08-31 | 2020-09-06 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-01 19:51 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-31 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-09-01 19:51 | Continuant | FALSE | FALSE | <p>Tech Data: MyOrdertracker sends emails with order status updates <a href="https://tdcontent.techdata.com/Content/XMLGuide/index.htm" style="font-family: inherit; font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;">https://tdcontent.techdata.com/Content/XMLGuide/index.htm<br></a></p><p>Ingram Micro: We need to pull the order status, they don't proactively send info</p><p>Synnex: We need to pull the order status, they don't proactively send info</p> |  | 9964 | 0 | 0 | 0 | 0 | Normal | Sprint 29
__export__.project_task_1041_a4d30a7f | Clicking Save re-directs them to the Create Auction Page | 2020-08-10 | 2020-08-16 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-13 02:56 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Kaesi Lee | 2020-08-13 02:56 | Cellpoint Corporation | FALSE | FALSE | <p>Create New Lot, Clicking Save re-directs them to the Create Auction Page</p> |  | 10437 | 0 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_338_bf65f665 | Carrier: Receive tracking numbers from dropshippers | 2020-09-14 | 2020-09-20 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-17 00:58 | FALSE | Continuant | 44.1875 | 49.1875 | 353.7145 | 393.7145 | 2020-09-14 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE | <p><br></p> | 2020-09-24 00:42 | 11092 | 0 | 0 | 0 | 0 | Normal | Sprint 31
__export__.project_task_173_01b2d35a | Prevent Duplicate Entries | 2020-08-17 | 2020-08-23 | Studio | Heronswood: Events (P3) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 | 2020-06-04 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-06-02 19:55 | FALSE | Port Gamble S’Klallam Foundation | 0 | 0 | 0 | 0 | 2020-08-17 | Complete | Naseeb Razaq | Done | FALSE |  | Nick Foy | 2020-06-02 19:55 | Port Gamble S’Klallam Foundation, Ross Bayton | Executive / Delivery / Alpha | FALSE | <p>User wants to prevent duplicate entries in the following tables:</p><p><br></p><p>Plant Family</p><p>Genus</p><p>Species</p> |  | 12148 | 0 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_4585_6d35d360 | Critical Test Cases have been completely run on production database (Copy of Production on Staging) (copy) |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | FALSE | 0 | 0 | 3 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-13 19:11 | TRUE | Zuma Sales LLC | 0 | 0.875 | 0 | 6.7487 |  | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-13 19:11 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-08-16 16:56 | 1661 | 3 | 0 | 0 | 0 | Normal
__export__.project_task_4447_eff91d06 | UEDF Validations Required | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 3.17 | 3.17 | 0.33 | 90.57 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-06 16:29 | TRUE | Cellpoint Corporation | 0 | 11.6875 | 0 | 93.4233 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Muhammad Zubair | 2021-08-06 16:03 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>There is a number of validations that are required but are missing at the moment:</p><p><br></p><ol><li><p>UEDF Activation File can only be run if: </p><ol><li><p>Disposition Code is: ID not Found</p></li><li><p>Serial State is Received or ahead of it</p></li></ol></li></ol> | 2021-08-25 02:25 | 1832 | 3.5 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3265_a3babc83 | Gift Price should not be picked in Sales Order line in case of changing quantity on line | 2021-04-05 | 2021-04-11 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Muhammad Bilal | 1.92 | 1.92 | 1.08 | 64 | 2021-03-31 | 2 | Complete | TRUE | Muhammad Saqlain Alam | 2021-03-30 16:01 | TRUE | Mid-America Gardens, LLC | 0 | 13.625 | 0.00012918 | 108.9801 | 2021-04-05 | Complete | Naseeb Razaq | Done | FALSE |  | Naseeb Razaq | 2021-03-30 16:01 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Find attached video for explanation </p> | 2021-04-18 00:35 | 4928 | 3 | 0 | 0 | 0 | Normal | Sprint 2115
__export__.project_task_2659_8736d1ce | payment credentials | 2021-02-01 | 2021-02-07 | Configuration | Mid-America: Odoo Implementation (P37) | Levi Barnes | Levi Barnes | 0.25 | 0.25 | -0.25 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-02-04 07:49 | TRUE | Mid-America Gardens, LLC | 0 | 7.875 | 0 | 62.9853 | 2021-02-01 | Complete | Naseeb Razaq | Done | FALSE |  | Levi Barnes | 2021-02-04 07:49 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>add payment credentials in paypal and evalon.</p> | 2021-02-15 20:59 | 6232 | 0 | 0 | 0 | 0 | Normal | Sprint 2107
__export__.project_task_1787_acee0dfc | Move Bid Limit field | 2020-12-07 | 2020-12-13 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Fahad Hassan | 0.17 | 0.17 | 0.83 | 17 |  | FALSE | Complete | TRUE | FALSE | 2020-12-05 05:45 | FALSE | Cellpoint Corporation | 0 | 12.8125 | 0 | 102.5861 | 2020-12-07 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Nick Foy | 2020-12-05 05:45 | Cellpoint Corporation | FALSE | Silverdale Technology LLC | <p>Move Bid Limit to be the last column on all the Auction Views. </p> | 2020-12-23 20:35 | 7698 | 1 | 0 | 0 | 0 | Normal | Sprint 2050
__export__.project_task_1512_7ee6c995 | Data Migration from Odoo to Azure |  |  | Development | Continuant: Power BI Integration (P30) | Levi Barnes | Muzher Siddique | 107.87 | 8.83 | -107.87 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-10-31 01:49 | FALSE | Continuant | 0 | 27 | 0 | 215.9042 |  | Complete | Muhammad Zubair | Cancelled | FALSE |  | Kaesi Lee | 2020-10-31 01:36 | Continuant | FALSE | Silverdale Technology LLC | <p>As a business analyst I would like to migrate data from Odoo to an Azure server, so that I can access data from applications that integrate with Azure. </p><p><br></p><p><b>Acceptance Criteria</b></p><p><b><br></b></p><p>Scenario: Green Path</p><p>Given that data is ready for export in Odoo, when the scheduled action initiates the transfer of data, then the data is stored in Azure. </p><p><br></p><p>Scenario: Failed Transmission</p><p>Given that the transmission of data has failed, when the azure gives a response error, then a error is generated and sent to an IT person via email.</p><p><br></p><p> </p><p><br></p><p><br></p><p><br></p> | 2020-12-08 21:54 | 8542 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_1322_939618fc | Display Name on Contact | 2020-11-02 | 2020-11-08 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 11.83 | 11.83 | -3.83 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-11-03 22:14 | TRUE | EquityTeam | 25 | 34 | 200 | 272 | 2020-11-02 | Complete | Farman Ahmad Cheema | Done | FALSE | External - Client | Nick Foy | 2020-09-30 04:49 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <h3>Background</h3><p><br></p><p>Each Contact can have multiple roles. Client has a custom field in Contact called x_contact_type. This is a many2many field set on the Contact and assigns roles to each contact. When the client selects a contact (in any Module) they want to the contact type to appear after the contact name. For example:</p><p><br></p><p>Contact Name: Nick Foy</p><p>Contact Type: Building</p><p><br></p><p>Would appear as "Nick Foy (Building)"</p><p><br></p><p>For contacts that are linked (such as Company and Individual) the example would be:</p><p><br></p><p>Company Name: Silverdale Tech</p><p>Contact Type: Building</p><p>Contact Name: Nick Foy</p><p>Contact Type: Unit, Property Manager</p><p><br></p><p>Would appear as "Silverdale Tech (Building), Nick Foy (Unit, Property Manager)"</p><p><br></p><h3>Requirements:</h3><p><br></p><ol><li><p>Use the Contact Display Name field and create a text string based on the Contact Name and the assigned Names of Contact Types</p></li><li><p>Use the Display Name as the default for Customer selections in all modules <font style="background-color: rgb(255, 255, 0);">(or do we override the default field that is already in place?)</font></p></li></ol><p><br></p> | 2020-11-17 05:04 | 9283 | 8 | 0 | 0 | 0 | Normal | Sprint 2045
__export__.project_task_1135_3a0ff575 | Sales Delivery Order Automation | 2020-08-24 | 2020-08-30 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-26 02:12 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-24 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-26 02:12 | Continuant | FALSE | FALSE | <p>Create Backorder by default if the vendor ships a partial drop ship order. (See attached for screenshot). </p> |  | 10126 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_1075_5d310607 | Deploy as a Module | 2020-08-31 | 2020-09-06 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-14 20:36 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-31 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-14 20:36 | Continuant | FALSE | FALSE | <p>We need to start packaging our code as modules when we release them to Continuant. This way the changes that we make can be contained and we can reverse those changes if necessary. </p> |  | 10395 | 0 | 0 | 0 | 0 | Normal | Sprint 29
__export__.project_task_928_032f4b95 | API:Make an offer:Postman | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-29 12:27 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-29 12:27 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10788 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_841_de9ae46d | Get batch API iOS-Implementation | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_588_8e418716 | API:Login:APPMAVEN | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 5 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-23 11:53 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-23 11:53 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10932 | 5 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_544_9f0f369f | API:Tag list | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:48 | FALSE | Cellpoint Corporation | 1.375 | 0 | 10.7981 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p>method: POST</p><p>Description: On the basis of this API user can get the Category tag to get Auctions Lot List it also works like to filter the list on the basis of Tag.</p><p>Parameter : user_id</p><p>API will check the user_id and fetch tag data from the table (cpbids.tag) with the condition (active_chk=True)</p><p>append tag.id, tag.name into JSON</p><p>Retrieve the JSON data</p><p><br></p><p><br></p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_534_a1f0c54e | API:Forgot Password | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:44 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.7256 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p>method: POST</p><p>Description: This API is used to reset the account password. User needs to enter email ID registered with the application. If Email is not registered or incorrect email is entered then, Alert message is shown to the user to check email. The user gets the reset password link on their email. User needs to click on that email and they are redirected to a page where user can change the password for their account.</p><p>parameter: email</p><p>API will check the user based on a mail-in user database table (res.partner), and the user will get the reset password link via mail.</p><p>Retrieve data with a message ( Check Mail )</p><p><br></p><p><br></p><p><br></p><p><br></p><p><br></p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_4584_d16b100e | Critical Test Cases have been completely run on production database (Copy of Production on Staging) |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hassan | 0 | 0 | 3 | 0 | 2021-08-20 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-13 19:10 | TRUE | Zuma Sales LLC | 0 | 0.875 | 0 | 6.7613 |  | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-13 19:10 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-08-16 16:56 | 1661 | 3 | 0 | 0 | 0 | Normal
__export__.project_task_4450_ac09f329 | UEDF File Status on Stock Production Lot | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 6.75 | 6.75 | 0.75 | 90 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-06 16:57 | TRUE | Cellpoint Corporation | 0 | 11.6875 | 0 | 93.4233 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Muhammad Zubair | 2021-08-06 16:57 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>UEDF File:</p><p>-if processed will update the processed status on Serial (ASN Processed)</p><p>-if UEDF file is generated then status of UEDF on Serial (ASN Requested Before)</p><p>- add field UDEF file type in boost.file model with values (UDF asn and UDF activation).<br>- if UDEF activation file is generated the file type should be udef activation</p><p>-if the udef asn is generated the file type should be udef asn.</p><p><br></p> | 2021-08-25 02:25 | 1831 | 7.5 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3432_82fc5c34 | Set up and verify User groups and access rights |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | FALSE | 0 | 0 | 0 | 0 | 2021-07-04 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-07-19 18:59 | TRUE | Zuma Sales LLC | 57.6875 | 49.8125 | 461.2711 | 398.3233 |  | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-04-23 21:43 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-07-07 20:03 | 4346 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_3430_76bb8762 | Secure access to the production environment |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 | 0 | 0 | 2021-08-08 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-07-19 18:59 | TRUE | Zuma Sales LLC | 57.6875 | 65.0625 | 461.2842 | 520.3123 |  | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-04-23 21:42 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-07-30 00:21 | 4346 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_3264_3dfae8de | Stock Availability Message | 2021-04-05 | 2021-04-11 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Aleem khan | 3.17 | 3.17 | -0.67 | 100 |  | 2 | Complete | TRUE | Muhammad Saqlain Alam | 2021-03-30 15:16 | TRUE | Mid-America Gardens, LLC | 0 | 13.6875 | 0 | 109.726 | 2021-04-05 | Complete | Naseeb Razaq | Done | FALSE |  | Fahad Hussain Malik | 2021-03-30 15:16 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Ticket 1093</p><p>The customer needs to show the stock availability message on the categories page. I have explained the whole scenario in the video attached.<br></p> | 2021-04-18 00:35 | 4929 | 2.5 | 0 | 0 | 0 | Normal | Sprint 2115
__export__.project_task_2316_7a4f4c74 | image facebook | 2021-01-25 | 2021-01-31 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Muzher Siddique | 2.5 | 2.5 | 3.5 | 41.67 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-14 21:22 | TRUE | Mid-America Gardens, LLC | 0 | 33.8125 | 0 | 270.7308 | 2021-01-25 | Complete | Naseeb Razaq | Done | FALSE |  | Levi Barnes | 2021-01-14 21:22 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | The content of this cell is too long for an XLSX file (more than 32767 characters). Please use the CSV format for this export. | 2021-03-03 20:06 | 6723 | 6 | 0 | 0 | 0 | Normal | Sprint 2105
__export__.project_task_1826_627d884c | Deployment AV Warehouse 2049 | 2020-11-30 | 2020-12-06 | Configuration | Continuant: AV Warehouse (P34) | Muzher Siddique | FALSE | 1.58 | 1.58 | -0.58 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-12-08 18:48 | FALSE | Continuant | 0 | 0 | 0 | 0.0013433 | 2020-11-30 | Complete | Muhammad Zubair | Done | FALSE |  | Muzher Siddique | 2020-12-08 18:48 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><br></p> | 2020-12-08 18:49 | 7613 | 1 | 0 | 0 | 0 | Normal | Sprint 2049
__export__.project_task_1657_70257fcf | Test both applications for API response time | 2020-11-23 | 2020-11-29 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 2 | 2 | -2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-11-25 16:26 | FALSE | Cellpoint Corporation | 0 | 8.5625 | 0.13606 | 68.7033 | 2020-11-23 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Apps Maven | 2020-11-25 16:18 | Cellpoint Corporation | FALSE | Apps Maven | <p><br></p> | 2020-12-08 05:42 | 7928 | 0 | 0 | 0 | 0 | Normal | Sprint 2048
__export__.project_task_1607_e76ad7ca | Process AV Items at Receipt | 2020-11-23 | 2020-11-29 | Development | Continuant: AV Warehouse (P34) | Kaesi Lee | Danish Hassan | 3.42 | 3.42 | -0.75333 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-11-17 02:55 | FALSE | Continuant | 1 | 16 | 8 | 128 | 2020-11-23 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-11-14 05:00 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>When AV Items are received, we want to carry out certain checks and record the results.</p><p><br></p><p>Requirements:</p><p><br></p><ol><li><p>On AV Tracker: Items, create fields for:</p><ol><li><p>Mac Address - short text field</p></li><li><p>Power-On - Drop-down with 3 options "n/a, Pass, Fail"</p></li><li><p>More to come...</p></li></ol></li></ol> | 2020-12-08 05:42 | 8203 | 2.6667 | 0 | 0 | 0 | Normal | Sprint 2048
__export__.project_task_1138_5d3b5bb6 | Check Availability: Display all three vendors | 2020-08-24 | 2020-08-30 | Development | Continuant: eCommerce (P9) | Gadha Continuant | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-26 19:37 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-24 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-26 19:37 | Continuant | FALSE | FALSE | <p>When you click check availability on the product details page, all of the vendors should be displayed. If there is no availability with a particular vendor, that vendor should be grayed out and the add to cart button should not be visible for that vendor. </p> |  | 10108 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_1059_1f03e0ac | Seller Permissions Group: Bug with "invite selected buyers" Selecting individual buyers then unselecting the invite selected buyers removes the buyer list from view. | 2020-08-24 | 2020-08-30 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-28 13:23 | FALSE | Cellpoint Corporation | 11.0625 | 0 | 88.3803 | 0 | 2020-08-24 | Complete | Muhammad Afzaal | Done | FALSE |  | Kaesi Lee | 2020-08-13 02:56 | Cellpoint Corporation | FALSE | FALSE | <p>Create Auction, Bug with "invite selected buyers" Selecting individual buyers then unselecting the invite selected buyers removes the buyer list from view. </p> |  | 10437 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_894_71094e60 | Seller list Android-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_592_262178fa | API:Version updation:APPMAVEN | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-23 11:56 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-23 11:56 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10932 | 2 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_541_30e0f1b9 | API:Select state | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:44 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.7361 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p>method: GET</p><p>Parameter: type value </p><p>Description: User has to send state in type parameter in to get state list, and in the value, parameter user have to send the country id</p><p>List states from the database table (res.country.state) with condition (country_id=value)</p><p>Append state_id,country_id,name into JSON </p><p>Retrieve json data</p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_205_14855eb2 | Using Multiple devices | 2020-07-12 | 2020-07-19 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan | FALSE | 0 | 0 | 8 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-10 12:11 | FALSE | Cellpoint Corporation | 12.3125 | 0 | 98.4689 | 0 | 2020-07-12 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-06-23 19:32 | Cellpoint Corporation | FALSE | FALSE | <p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 13.999999999999998pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 700; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">Not allowed to login from 2 devices:</span></p><p><b id="docs-internal-guid-3c20093e-7fff-c51e-9688-b0f45072a511" style="caret-color: rgb(0, 0, 0); color: rgb(0, 0, 0); font-family: -webkit-standard; font-style: normal; font-variant-caps: normal; letter-spacing: normal; orphans: auto; text-align: start; text-indent: 0px; text-transform: none; white-space: normal; widows: auto; word-spacing: 0px; -webkit-text-size-adjust: auto; -webkit-text-stroke-width: 0px; text-decoration: none; font-weight: normal;"><br></b></p><p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">Buyers can only login from one device at a time. We would like to modify this feature and allow our buyers logged in from mobile and web auction at the same time </span></p><p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">But from only one mobile device.</span></p><p><span style="caret-color: rgb(0, 0, 0); color: rgb(0, 0, 0); font-family: -webkit-standard;"><br></span></p> |  | 11645 | 8 | 0 | 0 | 0 | Normal | Sprint 22
__export__.project_task_4583_0d921f09 | Client Domain pointing to Odoo.sh address has been configured | 2021-08-30 | 2021-09-05 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Raheel Aslam | 0 | 0 | 0 | 0 | 2021-09-07 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-13 19:09 | TRUE | Zuma Sales LLC | 0 | 16.6875 | 0 | 133.4208 | 2021-08-30 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-13 19:09 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-09-08 02:25 | 1661 | 0 | 0 | 0 | 0 | Normal | Sprint 2136
__export__.project_task_4446_da2e2ddf | Menus for Custom Models | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 4 | 4 | 0 | 100 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-06 16:02 | TRUE | Cellpoint Corporation | 0 | 11.6875 | 0 | 93.4233 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Muhammad Zubair | 2021-08-06 15:55 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Create menus for custom models: </p><p><br></p><p><br></p><ol><li><p>Phone Model</p></li><li><p>Phone Model Number</p></li><li><p>Phone Color</p></li><li><p>Phone Capacity</p></li><li><p>Sim Technology</p></li></ol><p> these data should be in uppercase.<br></p><p>Where to add: <br><br>Inventory &gt; Configuration &gt; Products</p><p><br></p><p><br></p><p>Views: List + Form</p><p><br></p> | 2021-08-25 02:25 | 1832 | 4 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3429_60948b5e | Install the system management tools |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 | 0 | 0 | 2021-08-06 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-07-19 18:59 | TRUE | Zuma Sales LLC | 57.6875 | 65.0625 | 461.295 | 520.3228 |  | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-04-23 21:42 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-07-30 00:21 | 4346 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_3263_c3afe3a2 | Two decimal to set on minimum order msg, on website. | 2021-04-05 | 2021-04-11 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Muhammad Bilal | 1.33 | 1.33 | 0.17 | 88.67 |  | 1 | Complete | TRUE | Muhammad Saqlain Alam | 2021-03-30 15:10 | TRUE | Mid-America Gardens, LLC | 0 | 13.75 | 0 | 109.8368 | 2021-04-05 | Complete | Naseeb Razaq | Done | FALSE |  | Fahad Hussain Malik | 2021-03-30 15:10 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; white-space: pre-wrap;'>On website we set a msg on minimum order, so in that msg the customer needs to have 2 decimals. For example "25.00$" instead of "25.0$".</span><br></p> | 2021-04-18 00:35 | 4929 | 1.5 | 0 | 0 | 0 | Normal | Sprint 2115
__export__.project_task_2740_3de63114 | shop/address modifications | 2021-02-15 | 2021-02-21 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Raheel Aslam | 4.25 | 4.25 | -0.41667 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-02-12 18:02 | TRUE | Mid-America Gardens, LLC | 0 | 13.3125 | 0 | 106.4642 | 2021-02-15 | Complete | Naseeb Razaq | Done | FALSE |  | Levi Barnes | 2021-02-12 18:02 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | The content of this cell is too long for an XLSX file (more than 32767 characters). Please use the CSV format for this export. | 2021-03-03 20:30 | 6030 | 3.8333 | 0 | 0 | 0 | Normal | Sprint 2109
__export__.project_task_1572_36125ea4 | Invoice Portal Access Data from Excel | 2020-11-09 | 2020-11-15 | Development | Continuant: Customer Invoice Delivery Preferences (P33) | Kaesi Lee | Muzher Siddique | 4.83 | 4.83 | 1.17 | 80.5 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-11-10 00:06 | FALSE | Continuant | 0 | 9.875 | 0 | 79.2092 | 2020-11-09 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-11-10 00:06 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>As a User, I have an excel sheet that I refer to for Contacts which tells me the client's invoice portal details. I want to be able to access this information in Odoo, ensuring that only Users who are authorized, can see the data as the data contains usernames and password.</p><p><br></p><p>Requirements:</p><p><br></p><ol><li><p>Create a new Model for Invoicing Portal Data with fields:</p><ol><li><p>Linked To Contact (many2one from Contacts)</p></li><li><p>Portal Name (drop-down list)</p></li><li><p>Portal URL (url field)</p></li><li><p>Username (short text)</p></li><li><p>Password (short text)</p></li><li><p>Active (tick box, default to Ticked i.e. Active)</p></li><li><p>Notes (multiline text)</p></li></ol></li><li><p>Create 2 new User Groups</p><ol><li><p>Invoicing Portal Data Users (view only access to the data)</p></li><li><p>Invoicing Portal Data Admin (read, edit, delete, create access)</p></li></ol></li><li><p>On Contacts, create a new tab for Invoicing Portal Data</p><ol><li><p>tab should only show to the 2 User groups</p></li><li><p>Show related entries from Invoicing Portal Data in a table (each contact can have more than one entry in the Invoicing Portal Data table)</p><ol><li><p>Portal Name (drop-down list, set-up as a new table so Users can configure new Portal Names as required)</p></li><li><p>Portal URL (url field)</p></li><li><p>Username (short text)</p></li><li><p>Password (short text)</p></li><li><p>Notes (multiline text)</p></li></ol></li></ol></li></ol><p><br></p><p><br></p><p><br></p><p><br></p><p><br></p> | 2020-11-23 21:13 | 8304 | 6 | 0 | 0 | 0 | Normal | Sprint 2046
__export__.project_task_1431_00ee4072 | CPBids Mobile App: App Crashing | 2020-11-02 | 2020-11-08 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-10-16 21:53 | FALSE | Cellpoint Corporation | 0 | 5 | 0 | 40.1103 | 2020-11-02 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Kaesi Lee | 2020-10-16 21:53 | Cellpoint Corporation | FALSE | Apps Maven | <p>I observed on 10/16/2020 during monitoring Belmont auctions that the app frequently crashes. </p><p><br></p><p>Phone Model: LG V60 ThinQ 5G</p><p>Android Version: 10</p><p>App Version: 3.0.1</p><p><br></p><p>The app seemed to crash every time auctions closed. Card view would continually refresh (refresh animation repeating rapidly)</p><p>I would click on an auction to go to the details page during this time and the view would load for a few seconds and then the app would crash and my phone would return to the home screen. Muhammad has also seen this issue on android as well. </p> | 2020-10-24 00:46 | 8882 | 0 | 0 | 0 | 0 | Normal | Sprint 2045
__export__.project_task_1190_b0981695 | Distributor Status: Set default to N/A | 2020-09-07 | 2020-09-13 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-11 00:42 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-09-07 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-09-11 00:42 | Continuant | FALSE | FALSE | <p>Set default purchase order distributor status to N/A. </p> |  | 9743 | 0 | 0 | 0 | 0 | Normal | Sprint 30
__export__.project_task_1147_052bcb12 | Deploy Shipping Uplift | 2020-08-24 | 2020-08-30 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-27 02:59 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-24 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-27 02:59 | Continuant | FALSE | FALSE | <p>We established the shipping price uplift would be 5%. Continuant will be charging an additional 5% for shipping costs. Please include this uplift in calculating the shipping cost. </p><p><br></p><p>For example: If the calculated shipping cost is $10 from Fedex or UPS, the amount charged and displayed to the customer would be $10.05. </p> |  | 10101 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_890_b424faca | Select state Android-Implementation | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_887_f257d0a3 | Lot view Android-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_817_1d3e4dbe | Place a bid iOS-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 2 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_598_56c75f02 | API:Tag list :APPMAVEN | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 3 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-23 12:01 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-23 12:01 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10932 | 3 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_596_97203851 | API:Forcefully Update:APPMAVEN | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 3 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-23 11:59 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-23 11:59 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10932 | 3 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_560_5132d979 | API:Notification list api | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 6 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:40 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.6608 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 11009 | 6 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_4582_8587a9ea | Email Configuration has been tested | 2021-08-23 | 2021-08-29 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.5 | 0.5 | 0 | 100 | 2021-08-27 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-13 19:09 | TRUE | Zuma Sales LLC | 0 | 5 | 0 | 40 | 2021-08-23 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-13 19:09 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-08-23 13:53 | 1661 | 0.5 | 0 | 0 | 0 | Normal | Sprint 2135
__export__.project_task_4448_fe3fb5e8 | Product Form(product.product) should be same as Product Template | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Kaleem Khan | 2.5 | 2.5 | -0.5 | 100 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-06 16:53 | TRUE | Cellpoint Corporation | 0 | 11.6875 | 0 | 93.4233 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Muhammad Zubair | 2021-08-06 16:53 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>H Type, variant fields are missing on product.product.</p><p>check other custom fields if missing.</p> | 2021-08-25 02:25 | 1831 | 2 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3428_479ffdd3 | Configure the standard applications database objects | 2021-06-21 | 2021-06-27 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | FALSE | 0 | 0 | 0 | 0 | 2021-06-24 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-07-19 18:59 | TRUE | Zuma Sales LLC | 57.6875 | 42.0625 | 461.3003 | 336.3089 | 2021-06-21 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-04-23 21:41 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-06-26 01:00 | 4346 | 0 | 0 | 0 | 0 | Normal | Sprint 2126
__export__.project_task_3246_2e702c2b | Need to add a selection field on SO for Gift & Substitute items | 2021-03-29 | 2021-04-04 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Raheel Aslam | 2.58 | 2.58 | -0.58 | 100 |  | 1 | Complete | TRUE | Muhammad Saqlain Alam | 2021-03-26 16:07 | TRUE | Mid-America Gardens, LLC | 0 | 15.625 | 0 | 124.8827 | 2021-03-29 | Complete | Naseeb Razaq | Done | FALSE |  | Naseeb Razaq | 2021-03-26 16:07 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>On SO line items, there should be a selection field with the name </p><p>Gift</p><p>Substitute</p><p>That selections should be reflected automatically on Delivery</p><p>So for dig list report we can tag the items whether its a gift or substitute.</p> | 2021-04-18 00:35 | 5024 | 2 | 0 | 0 | 0 | Normal | Sprint 2114
__export__.project_task_2883_638e2dbd | Appraisal & Evaluations Planning Tribe |  |  | Other | Silverdale: Time Tracking (P56) | Faisal Huda Khan | Wajahat Ali | 0 | 0 | 0 | 0 |  | FALSE | Cancelled | TRUE | FALSE | 2021-03-09 23:20 | FALSE | Silverdale Technology LLC | 1 | 28.5625 | 8 | 228.3981 |  | Cancelled | Muhammad Afzaal | InProgress | FALSE |  | Muzher Siddique | 2021-03-08 22:30 | FALSE | FALSE | Silverdale Technology LLC | <p><br></p> | 2021-04-16 18:24 | 5450 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_2652_4f3a8a1d | shipping receive by: Backup Restoration | 2021-02-01 | 2021-02-07 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Kaleem Khan | 3.5 | 3.5 | 0 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-02-02 23:24 | TRUE | Mid-America Gardens, LLC | 0 | 0.4375 | 0 | 3.5311 | 2021-02-01 | Complete | Naseeb Razaq | Done | FALSE |  | Kaleem Khan | 2021-02-02 23:24 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Getting backup of midAmerica , restoring it on local environment , solving the issues, setting local environment for odoo14 and so on.</p> | 2021-02-03 16:32 | 6265 | 3.5 | 0 | 0 | 0 | Normal | Sprint 2107
__export__.project_task_2294_d5cf8aee | Deerfield: Add email addresses to Blacklist | 2021-01-11 | 2021-01-17 | Configuration | PWX: Help (P23) | Levi Barnes | Nick Foy | 0.08 | 0.08 | -0.08 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-13 18:04 | TRUE | EquityTeam | 0 | 12.5 | 0 | 99.9307 | 2021-01-11 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Nick Foy | 2021-01-13 18:04 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>Add email addresses to the Email Blacklist as per the shared google sheet (Main Email Subscription Status column)</p> | 2021-01-30 05:26 | 6750 | 0 | 0 | 0 | 0 | Normal | Sprint 2103
__export__.project_task_2115_a6958ede | Deployed tasks Meeting | 2021-01-04 | 2021-01-10 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 0.33 | 0.33 | 0.17 | 66 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-05 16:56 | TRUE | Wild Leaf Beverage | 0 | 0.4375 | 0.074206 | 3.7164 | 2021-01-04 | Complete | Abdul Hameed | In Warranty | FALSE |  | Raheel Aslam | 2021-01-05 16:52 | Wild Leaf Beverage, Thomas Walker_ | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-01-05 21:35 | 6943 | 0.5 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_1581_ebf13508 | Customer Quotation Response | 2021-01-25 | 2021-01-31 | Development | Continuant: Quotation Management / Automation (P31) | Kaesi Lee | Danish Hassan | 17.83 | 17.83 | 1.5033 | 92.22 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-11-11 01:27 | FALSE | Continuant | 0 | 55.75 | 0 | 446.0803 | 2021-01-25 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-11-11 01:27 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>As a customer I need to select accept and pay in response to a quotation that is sent to me from Continuant because customers will respond to a quotation that is sent from a salesperson. </p><p><br></p><p>The quotation sent to a customer should contain a link that takes them to the customer portal and opens the quotation that was sent to them in that portal. That quotation should give the customer an option to Accept or Accept and Pay Online. </p><p><br></p><p>Accept and Pay Online should redirect them to the online payment gateway.</p> | 2021-01-27 20:05 | 8279 | 19.3333 | 0 | 0 | 0 | Normal | Sprint 2105
__export__.project_task_1426_5d61ca8c | iOS List View Display Issue | 2020-11-02 | 2020-11-08 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-10-15 21:04 | FALSE | Cellpoint Corporation | 0.0625 | 22.1875 | 0.40491 | 177.3344 | 2020-11-02 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Kaesi Lee | 2020-10-15 20:40 | Cellpoint Corporation | FALSE | Apps Maven | <p>There is a bug with the iOS list view display. (See attached screenshot).</p><p><br></p><p>the icons and text are continuing off of the auction tile. One attached image is the correct display. The other is not. </p> | 2020-11-17 05:04 | 8907 | 0 | 0 | 0 | 0 | Normal | Sprint 2045
__export__.project_task_1109_d8415f40 | Synnex: Obtain Pricing and Availability | 2020-08-24 | 2020-08-30 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-18 01:33 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-24 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-18 01:33 | Continuant | FALSE | FALSE | <p>Use API to obtain pricing and availability. </p> |  | 10318 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_888_e903ce76 | Version update Android-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_886_ef822e57 | Make an offer Android-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_825_968350c9 | Tag list iOS-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_540_61ae106e | API:Select country | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:44 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.7308 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p><p>method: GET</p><p>Description: user can get list of countries </p><p>Function parameter : type(country)</p><p>Retrieve all the Countries from Database Table (res.country ) </p><p>Append country_id,Contry_name,Country_code into Json</p><p>Retrive Json data</p><p> </p><p> </p><p><br></p><p><br></p><p><br></p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_359_3fff692b | Training: Prepare training materials | 2020-09-21 | 2020-09-27 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-09 22:29 | FALSE | Continuant | 16.1875 | 53.1875 | 129.7145 | 425.7145 | 2020-09-21 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE | <p><br></p> | 2020-09-30 02:12 | 11092 | 0 | 0 | 0 | 0 | Normal | Sprint 32
__export__.project_task_264_96e38a07 | Updated API Document | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 16 | 0 | 2020-07-16 | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:50 | FALSE | Cellpoint Corporation | 5.5625 | 0 | 44.115 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-13 20:43 | Cellpoint Corporation | FALSE | FALSE | <p>Updated document</p><p><a href="https://docs.google.com/document/d/11Uoj1aKa-pE4KWqzN1Zrrykd2zuHSs35Wg5dcTc80Cc/edit?usp=sharing">https://docs.google.com/document/d/11Uoj1aKa-pE4KWqzN1Zrrykd2zuHSs35Wg5dcTc80Cc/edit?usp=sharing</a><br></p><p><br></p><p>Old document</p><p><a href="https://docs.google.com/document/d/1JaRVp9Qxqz045Kkto52xjR43pgRHYp-epzPx5d1KrSA/edit" style="font-family: -webkit-standard;">https://docs.google.com/document/d/1JaRVp9Qxqz045Kkto52xjR43pgRHYp-epzPx5d1KrSA/edit</a><br></p> |  | 11163 | 16 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_226_ced35fd4 | Webkul Meeting | 2020-08-17 | 2020-08-23 | Development | Cellpoint: Odoo Back-End (P8) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-01 00:04 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-17 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-01 00:04 | Cellpoint Corporation | FALSE | FALSE |  |  | 11472 | 0 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_4569_188fb15f | Review the options on the Settings screen for Default taxes | 2021-08-23 | 2021-08-29 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 | 0.16667 | 0 | 2021-08-27 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-13 18:59 | TRUE | Zuma Sales LLC | 0 | 5 | 0 | 40 | 2021-08-23 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-13 18:59 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-08-23 14:05 | 1661 | 0.16667 | 0 | 0 | 0 | Normal | Sprint 2135
__export__.project_task_4460_e18a1d5d | Parent Package and POS Label Scanning | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 5.08 | 5.08 | -1.08 | 100 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-06 19:13 | TRUE | Cellpoint Corporation | 0 | 11.6875 | 0 | 93.4233 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Muhammad Zubair | 2021-08-06 19:09 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Package Type:</p><p><br></p><p>Has Parent Field: If true, Parent Package Type</p><p>For Has Parent: Qty Limit</p><p>For without Has Parent: Package Limit</p><p><br></p><p><br></p><p>Package:</p><p><br></p><p>If Package Type &gt; has parent True, Parent Package field (Data: only packages with package type same as current package's &gt; Package Type &gt; Parent Package Type)</p><p>If Parent: Show Content and allow POS Scanning</p><p>if no Parent: Only show Sub-Packages and do not allow POS Scanning</p><p><br></p><p><br></p><p><br></p> | 2021-08-25 02:25 | 1829 | 4 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3245_87b37039 | Error on Payment (Pay to Card) | 2021-04-05 | 2021-04-11 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Raheel Aslam | 6.83 | 6.83 | 0.17 | 97.57 |  | 4 | Complete | TRUE | Muhammad Saqlain Alam | 2021-03-26 15:55 | TRUE | Mid-America Gardens, LLC | 0 | 15.625 | 0 | 125.0854 | 2021-04-05 | Complete | Naseeb Razaq | Done | FALSE | Internal | Fahad Hussain Malik | 2021-03-26 15:55 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; white-space: pre-wrap;'>When the customer tries to pay the invoice by copying the link and then pasting it in the browser. And when he selects pay to card it gives an error. The video is attached with all the scenario explained. </span><br><br></p><p><br></p><p>This error occurs due to previous version of Evalon, so we are upgrading to resolve this issue.</p> | 2021-04-18 00:35 | 5024 | 7 | 0 | 0 | 0 | Normal | Sprint 2115
__export__.project_task_2776_a7f251d0 | Continuant QM Deployment 2107 | 2021-02-15 | 2021-02-21 | Other | Continuant: Quotation Management / Automation (P31) | Nick Foy | Muzher Siddique | 0.42 | 0.42 | 0.58 | 42 |  | FALSE | Complete | TRUE | Fahad Hassan | 2021-02-17 18:06 | FALSE | Continuant | 0 | 0 | 0 | 0.042565 | 2021-02-15 | Complete | Muhammad Zubair | Done | FALSE |  | Muzher Siddique | 2021-02-17 18:06 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><br></p><p>Modules: </p><p>[New]: sale_portal_terms_conditions for 2398</p><p>[New]: website_logo_size for 2400</p> | 2021-02-17 18:09 | 5910 | 1 | 0 | 0 | 0 | Normal | Sprint 2109
__export__.project_task_2315_930986a5 | facebook | 2021-01-25 | 2021-01-31 | Configuration | Mid-America: Odoo Implementation (P37) | Levi Barnes | Levi Barnes | 0.17 | 0.17 | -0.17 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-14 21:21 | TRUE | Mid-America Gardens, LLC | 0 | 33.8125 | 0 | 270.7394 | 2021-01-25 | Complete | Naseeb Razaq | Done | FALSE |  | Levi Barnes | 2021-01-14 21:21 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>configure facebook</p> | 2021-03-03 20:06 | 6723 | 0 | 0 | 0 | 0 | Normal | Sprint 2105
__export__.project_task_2288_8fa4497c | General 2102 |  |  | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 1.25 | 1.25 | -1.25 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-13 05:10 | TRUE | EquityTeam | 0 | 4 | 0 | 32 |  | Complete | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2021-01-13 05:09 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-01-19 02:31 | 6763 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_2114_d733a443 | Propertyworx Deployment 2053 | 2021-01-04 | 2021-01-10 | Configuration | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 1.17 | 1.17 | 0.83 | 58.5 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-05 16:51 | TRUE | EquityTeam | 0 | 0.0625 | 0.037667 | 0.56794 | 2021-01-04 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Muzher Siddique | 2021-01-05 16:49 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>Tasks 1843.</p><p><br></p><p>QA task# 2020 on production server as it was just the configuration task and move to ELS if all good.</p><p><br></p> | 2021-01-05 18:23 | 6943 | 2 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_1425_fb34dca7 | Priority 0: APPs are not updating | 2020-10-12 | 2020-10-18 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-10-15 13:29 | FALSE | Cellpoint Corporation | 0 | 6.9375 | 0 | 55.522 | 2020-10-12 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Muhammad Afzaal | 2020-10-15 13:29 | Cellpoint Corporation | FALSE | Deerom Technologies Pvt. Ltd. | <p>Issue 01</p><p><br></p><p>1, 6:25 AM UTC Philip notified auto updates are not working </p><p>2, It has been escalated to Deerom and APP MAVEN </p><p>3, Frontend team worked on identifying the issue</p><p>4, Backend team is working on fixing it </p><p><br></p><p>Initial Findings </p><p>Notifications were sent ok </p><p>Highest price was not updating in app</p><p>bid history was not updating in the app</p><p>Auction Lot KVSME: bid history was updated by highest price is not updated in the app</p><p><br></p><p><br></p><p>Issue 02</p><p><br></p><p>Auto bid errors </p><p>It is bidding itself against the user himself </p><p>Max bid was set to 8905 and auto bid changed current price to 8950</p><p><br></p><p><br></p><p>Issue 03</p><p><br></p><p>Auction wasn't extended ... GBDEF</p><p><br></p> | 2020-10-24 00:39 | 8915 | 0 | 0 | 0 | 0 | Normal | Sprint 2042
__export__.project_task_1187_f7de3692 | Sales Order / Quotation: Change PDF Template | 2020-09-07 | 2020-09-13 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-08 22:25 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-09-07 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-09-08 22:25 | Continuant | FALSE | FALSE | <p class="MsoNormal" style="margin-bottom:12.0pt">Default the outgoing sales order / quotation pdf template to “Solution Quote” instead of “Quotation / Order”. See attached file for further info. <p></p></p> |  | 9794 | 0 | 0 | 0 | 0 | Normal | Sprint 30
__export__.project_task_1113_904b78ec | Synnex: Generate Shipping Quoatation | 2020-08-17 | 2020-08-23 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-18 01:36 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-17 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-18 01:36 | Continuant | FALSE | FALSE | <p>Dropship functionality will require a shipping quotation. Please use the following link for API documentation specific to this function. </p><p><br></p><p><a href="https://www.synnexcorp.com/esolutions/wp-content/uploads/sites/63/2017/07/Guide_eeserviceV2.pdf">https://www.synnexcorp.com/esolutions/wp-content/uploads/sites/63/2017/07/Guide_eeserviceV2.pdf</a><br></p> |  | 10318 | 0 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_938_febcdaa7 | API:MyWatch Product List:Postman | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-30 19:59 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-30 19:59 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10756 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_918_87e7d573 | API:Change Password:Postman | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 0.5 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-29 11:34 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-29 11:34 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10788 | 0.5 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_842_83231376 | Get marketplace list iOS-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_591_cd36949e | API:Select state:APPMAVEN | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 3 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-23 11:55 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-23 11:55 | Cellpoint Corporation | FALSE | FALSE | <p> </p><p> </p> |  | 10932 | 3 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_562_511f93db | API:Set Batch Api | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 3 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:39 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.6517 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 11009 | 3 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_291_9c2506be | Distributor: Research Distributor API | 2020-08-10 | 2020-08-16 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 8 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-25 00:23 | FALSE | Continuant | 7 | 0 | 56 | 0 | 2020-08-10 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-16 00:16 | Continuant | FALSE | FALSE | <p>Synnex, Tech Data, Ingram, Scansource. </p><p><br></p><p><br></p> |  | 11112 | 8 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_200_7bc9e4eb | Allow bid from List view Web | 2020-08-17 | 2020-08-23 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan | FALSE | 0 | 0 | 16 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-10 12:31 | FALSE | Cellpoint Corporation | 12.3125 | 0 | 98.5582 | 0 | 2020-08-17 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-06-23 19:26 | Cellpoint Corporation | FALSE | FALSE | <p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">Buyers can bid from the list view without going into the details page on our app.</span></p><p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">We would like to have the same available for web auctions as well.</span></p><p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">If enter bid field </span></p><p><span id="docs-internal-guid-cc9991b5-7fff-5d09-9608-93ac7e7c7bf7" style="caret-color: rgb(0, 0, 0); color: rgb(0, 0, 0); font-family: -webkit-standard;"></span><br class="Apple-interchange-newline" style="caret-color: rgb(0, 0, 0); color: rgb(0, 0, 0); font-family: -webkit-standard;"></p> |  | 11645 | 16 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_4568_dd41e7c9 | Review the options on the Settings screen for Cash Rounding | 2021-08-23 | 2021-08-29 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.25 | 0.25 | 0.25 | 50 | 2021-08-27 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-13 18:59 | TRUE | Zuma Sales LLC | 0 | 8.5 | 0 | 68.2244 | 2021-08-23 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-13 18:59 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-08-27 01:13 | 1661 | 0.5 | 0 | 0 | 0 | Normal | Sprint 2135
__export__.project_task_4456_7305f06b | UEDF Activation | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 4.92 | 4.92 | 1.08 | 82 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-06 18:38 | TRUE | Cellpoint Corporation | 0 | 11.6875 | 0 | 93.4233 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Muhammad Zubair | 2021-08-06 18:38 | Cellpoint Corporation, Ehsan Gharatappeh | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Related Task 4404:</p><p><br></p><p>UEDF Activation file export can be done for multiple SKUs at the same time</p><p><br></p><p>UEDF activation can only be done if</p><p><br></p><ol><li><p>Disposition Code is (ID not found) </p></li><li><p>Serial State is Received. </p></li><li><p>Remove nms bounce and add it to Lot view with all the reports.<br></p></li></ol> | 2021-08-25 02:25 | 1829 | 6 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3244_2536bed0 | Gift should be counted in the total count | 2021-03-29 | 2021-04-04 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Raheel Aslam | 1.67 | 1.67 | -0.67 | 100 |  | 2 | Complete | TRUE | Muhammad Saqlain Alam | 2021-03-26 15:26 | TRUE | Mid-America Gardens, LLC | 0 | 15.6875 | 0 | 125.5661 | 2021-03-29 | Complete | Naseeb Razaq | Done | FALSE |  | Fahad Hussain Malik | 2021-03-26 15:26 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Updated </p><p>On the production, Sales Order no 890, the gifts are not counted. When we print the sales order the count is 10 and on the screen, it is also 10 (it is excluding gifts now), but when we print its delivery slip with and without pricing its count is 12. It should be 10 on the sales order screen as well as on the print of the sales order. I have attached the video for the bug recreation for better understanding.<br></p> | 2021-04-18 00:35 | 5025 | 1 | 0 | 0 | 0 | Normal | Sprint 2114
__export__.project_task_2768_3b4a96c7 | Continuant AV Warehouse Deployment 2107 | 2021-02-15 | 2021-02-21 | Other | Continuant: AV Warehouse (P34) | Nick Foy | Muzher Siddique | 1 | 1 | 0 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2021-02-16 18:59 | FALSE | Continuant | 0 | 0.375 | 0 | 3.0104 | 2021-02-15 | Complete | Muhammad Zubair | Done | FALSE |  | Muzher Siddique | 2021-02-16 18:59 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><br></p><p>New Module: av_tracker</p> | 2021-02-17 01:49 | 5933 | 1 | 0 | 0 | 0 | Normal | Sprint 2109
__export__.project_task_2281_f12dd62d | FW: You have been assigned to Deerfield Contacts Import (305): update invoices | 2021-01-11 | 2021-01-17 | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 0.5 | 0.5 | -0.5 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-12 20:45 | TRUE | EquityTeam | 0 | 14.875 | 0 | 118.8094 | 2021-01-11 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2021-01-12 20:45 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>after default accounting account is updated for donation digital product, update invoices associated.</p> | 2021-02-02 19:33 | 6771 | 0 | 0 | 0 | 0 | Normal | Sprint 2103
__export__.project_task_2113_b6da3bd4 | Deployment and Post QA on Production | 2021-01-04 | 2021-01-10 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | FALSE | 2.67 | 2.67 | -0.0033333 | 100 |  | FALSE | Complete | TRUE | FALSE | 2021-01-05 16:10 | FALSE | Cellpoint Corporation | 0 | 0.125 | 0.014077 | 1.0974 | 2021-01-04 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Wajahat Ali | 2021-01-05 16:09 | Cellpoint Corporation | FALSE | Silverdale Technology LLC | <p><br></p> | 2021-01-05 18:15 | 6944 | 2.6667 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_1952_bfc1d310 | Import Products | 2020-12-28 | 2021-01-03 | Configuration | Mid-America: Odoo Implementation (P37) | Levi Barnes | Nick Foy | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-21 20:25 | TRUE | Mid-America Gardens, LLC | 1.8125 | 10 | 14.4119 | 80 | 2020-12-28 | Complete | Naseeb Razaq | Done | FALSE | External - 3rd Party | Nick Foy | 2020-12-18 06:48 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Download from existing site</p><p>Create import friendly file</p><p>Test import in staging</p><p>Verify</p><p>Repeat in Live</p> | 2021-01-01 04:23 | 7385 | 0 | 0 | 0 | 0 | Normal | Sprint 2053
__export__.project_task_1639_74968361 | Continuanat deployment | 2020-11-16 | 2020-11-22 | Configuration | Continuant: Power BI Integration (P30) | Muzher Siddique | FALSE | 0.5 | 0.5 | -0.5 | 0 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-11-23 22:32 | FALSE | Continuant | 0 | 0.6875 | 0 | 5.4422 | 2020-11-16 | Complete | Muhammad Zubair | Cancelled | FALSE |  | Muzher Siddique | 2020-11-23 22:32 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><br></p> | 2020-11-24 19:27 | 7970 | 0 | 0 | 0 | 0 | Normal | Sprint 2047
__export__.project_task_1396_fb4a497a | Auto Update for iOS:APP MAVEN | 2020-10-12 | 2020-10-18 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-10-09 22:08 | FALSE | Cellpoint Corporation | 0 | 2 | 0 | 16 | 2020-10-12 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Muhammad Afzaal | 2020-10-09 22:08 | Cellpoint Corporation | FALSE | Apps Maven | <p><br></p> | 2020-10-13 23:11 | 9050 | 0 | 0 | 0 | 0 | Normal | Sprint 2042
__export__.project_task_1083_64302271 | Product Mapping: GFK to Ingram Micro | 2020-08-17 | 2020-08-23 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-14 20:42 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-17 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-14 20:42 | Continuant | FALSE | FALSE | <p>Identify what data is necessary to map GFK products to Ingram Micro Products. </p> |  | 10395 | 0 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_954_5c3cdf19 | Add Product Pricing Uplift | 2020-08-17 | 2020-08-23 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-17 20:58 | FALSE | Continuant | 5.875 | 0 | 46.9594 | 0 | 2020-08-17 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-08 01:47 | Continuant | FALSE | FALSE | <p>Product Pricing uplift will be 1.36. </p> |  | 10558 | 0 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_926_1663553d | API:Lot view :Postman | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-29 12:26 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-29 12:26 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10788 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_911_e6eeb087 | Manifest API Android-Implementation | 2020-08-17 | 2020-08-23 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:46 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00016651 | 0 | 2020-08-17 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 2 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_897_015ebe45 | Product status Android-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_813_a9894bd8 | Login API iOS-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_557_d7bba3fc | API:Logout | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:49 | FALSE | Cellpoint Corporation | 1.375 | 0 | 10.8092 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_546_b40fd201 | API:Location List | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:46 | FALSE | Cellpoint Corporation | 1.375 | 0 | 10.7622 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p>method: POST</p><p>Description: On the basis of this API user can get the List of Locations on a filter screen to get filtered data in the Auction list on the bases of location</p><p>Parameters: user_id ,verify_tocken </p><p>API checking the user in database table (res.partner) , verify the token and status. Fetch the location data from the table (cpbids.locations)</p><p>append location.id,location.name, data, status into JSON</p><p>retrieve the JSON Data</p><p><br></p><p><br></p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_4566_ce0d4d72 | Review the options on the Settings screen for Batch Payments | 2021-08-23 | 2021-08-29 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.5 | 0.5 | 0 | 100 | 2021-08-27 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-13 18:58 | TRUE | Zuma Sales LLC | 0 | 5 | 0 | 40 | 2021-08-23 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-13 18:58 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-08-23 14:09 | 1661 | 0.5 | 0 | 0 | 0 | Normal | Sprint 2135
__export__.project_task_4533_5e1968ce | On Delivery Order (stock.picking) changes | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 3.42 | 3.42 | 3.58 | 48.86 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-12 05:28 | TRUE | Cellpoint Corporation | 0 | 11.6875 | 0 | 93.4244 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-08-12 05:28 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><font class="text-black">1. Destination Package should contain list of Packages (Master Carton) too (attached screenshot for reference)</font></p><p><font class="text-black">2. On Delivery Order, Under Source Document need the field of Customer Reference (This should be taken from Sales Order &gt; Other info tab &gt; Customer Reference)</font></p><p><font class="text-black">3. Need to have fields for Dimensions of Package (Height, Width, Length)</font></p><p><font class="text-black">4. ASN-1 csv file need to be generated from print option (Right now only option of UEDF ASN Report xml file is there)</font></p><p><font class="text-black">5. On Delivery Order, under Parent Package field need to show the Parent Package there (Right now nothing is showing) - (attached screenshot is for reference).</font></p> | 2021-08-31 02:25 | 1699 | 7 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3232_be66366f | Gifts in different section on delivery order | 2021-03-29 | 2021-04-04 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Raheel Aslam | 4.17 | 4.17 | 0.33 | 92.67 |  | 2 | Complete | TRUE | Muhammad Saqlain Alam | 2021-03-25 16:33 | TRUE | Mid-America Gardens, LLC | 0 | 16.5625 | 1.9563e-05 | 132.4492 | 2021-03-29 | Complete | Naseeb Razaq | Done | FALSE |  | Fahad Hussain Malik | 2021-03-25 16:33 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>I have added the whole video with all the description required to create and solve the issue. </p><p>The customer needs to have separate sections of gifts on the delivery order print slip in alphabetical order. </p><p>Time: 3:35 to 6:00</p> | 2021-04-18 00:35 | 5047 | 4.5 | 0 | 0 | 0 | Normal | Sprint 2114
__export__.project_task_2746_766308b6 | AV IQ Credentials |  |  | Other | Continuant: Quotation Management / Automation (P31) | Nick Foy | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | Fahad Hassan | 2021-02-13 20:27 | FALSE | Continuant | 0 | 0 | 0 | 0 |  | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2021-02-13 20:27 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>User Name: Continuant</p><p>Password: Kehotgs$5467</p><p>Client Id: 7c9c9a1772a74d37b3c5a6bfc94e0669</p><p>UID: Continuant</p><p>Manufacturers URL: http://api-v2.av-iq.com:9100/software/v3.1/get/getmanufacturersjson</p><p>Products Url: http://api-v2.av-iq.com:9100/software/v3.1/get/getproductsjs </p><p>Products Url Specs: http://api-v2.av-iq.com:9100/software/v3.1/get/getproductspecsjson</p> | 2021-02-13 20:32 | 6004 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_2707_14f74b7e | Set discussion for how to track credit card receipts and deal with expense reports. |  |  | Configuration | Wild Leaf: Accounting (P64) | Jeff Gross | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Cancelled | TRUE | Muhammad Saqlain Alam | 2021-03-06 03:01 | FALSE | Wild Leaf Beverage | 20 | 65.9375 | 160 | 527.5608 |  | Cancelled | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2021-02-06 06:22 | Wild Leaf Beverage, Ryan Mason | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-05-10 21:34 | 6186 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_2643_ebc668fa | Mid America Deployment 2104 | 2021-02-01 | 2021-02-07 | Other | Mid-America: Odoo Implementation (P37) | Levi Barnes | Muzher Siddique | 1.67 | 1.67 | -0.67 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-02-02 15:36 | TRUE | Mid-America Gardens, LLC | 0 | 0.25 | 0 | 1.899 | 2021-02-01 | Complete | Naseeb Razaq | Done | FALSE |  | Muzher Siddique | 2021-02-02 15:36 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Deployed 2316.2317, 2318, 2319 in deployment_2104 branch.</p> | 2021-02-02 18:30 | 6272 | 1 | 0 | 0 | 0 | Normal | Sprint 2107
__export__.project_task_2261_9774b946 | Deployment of Propertyworx 2101 | 2021-01-11 | 2021-01-17 | Configuration | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 0.25 | 0.25 | 0 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-12 16:56 | TRUE | EquityTeam | 0 | 0 | 0 | 0.18662 | 2021-01-11 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Muzher Siddique | 2021-01-12 16:56 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>2161 deployed on production.</p> | 2021-01-12 18:08 | 6775 | 0.25 | 0 | 0 | 0 | Normal | Sprint 2103
__export__.project_task_2103_7a204ac0 | Bank Details | 2021-01-04 | 2021-01-10 | Development | Silverdale: Help (P12) | Muhammad Afzaal | Kaleem Khan | 2.17 | 2.17 | -0.17 | 100 |  | FALSE | Complete | TRUE | FALSE | 2021-01-04 18:37 | FALSE | Silverdale Technology LLC | 0 | 0.3125 | 0.058871 | 2.7203 | 2021-01-04 | Complete | Muhammad Zubair | InProgress | FALSE |  | Muzher Siddique | 2021-01-04 18:33 | Silverdale Technology LLC, Nick Foy | Executive / Mechanisms | Silverdale Technology LLC | <p>Add new fields in res.partner.bank</p><p>Branch City</p><p>Branch code<br></p><p>IBAN#</p><p><br></p> | 2021-01-04 21:17 | 6965 | 2 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_1314_0c3c6ad1 | Mark Bids for Web/APP | 2020-10-05 | 2020-10-11 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | FALSE | 6 | 6 | -6 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-29 20:51 | FALSE | Cellpoint Corporation | 0 | 5.625 | 0 | 45.1497 | 2020-10-05 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Muhammad Afzaal | 2020-09-29 20:51 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> | 2020-10-07 17:43 | 9291 | 0 | 0 | 0 | 0 | Normal | Sprint 2041
__export__.project_task_1164_d8d03cee | Check Out Process: Input Email | 2020-09-07 | 2020-09-13 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-29 04:10 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-09-07 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-29 04:10 | Continuant | FALSE | FALSE | <p>During the checkout process, on the address page, there should be a list of contacts within the selected customer and also an Add customer contact button that allows you to create a new contact in that company with fields for first name, last name, email, phone number. </p> |  | 10052 | 0 | 0 | 0 | 0 | Normal | Sprint 30
__export__.project_task_1159_119f7ec7 | All Buyers | 2020-08-24 | 2020-08-30 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-28 16:59 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-24 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-08-28 16:59 | Cellpoint Corporation | FALSE | FALSE | <p> if I am not selecting any buyers in invite buyer </p><p>Auctions are not showing to all buyers assigned to that seller </p><p><br></p><p>At the moment we can only see an auction as buyer if that buyer is invited to that auction </p> |  | 10063 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_1136_9625007a | Mail Server Issue | 2020-08-24 | 2020-08-30 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-26 19:34 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-24 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-26 19:34 | Continuant | FALSE | FALSE | <p>This task was created to track an issue with the mail server. Emails are not being sent on Anusha's local so she's going to test again on the server. </p> |  | 10108 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_1100_ca13141f | Number of Views not populated | 2020-08-24 | 2020-08-30 | Bug Fix | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-24 10:12 | FALSE | Cellpoint Corporation | 5 | 0 | 40 | 0 | 2020-08-24 | Complete | Muhammad Afzaal | Done | FALSE |  | Nick Foy | 2020-08-15 23:48 | Cellpoint Corporation | FALSE | FALSE | <p>On Auction Details screen, Number of Views not populated</p> |  | 10368 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_972_abf856f3 | Post and Rename Database Versions | 2020-08-10 | 2020-08-16 | Configuration | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-11 21:48 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-10 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-11 21:48 | Continuant | FALSE | FALSE | <p><br></p> |  | 10466 | 0 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_843_144dc28b | Manifest API iOS-Implementation | 2020-08-17 | 2020-08-23 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-08-17 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 2 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_836_1351c626 | Logout iOS-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_816_bb2db51c | Auction detail iOS-Implementation | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 2 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_599_32831466 | API:Update Terms and condition:APPMAVEN | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 3 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-23 12:02 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-23 12:02 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10932 | 3 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_4561_2fdb7086 | Review the options on the Settings screen for Online Payment of Invoices | 2021-08-23 | 2021-08-29 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.25 | 0.25 | 0.25 | 50 | 2021-08-27 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-13 18:55 | TRUE | Zuma Sales LLC | 0 | 8.5 | 0 | 68.0406 | 2021-08-23 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-13 18:55 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-08-27 01:02 | 1661 | 0.5 | 0 | 0 | 0 | Normal | Sprint 2135
__export__.project_task_4444_15e19088 | For different products should export different UEDF ASN xml files | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 8.08 | 8.08 | 1.92 | 80.8 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-05 18:45 | TRUE | Cellpoint Corporation | 0 | 16.6875 | 0 | 133.4244 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-08-05 18:45 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Associated Task: <a href="/web#id=4378&amp;action=443&amp;model=project.task&amp;view_type=form&amp;cids=1&amp;menu_id=295">Split UEDF by SKU (UEDF ASN xml) Task<br></a></p><p><br></p><p>1. The UEDF ASN xml file should be generated according to the the serials that have an NMS received and the conditions mentioned in associated task. </p><p>2. If the serials are related to multiple products, multiple xml files should be generated for those respective products. (Example if Serials are related to 5 products then 5 xml files should be generated. </p> | 2021-08-31 02:25 | 1853 | 10 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3424_4a39f946 | Back-up existing odoo.sh install | 2021-05-31 | 2021-06-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | FALSE | 0 | 0 | 0 | 0 | 2021-06-06 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-07-19 19:00 | TRUE | Zuma Sales LLC | 57.6875 | 35.625 | 461.3447 | 284.8994 | 2021-05-31 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-04-23 21:40 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-06-17 18:34 | 4346 | 0 | 0 | 0 | 0 | Normal | Sprint 2123
__export__.project_task_3229_4070d9f9 | In a single SO with multiple invoices showing extra Delivery charges | 2021-03-29 | 2021-04-04 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Raheel Aslam | 7.33 | 7.33 | -0.49667 | 100 |  | 2 | Complete | TRUE | Muhammad Saqlain Alam | 2021-03-25 15:51 | TRUE | Mid-America Gardens, LLC | 0 | 16.625 | 4.7506e-05 | 133.1478 | 2021-03-29 | Complete | Naseeb Razaq | Done | FALSE |  | Naseeb Razaq | 2021-03-25 15:51 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><br></p> | 2021-04-18 00:35 | 5048 | 6.8333 | 0 | 0 | 0 | Normal | Sprint 2114
__export__.project_task_2314_526eeb39 | paypal | 2021-01-25 | 2021-01-31 | Configuration | Mid-America: Odoo Implementation (P37) | Levi Barnes | Levi Barnes | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-14 21:21 | TRUE | Mid-America Gardens, LLC | 0 | 33.8125 | 0 | 270.7362 | 2021-01-25 | Complete | Naseeb Razaq | Done | FALSE |  | Levi Barnes | 2021-01-14 21:21 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>install paypal payment acquirer</p> | 2021-03-03 20:05 | 6723 | 0 | 0 | 0 | 0 | Normal | Sprint 2105
__export__.project_task_2256_29597099 | AV Warehouse Demo | 2021-01-11 | 2021-01-17 | Configuration | Continuant: AV Warehouse (P34) | Kaesi Lee | FALSE | 0.75 | 0.75 | -0.75 | 0 |  | FALSE | Complete | TRUE | Fahad Hassan | 2021-01-12 04:25 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2021-01-11 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2021-01-12 04:25 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><br></p> | 2021-01-12 04:26 | 6788 | 0 | 0 | 0 | 0 | Normal | Sprint 2103
__export__.project_task_304_3c8e4033 | Universal Appointments and Time Reservations |  |  | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-11 22:53 | TRUE | EquityTeam | 0 | 6.875 | 0 | 54.9253 |  | Complete | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2021-01-11 22:53 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>please fill in the blanks on this spreadsheet about this app.</p><p><br></p><p>https://docs.google.com/spreadsheets/d/1Mb_ufEv9l1woI1SfPubYEGydg_WXJ7VryAtDguHMMNw/edit#gid=0 </p><p><br></p><p>This seems like a great way to schedule for inspections but also for any home service, possibly even free consultation appointments with our Portfolio Managers with EquityTeam. I don't see anything else like this in Odoo but this seems like a must have for a service based business like us. It's refreshing to find an app that seems like it is designed for a service based business with flexibility.</p><p><br></p><p>Add all your notes and info to the spreadsheet please and if you want to add more details here, please do so in this task, OR let's plan to add this to a meeting to review over the phone.</p><p><br></p><p><br></p><p><br></p><p><br></p> | 2021-01-20 20:56 | 6793 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_2122_ff9c8a65 | General 2101 | 2021-01-04 | 2021-01-10 | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 1.5 | 1.5 | -1.5 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-05 19:33 | TRUE | EquityTeam | 0 | 4.3125 | 0.010522 | 34.4536 | 2021-01-04 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2021-01-05 19:33 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-01-11 23:34 | 6940 | 0 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_1682_df715f9a | Deployment Continuant: Quotation Management / Automation | 2020-11-23 | 2020-11-29 | Configuration | Continuant: Quotation Management / Automation (P31) | Muzher Siddique | FALSE | 1 | 1 | -0.5 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-12-01 16:55 | FALSE | Continuant | 0 | 0 | 0 | 0.083287 | 2020-11-23 | Complete | Muhammad Zubair | Done | FALSE |  | Muzher Siddique | 2020-12-01 16:55 | Continuant, Allison Beers | Executive / Delivery / Bravo | FALSE | <p><br></p> | 2020-12-01 17:51 | 7783 | 0.5 | 0 | 0 | 0 | Normal | Sprint 2048
__export__.project_task_1114_456f3c64 | Ingram: Generate Shipping Quotation | 2020-08-24 | 2020-08-30 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-18 01:39 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-24 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-18 01:39 | Continuant | FALSE | FALSE | <p>Dropship functionality will require a shipping quotation. Please use the following link for API documentation specific to this function. </p><p><br></p><p><a href="https://developer.ingrammicro.com/reseller-api-reference/reseller-order-apis#/orders/post-v5-orders-create">https://developer.ingrammicro.com/reseller-api-reference/reseller-order-apis#/orders/post-v5-orders-create</a><br></p> |  | 10318 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_1099_71998229 | Number of mywatch bidders not populated | 2020-08-24 | 2020-08-30 | Bug Fix | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-28 18:28 | FALSE | Cellpoint Corporation | 9.5625 | 0 | 76.465 | 0 | 2020-08-24 | Complete | Muhammad Afzaal | Done | FALSE |  | Nick Foy | 2020-08-15 23:48 | Cellpoint Corporation | FALSE | FALSE | <p>On Auction Details screen, Number of mywatch bidders not populated</p> |  | 10368 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_941_4c019893 | Carrier: Test Dropship Functionality | 2020-08-03 | 2020-08-09 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-03 22:37 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-03 22:37 | Continuant | FALSE | FALSE | <p><br></p> |  | 10657 | 0 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_934_fa5366ff | API:Get Batch Api:Postman | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-30 19:55 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-30 19:55 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10756 | 1 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_881_efa022bf | Login API Android-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_838_2247152a | Notification list iOS-Implementation | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_595_28c190a8 | API:Select City:APPMAVEN | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 3 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-23 11:59 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-23 11:59 | Cellpoint Corporation | FALSE | FALSE | <p><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.5);'> </span><br></p> |  | 10932 | 3 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_539_7ecca02d | API:Version updation | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-23 11:57 | FALSE | Cellpoint Corporation | 3 | 0 | 24 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p>method: POST </p><p>Description: This API is only to check the currently running version or for term and condition updation.if a user is not using the latest version then this API throws the alert to update API. Also if the user has not accepted the latest term condition it also throws alert.</p><p>Parameter : user_id </p><p>API will check the user existence, Fetch the data from the table (cpbid.version) with the condition (cpbid_status=active)</p><p>append data like android_version,ios_version,admin_term_version,term_version,term_link into json data</p><p>Retrive json data</p><p><br></p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_246_9556444d | Signup all on staging AWS | 2020-08-17 | 2020-08-23 | Development | Silverdale: Help (P12) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-08 21:08 | FALSE | Silverdale Technology LLC | 0 | 0 | 0 | 0 | 2020-08-17 | Complete | Muhammad Zubair | InProgress | FALSE |  | Muhammad Afzaal | 2020-07-08 21:08 | Silverdale Technology LLC | FALSE | FALSE | <p><br></p> |  | 11283 | 0 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_4556_aa5f93d2 | Set the clearing/suspense account on the Inventory Adjustment location so your summary suspense balance is cleared when the adjustment completes. | 2021-08-30 | 2021-09-05 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 | 0.16667 | 0 | 2021-09-03 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-13 18:45 | TRUE | Zuma Sales LLC | 0 | 13 | 0 | 104 | 2021-08-30 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-13 18:45 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p> </p> | 2021-09-02 18:30 | 1661 | 0.16667 | 0 | 0 | 0 | Normal | Sprint 2136
__export__.project_task_4539_4421c10f | Package and Parent Package label numbers | 2021-08-16 | 2021-08-22 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 5.5 | 5.5 | 0.5 | 91.67 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-12 19:05 | TRUE | Cellpoint Corporation | 0 | 11.6875 | 0 | 93.4244 | 2021-08-16 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-08-12 19:05 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Package reference number on stock.quant.package should be according to these conditions (Conditions document attached for reference):</p><p><br></p><p>1. First two digits 00</p><p>2. Next two digits 00</p><p>3. Next 6 digits should be extracted from the barcode of product.template.</p><p>4. Next 9 digits 123456789 are used to number the packages or parent packages, the number sequence shall only be used once and is not to be repeated. </p><p>5. Last digit is a Check Sum digit (It will change for each different Serial Number Range. </p><p><br></p><p><font class="bg-black">UPDATE 15 AUG:</font></p><p><br></p><p>1. Label numbers should be assigned as soon as the package is created.</p><p>2. The first 10 digits are static (this is the same for Package and Parent Package) which include: </p><ul></ul><ul></ul><ul></ul><div style="color: rgb(0, 0, 0); font-size: medium;"><table width="166" style="width: 125pt;"><colgroup><col width="166" style="width: 125pt;"></colgroup><tbody><tr height="20" style="height: 15pt;"><td width="166" height="20" style="padding-top: 1px; padding-right: 1px; padding-left: 1px; font-size: 11pt; font-family: Calibri, sans-serif; vertical-align: bottom; border: none; white-space: nowrap; width: 125pt; height: 15pt;"><b>0000760492</b></td></tr><tr height="20" style="height: 15pt;"><td width="166" height="20" style="padding-top: 1px; padding-right: 1px; padding-left: 1px; font-size: 11pt; font-family: Calibri, sans-serif; vertical-align: bottom; border: none; white-space: nowrap; width: 125pt; height: 15pt;">3. Next 9 digits are not to be repeated and sequence should start from:</td></tr><tr height="20" style="height: 15pt;"><td width="166" height="20" style="padding-top: 1px; padding-right: 1px; padding-left: 1px; font-size: 11pt; font-family: Calibri, sans-serif; vertical-align: bottom; border: none; white-space: nowrap; width: 125pt; height: 15pt;"><div style="font-size: medium; white-space: normal;"><table width="166" style="width: 125pt;"><colgroup><col width="166" style="width: 125pt;"></colgroup><tbody><tr height="20" style="height: 15pt;"><td width="166" height="20" style="padding-top: 1px; padding-right: 1px; padding-left: 1px; font-size: 11pt; font-family: Calibri, sans-serif; vertical-align: bottom; border: none; white-space: nowrap; width: 125pt; height: 15pt;"><div style="font-size: medium; white-space: normal;"><table width="166" style="width: 125pt;"><colgroup><col width="166" style="width: 125pt;"></colgroup><tbody><tr height="20" style="height: 15pt;"><td width="166" height="20" style="padding-top: 1px; padding-right: 1px; padding-left: 1px; font-size: 11pt; font-family: Calibri, sans-serif; vertical-align: bottom; border: none; white-space: nowrap; width: 125pt; height: 15pt;">For Master Carton (Package) 000006230<br>For Pallet (Parent Package) 130000000<br><div style="font-size: medium; white-space: normal;"><br></div></td></tr><tr height="20" style="height: 15pt;"><td width="166" height="20" style="padding-top: 1px; padding-right: 1px; padding-left: 1px; font-size: 11pt; font-family: Calibri, sans-serif; vertical-align: bottom; border: none; white-space: nowrap; width: 125pt; height: 15pt;">4. The last digit of the labelling should be calculated with following conditions:</td></tr><tr height="20" style="height: 15pt;"><td width="166" height="20" style="padding-top: 1px; padding-right: 1px; padding-left: 1px; font-size: 11pt; font-family: Calibri, sans-serif; vertical-align: bottom; border: none; white-space: nowrap; width: 125pt; height: 15pt;">- Starting from the 3rd digit of the label number and ending at the 19th Digit.<br>- Sum of all those digits<br>-The last digit of the sum should be taken and included as the last digit of the label number. <br><br><font style="color: rgb(255, 0, 0);">Example: </font><div style="font-size: medium; white-space: normal;"><table width="166" style="width: 125pt;"><colgroup><col width="166" style="width: 125pt;"></colgroup><tbody><tr height="20" style="height: 15pt;"><td width="166" height="20" style="padding-top: 1px; padding-right: 1px; padding-left: 1px; font-size: 11pt; font-family: Calibri, sans-serif; vertical-align: bottom; border: none; white-space: nowrap; width: 125pt; height: 15pt;"><font style="color: rgb(255, 0, 0);">00</font><b><font style="background-color: rgb(0, 255, 0); color: rgb(41, 82, 24);">00760492000006229</font></b><font style="color: rgb(0, 0, 255);"><b>7</b></font><font style="color: rgb(255, 0, 0);"> - If this is the label number, lets see how 7 is calculated:</font></td></tr><tr height="20" style="height: 15pt;"><td width="166" height="20" style="padding-top: 1px; padding-right: 1px; padding-left: 1px; font-size: 11pt; font-family: Calibri, sans-serif; vertical-align: bottom; border: none; white-space: nowrap; width: 125pt; height: 15pt;"><font style="color: rgb(255, 0, 0);">Taking sum of the digits in bold green color 0+0+7+6+0+4+9+2+0+0+0+0+0+6+2+2+9=47 , therefore the last digit of the sum is 7 and that is taken as the last digit of the label number.<br><br>New Update 16/7 5:59:<br><p style='color: rgb(102, 102, 102); font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; white-space: normal;'>Now That We Are Not Using Product Bar Code Under Our Sequience Lable For Packing</p><p style='color: rgb(102, 102, 102); font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; white-space: normal;'><br></p><p style='color: rgb(102, 102, 102); font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; white-space: normal;'>First 10 Static Digits <span style="color: rgb(255, 0, 0); font-family: Calibri, sans-serif; font-size: 14.6667px; font-weight: bolder; text-align: inherit; white-space: nowrap;">0000760492</span><br><br>Next 9 <span style="color: rgb(255, 0, 0); font-family: Calibri, sans-serif; font-size: 14.6667px; font-weight: inherit; text-align: inherit; white-space: nowrap;">For Master Carton (Package) 000006230</span></p><p style='color: rgb(102, 102, 102); font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; white-space: normal;'><span style="color: rgb(255, 0, 0); font-family: Calibri, sans-serif; font-size: 14.6667px; white-space: nowrap;"> For Pallet (Parent Package) 130000000</span><br><span style="color: rgb(255, 0, 0); font-family: Calibri, sans-serif; font-size: 14.6667px; white-space: nowrap;">Note:: System Should Increment Against These 9 digits Only upon new creations</span><br><br><span style="color: rgb(255, 0, 0); font-family: Calibri, sans-serif; font-size: 14.6667px; white-space: nowrap;"><br></span></p><p style='color: rgb(102, 102, 102); font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; white-space: normal;'><br></p><p style='color: rgb(102, 102, 102); font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; white-space: normal;'>Last Digit Index Addition 2+---+18</p><p style='color: rgb(102, 102, 102); font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; white-space: normal;'></p><p style='color: rgb(102, 102, 102); font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; white-space: normal;'></p><p style='color: rgb(102, 102, 102); font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; white-space: normal;'><br></p><p style='color: rgb(102, 102, 102); font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; white-space: normal;'></p><p style='color: rgb(102, 102, 102); font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; white-space: normal;'></p>i.e If Sum =24----&gt; Fetch 4 If Sum = 189 ------&gt; Fetch 9 As Last Digit </font></td></tr></tbody></table></div></td></tr><tr height="20" style="height: 15pt;"><td width="166" height="20" style="padding-top: 1px; padding-right: 1px; padding-left: 1px; font-size: 11pt; font-family: Calibri, sans-serif; vertical-align: bottom; border: none; white-space: nowrap; width: 125pt; height: 15pt;"><br></td></tr></tbody></table></div></td></tr></tbody></table></div></td></tr></tbody></table></div> | 2021-08-31 02:25 | 1685 | 6 | 0 | 0 | 0 | Normal | Sprint 2134
__export__.project_task_3228_d9f62e8d | Gift prices reflect in delivery report | 2021-04-05 | 2021-04-11 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Raheel Aslam | 2.42 | 2.42 | 0.58 | 80.67 |  | 3 | Complete | TRUE | Muhammad Saqlain Alam | 2021-03-25 15:44 | TRUE | Mid-America Gardens, LLC | 0 | 16.6875 | 0 | 133.2604 | 2021-04-05 | Complete | Naseeb Razaq | Done | FALSE |  | Naseeb Razaq | 2021-03-25 15:44 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>There are two types of delivery report</p><p>1. Delivery slip</p><p>2. Delivery slip with price</p><p><br></p><p>In the second report, the price for gift item should not be reflected. </p> | 2021-04-18 00:35 | 5048 | 3 | 0 | 0 | 0 | Normal | Sprint 2115
__export__.project_task_2705_1d8e96db | Set bank connections for WildPack Beverage Inc. (CIBC - CDN bank) |  |  | Configuration | Wild Leaf: Accounting (P64) | Jeff Gross | FALSE | 0 | 0 | 0 | 0 | 2021-06-25 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-03-06 03:01 | FALSE | Wild Leaf Beverage | 20 | 85.6875 | 160 | 685.6175 |  | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2021-02-06 06:22 | Wild Leaf Beverage, Ryan Mason | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-06-10 19:37 | 6186 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_2317_0d34706a | shopping ux | 2021-01-25 | 2021-01-31 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Muzher Siddique | 3.83 | 3.83 | 1.17 | 76.6 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-14 21:22 | TRUE | Mid-America Gardens, LLC | 0 | 33.8125 | 0 | 270.6823 | 2021-01-25 | Complete | Naseeb Razaq | Done | FALSE |  | Levi Barnes | 2021-01-14 21:22 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | The content of this cell is too long for an XLSX file (more than 32767 characters). Please use the CSV format for this export. | 2021-03-03 20:03 | 6723 | 5 | 0 | 0 | 0 | Normal | Sprint 2105
__export__.project_task_202_0343330d | Activity Bundle |  |  | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-11 22:53 | TRUE | EquityTeam | 0 | 6.875 | 0 | 54.9275 |  | Complete | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2021-01-11 22:53 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>see about replicating this:</p><p><br></p><p>https://apps.odoo.com/apps/modules/14.0/schedule_activity_bundle/<br></p> | 2021-01-20 20:56 | 6793 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_2137_7b136c11 | Consignment Receiving Training | 2021-01-04 | 2021-01-10 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | FALSE | 0.5 | 0.5 | -0.5 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-06 02:16 | TRUE | Wild Leaf Beverage | 0 | 1.75 | 0 | 14.1469 | 2021-01-04 | Complete | Abdul Hameed | In Warranty | FALSE |  | Kaesi Lee | 2021-01-06 02:16 | Wild Leaf Beverage, Thomas Walker_ | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-01-07 20:09 | 6934 | 0 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_2053_17cd0fa8 | Deployment of Continuant AV Warehouse | 2020-12-21 | 2020-12-27 | Configuration | Continuant: AV Warehouse (P34) | Kaesi Lee | Muzher Siddique | 0.5 | 0.5 | 0.5 | 50 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-12-29 17:43 | FALSE | Continuant | 0 | 0.0625 | 0 | 0.25028 | 2020-12-21 | Complete | Muhammad Zubair | Done | FALSE |  | Muzher Siddique | 2020-12-29 17:43 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>1840 deployed and av_tracker module needs to be upgrade.</p> | 2020-12-29 18:15 | 7110 | 1 | 0 | 0 | 0 | Normal | Sprint 2052
__export__.project_task_1120_d358bc20 | Ingram: Obtain Order Confirmation | 2020-08-24 | 2020-08-30 | Development | Continuant: eCommerce (P9) | Gadha Continuant | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-21 21:13 | FALSE | Continuant | 3.875 | 0 | 31.2225 | 0 | 2020-08-24 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-18 01:45 | Continuant | FALSE | FALSE | <p>Use the distributor API to obtain a customer's order confirmation. </p> |  | 10318 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_1118_0fd66f4c | Synnex: Obtain Order Confirmation | 2020-08-24 | 2020-08-30 | Development | Continuant: eCommerce (P9) | Gadha Continuant | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-21 21:14 | FALSE | Continuant | 3.875 | 0 | 31.2325 | 0 | 2020-08-24 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-18 01:44 | Continuant | FALSE | FALSE | <p>Use the distributor API to obtain a customer's order confirmation. </p> |  | 10318 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_1080_bb6aa0ff | Product Mapping: GFK to Tech Data | 2020-08-17 | 2020-08-23 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-14 20:41 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-17 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-14 20:41 | Continuant | FALSE | FALSE | <p>Identify what data is necessary to map GFK products to Tech Data Products. </p> |  | 10395 | 0 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_922_7ecf0f1c | API:Get List of MarketPlaces:Postman | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 0.5 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-29 11:42 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-29 11:42 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10788 | 0.5 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_902_225ab054 | Change passord Android-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:46 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00016651 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_832_48c02911 | My watch product list iOS-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 2 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_821_37e10709 | Select country iOS-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_561_b80eea6a | API:My Bids | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 6 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:39 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.6561 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>1, Create a URL </p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>2, Fetch all Products / Bids </p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>3, Sharing response over API</p> |  | 11009 | 6 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_558_2ed97dad | API:Forcefully Update | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:49 | FALSE | Cellpoint Corporation | 1.375 | 0 | 10.8214 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p>method: GET</p><p>Description: This API forces the user to update the app if the user is not having the latest version of the app</p><p>Fetch the data from the table (cpbids.versions)</p><p>append android ios data into JSON </p><p>retrieve the JSON data </p><p><br></p><p><br></p><p><br></p><p><br></p><p><br></p><p><br></p><p><br></p><p> </p><p><br></p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_172_8f3780eb | Date and Time for Pictures | 2020-08-17 | 2020-08-23 | Studio | Heronswood: Events (P3) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 | 2020-06-04 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-06-02 19:53 | FALSE | Port Gamble S’Klallam Foundation | 0 | 0 | 0 | 0 | 2020-08-17 | Complete | Naseeb Razaq | Done | FALSE |  | Nick Foy | 2020-06-02 19:53 | Port Gamble S’Klallam Foundation, Ross Bayton | Executive / Delivery / Alpha | FALSE | <p>When a User uploads a picture to any of the Picture fields in My Collection, they want to see the date and time of the picture.</p><p><br></p> |  | 12148 | 0 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_4554_bf3d6346 | Enter your default Terms & Conditions. | 2021-08-23 | 2021-08-29 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.17 | 0.17 | -0.0033333 | 100 | 2021-09-01 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-13 18:44 | TRUE | Zuma Sales LLC | 0 | 7 | 0 | 56 | 2021-08-23 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-13 18:44 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>Asfand needs to get info from the client, </p> | 2021-08-25 17:49 | 1661 | 0.16667 | 0 | 0 | 0 | Normal | Sprint 2135
__export__.project_task_4528_e69c2856 | Phone check import successful message | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Kaleem Khan | 5.58 | 5.58 | 0.42 | 93 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-12 00:54 | TRUE | Cellpoint Corporation | 0 | 8.1875 | 0 | 65.4233 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-08-12 00:54 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>1. When phone check import is done successfully it should display a message - Phone Check import is successful</p><p>2. IMEI2 field on Serial form should not be mandatory</p><p> </p> | 2021-08-25 02:25 | 1703 | 6 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3426_4d553775 | Configure the file system on the servers |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-07-19 18:59 | TRUE | Zuma Sales LLC | 57.6875 | 65.0625 | 461.3158 | 520.3435 |  | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-04-23 21:41 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-07-30 00:22 | 4346 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_3422_5d45b40c | Acquiring the Master Data as appropriate (I would make multiple tasks for each set of data) | 2021-06-21 | 2021-06-27 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | FALSE | 0 | 0 | 0 | 0 | 2021-06-25 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-07-19 18:59 | TRUE | Zuma Sales LLC | 57.6875 | 42.0625 | 461.3401 | 336.3487 | 2021-06-21 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-04-23 21:39 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-06-26 01:01 | 4346 | 0 | 0 | 0 | 0 | Normal | Sprint 2126
__export__.project_task_3222_7bf838e1 | Language switcher to Chinese not working for auction list |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 4.33 | 4.33 | -1.33 | 100 |  | 3 | Complete | TRUE | Fahad Hassan | 2021-03-24 19:54 | FALSE | Cellpoint Corporation | 0 | 17.25 | 0 | 138.1019 |  | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Bilal Ahmad Khan | 2021-03-24 19:54 | Cellpoint Corporation, Ehsan Gharatappeh | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>This task will: Fix the button which is used to switch to the Chinese language.</p><p><br></p><p>What are you trying to accomplish?</p><p>when the language switcher button is pressed, it should be switching to the Chinese language.</p> | 2021-04-18 00:42 | 5068 | 3 | 0 | 0 | 0 | Normal
__export__.project_task_2657_9c2831d4 | Deployment continuant Unit Test | 2021-02-01 | 2021-02-07 | Other | Continuant: Unit Testing (P51) | Kaesi Lee | Muzher Siddique | 2 | 2 | -2 | 0 |  | FALSE | Complete | TRUE | Fahad Hassan | 2021-02-04 00:12 | FALSE | Continuant | 0 | 1.5 | 0 | 12 | 2021-02-01 | Complete | Muhammad Zubair | Done | FALSE |  | Muzher Siddique | 2021-02-04 00:12 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><br></p> | 2021-02-05 17:06 | 6240 | 0 | 0 | 0 | 0 | Normal | Sprint 2107
__export__.project_task_2318_2188b37f | SO line item total count | 2021-01-25 | 2021-01-31 | Development | Mid-America: Odoo Implementation (P37) | Levi Barnes | Danish Hassan | 3.92 | 3.92 | -0.42 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-14 21:23 | TRUE | Mid-America Gardens, LLC | 0 | 33.8125 | 0 | 270.6868 | 2021-01-25 | Complete | Naseeb Razaq | Done | FALSE |  | Levi Barnes | 2021-01-14 21:23 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | The content of this cell is too long for an XLSX file (more than 32767 characters). Please use the CSV format for this export. | 2021-03-03 20:04 | 6723 | 3.5 | 0 | 0 | 0 | Normal | Sprint 2105
__export__.project_task_2164_0965579a | Belmont Azure Client Feedback:Export the invoices data,match column with schema | 2021-01-04 | 2021-01-10 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 4.5 | 4.5 | -4.5 | 0 |  | FALSE | Complete | TRUE | FALSE | 2021-01-07 16:46 | FALSE | Cellpoint Corporation | 0 | 12 | 9.6839e-05 | 96.232 | 2021-01-04 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Muzher Siddique | 2021-01-07 16:46 | Cellpoint Corporation | FALSE | Silverdale Technology LLC | <p><br></p> | 2021-01-25 17:30 | 6895 | 0 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_2109_a0c784ac | Says "not connected" to employee profile (#40) |  |  | Bug Fix | PWX: Help (P23) | Levi Barnes | Danish Hassan | 0.75 | 0.75 | 0.25 | 75 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-05 03:48 | TRUE | EquityTeam | 0 | 18 | 0 | 144 |  | Complete | Farman Ahmad Cheema | Done | FALSE | External - Client | Levi Barnes | 2021-01-05 03:48 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | The content of this cell is too long for an XLSX file (more than 32767 characters). Please use the CSV format for this export. | 2021-01-29 00:02 | 6956 | 1 | 0 | 0 | 0 | Normal
__export__.project_task_2025_1b35d0c6 | Deployment Continuant Power BI Integration 2051 | 2020-12-14 | 2020-12-20 | Configuration | Continuant: Power BI Integration (P30) | Kaesi Lee | Muzher Siddique | 0.28 | 0.28 | -0.28 | 0 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-12-22 18:27 | FALSE | Continuant | 0 | 0.875 | 4.1766e-05 | 7.2173 | 2020-12-14 | Complete | Muhammad Zubair | Cancelled | FALSE |  | Muzher Siddique | 2020-12-22 18:27 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>List of tasks Deployed.</p><p><br></p><p><img class="img-fluid o_we_custom_image img-thumbnail" src="/web/image/14178/Screenshot from 2020-12-22 18-26-37.png?access_token=5f2b8197-f4dc-472a-9da7-843c4ff7777b"><br></p> | 2020-12-23 16:40 | 7278 | 0 | 0 | 0 | 0 | Normal | Sprint 2051
__export__.project_task_900_934de814 | My watch product list Android-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:46 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00016651 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_556_690b3688 | API:Edit Profile | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 4 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:40 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.6658 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 11009 | 4 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_554_ee9f13af | API:Add to watchlist | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:40 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.6706 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 11009 | 0 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_553_da979c05 | API:MyWatch Product List | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 3 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:41 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.6758 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 11009 | 3 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_543_1cc4bf4e | API:Download csv | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:45 | FALSE | Cellpoint Corporation | 1.375 | 0 | 10.7508 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p>method: POST </p><p>Description: This API is used to send the manifest CSV to the user mail</p><p>parameters : product_id, user_email</p><p>API will check Product_id and email in the corresponding Table(res.partner). and send a mail with a message ( Manifest has been sent to your registered email ) </p><p>retrieve JSON data with same message </p><p><br></p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_356_8de90f87 | Sponsor Meeting #6 | 2020-08-24 | 2020-08-30 | Development | Continuant: eCommerce (P9) | Nick Foy | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0 | 0 | 0.00032117 | 0 | 2020-08-24 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE |  |  | 11092 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_354_f87dba42 | Sponsor Meeting #4 | 2020-08-10 | 2020-08-16 | Development | Continuant: eCommerce (P9) | Nick Foy | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0 | 0 | 0.00032117 | 0 | 2020-08-10 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE |  |  | 11092 | 0 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_273_aa455370 | Group Sellers - Marketplace | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan | FALSE | 0 | 0 | 12 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-15 15:30 | FALSE | Cellpoint Corporation | 0.125 | 0 | 1.2192 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-15 14:17 | Cellpoint Corporation | FALSE | FALSE | <p>Group Sellers under one Marketplace</p><p>We will have field available on seller view to assign seller to one of the available marketplaces </p> |  | 11122 | 12 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_201_edb7ed7b | Marketplace for Web | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan | FALSE | 0 | 0 | 16 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-15 15:29 | FALSE | Cellpoint Corporation | 15.625 | 0 | 125.0263 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-06-23 19:28 | Cellpoint Corporation | FALSE | FALSE | <p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 13.999999999999998pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 700; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">Seller</span></p><p><b id="docs-internal-guid-df0ba1d7-7fff-72da-b226-4ae132a9b5fb" style="caret-color: rgb(0, 0, 0); color: rgb(0, 0, 0); font-family: -webkit-standard; font-style: normal; font-variant-caps: normal; letter-spacing: normal; orphans: auto; text-align: start; text-indent: 0px; text-transform: none; white-space: normal; widows: auto; word-spacing: 0px; -webkit-text-size-adjust: auto; -webkit-text-stroke-width: 0px; text-decoration: none; font-weight: normal;"><br></b></p><p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">We have a master seller, main seller account that is launching auctions and all buyers has access to that seller’s auctions. </span></p><p><b style="caret-color: rgb(0, 0, 0); color: rgb(0, 0, 0); font-family: -webkit-standard; font-style: normal; font-variant-caps: normal; letter-spacing: normal; orphans: auto; text-align: start; text-indent: 0px; text-transform: none; white-space: normal; widows: auto; word-spacing: 0px; -webkit-text-size-adjust: auto; -webkit-text-stroke-width: 0px; text-decoration: none; font-weight: normal;"><br></b></p><p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">We also allow external sellers to launch their auctions through our platform and we use a marketplace option to separate their auctions from master and other sellers.</span></p><p><span style="caret-color: rgb(0, 0, 0); color: rgb(0, 0, 0); font-family: -webkit-standard;"></span><br class="Apple-interchange-newline" style="caret-color: rgb(0, 0, 0); color: rgb(0, 0, 0); font-family: -webkit-standard;"></p><p>We should be able to assign new sellers to marketplaces </p> |  | 11645 | 16 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_4552_e9dae999 | Define income, expense and cost of revenue accounts on your Product categories. | 2021-08-23 | 2021-08-29 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 | 0.16667 | 0 | 2021-08-27 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-13 18:43 | TRUE | Zuma Sales LLC | 0 | 9 | 0 | 72 | 2021-08-23 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-13 18:43 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>Asfand needs to get info from the client, </p> | 2021-08-27 17:49 | 1661 | 0.16667 | 0 | 0 | 0 | Normal | Sprint 2135
__export__.project_task_4527_7cb7813d | Done quantity should not be done on ASN Import | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 4.83 | 4.83 | 0.17 | 96.6 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-12 00:48 | TRUE | Cellpoint Corporation | 0 | 8.1875 | 0 | 65.4233 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-08-12 00:48 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>On Transfer form, when ASN is imported, the done quantities should not be done. It should be done when phone check file import is done.<br></p> | 2021-08-25 02:25 | 1703 | 5 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3425_1052bca2 | Create user accounts on the servers |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-07-19 18:59 | TRUE | Zuma Sales LLC | 57.6875 | 55.0625 | 461.3223 | 440.3309 |  | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-04-23 21:40 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-07-15 01:04 | 4346 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_3421_68caa507 | Discussion and finalization on what do we do with historical data |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-07-19 18:59 | TRUE | Zuma Sales LLC | 57.6875 | 45.75 | 461.3487 | 365.6117 |  | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-04-23 21:39 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-07-01 19:15 | 4346 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_3210_d3ab415d | Wildleaf: Add sale person as a follower in all invoices related to SO | 2021-03-29 | 2021-04-04 | Development | Wild Leaf: Help (P22) | Jeff Gross | Danish Hassan | 2.67 | 2.67 | -0.33667 | 100 |  | 2 | Complete | TRUE | Muhammad Saqlain Alam | 2021-03-23 17:48 | TRUE | Wild Leaf Beverage | 0 | 18.5 | 0 | 148 | 2021-03-29 | Complete | Abdul Hameed | In Warranty | FALSE |  | Umer Farooq | 2021-03-23 17:48 | Wild Leaf Beverage, Thomas Walker_ | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p><p>What are you trying to accomplish?</p><p>As a Sales person, I want to be added in the followers in all invoices related to the sales order so i can track the progress.</p><p><br></p><p>Pre-requisites:</p><p>Must have Customers set-up</p><p>Must have Sales Module</p><p>Sale order must be created</p><p>Sales person should be set in the other info tab on SO</p><p>Invoices must be created against the SO</p><p><br></p><p>User Steps:</p><p><br></p><p>1- Make sure customer is created and sale person is set </p><p>2- Create a sales order and make sure sale person is set in other info tab. By default, it should come from customer profile</p><p>3- Create an invoice</p><p><br></p><p><br></p><p>To Do:</p><p><br></p><p>The sale person should be added in followers in all invoices related to the sales order</p><p><br></p><p><br></p><p>Views and Filters:</p><p>None</p><p><br></p><p><br></p><p>Reports:</p><p>None</p><p><br></p><p>Security:</p><p><br></p><p>No changes to std User rights</p><p><br></p><p><br></p><p>list Of Dependencies</p> | 2021-04-18 00:35 | 5094 | 2.3333 | 0 | 0 | 0 | Normal | Sprint 2114
__export__.project_task_2674_9c87d50f | Move from Constant Contact to Odoo Email Marketing |  |  | Configuration | Heronswood: Help (P54) OLD DO NOT USE | Jeff Gross | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Cancelled | TRUE | Muhammad Saqlain Alam | 2021-03-06 03:06 | TRUE | Port Gamble S’Klallam Foundation | 21 | 50.8125 | 168 | 406.3022 |  | Cancelled | Naseeb Razaq | In Warranty | TRUE |  | Nick Foy | 2021-02-05 02:37 | Port Gamble S’Klallam Foundation, Ross Bayton | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>Set-up email marketing</p><p><br></p><p>Need to move over the media files to Odoo</p><p><br></p><p>Look at how the email list is coded i.e. how they split the email distributions</p><p><br></p><p>Volunteer coding is in excel</p><p><br></p><p>Most extensive list of interest emails</p><p><br></p><p>Training for Odoo email</p><p><br></p><p>Patrick</p><p>Ross</p><p>Joan</p><p><br></p><p><br></p> | 2021-04-16 20:18 | 6213 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_2121_ac9474f1 | Silverdale Deployment 2053 | 2021-01-04 | 2021-01-10 | Configuration | Mid-America: Odoo Implementation (P37) | Levi Barnes | Muzher Siddique | 0.75 | 0.75 | 1.25 | 37.5 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-05 19:03 | TRUE | Mid-America Gardens, LLC | 0 | 0.1875 | 0 | 1.5313 | 2021-01-04 | Complete | Naseeb Razaq | Done | FALSE |  | Muzher Siddique | 2021-01-05 19:03 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Tasks: 1849, 2105, 2042, 2120, 1899, 2043</p> | 2021-01-05 20:35 | 6941 | 2 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_2072_c7b1a141 | FW: constantly being kicked out of odoo |  |  | Bug Fix | PWX: Help (P23) | Levi Barnes | FALSE | 0.25 | 0.25 | -0.25 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-12-31 04:07 | TRUE | EquityTeam | 0 | 2.9375 | 0 | 23.4342 |  | Complete | Farman Ahmad Cheema | Done | FALSE | External - Client | Levi Barnes | 2020-12-31 04:07 | Silverdale Technology LLC, Levi Barnes | Executive / Mechanisms | FALSE | <p><br></p> | 2021-01-04 21:26 | 7076 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_1888_62c87d50 | Continuant AV Warehouse Deployment 2050 | 2020-12-07 | 2020-12-13 | Configuration | Continuant: AV Warehouse (P34) | Muzher Siddique | Muzher Siddique | 0.42 | 0.42 | 0.58 | 42 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-12-15 20:04 | FALSE | Continuant | 0 | 0.0625 | 0 | 0.26317 | 2020-12-07 | Complete | Muhammad Zubair | Done | FALSE |  | Muzher Siddique | 2020-12-15 20:04 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p> 1803 is deployed.<br></p> | 2020-12-15 20:20 | 7444 | 1 | 0 | 0 | 0 | Normal | Sprint 2050
__export__.project_task_1681_6f85573c | Deployment Continuant: Customer Portal AR | 2020-11-23 | 2020-11-29 | Development | Continuant: Customer Portal AR (P32) | Muzher Siddique | FALSE | 0.17 | 0.17 | 0.33 | 34 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-12-01 16:53 | FALSE | Continuant | 0 | 0 | 0 | 0.12024 | 2020-11-23 | Complete | Muhammad Zubair | Done | FALSE |  | Muzher Siddique | 2020-12-01 16:53 | Continuant, Allison Beers | Executive / Delivery / Bravo | FALSE | <p><br></p> | 2020-12-01 17:56 | 7783 | 0.5 | 0 | 0 | 0 | Normal | Sprint 2048
__export__.project_task_1652_0dc621f1 | Parameter mis match while adding product in watchlist if no bid is placed | 2020-11-23 | 2020-11-29 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 1.5 | 1.5 | -1.5 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-11-25 16:29 | FALSE | Cellpoint Corporation | 0.0625 | 8.625 | 0.40152 | 68.9168 | 2020-11-23 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Apps Maven | 2020-11-25 16:05 | Cellpoint Corporation | FALSE | Apps Maven | <p><br></p> | 2020-12-08 05:42 | 7928 | 0 | 0 | 0 | 0 | Normal | Sprint 2048
__export__.project_task_1060_769bac42 | Seller Permissions Group: Action>Remove Duplicate Buyers | 2020-08-24 | 2020-08-30 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-28 13:51 | FALSE | Cellpoint Corporation | 11.125 | 0 | 88.8572 | 0 | 2020-08-24 | Complete | Muhammad Afzaal | Done | FALSE |  | Kaesi Lee | 2020-08-13 02:56 | Cellpoint Corporation | FALSE | FALSE | <p>Seller Buyer Form View: Action&gt;Remove Duplicate</p> |  | 10437 | 0 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_951_07b72061 | Integration GFK Catalog: Replace default photo with GFK photo | 2020-08-10 | 2020-08-16 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-06 23:08 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-10 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-06 23:07 | Continuant | FALSE | FALSE | <p>Change product photo from default image to image pulled from GFK. Remove default image from product images after GFK image is imported. </p><p><br></p><p> </p> |  | 10585 | 0 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_935_4b783045 | API:Set Batch Api:Postman | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-30 19:57 | FALSE | Cellpoint Corporation | 0 | 0 | 0.0076269 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-30 19:56 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10756 | 1 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_905_fc899179 | Forcefully update Android-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:46 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00016651 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_898_50dfbe4e | Bid history Android-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:46 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00016651 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_548_fae73e2a | API:Product status | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 6 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:41 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.6858 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 11009 | 6 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_537_8bf158a3 | API:Make an offer | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:42 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.6992 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_306_9c2e2097 | eCommerce: Release Module | 2020-08-03 | 2020-08-09 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0.8125 | 0 | 6.2856 | 0 | 2020-08-03 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-16 02:45 | Continuant | FALSE | FALSE | <p><br></p> |  | 11109 | 0 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_4551_dfef5a08 | Define your Inventory costing and valuation methods (if using the Inventory App) for your Product Categories. | 2021-08-23 | 2021-08-29 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 | 0.16667 | 0 | 2021-08-27 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-13 18:43 | TRUE | Zuma Sales LLC | 0 | 4.0625 | 0 | 32.7072 | 2021-08-23 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-13 18:43 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>Asfand needs to get info from the client, </p> | 2021-08-20 20:42 | 1661 | 0.16667 | 0 | 0 | 0 | Normal | Sprint 2135
__export__.project_task_4440_2e9948be | Message for User for NMS has already been sent | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 3.83 | 3.83 | 0.17 | 95.75 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-05 02:28 | TRUE | Cellpoint Corporation | 0 | 13 | 0 | 103.9606 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-08-05 02:28 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>1. When for those IMEIs that have already been included in NMS export file before and have the NMS status as sent. </p><p>2. When they selected and NMS export is done, then the message for the user should read "NMS has already been sent".</p><p>3. For different Product it should allow to export NMS. </p><p> </p><p><br></p> | 2021-08-25 02:25 | 1870 | 4 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3420_f5074a7b | Communicate go-live timeline to customers and vendors as appropriate |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | FALSE | 0 | 0 | 0 | 0 | 2021-07-30 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-07-19 18:59 | TRUE | Zuma Sales LLC | 57.6875 | 56.75 | 461.3609 | 454.1012 |  | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-04-23 21:38 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-07-16 19:44 | 4346 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_3209_5604db02 | Web Lot detail view in Chinese | 2021-04-05 | 2021-04-11 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 6.5 | 6.5 | 0 | 100 |  | 2 | Complete | TRUE | Fahad Hassan | 2021-03-23 17:47 | FALSE | Cellpoint Corporation | 0 | 18.5 | 0 | 148 | 2021-04-05 | Complete | Farman Ahmad Cheema | InProgress | FALSE | External - Client | Muhammad Afzaal | 2021-03-23 17:46 | Cellpoint Corporation, Ehsan Gharatappeh | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>We need to translate web lot detail view into Chinese through language switcher.</p> | 2021-04-18 00:35 | 5094 | 6.5 | 0 | 0 | 0 | Normal | Sprint 2115
__export__.project_task_2672_7f4116b6 | Volunteer Shift Management |  |  | Configuration | Heronswood: Help (P54) OLD DO NOT USE | Jeff Gross | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Cancelled | TRUE | Muhammad Saqlain Alam | 2021-03-06 03:06 | TRUE | Port Gamble S’Klallam Foundation | 21 | 50.8125 | 168 | 406.3133 |  | Cancelled | Naseeb Razaq | In Warranty | TRUE |  | Nick Foy | 2021-02-05 02:33 | Port Gamble S’Klallam Foundation, Ross Bayton | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>Demo of the Odoo shift management function</p><p><br></p><p>Ross &amp; Debbie</p><p><br></p><p><br></p> | 2021-04-16 20:19 | 6213 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_2669_95af32cf | Fw: Task Notification Alterations |  |  | Configuration | PWX: Help Desk (P65) | Levi Barnes | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Cancelled | TRUE | FALSE | 2021-02-05 00:56 | FALSE | EquityTeam | 0 | 115.375 | 0 | 922.8097 |  | Cancelled | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2021-02-05 00:56 | Silverdale Technology LLC, Levi Barnes | Executive / Mechanisms | Silverdale Technology LLC | <p><a href="https://www.pwxusa.com/web#id=1010&amp;action=506&amp;active_id=66&amp;model=project.task&amp;view_type=form&amp;cids=&amp;menu_id=375">Task Notification Alterations - Odoo (pwxusa.com)</a><br><br></p><p>Is it possible for an email to be used with a button for approving VBI or Expense approvals?</p> | 2021-07-22 03:26 | 6215 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_2119_dafb4cd1 | Continuant AV Warehouse Deployment 2053 | 2021-01-04 | 2021-01-10 | Configuration | Mid-America: Odoo Implementation (P37) | Levi Barnes | Muzher Siddique | 0.2 | 0.2 | 0.8 | 20 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-05 18:13 | TRUE | Mid-America Gardens, LLC | 0 | 0 | 0 | 0.1173 | 2021-01-04 | Complete | Naseeb Razaq | Done | FALSE |  | Muzher Siddique | 2021-01-05 18:13 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Deployed: 1901 on av_warehouse_2049 branch.</p> | 2021-01-05 18:20 | 6942 | 1 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_2069_3c0b09ec | Consulting |  |  | Configuration | PWX: Help (P23) | Levi Barnes | FALSE | 1.5 | 1.5 | -1.5 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-30 23:27 | TRUE | EquityTeam | 0 | 0 | 0 | 0 |  | Complete | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2020-12-30 23:27 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | FALSE | <p><br></p> | 2020-12-30 23:28 | 7081 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_1858_ee42da84 | Option to add SSL Certificates to Encrypt Connections | 2020-12-14 | 2020-12-20 | Development | Continuant: Power BI Integration (P30) | Kaesi Lee | Fahad Hassan | 7.17 | 7.17 | -2.17 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-12-10 22:08 | FALSE | Continuant | 0 | 12.5 | 0 | 100 | 2020-12-14 | Complete | Muhammad Zubair | Cancelled | FALSE |  | Kaesi Lee | 2020-12-10 22:08 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>As a system admin, I want the option to enable SSL certificates to encrypt the connection between Odoo and the Azure SQL Server. </p> | 2020-12-29 17:10 | 7562 | 5 | 0 | 0 | 0 | Normal | Sprint 2051
__export__.project_task_1506_0e69b0b5 | Scheduled Action |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Raheel Aslam | 28.41 | 11.33 | -15.41 | 100 |  | FALSE | Complete | TRUE | FALSE | 2020-10-30 20:54 | FALSE | Cellpoint Corporation | 0 | 27.125 | 0 | 216.9977 |  | Complete | Farman Ahmad Cheema | InProgress | FALSE | Internal | Muhammad Afzaal | 2020-10-30 20:54 | Cellpoint Corporation | FALSE | Silverdale Technology LLC | <p><br></p> | 2020-12-08 21:54 | 8547 | 13 | 0 | 0 | 0 | Normal
__export__.project_task_1180_bc8a8fe5 | API Configuration Form View | 2020-09-07 | 2020-09-13 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-04 22:54 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-09-07 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-09-04 22:54 | Continuant | FALSE | FALSE | <p>Each of the Continuant APIs should have a configuration page. Use the attached screenshot for Ava API as a template. It should allow Continuant to configure the necessary information without editing the code. </p><p><br></p><p>1. GFK</p><p>2. Tech Data API</p><p>3. Ingram Micro Distributor API</p><p>4. Synnex API </p><p><br><br></p> |  | 9889 | 0 | 0 | 0 | 0 | Normal | Sprint 30
__export__.project_task_937_12feae8c | API:Add to watchlist : | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-30 19:59 | FALSE | Cellpoint Corporation | 0 | 0 | 0.021223 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-30 19:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10756 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_925_60a4f324 | API:Product status:Postman | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-29 12:29 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-29 12:24 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10788 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_920_ee3bf504 | API:Product List:Postman | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 0.5 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-29 11:40 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-29 11:40 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10788 | 0.5 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_835_23f18916 | Edit profile iOS-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_582_e29e1176 | Updated API Document:APPMAVEN | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Muhammad Afzaal | FALSE | 0 | 0 | 5 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-23 17:14 | FALSE | Cellpoint Corporation | 1.5 | 0 | 12 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-22 09:39 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10958 | 5 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_363_4e677992 | CPBids Website Status Page | 2020-07-20 | 2020-07-26 | Development | Cellpoint CPBids: Help (P7) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 23:48 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-20 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Kaesi Lee | 2020-07-16 23:48 | Cellpoint Corporation | FALSE | FALSE | <p>Create a support page which will display known impacting issues with the app function. Also include FAQ, which can be categorized by seller or general app functionality. Can include Seller grading levels. </p> |  | 11088 | 0 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_357_43b2ae09 | Sponsor Meeting #7 | 2020-08-31 | 2020-09-06 | Development | Continuant: eCommerce (P9) | Nick Foy | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0 | 0 | 0.00032117 | 0 | 2020-08-31 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE |  |  | 11092 | 0 | 0 | 0 | 0 | Normal | Sprint 29
__export__.project_task_275_7ba5dbb5 | Group Buyers: Super Selection | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan | FALSE | 0 | 0 | 8 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-15 15:28 | FALSE | Cellpoint Corporation | 0 | 0 | 0.010754 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-15 15:28 | Cellpoint Corporation | FALSE | FALSE | <p>When sellers are creating auctions, they can super select few buyers out of their buyer list <br></p> |  | 11121 | 8 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_268_bd91de66 | Share Github Account ID with Allison | 2020-07-12 | 2020-07-19 | Development | Continuant: eCommerce (P9) | Deepak Krishnan | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 1.8125 | 0 | 14.2858 | 0 | 2020-07-12 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-15 00:29 | Continuant | FALSE | FALSE | <p> </p> |  | 11136 | 0 | 0 | 0 | 0 | Normal | Sprint 22
__export__.project_task_4547_1dbe91dc | Verify Fiscal Positions are setup and support your needs - potentially having a Tax Exempt position. | 2021-08-23 | 2021-08-29 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.25 | 0.25 | 0.25 | 50 | 2021-08-27 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-13 18:04 | TRUE | Zuma Sales LLC | 0 | 8.5 | 0 | 68.0739 | 2021-08-23 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-13 18:04 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>Asfand needs to get confirmation from client</p> | 2021-08-27 01:04 | 1662 | 0.5 | 0 | 0 | 0 | Normal | Sprint 2135
__export__.project_task_4438_9151c699 | NMS Export file has imei's repeated and last space | 2021-08-09 | 2021-08-15 | Bug Fix | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 3.58 | 3.58 | -1.58 | 100 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-05 02:16 | TRUE | Cellpoint Corporation | 0 | 13 | 0 | 104.1539 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-08-05 02:16 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>1. NMS Export file has imei's repeated and last space after the last imei record it should not go to next line. (Example NMS export file is attached for reference - that file was generated in the Training Branch).</p><p><br></p><p>2. filename is also wrong (Date should be Mountain)</p> | 2021-08-25 02:25 | 1870 | 2 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3419_662ca865 | Finalize cutover plan and checklists |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | FALSE | 0 | 0 | 0 | 0 | 2021-07-18 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-07-19 18:59 | TRUE | Zuma Sales LLC | 57.6875 | 56.75 | 461.3712 | 454.1145 |  | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-04-23 21:37 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-07-16 19:44 | 4346 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_3207_400ec443 | Deployment 2112:PWX | 2021-03-29 | 2021-04-04 | Configuration | PWX: Survey (P70) | Levi Barnes | Wajahat Ali | 1.58 | 1.58 | -1.58 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-03-23 17:11 | FALSE | EquityTeam | 0 | 18.5 | 0 | 148 | 2021-03-29 | Complete | Naseeb Razaq | In Warranty | FALSE |  | Wajahat Ali | 2021-03-23 17:06 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>Tasks need to deploy and test:<br> 2856,</p><p>2729</p> | 2021-04-18 00:35 | 5095 | 0 | 0 | 0 | 0 | Normal | Sprint 2114
__export__.project_task_2391_c67ec151 | Display Customer Statements in Customer Portal | 2021-02-15 | 2021-02-21 | Development | Continuant: Customer Portal AR (P32) | Nick Foy | Muhammad Bilal | 11.37 | 11.37 | -3.37 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2021-02-02 04:15 | FALSE | Continuant | 8.0625 | 29.875 | 64.5432 | 239.0046 | 2021-02-15 | Complete | Muhammad Zubair | Done | FALSE | External - Client | Kaesi Lee | 2021-01-20 21:27 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>This task will: Create a new Module</p><p><br></p><p>Module name: Customer Statements in Portal</p><p><br></p><p>What are you trying to accomplish?</p><p>As a Customer with portal access, I want to see my current statement to see the outstanding invoices and credit notes I have with the company, in order to make sure my account is in good standing with the Company</p><p><br></p><p>Pre-requisites:</p><p>Customer must have portal access</p><p>Customer must have either outstanding Sales Invoices or Sales Credits on there account</p><p><br></p><p>User Steps:</p><p>1. Log in to the customer portal [std]</p><p>2. Click on Statement [dev]</p><p>3. View my statement [dev]</p><p><br></p><p>The Statement is pulled from Accounting &gt; Customers &gt; Customer Statements and we need the table of outstanding items to show with the total. Some of the columns should be removed (see attached picture)</p><p><br></p><p>Views and Filters:</p><p>New Portal view for Statements</p><p><br></p><p>Reports:</p><p>None</p><p><br></p><p>Security:</p><p><br></p><p>Only logged in customers using the portal should see the statements</p><p><br></p><p>Compatibility:</p><p>v12 - yes</p><p>v13 - no</p><p>v14 - no</p><p><br></p><p><br></p> | 2021-03-03 20:28 | 6579 | 8 | 0 | 0 | 0 | Normal | Sprint 2109
__export__.project_task_2118_0142a538 | Wild Leaf General Deployment 2053 | 2021-01-04 | 2021-01-10 | Configuration | Mid-America: Odoo Implementation (P37) | Levi Barnes | Muzher Siddique | 0.97 | 0.97 | 1.03 | 48.5 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-05 17:55 | TRUE | Mid-America Gardens, LLC | 0 | 0.1875 | 0 | 1.2569 | 2021-01-04 | Complete | Naseeb Razaq | Done | FALSE |  | Muzher Siddique | 2021-01-05 17:55 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Tasks: 1867</p> | 2021-01-05 19:15 | 6942 | 2 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_2060_cc4b6a05 | New system@pwxusa.com credentials | 2020-12-21 | 2020-12-27 | Configuration | PWX: Help (P23) | Levi Barnes | FALSE | 0.17 | 0.17 | -0.17 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-30 18:12 | TRUE | EquityTeam | 0 | 5.125 | 0 | 40.6223 | 2020-12-21 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Levi Barnes | 2020-12-30 18:12 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | FALSE | <p><br></p> | 2021-01-06 18:49 | 7086 | 0 | 0 | 0 | 0 | Normal | Sprint 2052
__export__.project_task_1840_9a9ba1b0 | Send to Pick: Delivery Order Selection | 2020-12-21 | 2020-12-27 | Development | Continuant: AV Warehouse (P34) | Kaesi Lee | Danish Hassan | 29.09 | 13.17 | -23.09 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-12-09 03:04 | FALSE | Continuant | 0 | 20.625 | 0 | 164.8297 | 2020-12-21 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-12-09 03:04 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>As a warehouse worker when I click "Send to Pick" on an AV Picklist, a window should pop-up with a list of WH/OUT delivery orders. This list is limited to those that are assigned to the Related Contract (Project) that the AV Picklist is assigned to. This list is also limited to WH/OUT delivery orders that are not in the "done" status. This list should display the delivery order number and the source document of that delivery order. Clicking on that delivery order should open up an preview of the Operations tab of that delivery order.</p><p><br></p><p>Once a WH/OUT delivery order is selected, there should be a button labeled "Send to Pick" in the pop-up window. Clicking this button will compare the list of items in the pick list to the items in the selected WH/OUT delivery order.</p><p><br></p><p>If none of the items match, a message should display "None of the items in your pick list match the products in the selected delivery order. Please select a different order."</p><p><br></p><p>If some or all of the items match, then Odoo will automatically update the reserved quantity of each of the items in the WH/OUT delivery order with the quantity of that item that was in the AV Picklist. </p><p><br></p> | 2021-01-06 18:50 | 7605 | 6 | 0 | 0 | 0 | Normal | Sprint 2052
__export__.project_task_1354_6877ff2e | Beta Feedback Oct 1 | 2020-10-05 | 2020-10-11 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | FALSE | 31 | 31 | -31 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-10-02 01:44 | FALSE | Cellpoint Corporation | 0 | 8 | 0 | 63.9822 | 2020-10-05 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Nick Foy | 2020-10-01 22:48 | Cellpoint Corporation | FALSE | Deerom Technologies Pvt. Ltd. | <p>Feedback from Buyer beta session on web enabled bidding</p><p><br></p><p><font class="bg-alpha">Fixed</font></p><p><font class="bg-epsilon">Required for go-live</font></p><p><font class="bg-beta">Fast Follow</font></p><p><font style="background-color: rgb(255, 255, 255);">Low priority</font></p><p><font class="bg-epsilon"><br></font></p><p><font class="bg-epsilon"><br></font></p><p><br></p><ol><li id="checklist-id-1"><p><font class="bg-alpha">Font used within the table is too feint - please change color to Black text</font></p></li><li id="checklist-id-2"><p><font class="bg-alpha">The blue color font used in the time remaining field is difficult to read, please change to black font </font></p></li><li id="checklist-id-3"><p><font class="bg-alpha">In the detail page, can the Manifest be a pop-up showing the manifest details with the option to download [note: this was how we had it before]</font></p></li><li id="checklist-id-4"><p><font class="bg-alpha">The red background is too </font><font class="bg-alpha">red</font><font class="bg-alpha">, cannot read the text. Change to a </font><font style="color: rgb(0, 0, 0);" class="bg-alpha">softer red</font></p></li><li id="checklist-id-5"><p><font class="bg-alpha">Need more than just the color background for winning / losing. Please add a field that has "Winning" or "Losing" as well as color background</font></p></li><li id="checklist-id-6"><p><font class="bg-alpha">Add Sort By End Date Time </font></p></li><li id="checklist-id-7"><p><font class="bg-alpha">Go to Auction Button Takes me back to the marketplace, if this is the intended function, change the name of the button to Marketplace</font></p></li><li id="checklist-id-8"><p><font class="bg-alpha">I</font><font class="bg-alpha">ncrease the size of the my max bid field so the entire number is displayed - (work on title field)</font></p></li><li id="checklist-id-9"><p><font class="bg-alpha">Add Log Out and Log In option to user interface</font></p></li><li id="checklist-id-10"><p><font class="bg-alpha">Make refresh countdown all uppercase letters or change its location so it's not in the same row as the column headers </font></p></li><li id="checklist-id-11"><p><font class="bg-epsilon">Soonest closing auctions should be on top </font></p></li><li id="checklist-id-12"><p><font class="bg-alpha">1 extra hour is showing on web versus app </font></p></li><li id="checklist-id-13"><p><font class="bg-alpha">Remove Decimal point in highest bid </font></p></li><li id="checklist-id-14"><p><font class="bg-alpha">Unit price is not working</font></p></li><li id="checklist-id-16"><p><font class="bg-alpha">Lots showing as Losing when Kaesi didn't bid</font></p></li><li id="checklist-id-17"><p><font class="bg-alpha">Sort By field doesn't work - remove the Sort options for now</font></p></li><li id="checklist-id-17"><p><font class="bg-alpha">No Winning / Losing message on the Detail page</font></p></li><li id="checklist-id-17"><p>Icons on the detail page are different sizes - need to standardize</p></li><li id="checklist-id-17"><p>Fonts and text sizes are inconsistent on the Detail page</p></li><li id="checklist-id-17"><p>Detail page lot title is too large</p></li><li id="checklist-id-17"><p><font class="bg-alpha">Emails being sent when you join an auction (add to watchlist or start bidding)</font></p></li><li id="checklist-id-17"><p><font class="bg-alpha">Pending Auctions showing as well on web auctions</font></p></li></ol> | 2020-10-13 21:59 | 9241 | 0 | 0 | 0 | 0 | Normal | Sprint 2041
__export__.project_task_924_fae5c57f | API:Bid History:Postman | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-29 11:44 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-29 11:43 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10788 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_909_5318ee06 | Get batch API Android-Implementation | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:46 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00016651 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_834_b4ff2226 | Change passord iOS-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_820_61edd43c | Version update iOS-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_607_8a075f4e | eCommerce: Add Customer Select Field | 2020-08-10 | 2020-08-16 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 5 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-27 20:58 | FALSE | Continuant | 0 | 0 | 0.17582 | 0 | 2020-08-10 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-27 20:47 | Continuant | FALSE | FALSE | <p>All of the shopping will be done by an account manager on behalf of the customer so when creating and editing a cart there needs to be an option to assign it to a specific customer. </p><p><br></p><p> For example: </p><p><br></p><p>Todd asks Continuant to place an order for 10 TVs.</p><p>Todd's account manager logs in using his account manager account to the Continuant eCommerce Website</p><p>Todd's account manager needs to be able to assign this cart to Todd's account so that the correct address and business info is populated for the shipping price and forwarded to the carrier. A search bar or a drop down menu that lists previous customer contacts. (See attachment photo)</p><p>a<span style="color: rgb(0, 0, 0); font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;">dd option to create new customer here, default the customer status to eCommerce. </span></p><p>Todd's account manager selects Todd as the customer</p><p>Todd's account manager adds 10 TVs to his shopping cart. </p><p>Todd's account manager opens the shopping cart, he is on the review order page. </p><p><br></p><p><br></p><p><br></p> |  | 10827 | 5 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_580_a90438db | POPDM: Database Record Error | 2020-07-27 | 2020-08-02 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 19:37 | FALSE | Cellpoint Corporation | 4.875 | 0 | 39.0483 | 0 | 2020-07-27 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Kaesi Lee | 2020-07-21 20:34 | Cellpoint Corporation | FALSE | FALSE | The content of this cell is too long for an XLSX file (more than 32767 characters). Please use the CSV format for this export. |  | 10971 | 0 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_345_b12a59c3 | Production Release #2 | 2020-08-10 | 2020-08-16 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0 | 0 | 0.00032117 | 0 | 2020-08-10 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE | <p><br></p> |  | 11092 | 0 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_271_21f74da7 | Marketplace- Backend | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-03 17:12 | FALSE | Cellpoint Corporation | 13.375 | 0 | 106.8069 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-15 14:12 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 11122 | 0 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_4546_0d3904f0 | Define which accounts can be used to write Checks and modify your layout if needed. | 2021-09-06 | 2021-09-12 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 | 2 | 0 | 2021-09-10 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-13 18:03 | TRUE | Zuma Sales LLC | 0 | 16 | 0 | 128 | 2021-09-06 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-13 18:03 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>Asfand needs to get confirmation from client</p> | 2021-09-07 17:47 | 1662 | 2 | 0 | 0 | 0 | Normal | Sprint 2137
__export__.project_task_4407_bd48f06e | Deploy report_xml to the database | 2021-08-16 | 2021-08-22 | Configuration | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 0.42 | 0.42 | -0.42 | 0 |  | FALSE | Complete | TRUE | Fahad Hassan | 2021-07-30 22:00 | TRUE | Cellpoint Corporation | 0 | 20.875 | 0 | 167.0585 | 2021-08-16 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-07-30 22:00 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><br></p> | 2021-08-31 21:04 | 1994 | 0 | 0 | 0 | 0 | Normal | Sprint 2134
__export__.project_task_3408_72c5c92a | A solution for saving credit card information |  |  | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | FALSE | 0 | 0 | 0 | 0 | 2021-08-06 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-07-19 18:59 | TRUE | Zuma Sales LLC | 58.625 | 66 | 468.9914 | 528.0192 |  | Complete | Asfand Yaar | In Warranty | FALSE |  | Bilal Ahmad Khan | 2021-04-23 00:15 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>What we are trying to accomplish?</p><p><br></p><p><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.5);'>A solution for saving credit card information that receives over the phone.</span><br><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.5);'> Many times return customers don't want to give us the same credit card number over and over again and ask us to just keep their cc info on hand.</span><br></p> | 2021-07-30 00:22 | 4368 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_2653_7b461370 | Daily Meetings |  |  | Internal Time Tracking | Silverdale: Time Tracking (P56) | Nick Foy | FALSE | 323.6 | 323.6 | -323.6 | 0 |  | FALSE | Cancelled | TRUE | FALSE | 2021-02-03 00:18 | FALSE | Silverdale Technology LLC | 0 | 52.5625 | 0 | 420.4036 |  | Cancelled | Muhammad Afzaal | InProgress | FALSE |  | Muzher Siddique | 2021-02-03 00:17 | FALSE | FALSE | Silverdale Technology LLC | <p><br></p> | 2021-04-16 18:24 | 6264 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_2117_7f7f95ca | Mid America Deployment 2053 | 2021-01-04 | 2021-01-10 | Configuration | Mid-America: Odoo Implementation (P37) | Levi Barnes | Muzher Siddique | 1.33 | 1.33 | 0.67 | 66.5 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-05 17:11 | TRUE | Mid-America Gardens, LLC | 0 | 0.0625 | 0 | 0.67389 | 2021-01-04 | Complete | Naseeb Razaq | Done | FALSE |  | Muzher Siddique | 2021-01-05 17:11 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>2028, 2029 and 2031 deployed.</p> | 2021-01-05 18:40 | 6943 | 2 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_2051_81547b3d | How to set up task search to search for reference #'s (#44) |  |  | Configuration | PWX: Help (P23) | Levi Barnes | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-29 05:47 | TRUE | EquityTeam | 0 | 6.625 | 0 | 52.8222 |  | Complete | Farman Ahmad Cheema | Done | FALSE |  | Nick Foy | 2020-12-29 05:47 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | FALSE | <p><br></p> | 2021-01-06 18:49 | 7122 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_1828_78c708bd | Data Migration Module Documentation | 2020-12-07 | 2020-12-13 | Configuration | Continuant: Power BI Integration (P30) | Kaesi Lee | FALSE | 1.5 | 1.5 | -1.5 | 0 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-12-08 20:10 | FALSE | Continuant | 0 | 11.0625 | 0 | 88.4215 | 2020-12-07 | Complete | Muhammad Zubair | Cancelled | FALSE |  | Kaesi Lee | 2020-12-08 20:10 | Continuant, Allison Beers | Executive / Delivery / Bravo | FALSE | <p><br></p> | 2020-12-23 20:35 | 7612 | 0 | 0 | 0 | 0 | Normal | Sprint 2050
__export__.project_task_1680_107bb996 | Deployment Continuant: Customer Invoice Delivery Preferences | 2020-11-23 | 2020-11-29 | Development | Continuant: Customer Invoice Delivery Preferences (P33) | Muzher Siddique | FALSE | 0.5 | 0.5 | 0 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-12-01 16:52 | FALSE | Continuant | 0 | 0 | 0 | 0.1401 | 2020-11-23 | Complete | Muhammad Zubair | Done | FALSE |  | Muzher Siddique | 2020-12-01 16:52 | Continuant, Allison Beers | Executive / Delivery / Bravo | FALSE | <p><br></p> | 2020-12-01 17:48 | 7783 | 0.5 | 0 | 0 | 0 | Normal | Sprint 2048
__export__.project_task_1311_778fa696 | Unable to approve Buyer | 2020-10-05 | 2020-10-11 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-29 19:34 | FALSE | Cellpoint Corporation | 0 | 10.3125 | 0 | 82.4268 | 2020-10-05 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Kaesi Lee | 2020-09-29 19:34 | Cellpoint Corporation | FALSE | FALSE | <p>I am receiving an error message when I click CPBids Credentials&gt;approved for Simon Levin and Elliot Tebele. </p><p><br></p><p>Error message: </p><p><br></p><pre style="font-size: 11.375px;">Odoo Server Error</pre><pre style="font-size: 11.375px;">Traceback (most recent call last): File "/home/odoo/src/odoo/odoo/http.py", line 656, in _handle_exception return super(JsonRequest, self)._handle_exception(exception) File "/home/odoo/src/odoo/odoo/http.py", line 314, in _handle_exception raise pycompat.reraise(type(exception), exception, sys.exc_info()[2]) File "/home/odoo/src/odoo/odoo/tools/pycompat.py", line 87, in reraise raise value File "/home/odoo/src/odoo/odoo/http.py", line 698, in dispatch result = self._call_function(**self.params) File "/home/odoo/src/odoo/odoo/http.py", line 346, in _call_function return checked_call(self.db, *args, **kwargs) File "/home/odoo/src/odoo/odoo/service/model.py", line 98, in wrapper return f(dbname, *args, **kwargs) File "/home/odoo/src/odoo/odoo/http.py", line 339, in checked_call result = self.endpoint(*a, **kw) File "/home/odoo/src/odoo/odoo/http.py", line 941, in __call__ return self.method(*args, **kw) File "/home/odoo/src/odoo/odoo/http.py", line 519, in response_wrap response = f(*args, **kw) File "/home/odoo/src/odoo/addons/web/controllers/main.py", line 962, in call_kw return self._call_kw(model, method, args, kwargs) File "/home/odoo/src/odoo/addons/web/controllers/main.py", line 954, in _call_kw return call_kw(request.env[model], method, args, kwargs) File "/home/odoo/src/odoo/odoo/api.py", line 759, in call_kw return _call_kw_multi(method, model, args, kwargs) File "/home/odoo/src/odoo/odoo/api.py", line 746, in _call_kw_multi result = method(recs, *args, **kwargs) File "/home/odoo/src/user/odoo_marketplace/models/res_partner.py", line 381, in write res = super(ResPartner, self).write(vals) File "/home/odoo/src/odoo/addons/partner_autocomplete/models/res_partner.py", line 183, in write res = super(ResPartner, self).write(values) File "/home/odoo/src/odoo/odoo/addons/base/models/res_partner.py", line 570, in write result = result and super(Partner, self).write(vals) File "/home/odoo/src/odoo/addons/mail/models/mail_thread.py", line 328, in write track_self.with_context(clean_context(self._context)).message_track(tracked_fields, initial_values) File "/home/odoo/src/odoo/addons/mail/models/mail_thread.py", line 640, in message_track tracking = self._message_track_get_changes(tracked_fields, initial_values) File "/home/odoo/src/odoo/addons/mail/models/mail_thread.py", line 601, in _message_track_get_changes result[record.id] = record._message_track(tracked_fields, initial_values[record.id]) File "/home/odoo/src/odoo/addons/mail/models/mail_thread.py", line 622, in _message_track tracking = self.env['mail.tracking.value'].create_tracking_values(initial_value, new_value, col_name, col_info, track_sequence) File "/home/odoo/src/odoo/addons/mail/models/mail_tracking_value.py", line 60, in create_tracking_values 'old_value_char': initial_value and dict(col_info['selection'])[initial_value] or '', KeyError: 'invite'</pre> | 2020-10-14 01:12 | 9292 | 0 | 0 | 0 | 0 | Normal | Sprint 2041
__export__.project_task_956_d4bfc946 | Review Cart: Make Quantity Read Only | 2020-08-10 | 2020-08-16 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-08 01:55 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-10 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-08 01:55 | Continuant | FALSE | FALSE | <p>Make quantity entry field read only, do not allow them to make adjustments to quantity on the review cart page (See attachment). </p> |  | 10558 | 0 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_919_cf8da367 | API:Edit Profile:Postman | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 0.5 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-29 11:39 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-29 11:39 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10788 | 0.5 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_913_0bbf2d0a | Filter Screen fuctionality Android-Implementation | 2020-08-24 | 2020-08-30 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:46 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00016651 | 0 | 2020-08-24 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 2 | 0 | 0 | 0 | Normal | Sprint 28
__export__.project_task_889_4f04aef3 | Select country Android-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_547_84e3927d | API:Category List | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:47 | FALSE | Cellpoint Corporation | 1.375 | 0 | 10.79 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p>method: POST </p><p>Description: On the basis of this API user can get the list of categories on the filter screen to get filtered data in the Auction list.</p><p>parameters: user_id ,verify_token </p><p>API will check user_id and verify token , And fetch the category data from the table (cp bids.category)</p><p>append category_id, category.name into JSON</p><p>Retrieve JSON data</p><p><br></p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_304_b4899f82 | Tax: Test Avalara Functionality: Obtain Credentials | 2020-07-12 | 2020-07-19 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0.8125 | 0 | 6.2858 | 0 | 2020-07-12 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-16 02:43 | Continuant | FALSE | FALSE |  |  | 11109 | 0 | 0 | 0 | 0 | Normal | Sprint 22
__export__.project_task_257_b9c039df | Manifest for web | 2020-07-12 | 2020-07-19 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan | FALSE | 0 | 0 | 24 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-10 12:19 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-12 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-10 12:19 | Cellpoint Corporation | FALSE | FALSE | <p><span lang="EN" style="font-size: 10pt; line-height: 15.333332061767578px; font-family: Arial; color: rgb(11, 83, 148);">Product Manifest should be displayed on the product page, Buyer should be able to view it or download on their computer</span><span style="caret-color: rgb(0, 0, 0); color: rgb(0, 0, 0); font-family: -webkit-standard; font-size: medium;"></span><br></p> |  | 11244 | 24 | 0 | 0 | 0 | Normal | Sprint 22
__export__.project_task_4535_303cc771 | Planning New Go-Live Plan | 2021-08-09 | 2021-08-15 | Other | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 3 | 3 | 0 | 100 | 2021-08-11 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-12 16:29 | TRUE | Zuma Sales LLC | 0 | 0 | 0 | 0.0078762 | 2021-08-09 | Complete | Asfand Yaar | In Warranty | FALSE |  | Asfand Yaar | 2021-08-12 16:29 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-08-12 16:30 | 1688 | 3 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_4406_f56fba4b | Custom fields to add | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Kaleem Khan | 1.5 | 1.5 | 0.5 | 75 | 2021-08-12 | 1 | Complete | TRUE | Fahad Hassan | 2021-07-30 17:26 | TRUE | Cellpoint Corporation | 0 | 16.6875 | 0 | 133.4236 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-07-30 17:26 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><font style="color: rgb(0, 0, 0);">1. A field (H Type) needs to be added on the product form with following values:</font></p><p><font style="color: rgb(0, 0, 0);">Field Type: Selection</font></p><p><font style="color: rgb(0, 0, 0);"> a) H</font></p><p><font style="color: rgb(0, 0, 0);"> b) H3</font></p><p><font style="color: rgb(0, 0, 0);"> c) H5</font></p><p><font style="color: rgb(0, 0, 0);"><br></font></p><p><font style="color: rgb(0, 0, 0);">2. Following fields to be added on the product form:</font></p><p><font style="color: rgb(0, 0, 0);"> a. Variant </font><span style="color: rgb(0, 0, 0); font-style: inherit; font-variant-caps: inherit; font-variant-ligatures: inherit; font-weight: inherit; text-align: inherit;">(Should be alphanumeric)</span></p><p><font style="color: rgb(0, 0, 0);"> </font></p><p><br></p><p><br></p> | 2021-08-25 02:25 | 1999 | 2 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3407_6ecb3d86 | Customer Equipment Management |  |  | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | FALSE | 0 | 0 | 0 | 0 | 2021-08-06 | FALSE | Cancelled | TRUE | Muhammad Saqlain Alam | 2021-07-19 18:59 | TRUE | Zuma Sales LLC | 58.625 | 66 | 468.9914 | 528.0192 |  | Cancelled | Asfand Yaar | In Warranty | FALSE |  | Bilal Ahmad Khan | 2021-04-23 00:11 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>What we are trying to accomplish is?</p><p><br></p><p><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.5);'> Our parts customers call regularly for parts for the same machine. </span><br><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.5);'> We need a database of all the equipment that the customer owns with year, make model serial number, unit number, etc. </span><br><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.5);'> That way our parts staff don't have to keep asking for the same equipment info.</span><br></p> | 2021-07-30 00:22 | 4368 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_3190_39a3eb7e | Need tech assistance to move Odoo instance |  |  | Development | DO NOT USE (old MMH: Help (P83)) | Jeff Gross | Levi Barnes | 3 | 3 | -3 | 0 |  | 4 | Complete | TRUE | Muhammad Saqlain Alam | 2021-03-19 17:59 | TRUE | Mountain Meadow Herbs | 0 | 20.5 | 0 | 164 |  | Complete | Naseeb Razaq | Done | FALSE | External - Client | Bilal Ahmad Khan | 2021-03-19 17:57 | Mountain Meadow Herbs, Gerry Carton | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-04-18 00:42 | 5190 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_2641_96a97384 | Create a list of Go-Live tasks for Wildleaf Las Vegas |  |  | Configuration | Wild Leaf: Las Vegas Go-Live (P57) | Jeff Gross | Fahad Hussain Malik | 0 | 0 | 0 | 0 |  | FALSE | Cancelled | TRUE | Muhammad Saqlain Alam | 2021-03-06 03:01 | FALSE | Wild Leaf Beverage | 24 | 53.8125 | 192 | 430.3181 |  | Cancelled | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2021-02-02 06:46 | Wild Leaf Beverage, Mitch Barnard_ | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>We need to acquire the following details:</p><p><br></p><p>1- Work centers Details</p><p>2- Cost per hour</p><p>3- Operations</p><p>4- Locations</p><p>5- Shipments</p><p>6- Routes</p><p>7- Putaway rules</p><p>8- Reordering rules</p> | 2021-04-16 20:19 | 6281 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_2116_2a14f980 | Deployed tasks Meeting | 2021-01-04 | 2021-01-10 | Configuration | Mid-America: Odoo Implementation (P37) | Levi Barnes | Raheel Aslam | 0.33 | 0.33 | 0.17 | 66 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-01-05 16:53 | TRUE | Mid-America Gardens, LLC | 0 | 0.3125 | 0.019178 | 2.4236 | 2021-01-04 | Complete | Naseeb Razaq | Done | FALSE |  | Raheel Aslam | 2021-01-05 16:52 | Mid-America Gardens, LLC, Thomas Johnson | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><br></p> | 2021-01-05 20:17 | 6943 | 0.5 | 0 | 0 | 0 | Normal | Sprint 2102
__export__.project_task_2022_a178d20b | Propertyworx Deployment 2051 | 2020-12-14 | 2020-12-20 | Configuration | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 5.05 | 5.05 | -5.05 | 0 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-22 16:08 | TRUE | EquityTeam | 0 | 0.5 | 0.0077037 | 3.9213 | 2020-12-14 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Muzher Siddique | 2020-12-22 16:07 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>List of tasks deployed.</p><p><br></p><p><img class="img-fluid o_we_custom_image img-thumbnail" src="/web/image/14169/Screenshot from 2020-12-22 16-07-49.png?access_token=08688f10-255d-4603-b5cd-3fa99abf65c4"><br></p> | 2020-12-22 21:02 | 7280 | 0 | 0 | 0 | 0 | Normal | Sprint 2051
__export__.project_task_1803_222bed44 | Project and AV Project List | 2020-12-07 | 2020-12-13 | Development | Continuant: AV Warehouse (P34) | Kaesi Lee | Danish Hassan | 5.42 | 5.42 | -1.42 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-12-07 21:15 | FALSE | Continuant | 0 | 11.875 | 0 | 95.3307 | 2020-12-07 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-12-07 21:15 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Every project in the Project module should be listed in the AV Tracker module (every existing project should have a corresponding AV Project).</p><p><br></p><p>When the AV Tracker module is installed an AV project should be created for every existing project in the Project module. </p> | 2020-12-23 20:35 | 7635 | 4 | 0 | 0 | 0 | Normal | Sprint 2050
__export__.project_task_1231_5e9787c9 | Error 403 for Portal Users | 2020-10-12 | 2020-10-18 | Bug Fix | Silverdale: Help (P12) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-22 20:37 | FALSE | Silverdale Technology LLC | 3.8125 | 23.8125 | 30.6125 | 190.625 | 2020-10-12 | Complete | Muhammad Zubair | InProgress | FALSE | External - 3rd Party | Nick Foy | 2020-09-17 02:20 | Silverdale Technology LLC | FALSE | FALSE | <p>Portal users are receiving an error when trying to post comments on a task.</p><p><br></p><p><br></p><p><br></p><p><br><span style="color: rgb(50, 50, 50); font-family: Poppins, sans-serif; font-size: 36px; font-weight: 700; letter-spacing: -0.5px; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; text-align: inherit;">403: Forbidden</span></p><p style="margin-bottom: 15px; padding: 0px; color: rgb(130, 130, 130); font-family: Poppins, sans-serif; font-size: 15px;">The page you were looking for could not be authorized.</p> | 2020-10-20 20:38 | 9598 | 0 | 0 | 0 | 0 | Normal | Sprint 2042
__export__.project_task_1175_c7c421dc | Splash Screen for Send Quotation | 2020-09-07 | 2020-09-13 | Development | Continuant: eCommerce (P9) | Gadha Continuant | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-04 02:53 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-09-07 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-09-04 02:53 | Continuant | FALSE | FALSE | <p>After you click send quotation, there should be a splash screen that appears when the quotation has been sent that says "Quotation has been sent!"</p> |  | 9909 | 0 | 0 | 0 | 0 | Normal | Sprint 30
__export__.project_task_940_b9d8e517 | Integrate GfK Etilize Catalog: Pull Tech Data U.S. and Ingram U.S. Product Codes | 2020-08-03 | 2020-08-09 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-10 21:49 | FALSE | Continuant | 7 | 0 | 55.8119 | 0 | 2020-08-03 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-30 22:42 | Continuant | FALSE | FALSE | <p>GFK Etilize keeps SKU numbers for Tech Data U.S. and Ingram U.S. We should be pulling that information and populating it in the Vendor Product ID field for Tech Data U.S. and Ingram U.S. It is likely this will be a separate API. </p> |  | 10753 | 0 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_923_551bcfec | API:My Bids:Postman | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-29 11:43 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-29 11:42 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10788 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_907_f0877797 | My bids Android-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:46 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00016651 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 2 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_896_a0f87a5a | Category list Android-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_839_0942fda6 | My bids iOS-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 2 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_833_6177f1fb | Add to watch list iOS-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_355_1b889e2b | Sponsor Meeting #5 | 2020-08-17 | 2020-08-23 | Development | Continuant: eCommerce (P9) | Nick Foy | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0 | 0 | 0.00032117 | 0 | 2020-08-17 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE |  |  | 11092 | 0 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_4534_cef3d137 | Revisiting the Project Requirements | 2021-08-09 | 2021-08-15 | Other | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 6 | 6 | 4 | 60 | 2021-08-13 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-12 16:22 | TRUE | Zuma Sales LLC | 0 | 2.0625 | 0 | 16.4082 | 2021-08-09 | Complete | Asfand Yaar | In Warranty | FALSE |  | Asfand Yaar | 2021-08-12 16:22 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-08-16 16:46 | 1688 | 10 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_4404_1fcdf732 | Split UEDF File that need activation (UEDF Activation File) | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 21.5 | 16.58 | -6.5 | 100 | 2021-08-12 | 2 | Complete | TRUE | Fahad Hassan | 2021-07-30 16:33 | TRUE | Cellpoint Corporation | 0 | 16.6875 | 0 | 133.4236 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-07-30 16:33 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Pre-requisite: <a href="https://www.silverdaletech.com/web#id=4364&amp;action=443&amp;model=project.task&amp;view_type=form&amp;cids=1&amp;menu_id=295">UEDF Export Import Utility Task</a></p><p><br></p><p><font style="color: rgb(0, 0, 0);">1. Export UEDF xml file based on the following:</font></p><p><font style="color: rgb(0, 0, 0);">a) Based on Status of the NMS Bounce response</font></p><p><font style="color: rgb(0, 0, 0);"><font style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; font-weight: 700; color: rgb(255, 156, 0);'><br></font></font></p><p><font style="color: rgb(0, 0, 0);"><font style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; color: rgb(255, 156, 0);'><b>Condition (For UEDF Activation):</b><br><b> - When disposition_id =<span style='color: rgb(255, 156, 0); font-family: "Lucida Grande", Helvetica, Verdana, Arial, sans-serif;'>'id does not exist' </span>, t</b></font><font style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; font-weight: 700; color: rgb(255, 156, 0);'>hen all these fields will be populated automatically with the mentioned default values (Please see xml file attached for naming of the fields):<br></font></font><font style="color: rgb(0, 0, 0);"><br></font></p><p><font style="color: rgb(0, 0, 0);"> i) Get the records based on Disposition_code is 'id does not exist' - from NMS model.</font></p><p><font style="color: rgb(0, 0, 0);"> ii) Create following xml files with following Data (An example xml activation file is attached)</font></p><ul><li><p><font style="color: rgb(0, 0, 0);">H - meidHex, meidDec, imeiDec</font></p></li><li><p><font style="color: rgb(0, 0, 0);">H3 - imeiDec</font></p></li><li><p><font style="color: rgb(0, 0, 0);">H5 - meidHex, meidDec, imei1, imei2</font></p></li><li><p><br></p></li></ul><p><font style="color: rgb(0, 0, 0);"> iii) xml report contains following fields data:</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'> <font color="#000000">a) Header Count (Default value=1)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'> <font color="#000000">b) Phone Type (Default Value= NW)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'> <font color="#000000">c) Phone Ownership (Default Value=DISH)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'> <font color="#000000">d) Transaction Type (Default Value=040)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'> <font color="#000000">e) Location Destination (Default Value=000)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'> <font color="#000000">f) uedf Revision Number (Default Value=XMLAUTH)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'> <font color="#000000">g) Eq</font><font style="color: rgb(0, 0, 0);" color="#000000">uipType (Default Value=CP)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><font style="color: rgb(0, 0, 0);"> h) ManufId (Default Value=436)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><font style="color: rgb(0, 0, 0);"> i) Manuf Name (Default Value= APPLE,INC) </font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><font style="color: rgb(0, 0, 0);"> j) msl (Default Value=0)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><font style="color: rgb(0, 0, 0);" color="#000000"></font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><font style="color: rgb(0, 0, 0);"> k) otks (Default Value=0)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><font style="color: rgb(0, 0, 0);"> l) File Sequence (Dynamic for each file and Should be 6 digits)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><font style="color: rgb(0, 0, 0);"> m) Device Count (according to number of devices or imeis included in the file)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><font style="color: rgb(0, 0, 0);"> n) PO Order (Taken from Purchase Order)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><font style="background-color: rgb(181, 239, 137); color: rgb(0, 0, 0);"> o) Factory Order (Dynamic for each file and should be like this with same number of digits for each Factory Order (0146-0013-02))</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><font style="color: rgb(0, 0, 0);"> p) Serial Type (This should be based on the Product type) Each file will have same Product type depending on the Variant (On the product form)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><font style="color: rgb(0, 0, 0);"> q) SKU (This is the Internal Reference from the Product)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><font style="color: rgb(0, 0, 0);"> r) SKU Name (This is the Internal Reference from the Product)<br></font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><font style="color: rgb(0, 0, 0);"> u) meidHex (From the NMS form)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><font style="color: rgb(0, 0, 0);"> v) meidDec (From the NMS form)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><font style="color: rgb(0, 0, 0);"> w) imeiDec (From the NMS form)</font></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'> <font class="text-black"> x) Software Version (Taken From the stock.production.lot)</font><font style="color: rgb(0, 0, 0);"><br></font></p><p><font style="color: rgb(0, 0, 0);">b) Naming convention of the file:</font></p><p><font style="color: rgb(0, 0, 0);"> </font><span style="color: rgb(0, 0, 0); font-family: inherit; font-style: inherit; font-variant-caps: inherit; font-variant-ligatures: inherit; font-weight: inherit; text-align: inherit;">spdish_YYYYMMDD_[run number].xml 5pm Mountain Standard Time is next day, exclude weekends and Holidays (YYYY is Year, MM is month, DD is Date, run number is unique and should not be repeated and should be 6 digits, no spacing)</span><br><br></p> | 2021-08-25 02:25 | 1999 | 15 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_3406_f907c49e | Customer portals | 2021-06-21 | 2021-06-27 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | FALSE | 0.17 | 0.17 | 9.83 | 1.7 | 2021-08-03 | FALSE | Cancelled | TRUE | Muhammad Saqlain Alam | 2021-07-19 18:59 | TRUE | Zuma Sales LLC | 58.625 | 41.1875 | 468.9914 | 329.3589 | 2021-06-21 | Cancelled | Asfand Yaar | In Warranty | FALSE |  | Bilal Ahmad Khan | 2021-04-23 00:09 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>What we are trying to accomplish?</p><p><br></p><p><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.5);'>An area they can see all their invoices, previous order history, etc.</span><br></p> | 2021-06-24 14:22 | 4368 | 10 | 0 | 0 | 0 | Normal | Sprint 2126
__export__.project_task_2036_db9f2b96 | Apply Filters to Transmitted Data |  |  | Development | Continuant: Power BI Integration (P30) | Kaesi Lee | Raheel Aslam | 0.33 | 0.33 | 2.67 | 11 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-12-24 02:19 | FALSE | Continuant | 0 | 19 | 0 | 152 |  | Complete | Muhammad Zubair | Cancelled | FALSE | Internal | Kaesi Lee | 2020-12-24 02:19 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Muzher has recommended creating a cache in order to filter the data that is being transferred. </p> | 2021-01-19 23:30 | 7246 | 3 | 0 | 0 | 0 | Normal
__export__.project_task_1890_3a7c515c | Fwd: Projects "tasks" not switching to different project after assignment (#37) | 2020-12-14 | 2020-12-20 | Configuration | PWX: Help (P23) | Levi Barnes | Nick Foy | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-12-15 20:16 | TRUE | EquityTeam | 0 | 1 | 0.038098 | 7.8445 | 2020-12-14 | Complete | Farman Ahmad Cheema | Done | TRUE |  | Nick Foy | 2020-12-15 20:14 | Silverdale Technology LLC, Nick Foy | Executive / Mechanisms | Silverdale Technology LLC | <p><br></p> | 2020-12-16 20:04 | 7444 | 0 | 0 | 0 | 0 | Normal | Sprint 2051
__export__.project_task_1630_d95e6121 | Display Proposal Summary and Statement of Work | 2021-02-15 | 2021-02-21 | Development | Continuant: Quotation Management / Automation (P31) | Nick Foy | Muzher Siddique | 4.33 | 4.33 | -0.66333 | 100 |  | FALSE | Complete | TRUE | Fahad Hassan | 2021-02-14 00:38 | FALSE | Continuant | 61 | 73.8125 | 488 | 590.4811 | 2021-02-15 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-11-20 02:16 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Each Sales Order has a Proposal Summary and a Statement of work, these should be visible to the customer via the client portal. <img class="img-fluid o_we_custom_image" src="/web/image/12824/Summary and Scope.jpg?access_token=b0c034bd-f8ed-4db6-9dbb-b5964436250d"></p> | 2021-03-03 20:29 | 8062 | 3.6667 | 0 | 0 | 0 | Normal | Sprint 2109
__export__.project_task_908_60a373f0 | Set batch API Android-Implementation | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:46 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00016651 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_903_ba76953d | Edit profile Android-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:46 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00016651 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_891_5a5112a8 | Select city Android-Implementation | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_552_2ef2bcd5 | API:Update Terms and condition | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:50 | FALSE | Cellpoint Corporation | 1.375 | 0 | 10.8272 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p>method: POST </p><p>Description: This API is used to update the details in the user table which shows that the user has accepted the latest terms and condition.</p><p>parameter : user_id,term_version</p><p>API will check user_id and existence user , and update term version into database table</p><p>retrieve the message (Updated the terms and conditions) </p><p><br></p><p> </p><p><br></p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_353_44990b59 | Sponsor Meeting #3 | 2020-08-03 | 2020-08-09 | Development | Continuant: eCommerce (P9) | Nick Foy | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0 | 0 | 0.00032117 | 0 | 2020-08-03 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE |  |  | 11092 | 0 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_344_420650a6 | Production Release #1 | 2020-08-03 | 2020-08-09 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-04 07:57 | FALSE | Continuant | 12.1875 | 0 | 97.7145 | 0 | 2020-08-03 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE | <p><br></p> |  | 11092 | 0 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_209_56ac4364 | Webkul Document | 2020-08-17 | 2020-08-23 | Development | Cellpoint: Odoo Back-End (P8) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-06-23 19:34 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-17 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-06-23 19:34 | Cellpoint Corporation | FALSE | FALSE | <p>Remaining Tasks</p><p><br></p><p><a href="https://docs.google.com/document/d/1hPX085Fz7Daockds11GO1MLrhMMrk7AXYd9300m-g4U/edit" style="font-family: -webkit-standard;">https://docs.google.com/document/d/1hPX085Fz7Daockds11GO1MLrhMMrk7AXYd9300m-g4U/edit</a><br><br></p><p>Test Script </p><p><br></p><p><a href="https://docs.google.com/spreadsheets/d/1kO1g3wmUVDgHpKVYB3jd_vV6_8myHun_TPj0BHBHs5U/edit?usp=drive_web&amp;ouid=116920360560259184307" style="font-family: -webkit-standard;">https://docs.google.com/spreadsheets/d/1kO1g3wmUVDgHpKVYB3jd_vV6_8myHun_TPj0BHBHs5U/edit?usp=drive_web&amp;ouid=116920360560259184307</a><br></p> |  | 11644 | 0 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_174_a0243bf8 | Tasks Outstanding and Past Due | 2020-08-17 | 2020-08-23 | Studio | Heronswood: Events (P3) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 | 2020-06-04 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-06-02 19:56 | FALSE | Port Gamble S’Klallam Foundation | 0 | 0 | 0 | 0 | 2020-08-17 | Complete | Naseeb Razaq | Done | FALSE |  | Nick Foy | 2020-06-02 19:56 | Port Gamble S’Klallam Foundation, Ross Bayton | Executive / Delivery / Alpha | FALSE | <p>On the My Collection Module, User will add Scheduled Actions.</p><p><br></p><p>User wants to add 2 Filter view that show:</p><p><br></p><p>1. Future Actions = My Collection items with an Action Schedule &gt; Today and Not Completed</p><p>2. Overdue Actions = My Collection items with an Action Scheduled =&lt; today and Not Completed</p><p><br></p><p><br></p> |  | 12148 | 0 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_4501_abbe390a | Deploy to Deployment + Production 2132 | 2021-08-09 | 2021-08-15 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hassan | 1.83 | 1.83 | -1.83 | 0 | 2021-08-11 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-10 18:06 | TRUE | Zuma Sales LLC | 0 | 1.5 | 0.019326 | 11.9229 | 2021-08-09 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-10 18:05 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>Tasks:</p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>4366</p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>4045</p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>Tickets</p> | 2021-08-11 23:35 | 1734 | 0 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_4361_7a841c38 | NMS Bounce Utility (In Operations Tab) | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Danish Hassan | 3.42 | 3.42 | 1.08 | 76 | 2021-08-12 | 1 | Complete | TRUE | Fahad Hassan | 2021-07-26 20:31 | TRUE | Cellpoint Corporation | 0 | 20.625 | 0 | 164.8985 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-07-26 20:31 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><font style="color: rgb(0, 0, 0);">1. Add a sub-menu in Operations Dropdown (In Inventory) that will open the '<b>NMS Bounce</b>' detail form. </font></p><p><font style="color: rgb(0, 0, 0);">2. The form should contain the following buttons</font></p><p><font style="color: rgb(0, 0, 0);"> Export NMS (</font><a href="/web#id=4362&amp;action=443&amp;model=project.task&amp;view_type=form&amp;cids=1&amp;menu_id=295"><font style="color: rgb(0, 0, 0);">Export NMS Button functionality task</font></a><font style="color: rgb(0, 0, 0);">)</font></p><p><font style="color: rgb(0, 0, 0);"> Import NMS (</font><a href="/web#action=443&amp;cids=1&amp;id=4369&amp;menu_id=295&amp;model=project.task&amp;view_type=form"><font style="color: rgb(0, 0, 0);">Import NMS button functionality task</font></a><font style="color: rgb(0, 0, 0);">)</font><br></p><p><font style="color: rgb(0, 0, 0);">3. Fields Required on the NMS Bounce detail form (Example of an ASN Vendor file is attached which contains these fields):</font></p><ul><li><p><font style="color: rgb(0, 0, 0);"> PO </font></p></li><li><p><font style="color: rgb(0, 0, 0);"> Supplier Name (Vendor)</font></p></li><li><p><font style="color: rgb(0, 0, 0);"> IMEI</font></p></li><li><p><font style="color: rgb(0, 0, 0);"> IMEI2</font></p></li><li><p><font style="color: rgb(0, 0, 0);"> meidHEX</font></p></li><li><p><font style="color: rgb(0, 0, 0);"> meidDEC</font><br></p></li><li><p><font style="color: rgb(0, 0, 0);"> Model</font></p></li><li><p><font style="color: rgb(0, 0, 0);"> Model Number</font></p></li><li><p><font style="color: rgb(0, 0, 0);"> Capacity</font><br></p></li><li><p><font style="color: rgb(0, 0, 0);"> Color</font></p></li><li><p><font style="color: rgb(0, 0, 0);"> SIM Technology </font></p></li></ul><p><br></p><p><br></p> | 2021-08-25 02:25 | 2092 | 4.5 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_2930_2ef96622 | Adding Role/Groups permission on accountability form | 2021-03-29 | 2021-04-04 | Development | PWX: Strategic Planning (P43) | Levi Barnes | Osama Khalid | 21.47 | 21.47 | -5.47 | 100 | 2021-03-17 | 3 | Complete | TRUE | Muhammad Saqlain Alam | 2021-03-09 20:55 | FALSE | EquityTeam | 0 | 28.125 | 0 | 225.0768 | 2021-03-29 | Complete | Naseeb Razaq | Done | FALSE |  | Levi Barnes | 2021-03-09 20:55 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>What we are trying to achieve? </p><p><br></p><p>As an employer, I would like to add role/group permissions to the accountability form, so that security management can be centralized.</p><p>As an employer, I would like user role/groups be inherited from both Odoo standard and accountability set on an employee, so that security management can be centralized.</p><p><br></p><p>What steps we need to follow:</p><p><br></p><p>1- Click on Brand Strategy module</p><p>2- Click on Accountability form</p><p>3- Add new "Security" tab on accountability form.</p><p>4- Add group lines like we did for task 2726</p><p><br></p><p>Acceptance Criteria:</p><p><br></p><p>Security groups are only removed on Employees/User, where security groups that have been added through accountability.</p><p>When security groups are removed from accountability, it removes the security group from all users associated through accountables_ids</p><p>When security groups are added from accountability, it adds the security group to all users associated through accountables_ids</p> | 2021-04-18 00:35 | 5427 | 16 | 0 | 0 | 0 | Normal | Sprint 2114
__export__.project_task_2635_c104bb8f | Daily Breaks/Dinner/Prayers |  |  | Internal Time Tracking | Silverdale: Time Tracking (P56) | Muhammad Afzaal | FALSE | 481.42 | 481.42 | -481.42 | 0 |  | FALSE | Cancelled | TRUE | FALSE | 2021-02-01 21:20 | FALSE | Silverdale Technology LLC | 0 | 53.625 | 0.0078713 | 429.0843 |  | Cancelled | Muhammad Afzaal | InProgress | FALSE |  | Muzher Siddique | 2021-02-01 21:20 | FALSE | FALSE | Silverdale Technology LLC | <p><br></p> | 2021-04-16 18:25 | 6291 | 0 | 0 | 0 | 0 | Normal
__export__.project_task_1885_6ae317eb | Propertyworx Deployment 2050 | 2020-12-07 | 2020-12-13 | Configuration | PWX: Help (P23) | Muzher Siddique | Muzher Siddique | 0.83 | 0.83 | 0.17 | 83 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-15 18:09 | TRUE | EquityTeam | 0 | 0.25 | 0 | 1.9098 | 2020-12-07 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Muzher Siddique | 2020-12-15 18:09 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>1528,1700,1692,1860,1845,1843,1719,1687 deployed on Production.<br></p> | 2020-12-15 20:04 | 7446 | 1 | 0 | 0 | 0 | Normal | Sprint 2050
__export__.project_task_1679_ec41e622 | Development Continuant: AV Warehouse | 2020-11-23 | 2020-11-29 | Configuration | Continuant: AV Warehouse (P34) | Muzher Siddique | FALSE | 0.33 | 0.33 | 0.17 | 66 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-12-01 16:45 | FALSE | Continuant | 0 | 0 | 0 | 0.24223 | 2020-11-23 | Complete | Muhammad Zubair | Done | FALSE |  | Muzher Siddique | 2020-12-01 16:45 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><br></p> | 2020-12-01 17:46 | 7783 | 0.5 | 0 | 0 | 0 | Normal | Sprint 2048
__export__.project_task_1664_c02ef44a | Schema for Belmont Integration | 2020-11-30 | 2020-12-06 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 0.5 | 0.5 | 4.5 | 10 |  | FALSE | Complete | TRUE | FALSE | 2020-11-25 22:59 | FALSE | Cellpoint Corporation | 0 | 13 | 0 | 104 | 2020-11-30 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Nick Foy | 2020-11-25 22:58 | Cellpoint Corporation | FALSE | Silverdale Technology LLC | <p>We need to provide a schema file to Belmont for sending over:</p><p><br></p><p>Auctions</p><p>Bids</p><p>Manifests</p><p>Invoice Lines</p><p>Buyers</p><p><br></p><p>The schema needs to be based on the field we pull for PowerBI reporting and not all fields.</p> | 2020-12-15 05:35 | 7921 | 5 | 0 | 0 | 0 | Normal | Sprint 2049
__export__.project_task_1515_09a31b5c | Test Connection from Power BI to Azure Server |  |  | Configuration | Continuant: Power BI Integration (P30) | Levi Barnes | Muzher Siddique | 0 | 0 | 1.5 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-10-31 02:01 | FALSE | Continuant | 0 | 4.125 | 0 | 32.7867 |  | Complete | Muhammad Zubair | Cancelled | FALSE |  | Kaesi Lee | 2020-10-31 02:00 | Continuant | FALSE | Silverdale Technology LLC | <p><br></p> | 2020-11-06 13:47 | 8542 | 1.5 | 0 | 0 | 0 | Normal
__export__.project_task_1205_95eb5c0f | Front End Fixes | 2020-09-07 | 2020-09-13 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-14 17:26 | FALSE | Cellpoint Corporation | 0 | 6.5 | 0 | 52 | 2020-09-07 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-09-14 17:26 | Cellpoint Corporation | FALSE | FALSE | <div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">1- Android push notification</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">2- Select category issue iOS</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">3- Select filter issue iOS</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">4- All bids filter issue</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">5- Address issue:</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">Address is automatically updated with “android family” when anything is edited in my profile.</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">6- Auction status is different in “My Bids” and “My Watchlist”</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">7- Country search issue ( iOS )</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">8- Download csv</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">9- Push notification in iOS</div><div style="caret-color: rgba(0, 0, 0, 0.847); color: rgba(0, 0, 0, 0.847); font-family: -apple-system-font; font-size: 12px;">10- Select city API: (Not getting complete city list)</div> | 2020-09-23 12:26 | 9655 | 0 | 0 | 0 | 0 | Normal | Sprint 30
__export__.project_task_942_5c506571 | Integrate GfK Etilize Catalog: Import Shorter Product Description | 2020-08-03 | 2020-08-09 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-04 03:43 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-04 03:43 | Continuant | FALSE | FALSE | <p>In the following link, GFK describes various tables that they use. There is a product descriptions table that has multiple types of description for each product. Use Type 2 which is a short description for the product description in odoo. </p><p><br></p><p><a href="http://docs.etilize.com/spexplus/2-2-database-tables/#Table_Attributenames" style="background-color: rgb(255, 255, 255);">http://docs.etilize.com/spexplus/2-2-database-tables/#Table_Attributenames</a><br></p><p><br></p><p>The link to the actual table which will have every product description and type is here: </p><p><br></p><p>ftp://ftp.etilize.com/content/EN_US/basic/basic_EN_US_current_mysql.zip<br></p><p><br></p> |  | 10652 | 0 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_827_d52925d6 | Location list iOS-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_826_f9317c2d | Seller list iOS-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_606_09b5330c | Test Ingram and Techdata Credentials | 2020-08-17 | 2020-08-23 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 4 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-25 02:43 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-17 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-25 02:43 | Continuant | FALSE | FALSE | <p><br></p> |  | 10893 | 4 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_549_4749478b | API:Bid History | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 4 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:41 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.6803 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 11009 | 4 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_538_72d14c9e | API:Lot view | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:42 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.6922 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_4515_2e143b2c | Fields to add, remove and functionality | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 2.42 | 2.42 | -0.42 | 100 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-08-11 06:19 | TRUE | Cellpoint Corporation | 0 | 8.6875 | 0 | 69.4236 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-08-11 06:19 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>1. Add the 'Hardware Version' field on product.template and product.product. It should be static with value = <b>A11 (APL1W72)</b></p><p>2. Remove <b>Hardware Version</b> field on IMEI form.</p><p><br></p> | 2021-08-25 02:25 | 1722 | 2 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_4461_5768a0dd | R&D Tax Cloud Calculation on Delivery Address | 2021-08-09 | 2021-08-15 | Research | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Raheel Aslam | 1.5 | 1.5 | 6.5 | 18.75 | 2021-08-13 | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2021-08-06 19:36 | TRUE | Zuma Sales LLC | 0 | 4.5 | 0 | 35.819 | 2021-08-09 | Complete | Asfand Yaar | In Warranty | FALSE |  | Fahad Hussain Malik | 2021-08-06 19:36 | Zuma Sales LLC, Jeremy Rabel | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><br></p> | 2021-08-13 14:25 | 1828 | 8 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_4369_ac882264 | NMS Bounce Form View (Import Utility) | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 13.33 | 13.33 | -1.33 | 100 | 2021-08-12 | 2 | Complete | TRUE | Fahad Hassan | 2021-07-27 21:37 | TRUE | Cellpoint Corporation | 0 | 19.5 | 0 | 155.8046 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-07-27 21:37 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><font style="color: rgb(0, 0, 0);">Pre-Requisite: (</font><a href="/web#id=4362&amp;action=443&amp;model=project.task&amp;view_type=form&amp;cids=1&amp;menu_id=295"><font style="color: rgb(0, 0, 0);">Task 4362</font></a><font style="color: rgb(0, 0, 0);">)</font><br><br><span style='color: rgb(0, 0, 0); font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>'Import NMS' file</span><br></p><p><br></p><p><font style="color: rgb(0, 0, 0);">1. 'Import NMS' Bounce Result Button on NMS Bounce Form</font></p><p><font style="color: rgb(0, 0, 0);">2. Need these fields in NMS Form (Attached file is for reference)</font></p><p><font style="color: rgb(0, 0, 0);"> a) Disposition Code </font></p><ul><li><p><font style="color: rgb(0, 0, 0);">0 - Acceptable</font></p></li><li><p><font style="color: rgb(0, 0, 0);">1 - Lost or Stolen (Unacceptable)</font></p></li><li><p><font style="color: rgb(0, 0, 0);">2 - Fraud (Unacceptable)</font></p></li><li><p><font style="color: rgb(0, 0, 0);">3 - Unprovisionable (Unacceptable)</font></p></li><li><p><font style="color: rgb(0, 0, 0);">ID does not exist - Requires an Activation Only UEDF</font></p></li></ul><p><font style="color: rgb(0, 0, 0);"> b) Activation Status</font><span style="color: rgb(0, 0, 0); font-style: inherit; font-variant-caps: inherit; font-variant-ligatures: inherit; font-weight: inherit; text-align: inherit;"><br> c) Activation Date</span><font style="color: rgb(0, 0, 0);"> </font></p><p><font style="color: rgb(0, 0, 0);"> d) De-activation Date</font></p><p><font style="color: rgb(0, 0, 0);"> e) Lock Status</font></p><ul><li><p><font style="color: rgb(0, 0, 0);">0 – Locked (only fails if Financial Eligibility Date has not yet occurred - if the date is in the future)</font></p></li><li><p><font style="color: rgb(0, 0, 0);">1 – Unlocked</font></p></li><li><p><font style="color: rgb(0, 0, 0);">2 – Unlocked</font></p></li><li><p><font style="color: rgb(0, 0, 0);">3 - Unlocked</font></p></li></ul><p><font style="color: rgb(0, 0, 0);"> f) Financial Eligibility Date</font></p><p><font style="color: rgb(0, 0, 0);"> g) Customer (res_partner)</font></p><p><font style="color: rgb(0, 0, 0);"> h) Valid TAC<br></font></p><p><font style="color: rgb(0, 0, 0);">3. When the file is selected and imported the values of above fields in file should reflect with each serial (IMEI)</font></p><p><font style="color: rgb(0, 0, 0);">4. Many2One relation with each Serial (IMEI) (stock.production.lot)</font></p><p><font style="color: rgb(0, 0, 0);">5. Add SKU field in NMS form. </font></p><p><font style="color: rgb(0, 0, 0);">6. Fields to be added in NMS Bounce form (The data received from Phone Check import, the values of the following fields should be updated accordingly):</font></p><p><font style="color: rgb(0, 0, 0);"></font></p><ul><li><p><font style="color: rgb(0, 0, 0);">MEIDHex2</font></p></li><li><p><font style="color: rgb(0, 0, 0);">MEIDDec2</font></p></li></ul><p><font style="color: rgb(0, 0, 0);"> </font></p> | 2021-08-25 02:25 | 2066 | 12 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_1869_b91e24d9 | Recurring Scheduled Actions |  |  | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 0.5 | 0.5 | 15.5 | 3.12 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-15 03:48 | TRUE | EquityTeam | 0.0625 | 26.9375 | 0.25731 | 215.1943 |  | Complete | Farman Ahmad Cheema | Done | FALSE | External - Client | Nick Foy | 2020-12-14 21:45 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p><span style="font-size: 11pt; font-family: Calibri; color: black;">Provide an estimate on hours for recreating this functionality:</span><br><br><a href="https://apps.odoo.com/apps/modules/14.0/project_recurring_task_checklist/#attr=" target="_blank" rel="noreferrer noopener" style='color: rgb(0, 58, 57); background-color: rgb(255, 255, 255); display: inline-block; word-break: break-all; font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>https://apps.odoo.com/apps/modules/14.0/project_recurring_task_checklist/#attr=</a><br><span style="font-size: 11pt; font-family: Calibri; color: black;"> </span><br></p> | 2021-01-20 20:56 | 7466 | 16 | 0 | 0 | 0 | Normal
__export__.project_task_1839_50faaffe | User Group for Data Migration Module Access | 2020-12-14 | 2020-12-20 | Development | Continuant: Power BI Integration (P30) | Kaesi Lee | Danish Hassan | 2.77 | 2.77 | 0.23 | 92.33 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-12-09 02:47 | FALSE | Continuant | 0 | 14.5 | 0 | 116 | 2020-12-14 | Complete | Muhammad Zubair | Cancelled | FALSE |  | Kaesi Lee | 2020-12-09 02:47 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>As a system admin, I want to limit who has access to the data migration module so I want to create a user group in Odoo called "Data Migration Module". Only Users that have been added to the user group "Data Migration Module" will be able to view, access and configure models in the Data Migration Module. </p> | 2020-12-29 17:10 | 7605 | 3 | 0 | 0 | 0 | Normal | Sprint 2051
__export__.project_task_1658_fc856d53 | Auto Bids are not in order (Bid history) | 2020-11-23 | 2020-11-29 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Shajahan | 6 | 6 | -6 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-11-25 16:27 | FALSE | Cellpoint Corporation | 0 | 8.5625 | 0 | 68.5442 | 2020-11-23 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Roshan Mecoth | 2020-11-25 16:27 | Cellpoint Corporation | FALSE | Deerom Technologies Pvt. Ltd. | <p><br></p> | 2020-12-08 05:42 | 7928 | 0 | 0 | 0 | 0 | Normal | Sprint 2048
__export__.project_task_1177_04213b2c | Product Details Page: Conditional Hide | 2020-09-07 | 2020-09-13 | Development | Continuant: eCommerce (P9) | Gadha Continuant | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-09-04 21:32 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-09-07 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-09-04 21:32 | Continuant | FALSE | FALSE | <p>If availability is zero or price is unavailable for a vendor on the product details page, "add to cart" should not be displayed. </p> |  | 9891 | 0 | 0 | 0 | 0 | Normal | Sprint 30
__export__.project_task_884_e2f027f7 | Auction detail Android-Implementation | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 2 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_818_410dc2c2 | Make an offer iOS-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_602_a2af43d7 | Custom Module Dependencies List | 2020-08-03 | 2020-08-09 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 | 2020-08-13 | FALSE | Complete | TRUE | FALSE | 2020-07-25 00:13 | FALSE | Continuant | 1 | 0 | 8 | 0 | 2020-08-03 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-23 23:56 | Continuant | FALSE | FALSE | <p>Create a list of custom module dependencies to provide to Continuant. </p> |  | 10920 | 0 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_536_1b27acf6 | API:Place a Bid | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 8 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:42 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.7036 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 11009 | 8 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_533_5437231f | API:Product List | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 4 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:43 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.7194 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>1, Create a URL </p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>2, Fetch all Products </p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>3, Sharing response over API</p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><br></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><br></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>Every APIs has some conditions and Status we need to share with team ... that will be done using API document shared </p> |  | 11009 | 4 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_532_7d9ed12f | API:Login | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:43 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.715 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p>method: POST</p><p>Description: User login from this API with email and password. If that email and password exist in the “users” table then only the user can log in to the app otherwise it shows an alert message to check the username and password.</p><p>parameter: Email, Password, DevToken, DevType, AppVersion</p><p>API will check email and password in database table (res.partner) and also check cpbid.versions in database. set user_location_id,user_location,verify token,cpbid_status using API.</p><p><br></p><p>In return send all these parameters and a “verify token”.</p><p><br></p><p>Verify token: It is used to verify a user that it can log in to a single device only. User already log in by one device a verify token is generated and save in the “users” table, if that user tries login to another device again a verify token is generated and previous verify token got expired, old user’s session got expired and logout from the device. One account can be accessed in only one device with a verify token</p><p><br></p><p>Status 1= for approved user</p><p> Status 2= in this case user need to verify his email to get approval from the admin </p><p>Status 3= in this case user email is verified but still not approved by admin. meanwhile, user can access demo feature in-app but not live<br></p><p><br></p><p><br></p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_337_44062e82 | Carrier: Create test labels | 2020-07-27 | 2020-08-02 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 8 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-30 01:52 | FALSE | Continuant | 9.1875 | 0 | 73.7145 | 0 | 2020-07-27 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE | <p><br></p> |  | 11092 | 8 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_335_e4e8b7a2 | Carrier: agree service levels to be offered | 2020-07-27 | 2020-08-02 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-25 00:22 | FALSE | Continuant | 6.1875 | 0 | 49.7145 | 0 | 2020-07-27 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE | <p><br></p> |  | 11092 | 0 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_302_33176a79 | Payment: Get Stripe credentials | 2020-07-20 | 2020-07-26 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0.8125 | 0 | 6.2858 | 0 | 2020-07-20 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-16 02:41 | Continuant | FALSE | FALSE |  |  | 11109 | 0 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_295_04ce3826 | Website: Install Module | 2020-07-20 | 2020-07-26 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0.8125 | 0 | 6.2858 | 0 | 2020-07-20 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-16 02:36 | Continuant | FALSE | FALSE |  |  | 11109 | 0 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_292_6a965156 | Hosting: Get Hosting Information | 2020-07-12 | 2020-07-19 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0.8125 | 0 | 6.2856 | 0 | 2020-07-12 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-16 00:17 | Continuant | FALSE | FALSE | <p>C-Panel access is required in order to redirect the web domain to Odoo if they haven't created the website yet. </p> |  | 11112 | 0 | 0 | 0 | 0 | Normal | Sprint 22
__export__.project_task_272_e436a079 | Group Auctions - Marketplace | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan | FALSE | 0 | 0 | 32 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-15 15:30 | FALSE | Cellpoint Corporation | 0.1875 | 0 | 1.2571 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-15 14:15 | Cellpoint Corporation | FALSE | FALSE | <p>Group auctions to show under marketplace on Web + APPs</p><p>When a marketplace is selected from web or mobile interface </p><p>We will be showing auctions grouped based to sellers assigned to that marketplace </p><p><br></p> |  | 11122 | 32 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_223_89282658 | Create and send initial proposal | 2020-07-06 | 2020-07-12 | Development | Continuant: eCommerce (P9) | Nick Foy | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 14.8125 | 0 | 118.2856 | 0 | 2020-07-06 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-06-26 02:52 | Continuant | FALSE | FALSE | <p><br></p> |  | 11589 | 0 | 0 | 0 | 0 | Normal | Sprint 21
__export__.project_task_222_c4f06cef | Prepare estimate | 2020-07-06 | 2020-07-12 | Development | Continuant: eCommerce (P9) | Nick Foy | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 14.8125 | 0 | 118.2858 | 0 | 2020-07-06 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-06-26 02:52 | Continuant | FALSE | FALSE | <p><br></p> |  | 11589 | 0 | 0 | 0 | 0 | Normal | Sprint 21
__export__.project_task_4388_fb1d01aa | Scan POS Label | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 7.92 | 7.92 | 0.08 | 99 | 2021-08-12 | FALSE | Complete | TRUE | Fahad Hassan | 2021-07-29 23:40 | TRUE | Cellpoint Corporation | 0 | 21.25 | 0 | 169.7643 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-07-29 23:40 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Add a field config setting under inventory section : Max number of POS in Package. </p><p>Create a new button on packages named "Scan POS Label" if it will be visible only is_parent field is <font style="background-color: rgb(255, 0, 0);">false</font> (Created by <a href="/web#id=4358&amp;action=443&amp;model=project.task&amp;view_type=form&amp;cids=1&amp;menu_id=295">https://silverdaletech.odoo.com/web#id=4358&amp;action=443&amp;model=project.task&amp;view_type=form&amp;cids=1&amp;menu_id=295</a>) and len(content) &lt; <span style="color: rgb(0, 0, 0); font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;">Max number of POS in Package</span></p><p><br></p><p>It will open up a new wizard.<br>Fields in wizard:</p><p><br></p><p>Type: many2one, Package (Readonly as it will be auto selected)</p><p>Type: one2many field (POS Labels) --- (Fields: Label (Char))</p><p><br></p><p>When the len(<span style="color: rgb(0, 0, 0); font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;">one2many) + len(content of packages) == </span><span style="color: rgb(0, 0, 0); font-size: inherit; font-style: inherit; font-variant-ligatures: inherit; font-variant-caps: inherit; font-weight: inherit; text-align: inherit;">Max number of POS in Package, it will automatically close the wizard, will create records in packages content tab.</span><br><br></p><p>Status change of all Serials to: Pack</p><p><br></p><p><br></p><p><br></p><p><br></p> | 2021-08-31 02:25 | 2016 | 8 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_4378_25b614d3 | Split UEDF File by SKU | 2021-08-16 | 2021-08-22 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 18.42 | 18.42 | -3.42 | 100 | 2021-08-12 | 2 | Complete | TRUE | Fahad Hassan | 2021-07-29 03:13 | TRUE | Cellpoint Corporation | 0 | 21.9375 | 0 | 175.205 | 2021-08-16 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-07-29 03:13 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Pre-requisite: <a href="https://www.silverdaletech.com/web#id=4364&amp;action=443&amp;model=project.task&amp;view_type=form&amp;cids=1&amp;menu_id=295">UEDF Export Import Utility Task</a></p><p><br></p><p><font style="color: rgb(0, 0, 0);">1. Export UEDF xml file based on the following:</font></p><p><font style="color: rgb(0, 0, 0);">a) Based on Status of the NMS Bounce response</font></p><p><font style="color: rgb(0, 0, 0);"> i) Get the records based on Disposition_code is '0' - from NMS model.</font></p><p><font style="color: rgb(0, 0, 0);"> ii) Create following xml files with following Data (An example xml activation file is attached)</font></p><ul><li><p><font style="color: rgb(0, 0, 0);">H - meidHex, meidDec, imeiDec</font></p></li><li><p><font style="color: rgb(0, 0, 0);">H3 - imeiDec</font></p></li><li><p><font style="color: rgb(0, 0, 0);">H5 - meidHex, meidDec, imei1, imei2</font></p></li></ul><p><font style="color: rgb(0, 0, 0);"> iii) xml report contains following fields data in the header:</font></p><p> <font color="#000000">Condition (For UEDF ASN): When disposition_id =0 , then all these fields will be populated automatically with the mentioned default values (Please see xml file attached for naming of the fields):</font></p><p> <font color="#000000"> </font></p><p> <font color="#000000">a) Header Count (Default value=1)</font></p><p> <font color="#000000">b) Phone Type (Default Value= RW)</font></p><p> <font color="#000000">c) Phone Ownership (Default Value=DISH)</font></p><p> <font color="#000000">d) Transaction Type (Default Value=10)</font></p><p> <font color="#000000">e) Location Destination (Default Value=22)</font></p><p> <font color="#000000">f) uedf Revision Number (Default Value=XMLAUTH)</font></p><p> <font color="#000000">g) Eq</font><font color="#000000" style="color: rgb(0, 0, 0);">uipType (Default Value=CP)</font></p><p><font style="color: rgb(0, 0, 0);"> h) ManufId (Default Value=436)</font></p><p><font style="color: rgb(0, 0, 0);"> i) Manuf Name (Default Value= APPLE,INC) </font></p><p><font style="color: rgb(0, 0, 0);"> j) msl (Default Value=0)</font></p><p><font style="color: rgb(0, 0, 0);" color="#000000"></font></p><p><font style="color: rgb(0, 0, 0);"> k) otks (Default Value=0)</font></p><p><font style="color: rgb(0, 0, 0);"> l) File Sequence (Dynamic for each file and Should be 6 digits)</font></p><p><font style="color: rgb(0, 0, 0);"> m) Device Count (according to number of devices or imeis included in the file)</font></p><p><font style="color: rgb(0, 0, 0);"> n) PO Order (Taken from Purchase Order)</font></p><p><font style="color: rgb(0, 0, 0);"> o) Factory Order (Dynamic for each file and should be like this with same number of digits for each Factory Order (0146-0013-02))</font></p><p><font style="color: rgb(0, 0, 0);"> p) Serial Type (This should be based on the Product type) Each file will have same Product type depending on the Variant (On the product form)</font></p><p><font style="color: rgb(0, 0, 0);"> q) SKU (This is the Internal Reference from the Product)</font></p><p><font style="color: rgb(0, 0, 0);"> r) SKU Name (This is the Internal Reference from the Product)<br> s) Lpn (This is the Pallet label number - each file will have different) </font><font style="color: rgb(255, 156, 0);">Update: The value of lpn will be taken from Parent Package number</font></p><p><font style="color: rgb(0, 0, 0);"> t) Carton (This is the Carton label number - this will change after every 10 IMEIs) </font><font style="color: rgb(255, 156, 0);">Update: The value of Carton will be taken from Package number</font></p><p><font style="color: rgb(0, 0, 0);"> u) meidHex (From the NMS form)</font></p><p><font style="color: rgb(0, 0, 0);"> v) meidDec (From the NMS form)</font></p><p><font style="color: rgb(0, 0, 0);"> w) imeiDec (From the NMS form)</font><br></p><p> <br></p><p><font style="color: rgb(0, 0, 0);">b) Naming convention of the file:</font></p><p><font style="color: rgb(0, 0, 0);"> </font><span style="color: rgb(0, 0, 0); font-family: inherit; font-style: inherit; font-variant-caps: inherit; font-variant-ligatures: inherit; font-weight: inherit; text-align: inherit;">spdish_YYYYMMDD_[run number].xml 5pm Mountain Standard Time is next day, exclude weekends and Holidays (YYYY is Year, MM is month, DD is Date, run number is unique and should not be repeated and should be 6 digits, no spacing)</span><br><br></p><p><font style="color: rgb(255, 156, 0);">2. Adding Filename field and filling contents (</font><b><font style="color: rgb(255, 156, 0);">Updated Description Aug 2)</font></b><font style="color: rgb(255, 156, 0);">:</font></p><p><br></p><p><font style="color: rgb(255, 156, 0);">a) Add field UEDF Filename on Transfer Form.</font></p><p><font style="color: rgb(255, 156, 0);">b) The contents of the filename that is created above should be populated in this field.</font></p><p><br></p><p><font style="color: rgb(255, 156, 0);">3. Export UEDF ASN Button (</font><span style="color: rgb(255, 156, 0); font-style: inherit; font-variant-caps: inherit; font-variant-ligatures: inherit; font-weight: inherit; text-align: inherit;">Updated Description (Aug 2)):</span><br><font style="color: rgb(255, 156, 0);">a) Export UEDF ASN button should be in Package model</font></p><p><font class="text-black"> </font></p><p><br></p><p><br></p> | 2021-08-31 02:25 | 2037 | 15 | 0 | 0 | 0 | Normal | Sprint 2134
__export__.project_task_1825_4375fd75 | Propertyworx Deployment 2049 | 2020-11-30 | 2020-12-06 | Configuration | PWX: Help (P23) | Muzher Siddique | FALSE | 2 | 2 | 0 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-08 18:16 | TRUE | EquityTeam | 0 | 1.9375 | 0 | 15.7318 | 2020-11-30 | Complete | Farman Ahmad Cheema | Done | FALSE |  | Muzher Siddique | 2020-12-08 18:16 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>Modules deployed: company_strategy, propertyworx_ext for 2 tasks (1694,1675)</p><p>Steps to follow:</p><p>Please test the complete AV Tracker module and record the video during QA. And please mention date and time on recording before you start it.</p><p>Attach the video in this task. </p><p><br></p> | 2020-12-10 17:47 | 7614 | 2 | 0 | 0 | 0 | Normal | Sprint 2049
__export__.project_task_1643_2b6bbc33 | Continuant: Deploy AV Tracker Code 2047 | 2020-11-16 | 2020-11-22 | Configuration | Continuant: AV Warehouse (P34) | Muzher Siddique | FALSE | 0.5 | 0.5 | 0.5 | 50 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-11-24 19:50 | FALSE | Continuant | 0 | 7.25 | 0 | 58.1749 | 2020-11-16 | Complete | Muhammad Zubair | Done | FALSE |  | Muzher Siddique | 2020-11-24 19:50 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>Deploy Code of AV Warehouse. </p> | 2020-12-03 22:52 | 7948 | 1 | 0 | 0 | 0 | Normal | Sprint 2047
__export__.project_task_1628_07cc45a3 | Wrong Winner Updated | 2020-11-16 | 2020-11-22 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 9.5 | 9.5 | -9.5 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-11-19 20:17 | FALSE | Cellpoint Corporation | 0 | 10.1875 | 0 | 81.7249 | 2020-11-16 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Muhammad Afzaal | 2020-11-19 20:17 | Cellpoint Corporation | FALSE | Deerom Technologies Pvt. Ltd. | <p><br></p> | 2020-12-03 22:53 | 8068 | 0 | 0 | 0 | 0 | Normal | Sprint 2047
__export__.project_task_906_8f50dbd6 | Notification list Android-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:46 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00016651 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_597_ec67c3a9 | API:Category List :APPMAVEN | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 3 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-23 12:00 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-23 12:00 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10932 | 3 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_303_58c8e363 | Carrier: Get Credentials for FedEx and UPS | 2020-07-12 | 2020-07-19 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0.8125 | 0 | 6.2856 | 0 | 2020-07-12 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-16 02:42 | Continuant | FALSE | FALSE | <p><br></p> |  | 11109 | 0 | 0 | 0 | 0 | Normal | Sprint 22
__export__.project_task_296_07563dbc | Website: Configure Module | 2020-07-20 | 2020-07-26 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0.8125 | 0 | 6.2858 | 0 | 2020-07-20 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-16 02:36 | Continuant | FALSE | FALSE |  |  | 11109 | 0 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_290_33ed0d91 | Website: Create Website with Basic Functionality | 2020-07-20 | 2020-07-26 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 16:19 | FALSE | Continuant | 3.4375 | 0 | 27.3097 | 0 | 2020-07-20 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-16 00:16 | Continuant | FALSE | FALSE | <p><br></p> |  | 11112 | 2 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_267_755664e4 | Setup Continuant Project Access For Allison | 2020-07-12 | 2020-07-19 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 1.8125 | 0 | 14.2858 | 0 | 2020-07-12 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-15 00:29 | Continuant | FALSE | FALSE | <p><br></p> |  | 11136 | 0 | 0 | 0 | 0 | Normal | Sprint 22
__export__.project_task_221_025e41b2 | Initial Review of Requirements | 2020-07-06 | 2020-07-12 | Development | Continuant: eCommerce (P9) | Nick Foy | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 14.8125 | 0 | 118.2856 | 0 | 2020-07-06 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-06-26 02:51 | Continuant | FALSE | FALSE | <p><br></p> |  | 11589 | 0 | 0 | 0 | 0 | Normal | Sprint 21
__export__.project_task_204_aeb33e0e | Lot Extension | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan | FALSE | 0 | 0 | 6 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-10 12:10 | FALSE | Cellpoint Corporation | 12.3125 | 0 | 98.4796 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-06-23 19:31 | Cellpoint Corporation | FALSE | FALSE | <p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">We’ve 2 minutes extension feature in the app which is custom development from the webkul team.</span></p><p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">It is require some fixing in order to work according to our requirements</span></p><p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">When 2 buyers are placing same mymaxbid limit</span></p><p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;"> Buyer one is the winner in this case. Now if buyer one increases his maxbid limit, bid is increased by increment rule as well as 2 extension.</span></p><p><b id="docs-internal-guid-41a15921-7fff-33c0-5b4b-09cbacb5a250" style="caret-color: rgb(0, 0, 0); color: rgb(0, 0, 0); font-family: -webkit-standard; font-style: normal; font-variant-caps: normal; letter-spacing: normal; orphans: auto; text-align: start; text-indent: 0px; text-transform: none; white-space: normal; widows: auto; word-spacing: 0px; -webkit-text-size-adjust: auto; -webkit-text-stroke-width: 0px; text-decoration: none; font-weight: normal;"><br></b></p><p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">Correction: We want bid increased or 2 minutes extended if buyer 2 (who losing the auction) places a bid</span></p><p><span style="caret-color: rgb(0, 0, 0); color: rgb(0, 0, 0); font-family: -webkit-standard;"></span><br class="Apple-interchange-newline" style="caret-color: rgb(0, 0, 0); color: rgb(0, 0, 0); font-family: -webkit-standard;"></p> |  | 11645 | 6 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_199_25d4592a | Make an offer for Web | 2020-07-12 | 2020-07-19 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan | FALSE | 0 | 0 | 16 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-10 12:22 | FALSE | Cellpoint Corporation | 12.3125 | 0 | 98.5646 | 0 | 2020-07-12 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-06-23 19:26 | Cellpoint Corporation | FALSE | FALSE | <p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">Buyers can make an offer if they think the reserve for a product is too high. Offer should be less than reserver price.</span></p><p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">We’ve a separate table to maintain that. </span></p><p dir="ltr" style="line-height: 1.38; margin-top: 0pt; margin-bottom: 0pt;"><span style="font-size: 11pt; font-family: Arial; color: rgb(0, 0, 0); background-color: transparent; font-weight: 400; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; font-variant-east-asian: normal; font-variant-position: normal; text-decoration: none; vertical-align: baseline; white-space: pre-wrap;">We would like to have that available for our web users as well</span></p><p><span id="docs-internal-guid-52b85447-7fff-39b6-7360-574859b5b8d7" style="caret-color: rgb(0, 0, 0); color: rgb(0, 0, 0); font-family: -webkit-standard;"></span><br class="Apple-interchange-newline" style="caret-color: rgb(0, 0, 0); color: rgb(0, 0, 0); font-family: -webkit-standard;"></p> |  | 11645 | 16 | 0 | 0 | 0 | Normal | Sprint 22
__export__.project_task_4364_0051b8f4 | UEDF File Import Export Utility | 2021-08-09 | 2021-08-15 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Danish Hassan | 3.5 | 3.5 | 0.5 | 87.5 | 2021-08-12 | 1 | Complete | TRUE | Fahad Hassan | 2021-07-27 01:33 | TRUE | Cellpoint Corporation | 0 | 20.125 | 0 | 160.8717 | 2021-08-09 | Complete | Farman Ahmad Cheema | In Warranty | FALSE |  | Farman Ahmad Cheema | 2021-07-27 01:33 | Cellpoint Corporation, Juan Carlos | Executive / Delivery / Bravo | Silverdale Technology LLC | <p>1. On the NMS Bounce Utility view, have to add the following buttons:</p><p><br></p><p>a) Export UEDF ASN button </p><p><br></p><p>b) Export UEDF Activation button</p><p> </p><p>c) Import UEDF Response button</p><p><br></p><p>2. Have to add the following fields on the Serial Form and NMS Bounce Form:</p><p><br></p><p>a) 'UEDF Status' with following values:</p><p> i) <span style="text-align: inherit;">UEDF Activated</span><br></p><p> ii) ASN Requested Before</p><p> iii) ASN Processed</p> | 2021-08-25 02:25 | 2086 | 4 | 0 | 0 | 0 | Normal | Sprint 2133
__export__.project_task_1720_7546b653 | activity view: Research Activity Access Rights | 2020-12-07 | 2020-12-13 | Configuration | PWX: Help (P23) | Levi Barnes | Fahad Hassan | 4 | 4 | 1 | 80 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-03 16:03 | TRUE | EquityTeam | 0 | 5.3125 | 0 | 42.5138 | 2020-12-07 | Complete | Farman Ahmad Cheema | Done | TRUE |  | Muzher Siddique | 2020-12-03 16:03 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | Silverdale Technology LLC | <p>Research if it is possible to view the schedule activities of all users. </p> | 2020-12-10 19:33 | 7736 | 5 | 0 | 0 | 0 | Normal | Sprint 2050
__export__.project_task_1580_1c508c43 | Require Avalara Tax Calculation to Send Quotation | 2020-11-23 | 2020-11-29 | Development | Continuant: Quotation Management / Automation (P31) | Kaesi Lee | Raheel Aslam | 3.83 | 3.83 | 0.0033333 | 99.91 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-11-11 01:27 | FALSE | Continuant | 0 | 19 | 0 | 152 | 2020-11-23 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-11-11 01:27 | Continuant, Allison Beers | Executive / Delivery / Bravo | Silverdale Technology LLC | <p><span style='font-size:11.0pt;font-family:"Calibri",sans-serif; mso-fareast-font-family:Calibri;mso-fareast-theme-font:minor-latin;mso-ansi-language: EN-US;mso-fareast-language:EN-US;mso-bidi-language:AR-SA'>Prevent account executive from sending quotation to the customer if Avalara tax amount is not calculated. </span></p> | 2020-12-08 05:42 | 8279 | 3.8333 | 0 | 0 | 0 | Normal | Sprint 2048
__export__.project_task_1081_daa32d48 | Product Mapping: GFK to Synnex | 2020-08-17 | 2020-08-23 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-14 20:42 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-08-17 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-08-14 20:42 | Continuant | FALSE | FALSE | <p>Identify what data is necessary to map GFK products to Synnex Products. </p> |  | 10395 | 0 | 0 | 0 | 0 | Normal | Sprint 27
__export__.project_task_939_512e683c | Integrate GfK Etilize Catalog: Include Weight Unit Conversion | 2020-07-27 | 2020-08-02 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-30 22:40 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-30 22:40 | Continuant | FALSE | FALSE | <p>The unit of measurement for weight that GFK uses is lbs and oz. We need to convert that to KGs in API. </p> |  | 10753 | 0 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_932_4b615bd8 | Create Clean Continuant Database | 2020-07-27 | 2020-08-02 | Configuration | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-29 22:06 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-29 22:06 | Continuant | FALSE | FALSE | <p>We need to have a database that hasn't been changed from the database dump file that Continuant provided. We will use this database as a reference for their current configuration. </p> |  | 10778 | 0 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_921_b5752446 | API:Place a Bid:Postman | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-29 11:41 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-29 11:41 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10788 | 1 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_555_15a897d7 | API:Change Password | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 3 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:49 | FALSE | Cellpoint Corporation | 1.375 | 0 | 10.8153 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 11009 | 3 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_274_1ba66ec2 | Group Buyers for Seller - Marketplace | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan | FALSE | 0 | 0 | 24 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-15 15:30 | FALSE | Cellpoint Corporation | 0.125 | 0 | 1.2003 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-15 14:18 | Cellpoint Corporation | FALSE | FALSE | <p>Group buyers for marketplace and Sellers</p><p><br></p><p>When we a new seller is created. </p><p>1, We either assign all CPBids buyers or only few CPBids buyers (or they bring their buyers on board) to that seller.</p><p>When this buyer launches an auction, only their assigned buyers will see those auctions</p><p><br></p><p><br></p> |  | 11122 | 24 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_248_62d59120 | Project Plan - Post 20th July | 2020-07-12 | 2020-07-19 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 5.875 | 0 | 46.9476 | 0 | 2020-07-12 | Complete | Muhammad Zubair | Done | FALSE |  | Muhammad Afzaal | 2020-07-08 21:20 | Continuant | FALSE | FALSE | <p><br></p> |  | 11283 | 0 | 0 | 0 | 0 | Normal | Sprint 22
__export__.project_task_1692_de752c7a | appraisals scorecard | 2020-12-07 | 2020-12-13 | Development | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 12.75 | 12.75 | -0.75 | 100 |  | FALSE | Complete | TRUE | Muhammad Saqlain Alam | 2020-12-01 22:55 | TRUE | EquityTeam | 0 | 15.8125 | 0 | 126.5861 | 2020-12-07 | Complete | Farman Ahmad Cheema | Done | FALSE | Internal | Levi Barnes | 2020-12-01 22:55 | EquityTeam, Mark Thompson | Executive / Delivery / Alpha | FALSE | <p><span> </span><span> </span>Form view<img src="https://documents.lucid.app/documents/e2f9a90f-ea20-4b56-bd16-3dda9494334d/pages/0_0?a=1030&amp;x=-48&amp;y=-1326&amp;w=1387&amp;h=1119&amp;store=1&amp;accept=image%2F*&amp;auth=LCA b38e6e0cd3fe4c45f997a3bd2ec8fafd052d8dcd-ts%3D1606935684" width="1041" height="839"><br>Score is the sum of all fields multplied by percentage(weight)</p><p><br></p><p><br></p><p>Form View</p><p><span> </span><img src="https://documents.lucid.app/documents/e2f9a90f-ea20-4b56-bd16-3dda9494334d/pages/0_0?a=1022&amp;x=206&amp;y=86&amp;w=1199&amp;h=953&amp;store=1&amp;accept=image%2F*&amp;auth=LCA d72243e423bf374be252ca48af6c6c7cb80fdf85-ts%3D1606935684" width="899" height="714"><br></p><p><br></p><p>score = (4.2 * .5) + (40 * .0625) = 4.1</p><p><br></p><p>If score is &gt; focus goal then make score text green</p><p>if score = focus goal keep text black</p><p>if score &lt; focus goal make text red</p><p><br></p><p><br></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><br></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>Score Cards assign employees to focus areas and based on frequency, will create a Score item based on frequency. A list view with employee, score, and focus area sorted newest to oldest</p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><br></p><p style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>A menu access point has not been determined for these views.</p> | 2020-12-23 20:35 | 7777 | 12 | 0 | 0 | 0 | Normal | Sprint 2050
__export__.project_task_882_9bf691b9 | Product list Android-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 2 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_829_7c1de471 | Product status iOS-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_594_e5222bd2 | API:Logout:APPMAVEN | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 4 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-23 11:58 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-23 11:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10932 | 4 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_340_da290258 | Carrier: Set-up service levels | 2020-07-27 | 2020-08-02 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-30 01:53 | FALSE | Continuant | 9.1875 | 0 | 73.7145 | 0 | 2020-07-27 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE | <p><br></p> |  | 11092 | 0 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_305_5e864ca3 | Website: Release Module | 2020-07-20 | 2020-07-26 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0.8125 | 0 | 6.2858 | 0 | 2020-07-20 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-16 02:45 | Continuant | FALSE | FALSE |  |  | 11109 | 0 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_289_f216b0dc | eCommerce: Develop a Product Template | 2020-08-10 | 2020-08-16 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-11 00:41 | FALSE | Continuant | 18 | 0 | 144 | 0 | 2020-08-10 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-16 00:13 | Continuant | FALSE | FALSE | <p><br></p> |  | 11112 | 0 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_266_d5a28454 | Setup Microsoft team for Continuent | 2020-07-12 | 2020-07-19 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 1.8125 | 0 | 14.2858 | 0 | 2020-07-12 | Complete | Muhammad Zubair | Done | FALSE |  | Muhammad Afzaal | 2020-07-14 22:03 | Continuant | FALSE | FALSE | <p><br></p> |  | 11138 | 0 | 0 | 0 | 0 | Normal | Sprint 22
__export__.project_task_904_94c13af9 | Logout Android-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:46 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00016651 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_814_a1669cd7 | Product list iOS-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 2 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_603_75589488 | Tax: Avalara: Review Current Configuration | 2020-07-27 | 2020-08-02 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-25 00:28 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-25 00:28 | Continuant | FALSE | FALSE | <p><br></p> |  | 10896 | 0 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_563_606674c9 | API:Get Batch Api | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 4 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:39 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.6478 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 11009 | 4 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_366_b18f1fda | Integrate GfK Etilize Catalog | 2020-08-03 | 2020-08-09 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 4 | 4 | 12 | 25 |  | FALSE | Complete | TRUE | FALSE | 2020-07-25 00:17 | FALSE | Continuant | 5 | 0 | 40 | 0 | 2020-08-03 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-17 22:32 | Continuant | FALSE | FALSE | <p><br></p> |  | 11066 | 16 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_247_7bc7af72 | List of Questions - Meeting | 2020-07-06 | 2020-07-12 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | Fahad Hassan | 2020-07-16 20:17 | FALSE | Continuant | 5.875 | 0 | 47.0251 | 0 | 2020-07-06 | Complete | Muhammad Zubair | Done | FALSE |  | Muhammad Afzaal | 2020-07-08 21:16 | Continuant, Allison Beers | Executive / Delivery / Bravo | FALSE | <p>Requirements/ Questions for meeting</p><p><br></p><p>Contacts details for hosting company</p><p>Login IDs for servers</p> |  | 11283 | 0 | 0 | 0 | 0 | Normal | Sprint 21
__export__.project_task_883_3c4708d0 | Forgot password Android-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_535_046adb83 | API:Auction detail | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 6 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:43 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.7089 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 11009 | 6 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_301_38897f0a | Carrier: UPS and Fedex - check existing set-up | 2020-07-20 | 2020-07-26 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 16:28 | FALSE | Continuant | 3.4375 | 0 | 27.4711 | 0 | 2020-07-20 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-16 02:41 | Continuant | FALSE | FALSE | <p><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'>FedEx Developer Test Key</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'>Now that you've reviewed the documentation and downloaded the WSDLs, you're ready to test your application. You should have received your Test Key on the confirmation page when registering for credentials. Below are the remaining test credentials you requested. </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'>Test Account Information </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'>Test URL: </span><a target="_blank" rel="noreferrer noopener" href="https://wsbeta.fedex.com/web-services" style='display: inline-block; word-break: break-all; font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'>https://wsbeta.fedex.com:443/web-services</a><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'>Test Password: btyXHMRLaRRYX8azBBcdd7bhY </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'>FedEx Web Services Testing Information:</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> FedEx Shipping Account Number: 510087240 </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> FedEx Meter Number: 100468520</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'>FedEx SmartPost® Returns Testing Information: </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> FedEx Shipping Account Number: 510087020</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> FedEx Meter Number: 100468521</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> FedEx Hub ID (Outbound and Returns): 5531</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'>FedEx Web Services Freight LTL Testing Information (used in the Freight Shipment Detail):</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> FedEx Freight LTL Shipper</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> Account Number: 510087020</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> Address Line 1: 1202 Chalet Ln</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> Adress Line 2: Do Not Delete - Test Account</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> City: Harrison</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> State: AR</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> ZIP: 72601</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> FedEx Freight LTL Bill-To</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> Account Number: 510051408</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> Address Line 1: 2000 Freight LTL Testing</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> Address Line 2: Do Not Delete - Test Account</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> City: Harrison</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> State: AR</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> ZIP: 72601</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'>FedEx Office Web Services Testing Information:</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> FedEx Integrator ID: 123</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> FedEx Client Product ID: TEST</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> FedEx Client Product Version: 9999</span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'>FedEx Web Services for Office and Print </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'> </span><br style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif;'><span style='font-family: Roboto, "Odoo Unicode Support Noto", sans-serif; background-color: rgba(222, 226, 230, 0.498039);'>By default, your Developer Test Key is disabled for FedEx Web Services for Office and Print. Please complete the Office and Print Test Key Enablement Request form and submit it in order to enable your key to use these services.</span><br><br></p><p><img class="img-fluid o_we_custom_image" src="/web/image/6342/FedEx Test System Access.jpg?access_token=910eed40-7c79-4386-92b0-e8ede80328df"><br></p> |  | 11109 | 1 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_901_d6350b29 | Add to watch list Android-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:46 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00016651 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_840_c684d457 | Set batch API iOS-Implementation | 2020-08-10 | 2020-08-16 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00018745 | 0 | 2020-08-10 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 26
__export__.project_task_351_0470d6ae | Sponsor Meeting #1 | 2020-07-20 | 2020-07-26 | Development | Continuant: eCommerce (P9) | Nick Foy | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0 | 0 | 0.00032117 | 0 | 2020-07-20 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE |  |  | 11092 | 0 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_815_3a018001 | Forgot password iOS-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_564_3a9185bb | API:Get List of MarketPlaces | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:39 | FALSE | Cellpoint Corporation | 1.3125 | 0 | 10.6436 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p>1, Create a URL </p><p>2, Fetch all marketplaces </p><p>3, Sharing response over API</p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_336_d44c5546 | Carrier: Agree shipping pricing uplifts | 2020-07-27 | 2020-08-02 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-25 00:22 | FALSE | Continuant | 6.1875 | 0 | 49.7145 | 0 | 2020-07-27 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE | <p>Within Odoo, in shipping, you have the ability to charge the customer whatever shipping rate you want. </p> |  | 11092 | 0 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_944_cc3abc54 | List View for Buyers | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-08-04 08:15 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-08-04 08:15 | Cellpoint Corporation | FALSE | FALSE | <p>Please create list view for buyers so we can see all available labels </p> |  | 10648 | 2 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_910_aae19595 | Get marketplace list Android-Implementation | 2020-08-03 | 2020-08-09 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:46 | FALSE | Cellpoint Corporation | 0 | 0 | 0.00016651 | 0 | 2020-08-03 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 25
__export__.project_task_578_42291b10 | Delete Test Seller Accounts | 2020-07-20 | 2020-07-26 | Development | Cellpoint CPBids: Help (P7) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-20 23:12 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-20 | Complete | Farman Ahmad Cheema | InProgress | FALSE |  | Kaesi Lee | 2020-07-20 23:12 | Cellpoint Corporation | FALSE | FALSE | <p>Delete Test Seller Accounts</p> |  | 10993 | 0 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_299_b1aa1799 | eCommerce: Test Module | 2020-07-20 | 2020-07-26 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-27 18:17 | FALSE | Continuant | 7.5625 | 0 | 60.2783 | 0 | 2020-07-20 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-16 02:38 | Continuant | FALSE | FALSE | <p><br></p> |  | 11109 | 0 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_895_161f8137 | Location list Android-Implementation | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 1 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-28 18:45 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-28 18:45 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10805 | 1 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_601_d6256b0f | Test Connection to GfK Catalog | 2020-07-27 | 2020-08-02 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-23 22:04 | FALSE | Continuant | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-23 22:03 | Continuant | FALSE | FALSE | <p>Continuant wanted to make sure we could connect to the GfK Etilize catalog successfully if you could please confirm that. </p> |  | 10922 | 0 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_593_91cda87a | API:Location List:APPMAVEN | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 3 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-23 11:57 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-23 11:57 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10932 | 3 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_916_971d5b2f | API:Seller List :Postman | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-29 11:31 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-29 11:31 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10789 | 0 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_590_e380f9d2 | API:Select country:APPMAVEN | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 3 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-23 11:55 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-23 11:55 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10932 | 3 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_352_5265587f | Sponsor Meeting #2 | 2020-07-27 | 2020-08-02 | Development | Continuant: eCommerce (P9) | Nick Foy | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0 | 0 | 0.00032117 | 0 | 2020-07-27 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE |  |  | 11092 | 0 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_545_080f0ba7 | API:Seller List | 2020-07-20 | 2020-07-26 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:46 | FALSE | Cellpoint Corporation | 1.375 | 0 | 10.7675 | 0 | 2020-07-20 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-20 06:58 | Cellpoint Corporation | FALSE | FALSE | <p>method: POST</p><p>Description: On the basis of this API user can get the List of Seller on the filter screen to get filtered data in the Auction list.</p><p>parameter : user_id ,verify token </p><p>API will check user exist and also verify the token, Fetch the seller data from (res.partner) with the condition (seller=True , status =Approved) </p><p>Append partner.id, partner.name,status,data into JSON</p><p>Retrieve JSON data</p><p><br></p> |  | 11009 | 2 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_298_ba2eb05b | eCommerce: Install Module | 2020-07-20 | 2020-07-26 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 0.16667 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 16:18 | FALSE | Continuant | 3.4375 | 0 | 27.2972 | 0 | 2020-07-20 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-16 02:38 | Continuant | FALSE | FALSE | <p><br></p> |  | 11109 | 0.16667 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_589_175393ad | API:Forgot Password:APPMAVEN | 2020-07-27 | 2020-08-02 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven | FALSE | 0 | 0 | 4 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-23 11:54 | FALSE | Cellpoint Corporation | 0 | 0 | 0 | 0 | 2020-07-27 | Complete | Muhammad Afzaal | Done | FALSE |  | Muhammad Afzaal | 2020-07-23 11:54 | Cellpoint Corporation | FALSE | FALSE | <p><br></p> |  | 10932 | 4 | 0 | 0 | 0 | Normal | Sprint 24
__export__.project_task_297_9ac4c2b0 | Website: Test Module | 2020-07-20 | 2020-07-26 | Development | Continuant: eCommerce (P9) | Kaesi Lee | FALSE | 0 | 0 | 0 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-16 20:17 | FALSE | Continuant | 0.8125 | 0 | 6.2858 | 0 | 2020-07-20 | Complete | Muhammad Zubair | Done | FALSE |  | Kaesi Lee | 2020-07-16 02:36 | Continuant | FALSE | FALSE |  |  | 11109 | 0 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_343_a6b77a32 | eCommerce: Configure Module | 2020-07-20 | 2020-07-26 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 2 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-21 15:43 | FALSE | Continuant | 2.5 | 0 | 20.4364 | 0 | 2020-07-20 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE | <p><br></p> |  | 11092 | 2 | 0 | 0 | 0 | Normal | Sprint 23
__export__.project_task_341_40f0d6dd | Carrier: Set-up shipping pricing | 2020-07-27 | 2020-08-02 | Development | Continuant: eCommerce (P9) | Anusha | FALSE | 0 | 0 | 8 | 0 |  | FALSE | Complete | TRUE | FALSE | 2020-07-25 00:18 | FALSE | Continuant | 6.1875 | 0 | 49.7145 | 0 | 2020-07-27 | Complete | Muhammad Zubair | Done | FALSE |  | Nick Foy | 2020-07-16 20:17 | Continuant | FALSE | FALSE | <p>Include shipping pricing and selection for each carrier in the check out process. </p> |  | 11092 | 8 | 0 | 0 | 0 | Normal | Sprint 24