## General Description
General Description:
Silverdale uses Tasks for Planning Resource Allocation of Project Tasks. Used for both client and internal projects.
In order to understand the purpose of tasks data fields, click on each header to get more insight about how each field is being used.

## Tasks Form
External ID | Title | Sprint | Sprint End Date | Task Type | Project | Assigned to | Responsbile | Hours Spent | Progress | Activities | Tags | Task Difficulty | Stage | Client | Hours Open | Initially Planned Hours | Remaining Hours | Working hours to assign | Working hours to close
__export__.project_task_4668_2132a98f | WildLeaf Deploy To Deployment + Production(2135) | Sprint 2135 | 2021-08-23 | Deployment | Wild Leaf: Help (P22) | Mir Muhammad Muzammil |  | 0 | 0 |  | SPLN |  | Complete | Wild Leaf Beverage | 514 | 0 | 0 | 0 | 24
__export__.project_task_4615_92c814c2 | NMS Export File Name Date Issue | Sprint 2134 | 2021-08-16 | Bug Fix | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 0.5 | 0 |  | Priority |  | Complete | Cellpoint Corporation | 720 | 0 | -0.5 | 0 | 23.2763
__export__.project_task_3811_375aea62 | Brand Strategy: Recruitment Intro | Sprint 2122 | 2021-05-24 | Development | PWX: HR (P61) | Muhammad Afzaal | Raheel Aslam | 3.42 | 57 |  |  | 3 | Complete | EquityTeam | 2857 | 6 | 2.58 | 0 | 96
__export__.project_task_3592_14b36f6e | Create a video for Dashboard activities |  |  | Configuration | Silverdale: Help (P12) | Muhammad Afzaal | Muhammad Zubair | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3189 | 0 | 0 | 0 | 62.0778
__export__.project_task_3580_f38d1800 | Personality: finish line2 | Sprint 2120 | 2021-05-10 | Development | PWX: Survey (P70) | Muhammad Afzaal | Raheel Aslam | 5.17 | 86.17 |  | MA Review | 3 | Complete | EquityTeam | 3220 | 6 | 0.83 | 6.3503e-05 | 40.2103
__export__.project_task_3368_42f01262 | Automatically change Sales Order quantities based on Received Quantities for Sleeves | Sprint 2136 | 2021-08-30 | Development | Wild Leaf: Consignment and Sales Improvements (P112) | Abdul Hameed | Muhammad Bilal | 105.92 | 99.92 | COE Required | MA Review | 3 | Complete | Wild Leaf Beverage | 3579 | 106 | 0.08 | 767.93 | 810.185
__export__.project_task_3352_2b81901d | VAT on invoice not reflecting correctly |  |  | Bug Fix | MMH Dr. Clark: Help (P106) | Jeff Gross | Muhammad Bilal | 20.42 | 100 |  |  | 4 | Complete | Mountain Meadow Herbs | 3699 | 5.3333 | -15.0867 | 0 | 408
__export__.project_task_3301_7a833859 | Deployment 06/04/2021: Continuant | Sprint 2116 | 2021-04-12 | Configuration | Continuant: AV Warehouse (P34) | Jeff Gross | Wajahat Ali | 1.5 | 0 |  |  |  | Complete | Continuant | 3896 | 0 | -1.5 | 0 | 4
__export__.project_task_3282_95ce833b | Add a "Print Pack Labels" button to Transfers page | Sprint 2115 | 2021-04-05 | Development | Wild Leaf: Help (P22) | Jeff Gross | Aleem khan | 6.67 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4019 | 2.5 | -4.17 | 0 | 93.5827
__export__.project_task_3026_c6c10ee4 | Survey Module | Sprint 2118 | 2021-04-26 | Configuration | Silverdale: Help (P12) | Naseeb Razaq | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4399 | 0 | 0 | 0.0099412 | 235.2986
__export__.project_task_3015_7e6d5c30 | QA/Deployment Process lucid chart | Sprint 2117 | 2021-04-19 | Configuration | Silverdale: Devops (P84) | Levi Barnes | Levi Barnes | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4414 | 0 | 0 | 0 | 200
__export__.project_task_3010_115d783c | git e-learning | Sprint 2114 | 2021-03-29 | Configuration | Silverdale: Devops (P84) | Levi Barnes | Levi Barnes | 6.83 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4414 | 0 | -6.83 | 0 | 112
__export__.project_task_2989_2024788d | shipping charging on gift/catalog | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 7.08 | 100 |  |  | 3 | Complete | Mid-America Gardens, LLC | 4493 | 6.5 | -0.58 | 4.0048e-05 | 86.6662
__export__.project_task_2947_a71f2d1c | Enable web bidding for CPBids and ecoATM marketplaces | Sprint 2113 | 2021-03-22 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 2.25 | 50 |  |  |  | Complete | Cellpoint Corporation | 4531 | 4.5 | 2.25 | 0 | 36
__export__.project_task_2854_0db64058 | Shop landing page modification | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 8.67 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 4682 | 8.3333 | -0.33667 | 0 | 133.3467
__export__.project_task_2814_8a5cb02b | Create csv for file "Inventory" | Sprint 2135 | 2021-08-23 | Development | Cellpoint: ecoATM API (P50) | Farman Ahmad Cheema | Fahad Hassan | 34.42 | 99.77 |  | SPLN | 2 | ELS | Cellpoint Corporation | 4758 | 34.5 | 0.08 | 968 | 0
__export__.project_task_2762_b57da081 | Change the field title for selected columns | Sprint 2110 | 2021-02-22 | Development | Cellpoint: ecoATM API (P50) | Nick Foy | Muhammad Bilal | 7.92 | 99 |  |  |  | Complete | Cellpoint Corporation | 5092 | 8 | 0.08 | 0 | 159.3758
__export__.project_task_2742_79c493c1 | Minimum order price | Sprint 2109 | 2021-02-15 | Development | Mid-America: Help (P37) | Levi Barnes | Muhammad Bilal | 9.92 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 5168 | 6 | -3.92 | 0 | 203.6641
__export__.project_task_2734_6cb30f26 | Confirm a sales quotation should be restricted to a Finance User group | Sprint 2109 | 2021-02-15 | Development | Wild Leaf: Accounting (P64) | Nick Foy | Danish Hassan | 3.83 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5180 | 3 | -0.83 | 0 | 110.4481
__export__.project_task_2697_a1a37041 | Go Live: Support | Sprint 2117 | 2021-04-19 | Development | Mid-America: Help (P37) | Levi Barnes |  | 1.5 | 18.75 |  |  |  | Complete | Mid-America Gardens, LLC | 5332 | 8 | 6.5 | 0 | 383.804
__export__.project_task_2637_1ba4f973 | Change the 10x bid limit rule to 5x:On IOS | Sprint 2107 | 2021-02-01 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 2.17 | 0 |  | 3.0.6 |  | Complete | Cellpoint Corporation | 5429 | 0 | -2.17 | 2.7951e-05 | 317.7475
__export__.project_task_2620_19ebde0f | Inventory Import - Production | Sprint 2107 | 2021-02-01 | Development | Wild Leaf: Help (P22) | Nick Foy | Raheel Aslam | 4 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5501 | 4 | 0 | 8.6541 | 96.6541
__export__.project_task_2427_ca3ba752 | invoice_delivery_method unit testing | Sprint 2108 | 2021-02-08 | Development | Continuant: Unit Testing (P51) | Nick Foy | Kaleem Khan | 5.5 | 91.67 |  |  |  | Complete | Continuant | 5589 | 6 | 0.5 | 40 | 214.3592
__export__.project_task_2416_4b8707cc | Development : The Integration of Helcim Payment Gateway with Odoo |  |  | Development | Wild Leaf: Helcim Integration (P38) | Jeff Gross | Wajahat Ali | 16.67 | 0 |  | Potential Silverdale App |  | Complete | Wild Leaf Beverage | 5602 | 0 | -92.82 | 236.8955 | 324.0494
__export__.project_task_2414_db110a23 | Research: The Integration of Helcim Payment Gateway with Odoo | Sprint 2105 | 2021-01-25 | Development | Wild Leaf: Helcim Integration (P38) | Kaesi Lee | Wajahat Ali | 3 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5602 | 3 | 0 | 0 | 12.6904
__export__.project_task_2408_d4375173 | Phase 1: Create a CSV file export module |  |  | Development | Cellpoint: ecoATM API (P50) | Nick Foy |  | 1.5 | 100 |  |  |  | Complete | Cellpoint Corporation | 5619 | 32 | -47.08 | 0 | 327.1561
__export__.project_task_2396_d57a96e0 | Customer Quotation Response: Avalara Error Message |  |  | Bug Fix | Continuant: Quotation Management / Automation (P31) | Jeff Gross | Fahad Hassan | 20.5 | 100 |  |  |  | Complete | Continuant | 5693 | 3 | -17.5 | 248.4484 | 248.4484
__export__.project_task_2303_4755c5a4 | FW: Delivery Status Notification (Failure) |  |  | Bug Fix | PWX: Help (P23) | Levi Barnes | Wajahat Ali | 2.67 | 89 |  |  |  | Complete | EquityTeam | 5887 | 3 | 0.33 | 0 | 50.5531
__export__.project_task_2283_fc1001c8 | Process Online Payments Using Helcim API:Trace & Validate Actual Flow of Transaction Processing in Odoo |  |  | Development | Wild Leaf: Helcim Integration (P38) | Kaesi Lee | Fahad Hassan | 32.42 | 100 |  |  |  | Cancelled | Wild Leaf Beverage | 5906 | 19.5833 | -12.8367 | 0 | 104
__export__.project_task_2235_5f6e0808 | Record Views - Contacts>Buildings |  |  | Development | PWX: Property (P58) | Levi Barnes | Muzher Siddique | 0.83 | 100 |  |  |  | Complete | EquityTeam | 5932 | 12 | -13.92 | 0 | 359.4411
__export__.project_task_2220_f75d903c | Belmont User cannot export from Buyers list | Sprint 2103 | 2021-01-11 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 1 | 0 |  |  |  | Complete | Cellpoint Corporation | 5996 | 0 | -2.17 | 0 | 112
__export__.project_task_2168_15fceec3 | Record Views - Contacts>Units |  |  | Configuration | PWX: Property (P58) | Levi Barnes |  | 0 | 100 |  |  |  | Complete | EquityTeam | 6025 | 19.0833 | -6.1667 | 0 | 216
__export__.project_task_2097_93794f65 | Create a test instance for demo and feedback | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Nick Foy | 1.75 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6144 | 0 | -1.75 | 0 | 38.1244
__export__.project_task_2071_de376440 | Manufacturing operations in multiple BoMs - change to many2many | Sprint 2103 | 2021-01-11 | Development | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 13.08 | 100 |  | Potential Silverdale App |  | Cancelled | Wild Leaf Beverage | 6215 | 13.1667 | -1.4133 | 0 | 192
__export__.project_task_1876_82447e48 | Web Platform: Auction Details Page Title Bug | Sprint 2052 | 2020-12-21 | Bug Fix | Cellpoint CPBids: Help (P7) | Kaesi Lee | Wajahat Ali | 2.08 | 100 |  |  |  | Complete | Cellpoint Corporation | 6599 | 1.5 | -0.58 | 0 | 132.6972
__export__.project_task_1857_6e8a0b48 | FW: Chart of Accounts |  |  | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Kaesi Lee | 1.75 | 0 |  | 2014-01-01 |  | Complete | Wild Leaf Beverage | 6701 | 0 | -1.75 | 0.067325 | 272.6465
__export__.project_task_1219_bc68a06d | WebFrom Signup | Sprint 31 | 2020-09-14 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8772 | 0 | 0 | 0.0039077 | 58.8881
__export__.project_task_1204_81793f96 | Web Auctions Details | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8799 | 0 | 0 | 0 | 118.5403
__export__.project_task_238_eac46663 | Estimate | Sprint 27 | 2020-08-17 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10477 | 0 | 0 | 244 | 1200
__export__.project_task_3802_d97f41f0 | Survey: hardest problem question | Sprint 2122 | 2021-05-24 | Development | PWX: Survey (P70) | Muhammad Afzaal | Raheel Aslam | 7.67 | 95.88 |  |  | 2 | Complete | EquityTeam | 2886 | 8 | 0.33 | 0 | 105.6096
__export__.project_task_3536_2bb7724b | Make CPBids Buyer Username Mandatory under certain conditions |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 1.75 | 87.5 |  |  | 2 | Complete | Cellpoint Corporation | 3383 | 2 | 0.25 | 0 | 160
__export__.project_task_3259_b9ac5b9e | PWX: Option to view the surveys score interviewer wise | Sprint 2115 | 2021-04-05 | Development | PWX: Survey (P70) | Levi Barnes | Danish Hassan | 10.08 | 100 |  |  | 3 | Complete | EquityTeam | 4087 | 6 | -4.08 | 0 | 115.1555
__export__.project_task_2849_68bec4cc | Remove Lot Validation | Sprint 2122 | 2021-05-24 | Development | Improvements for Belmont (P213) | Farman Ahmad Cheema | Kaleem Khan | 37 | 100 |  | LSC | 3 | Complete | Cellpoint Corporation | 4684 | 32.5 | -4.5 | 1031.3408 | 1031.3408
__export__.project_task_2818_e65ce873 | Create csv file for "Sold" | Sprint 2135 | 2021-08-23 | Development | Cellpoint: ecoATM API (P50) | Farman Ahmad Cheema | Fahad Hassan | 11.17 | 100 |  | SPLN | 2 | ELS | Cellpoint Corporation | 4758 | 11 | -0.17 | 968 | 0
__export__.project_task_2743_bc1c8d98 | Shipping should not charge | Sprint 2110 | 2021-02-22 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 7.17 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 5168 | 5.5 | -1.67 | 0 | 139.4986
__export__.project_task_2739_e25a1c08 | Add customer credit limit functionality | Sprint 2109 | 2021-02-15 | Development | Wild Leaf: Accounting (P64) | Jeff Gross |  | 0.58 | 38.67 |  |  |  | Complete | Wild Leaf Beverage | 5179 | 1.5 | 0.92 | 128 | 175.3311
__export__.project_task_2737_12ff313f | Sales Quotation restrict the Create Invoice to a User Group | Sprint 2110 | 2021-02-22 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Danish Hassan | 5.67 | 75.6 |  |  |  | Complete | Wild Leaf Beverage | 5180 | 7.5 | 1.83 | 128 | 175.3828
__export__.project_task_2663_52c5513d | Record Views - Contacts>Buildings:Part2 | Sprint 2108 | 2021-02-08 | Development | PWX: Property (P58) | Levi Barnes | Raheel Aslam | 9.67 | 100 |  |  |  | Complete | EquityTeam | 5362 | 9 | -0.67 | 0 | 155.7418
__export__.project_task_2636_c4b226c8 | Change the 10x bid limit rule to 5x:On Android | Sprint 2107 | 2021-02-01 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0.67 | 0 |  | 3.0.6 |  | Complete | Cellpoint Corporation | 5429 | 0 | -0.67 | 0.00013321 | 317.8326
__export__.project_task_2613_7359044b | Go Live |  |  | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0 | 0 |  | Template |  | Cancelled | Mid-America Gardens, LLC | 5541 | 0 | 0 | 0 | 376
__export__.project_task_2608_da75e1e3 | Associate Helcim.js with Pay Now Button | Sprint 2105 | 2021-01-25 | Development | Wild Leaf: Helcim Integration (P38) | Nick Foy | Wajahat Ali | 6 | 92.31 |  |  |  | Complete | Wild Leaf Beverage | 5546 | 6.5 | 0.5 | 24 | 198.1217
__export__.project_task_2409_b18ed121 | Phase 2: Create a CSV Import module (eco specific) | Sprint 2110 | 2021-03-01 | Development | Cellpoint: ecoATM API (P50) | Nick Foy | Muzher Siddique | 14.87 | 100 |  |  |  | Complete | Cellpoint Corporation | 5619 | 16 | -0.7 | 0 | 327.0783
__export__.project_task_2402_7d3dab66 | CPBidsUserName to the belmontlots table | Sprint 2107 | 2021-02-01 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 5.33 | 100 |  |  |  | Complete | Cellpoint Corporation | 5685 | 5 | -7 | 0 | 230.3356
__export__.project_task_2384_14bcc1c1 | FW: Error When Making Replenishment |  |  | Bug Fix | Wild Leaf: Help (P22) | Nick Foy | Fahad Hassan | 8.25 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5737 | 3.8333 | -11.7467 | 72 | 104
__export__.project_task_2284_4996063d | Process Online Payments Using Helcim API:Generate Invoice Based On Helcim Transaction | Sprint 2104 | 2021-01-18 | Development | Wild Leaf: Helcim Integration (P38) | Kaesi Lee | Fahad Hassan | 20 | 100 |  | MA Review |  | Cancelled | Wild Leaf Beverage | 5906 | 19.25 | -0.75 | 0 | 104
__export__.project_task_2033_a160fbcd | Error Message in Project > Studio | Sprint 2052 | 2020-12-21 | Bug Fix | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 0.5 | 0 |  |  |  | Complete | EquityTeam | 6387 | 0 | -0.5 | 0 | 76.7081
__export__.project_task_1875_8f29965b | Search on Web Bidding not working | Sprint 2051 | 2020-12-14 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 3.33 | 0 |  |  |  | Complete | Cellpoint Corporation | 6600 | 0 | -3.33 | 0 | 84
__export__.project_task_1870_a477091a | Process Online Payments Using Helcim API |  |  | Development | Wild Leaf: Helcim Integration (P38) | Kaesi Lee | Fahad Hassan | 42.25 | 100 |  | Difficulty 4 |  | Cancelled | Wild Leaf Beverage | 6604 | 37.0833 | -58.5867 | 0 | 272
NF Review
MA Review
__export__.project_task_1277_db1ddd82 | Release Plan:AWS Portal ReadOnly | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8581 | 0 | 0 | 0 | 24.2359
__export__.project_task_1269_80c0e94d | Web Auction List View | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8581 | 0 | 0 | 0 | 70.0552
__export__.project_task_4542_ecc2c958 | PWX Deploy To Deployment + Production(2133) | Sprint 2134 | 2021-08-16 | Deployment | PWX: Help (P23) | Farman Ahmad Cheema |  | 8.83 | 0 |  |  |  | Complete | EquityTeam | 802 | 0 | -8.83 | 0 | 89.0608
__export__.project_task_3805_fcd4ea7d | job website modification | Sprint 2122 | 2021-05-24 | Development | PWX: HR (P61) | Muhammad Afzaal | Raheel Aslam | 5.05 | 72.14 |  |  | 2 | Complete | EquityTeam | 2883 | 7 | 1.95 | 0 | 104
__export__.project_task_3396_b9877a29 | Appraisals & Evaluations Tribe |  |  | Internal Time Tracking | Silverdale: Help (P12) | Faisal Huda Khan | Muzher Siddique | 0.58 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3528 | 0 | -0.58 | 72 | 590.3236
__export__.project_task_3351_2de6dec0 | Error when scanning packages in transit | Sprint 2117 | 2021-04-19 | Development | Wild Leaf: Help (P22) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 3701 | 0 | 0 | 0 | 16.5651
__export__.project_task_3254_7419f4ce | PWX: Job selection field on employee form should be a multi selection field | Sprint 2117 | 2021-04-19 | Development | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 16.92 | 100 |  |  | 3 | Complete | EquityTeam | 4091 | 7 | -16.67 | 1.2549e-05 | 205.0956
__export__.project_task_3197_a0f89bfb | Change HOLD logic to only apply to Outgoing operation type | Sprint 2114 | 2021-03-29 | Development | Wild Leaf: Help (P22) | Jeff Gross | Osama Khalid | 10.33 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4297 | 4 | -6.33 | 52.5233 | 160
__export__.project_task_3012_92dde2dc | qa repo(s) setup | Sprint 2114 | 2021-03-29 | Configuration | Silverdale: Devops (P84) | Levi Barnes | Levi Barnes | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4414 | 0 | 0 | 0 | 53.5964
__export__.project_task_2774_71b34de2 | CTDI Onboarding |  |  | Internal Time Tracking | Cellpoint: CPBids Billable (P66) | Nick Foy | Nick Foy | 6 | 0 |  |  |  | Complete | Cellpoint Corporation | 5060 | 0 | -6 | 0 | 151.4444
__export__.project_task_2625_1b26fd09 | Labeling (non-real-time) | Sprint 2110 | 2021-02-22 | Development | Wild Leaf: Labeling (P60) | Jeff Gross | Muhammad Bilal | 12.33 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5497 | 8 | -7.16 | 200 | 247.3875
__export__.project_task_2411_308d99c8 | Phase 1: Create a CSV file export module: Create a Scheduler | Sprint 2109 | 2021-02-15 | Development | Cellpoint: ecoATM API (P50) | Nick Foy | Muzher Siddique | 4.83 | 100 |  |  |  | Complete | Cellpoint Corporation | 5619 | 4 | -0.83 | 0 | 287.3531
__export__.project_task_2388_92e76c50 | New Cellpoint Buyers still not seeing lots until Invite Selected Buyers is checked, saved and unchecked, saved |  |  | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 6.67 | 0 |  | MA Review |  | Complete | Cellpoint Corporation | 5732 | 0 | -6.67 | 0 | 264
__export__.project_task_2285_3d8661b5 | Process Online Payments Using Helcim API:Identify the factors effecting the transaction flow | Sprint 2104 | 2021-01-18 | Development | Wild Leaf: Helcim Integration (P38) | Kaesi Lee | Fahad Hassan | 1 | 14.29 |  |  |  | Cancelled | Wild Leaf Beverage | 5906 | 7 | 6 | 0 | 104
__export__.project_task_2169_c4079e4c | Sales Specification Delivery Method for Manufacturing Orders: Pallet Building Info Requirements | Sprint 2112 | 2021-03-15 | Development | Wild Leaf: Help (P22) | Umer Farooq | Muhammad Bilal | 6.58 | 98.7 |  |  |  | Complete | Wild Leaf Beverage | 6024 | 6.6667 | 0.086667 | 316.9536 | 453.1847
__export__.project_task_2034_063a6a0c | Error Message in Recruitment > Reporting | Sprint 2052 | 2020-12-21 | Bug Fix | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 0.25 | 0 |  |  |  | Complete | EquityTeam | 6387 | 0 | -0.25 | 0 | 76.7067
__export__.project_task_1970_13aa6742 | Import Customer Other Addresses | Sprint 2104 | 2021-01-18 | Development | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 4.08 | 92.38 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 4.4167 | 0.33667 | 14.4119 | 248
__export__.project_task_1802_7e833091 | Customer Payment Option Configuration | Sprint 2110 | 2021-03-01 | Development | Continuant: Quotation Management / Automation (P31) | Jeff Gross | Muhammad Bilal | 54.55 | 100 |  |  |  | Complete | Continuant | 6775 | 50 | -4.55 | 514.3688 | 554.3688
__export__.project_task_1278_c141aaee | Release Plan:Grant Portal Access | Sprint 32 | 2020-09-21 | Configuration | Cellpoint: Odoo Back-End (P8) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8581 | 0 | 0 | 0 | 23.7202
__export__.project_task_3809_eeed7521 | Brand Strategy: Job Accountable | Sprint 2122 | 2021-05-24 | Development | PWX: HR (P61) | Muhammad Afzaal | Raheel Aslam | 6.03 | 67 |  |  | 3 | Complete | EquityTeam | 2859 | 9 | 2.97 | 0 | 96
__export__.project_task_3547_b65d2f23 | Operations - QA and Deployment |  |  | Internal Time Tracking | Silverdale: Help (P12) | Muhammad Afzaal | Muzher Siddique | 0 | 0 |  | LSC |  | Complete | Silverdale Technology LLC | 3357 | 0 | 0 | 0 | 600
__export__.project_task_3375_fa6c49d1 | applicant: Personality tab | Sprint 2119 | 2021-05-03 | Development | PWX: Survey (P70) | Levi Barnes | Raheel Aslam | 20.5 | 100 |  |  | 2 | Complete | EquityTeam | 3555 | 9 | -11.5 | 0 | 120
__export__.project_task_3307_fdbfba08 | Inventory Adjustments must include an Analytic Account based on the destination warehouse | Sprint 2117 | 2021-04-19 | Development | Wild Leaf: Help (P22) | Jeff Gross | Fahad Hassan | 13.5 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 3877 | 6 | -7.5 | 0 | 95.8166
__export__.project_task_3035_dab46a30 | Setup Email Accounts for Customer Invoice Delivery | Sprint 2114 | 2021-03-29 | Configuration | Wild Leaf: Accounting (P64) | Jeff Gross | Umer Farooq | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 4375 | 0 | 0 | 0.022096 | 146.5618
__export__.project_task_2789_cc48d5b8 | Events: Validation BugFix | Sprint 2110 | 2021-02-22 | Bug Fix | Heronswood: Events (P3) | Nick Foy | Fahad Hassan | 29.25 | 100 |  |  |  | Cancelled | Port Gamble Sâ€™Klallam Foundation | 4998 | 4 | -25.25 | 0 | 47.4363
__export__.project_task_2772_fe7df4a9 | image size bug |  |  | Bug Fix | Dialed Supply: Help (P21) | Levi Barnes | Fahad Hassan | 41.12 | 0 |  |  |  | Complete | Dialed Supply | 5066 | 0 | -41.12 | 0 | 191.2036
__export__.project_task_2747_68a9ff2d | Client Electronic Invoice Delivery Preferences: Part3 | Sprint 2109 | 2021-02-15 | Development | Continuant: Customer Invoice Delivery Preferences (P33) | Jeff Gross | Raheel Aslam | 9.33 | 100 |  |  |  | Complete | Continuant | 5141 | 7 | -2.33 | 120 | 160
__export__.project_task_2662_a40918c9 | Record Views - Contacts>Buildings:Part1 | Sprint 2108 | 2021-02-08 | Development | PWX: Property (P58) | Levi Barnes | Fahad Hassan | 15.42 | 100 |  |  |  | Complete | EquityTeam | 5362 | 6.5 | -8.92 | 0 | 155.7072
__export__.project_task_2626_ef72cf74 | Sales Notes and Attachments in production order | Sprint 2112 | 2021-03-15 | Development | Wild Leaf: Help (P22) | Umer Farooq | Danish Hassan | 6.33 | 94.95 |  |  |  | Complete | Wild Leaf Beverage | 5496 | 6.6667 | 0.33667 | 188.9433 | 325.1883
__export__.project_task_2615_7af3432e | Go Live: Configure DNS |  |  | Configuration | Mid-America: Help (P37) | Levi Barnes | Levi Barnes | 3.83 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 5540 | 0 | -3.83 | 0 | 232
__export__.project_task_2601_3e8d44c9 | Customization on Checkout Page : | Sprint 2105 | 2021-01-25 | Development | Wild Leaf: Helcim Integration (P38) | Nick Foy | Wajahat Ali | 6.25 | 89.29 |  |  |  | Complete | Wild Leaf Beverage | 5549 | 7 | 0.75 | 24.8884 | 199.0075
__export__.project_task_2413_dc4a2b0c | Phase 1: Create a CSV file export module: Create a CSV to SFTP connector | Sprint 2108 | 2021-02-08 | Development | Cellpoint: ecoATM API (P50) | Nick Foy | Muzher Siddique | 8.83 | 100 |  |  |  | Complete | Cellpoint Corporation | 5619 | 6.3333 | -2.4967 | 0 | 287.3172
__export__.project_task_2377_90ebdf33 | Code Deployment Code Errors |  |  | Bug Fix | Continuant: Quotation Management / Automation (P31) | Kaesi Lee | Muzher Siddique | 3.13 | 89.43 |  |  |  | Complete | Continuant | 5742 | 3.5 | 0.37 | 2.3712e-05 | 33.3609
__export__.project_task_2333_9a20c148 | AV Project Form View: Add Pick List | Sprint 2104 | 2021-01-18 | Development | Continuant: AV Warehouse (P34) | Nick Foy | Danish Hassan | 1.67 | 83.5 |  |  |  | Complete | Continuant | 5837 | 2 | 0.33 | 89.132 | 263.1478
__export__.project_task_2076_9e14e555 | freight vendor email: footer | Sprint 2103 | 2021-01-11 | Development | KMI: Help (P41) | Levi Barnes | Danish Hassan | 3.92 | 100 |  | Difficulty 1 |  | Complete | KMI Zeolite | 6203 | 3.9167 | -0.0033333 | 2.2314e-06 | 173.5228
__export__.project_task_1320_4c3272ba | Projects: Visibility | Sprint 2118 | 2021-04-26 | Development | PWX: Help (P23) | Levi Barnes | Fahad Hassan | 31.58 | 100 |  | Project | 3 | Complete | EquityTeam | 8421 | 10 | -21.58 | 200 | 1231.5186
Potential Silverdale App
__export__.project_task_1108_8bc02d60 | Release Plan | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9460 | 0 | 0 | 0 | 232.2335
__export__.project_task_3563_28fa0dc7 | Personality: finish line | Sprint 2120 | 2021-05-10 | Development | PWX: Survey (P70) | Muhammad Afzaal | Raheel Aslam | 9.42 | 100 |  |  | 3 | Complete | EquityTeam | 3313 | 8 | -1.42 | 0 | 56
__export__.project_task_3288_3a6db8a0 | Deployment Thursday: Wildleaf | Sprint 2115 | 2021-04-05 | Configuration | Wild Leaf: Accounting (P64) | Jeff Gross | Wajahat Ali | 3.33 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4015 | 0 | -3.33 | 0 | 16.3202
__export__.project_task_2848_b95cd11e | Do not apply discounts to gifts | Sprint 2112 | 2021-03-15 | Development | Mid-America: Help (P37) | Levi Barnes | Osama Khalid | 1.67 | 33.4 |  |  |  | Complete | Mid-America Gardens, LLC | 4685 | 5 | 3.33 | 0 | 133.7659
__export__.project_task_2843_3bcc2a32 | New Buyer Signup - Part 1 | Sprint 2118 | 2021-04-26 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 15.5 | 100 |  |  | 2 | Complete | Cellpoint Corporation | 4688 | 11 | -4.5 | 0 | 339.5186
__export__.project_task_2795_f625f80d | Split Manufacturing Orders | Sprint 2116 | 2021-04-12 | Development | Wild Leaf: Help (P22) | Jeff Gross | Aleem khan | 18.7 | 100 |  |  | 4 | Complete | Wild Leaf Beverage | 4916 | 6 | -12.7 | 72 | 312
__export__.project_task_2709_a1f1aef9 | Resolve the sale order pay now issue on Wildleaf server: | Sprint 2109 | 2021-02-15 | Development | Wild Leaf: Helcim Integration (P38) | Nick Foy | Wajahat Ali | 15.83 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5266 | 0 | -15.83 | 0 | 139.156
__export__.project_task_2708_19c0cd1e | Import current assets |  |  | Configuration | Wild Leaf: Accounting (P64) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5324 | 0 | 0 | 160 | 320
__export__.project_task_2693_f2b47f95 | Default Analytic Account on Sales Invoices based on Production Location | Sprint 2109 | 2021-02-15 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Raheel Aslam | 8.55 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5334 | 6 | -2.55 | 162.0862 | 209.4476
__export__.project_task_2685_22a94aed | JP: Website | Sprint 2108 | 2021-02-08 | Development | PWX: HR (P61) | Levi Barnes | Raheel Aslam | 6 | 100 |  |  |  | Complete | EquityTeam | 5342 | 6 | 0 | 0 | 150.4194
__export__.project_task_2331_8b8e4d36 | QA Stage | Sprint 2104 | 2021-01-18 | Development | Continuant: AV Warehouse (P34) | Nick Foy | Danish Hassan | 1.83 | 91.5 |  |  |  | Complete | Continuant | 5837 | 2 | 0.17 | 89.2128 | 263.2272
__export__.project_task_2263_efc6d964 | Continuant QMA deployment 2101 | Sprint 2103 | 2021-01-11 | Configuration | Continuant: Quotation Management / Automation (P31) | Kaesi Lee | Muzher Siddique | 0.42 | 100 |  |  |  | Complete | Continuant | 5913 | 0.41667 | -0.0033333 | 0 | 0.87214
__export__.project_task_2234_3befe0ea | Record Views - Contacts>Portfolios |  |  | Development | PWX: Property (P58) | Levi Barnes | Muzher Siddique | 0.33 | 94.42 |  |  |  | Complete | EquityTeam | 5932 | 12 | 0.67 | 0 | 200
__export__.project_task_2172_09bf1339 | Calendar event invite error | Sprint 2103 | 2021-01-11 | Bug Fix | KMI: Help (P41) | Levi Barnes | Muzher Siddique | 3.67 | 100 |  | Difficulty 3 |  | Complete | KMI Zeolite | 6024 | 3.6667 | -0.0033333 | 0 | 120
__export__.project_task_2139_fa722437 | Create an Analytic Account Group for each Building and assign Unit and Building Analytic Accounts to the Building Group |  |  | Configuration | PWX: Field Service to Invoicing (P47) | Levi Barnes | Nick Foy | 1 | 100 |  |  |  | Complete | EquityTeam | 6071 | 0.5 | -0.5 | 0 | 391.4494
__export__.project_task_1957_b996a7e6 | Add Weights and Volumes | Sprint 2103 | 2021-01-11 | Configuration | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 2.58 | 96.75 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 2.6667 | 0.086667 | 14.4119 | 248
__export__.project_task_1273_9658335d | Release Plan:iOS Release | Sprint 32 | 2020-09-21 | Configuration | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8581 | 0 | 0 | 0 | 23.7892
__export__.project_task_1199_15b1c428 | Mapping Table for Vendor Fields | Sprint 2051 | 2020-12-14 | Development | Dialed Supply: Help (P21) | Levi Barnes | Raheel Aslam | 13.92 | 73.72 |  |  |  | Complete | Dialed Supply | 8855 | 32 | 8.41 | 359.2039 | 612
__export__.project_task_3323_cdb3c08c | FW: Studio Mode / Other Changes | Sprint 2117 | 2021-04-19 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Fahad Hassan | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 3850 | 0 | 0 | 0 | 44.4617
__export__.project_task_3283_93356b7e | Add a "Print Product Labels" button to Transfers page | Sprint 2115 | 2021-04-05 | Development | Wild Leaf: Help (P22) | Jeff Gross | Aleem khan | 8 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4019 | 2.5 | -5.5 | 0 | 93.5498
__export__.project_task_2926_b436810d | max item view by default | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 11.33 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 4568 | 9 | -2.33 | 3.4102 | 113.3052
__export__.project_task_2920_a6df3bef | Wildleaf: Add Assets description fields | Sprint 2112 | 2021-03-15 | Development | Wild Leaf: Help (P22) | Jeff Gross | Wajahat Ali | 1.42 | 94.67 |  |  |  | Complete | Wild Leaf Beverage | 4571 | 1.5 | 0.08 | 0 | 114.8967
__export__.project_task_2870_1b47ae5a | Changes to Traveller TRANSACTION_CHARGE field | Sprint 2135 | 2021-08-23 | Development | Cellpoint: ecoATM API (P50) | Farman Ahmad Cheema | Fahad Hassan | 9.5 | 100 |  | SPLN | 2 | ELS | Cellpoint Corporation | 4655 | 9.3333 | -0.16667 | 931.022 | 0
__export__.project_task_2735_7d4a8faf | Default Analytic Account on Vendor Bills based on Deliver To Location | Sprint 2110 | 2021-02-22 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Raheel Aslam | 28.25 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5180 | 7 | -21.25 | 128 | 175.39
__export__.project_task_2686_49f2e575 | Application: Main/Other | Sprint 2109 | 2021-02-15 | Development | PWX: HR (P61) | Levi Barnes | Raheel Aslam | 4.08 | 100 |  |  |  | Complete | EquityTeam | 5340 | 4 | -0.08 | 0 | 149.6722
__export__.project_task_2338_4b65057c | AV Project Form View: Add Project Stages | Sprint 2104 | 2021-01-18 | Development | Continuant: AV Warehouse (P34) | Nick Foy | Danish Hassan | 3.08 | 100 |  |  |  | Complete | Continuant | 5837 | 2 | -1.08 | 88.8801 | 262.8926
__export__.project_task_2232_76ba21f6 | Record Views - Contacts>Units: Accounting | Sprint 2105 | 2021-01-25 | Development | PWX: Property (P58) | Levi Barnes | Raheel Aslam | 2.67 | 66.75 |  |  |  | Complete | EquityTeam | 5932 | 4 | 1.33 | 0 | 294.2411
__export__.project_task_2177_14c9c7d6 | freight vendor email: add send from and send to addresses | Sprint 2103 | 2021-01-11 | Development | KMI: Help (P41) | Levi Barnes | Danish Hassan | 2.17 | 100 |  | Difficulty 1 |  | Complete | KMI Zeolite | 6005 | 2 | -0.17 | 0 | 120.841
__export__.project_task_2167_649dc00a | Helpdesk Emails | Sprint 2103 | 2021-01-11 | Bug Fix | Silverdale: Help (P12) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 6026 | 0 | 0 | 0 | 112
__export__.project_task_2128_db0a1c7d | Default Filter by User Location |  |  | Studio | Wild Leaf: Single OpCo (P48) | Kaesi Lee | Kaesi Lee | 0.5 | 0 |  | NF Review |  | Complete | Wild Leaf Beverage | 6073 | 0 | -0.5 | 64 | 120
__export__.project_task_2106_926ea12f | Test Scripts/QA - Planning |  |  | Development | Silverdale: Help (P12) | Muhammad Afzaal | Muhammad Afzaal | 3.83 | 100 |  | Difficulty 2 |  | Cancelled | Silverdale Technology LLC | 6103 | 12 | -3.76 | 0.035253 | 313.4933
__export__.project_task_1904_66d6384a | Can we deploy List View Manager on CPBids?: Remove functions for Sellers | Sprint 2052 | 2020-12-21 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 11.33 | 0 |  | P1 |  | Complete | Cellpoint Corporation | 6555 | 0 | -11.33 | 0 | 68
__export__.project_task_1901_941e9260 | Scan Items Button | Sprint 2053 | 2020-12-28 | Development | Continuant: AV Warehouse (P34) | Kaesi Lee | Danish Hassan | 16.75 | 100 |  |  |  | Complete | Continuant | 6557 | 16.1667 | -0.58333 | 0 | 152.8356
__export__.project_task_1279_4403b8bc | Release Plan:RollBack Plan | Sprint 32 | 2020-09-21 | Configuration | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8581 | 0 | 0 | 0 | 23.7073
__export__.project_task_3270_8dcbb149 | The unit of measure mg defined on the order line |  |  | Bug Fix | MMH: Help (P83) | Jeff Gross | Muhammad Bilal | 18.25 | 91.25 |  |  |  | Complete | Mountain Meadow Herbs | 4060 | 20 | 1.75 | 0 | 104.2516
__export__.project_task_2815_4c5d43a2 | Create csv file for "Received" | Sprint 2135 | 2021-08-23 | Development | Cellpoint: ecoATM API (P50) | Farman Ahmad Cheema | Fahad Hassan | 17.92 | 100 |  | SPLN | 2 | ELS | Cellpoint Corporation | 4758 | 17.6667 | -0.25333 | 968 | 0
__export__.project_task_2803_65afeb5b | sales order report modifications | Sprint 2112 | 2021-03-15 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 9.47 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 4866 | 6.6667 | -2.8033 | 0 | 143.1353
__export__.project_task_2424_b6ccd453 | av_tracker unit testing | Sprint 2108 | 2021-02-08 | Development | Continuant: Unit Testing (P51) | Nick Foy | Kaleem Khan | 9.67 | 96.7 |  |  |  | Complete | Continuant | 5590 | 10 | 0.33 | 40 | 214.3736
__export__.project_task_2176_ca725366 | Email setup: broken links in emails | Sprint 2103 | 2021-01-11 | Bug Fix | KMI: Help (P41) | Levi Barnes | Muzher Siddique | 2.5 | 83.33 |  |  |  | Complete | KMI Zeolite | 6005 | 3 | 0.5 | 0 | 112.8838
__export__.project_task_2081_e9208f66 | Hydrofarm API Product Search Integration: get all available | Sprint 2105 | 2021-01-25 | Development | Dialed Supply: Help (P21) | Levi Barnes | Raheel Aslam | 31.67 | 100 |  | Difficulty 3 |  | Complete | Dialed Supply | 6193 | 31.6667 | -0.0033333 | 0 | 350.1108
NF Review
__export__.project_task_2049_109aeb8b | elavon payment acquirer | Sprint 2105 | 2021-01-25 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 19.38 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 6262 | 6 | -25.29 | 0 | 202.7842
__export__.project_task_1275_2a8ac8ee | Release Plan:Deprecate Older versions | Sprint 32 | 2020-09-21 | Configuration | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8581 | 0 | 0 | 0 | 23.7551
__export__.project_task_1200_4a5a6d99 | Hydrofarm API Product Search Integration | Sprint 2051 | 2020-12-14 | Development | Dialed Supply: Help (P21) | Levi Barnes | Raheel Aslam | 17.42 | 100 |  | API |  | Complete | Dialed Supply | 8855 | 24 | -25.09 | 368 | 612
SPriority
__export__.project_task_573_5af19b43 | Time Update should be auto update | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10147 | 0 | 0 | 0 | 424
__export__.project_task_4854_5bcbdf4d | Final set-up of the Shopify connector |  |  | Configuration | Zuma: Odoo Implementation Phase 2 (P204) | Asfand Yaar | Asfand Yaar | 0 | 0 |  | 2016-09-01 |  | Planning | Zuma Sales LLC | 149 | 5 | 5 | 8.7095 | 0
__export__.project_task_3258_6f15e4bd | Unreserve Inventory Issues |  |  | Bug Fix | MMH: Help (P83) | Jeff Gross | Muhammad Bilal | 8.67 | 100 |  |  |  | Complete | Mountain Meadow Herbs | 4088 | 5 | -3.67 | 0 | 116
__export__.project_task_2993_ea13bc66 | Pay in advance with non-immediate payment method creates invoice and moves sales order to deposit pending | Sprint 2113 | 2021-03-22 | Development | Continuant: Quotation Management / Automation (P31) | Jeff Gross | Muhammad Bilal | 3.58 | 71.6 |  |  |  | Complete | Continuant | 4487 | 5 | 1.42 | 0 | 80
__export__.project_task_2937_07cfcedb | Salesorder total summary alteration | Sprint 2112 | 2021-03-15 | Development | Mid-America: Help (P37) | Levi Barnes | Muhammad Bilal | 4.58 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 4551 | 4.3333 | -0.24667 | 0 | 71.1331
__export__.project_task_2934_6cb613e7 | Remove Seller & location from lot add in auction:R&D and database restoration. | Sprint 2115 | 2021-04-05 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 12.42 | 100 |  |  | 3 | Complete | Cellpoint Corporation | 4563 | 8 | -4.42 | 0 | 178.9044
__export__.project_task_2850_16ce3baf | Remove Seller & location from lot add in auction |  |  | Development | Improvements for Belmont (P213) | Farman Ahmad Cheema | Kaleem Khan | 15.5 | 44.29 | Please add next activity |  | 3 | Planning | Cellpoint Corporation | 4684 | 35 | 19.5 | 1031.0948 | 0
__export__.project_task_2694_14c0adbf | Reserve and current highest price filters range on Apps. | Sprint 2112 | 2021-03-15 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 1 | 0 |  |  |  | Complete | Cellpoint Corporation | 5334 | 0 | -1 | 0.17159 | 286.9144
__export__.project_task_2618_d45371a7 | Go Live: Inventory mass update buttons | Sprint 2108 | 2021-02-08 | Development | Mid-America: Help (P37) | Levi Barnes | Muhammad Bilal | 7.33 | 61.08 |  |  |  | Complete | Mid-America Gardens, LLC | 5521 | 12 | 4.67 | 0 | 190.42
__export__.project_task_2339_d1075bac | freight vendor email: Sending Bugs |  |  | Bug Fix | KMI: Help (P41) | Levi Barnes | Fahad Hassan | 21.42 | 100 |  |  |  | Complete | KMI Zeolite | 5837 | 5 | -16.42 | 4.7868e-05 | 200.6862
__export__.project_task_2251_c57547f5 | Display Actual Location for Item | Sprint 2104 | 2021-01-18 | Development | Continuant: AV Warehouse (P34) | Nick Foy | Danish Hassan | 4.17 | 100 |  | Difficulty 1 |  | Complete | Continuant | 5928 | 4.1667 | -0.0033333 | 120 | 294.0119
__export__.project_task_2090_ddf0f939 | FW: You have been assigned to error on employees module (#47) |  |  | Bug Fix | PWX: Help (P23) | Levi Barnes | Danish Hassan | 2 | 0 |  |  |  | Complete | EquityTeam | 6190 | 0 | -2 | 0 | 160
__export__.project_task_1907_6d909dbc | cpbids auctions disappeared | Sprint 2051 | 2020-12-14 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 7.5 | 100 |  | P1 |  | Complete | Cellpoint Corporation | 6536 | 3.5 | -4 | 7.8231e-05 | 63.5481
__export__.project_task_1549_38aa0b23 | Import Parts List to Product Master: Parts Search Tool | Sprint 2109 | 2021-02-15 | Development | Continuant: Quotation Management / Automation (P31) | Nick Foy | Muzher Siddique | 18 | 100 |  |  |  | Complete | Continuant | 7559 | 18 | 0 | 504 | 678.4517
__export__.project_task_1274_2df7b5c7 | Release Plan:Redirect Signup Form | Sprint 32 | 2020-09-21 | Configuration | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8581 | 0 | 0 | 0 | 23.7744
__export__.project_task_3255_09a74084 | PWX: Change nature of "Job Location" field on job position form | Sprint 2115 | 2021-04-05 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 7.58 | 100 |  |  | 2 | Complete | EquityTeam | 4089 | 4 | -3.58 | 0 | 116.0419
__export__.project_task_2857_ffcedce5 | Create fields in Travellers Model | Sprint 2112 | 2021-03-15 | Development | Cellpoint: ecoATM API (P50) | Nick Foy | Muhammad Bilal | 2.28 | 100 |  |  |  | Complete | Cellpoint Corporation | 4665 | 2 | -0.28 | 0 | 91.436
__export__.project_task_2816_d83e9a2c | Create csv file for "Repaired" | Sprint 2135 | 2021-08-23 | Development | Cellpoint: ecoATM API (P50) | Farman Ahmad Cheema | Fahad Hassan | 7.83 | 100 |  | SPLN | 2 | ELS | Cellpoint Corporation | 4758 | 7.6667 | -0.16333 | 968 | 0
__export__.project_task_2687_58d95b93 | Application: Evaluations | Sprint 2108 | 2021-02-08 | Development | PWX: HR (P61) | Levi Barnes | Raheel Aslam | 6.75 | 100 |  |  |  | Complete | EquityTeam | 5340 | 6 | -0.75 | 0 | 149.6293
__export__.project_task_2619_a188aa9e | Go Live: SO sequence modifications | Sprint 2105 | 2021-01-25 | Configuration | Mid-America: Help (P37) | Levi Barnes | Levi Barnes | 0 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 5521 | 0 | 0 | 0 | 190.1097
__export__.project_task_2410_15a96321 | Phase 1: Create a CSV file export module: Edit the existing Odoo export function | Sprint 2110 | 2021-02-22 | Development | Cellpoint: ecoATM API (P50) | Nick Foy | Fahad Hassan | 51.83 | 100 |  |  |  | Complete | Cellpoint Corporation | 5619 | 18.6667 | -33.1633 | 0 | 287.4003
__export__.project_task_2310_18e44101 | Billing - Direct cost billing: Populate Analytic Account | Sprint 2105 | 2021-01-25 | Development | Wild Leaf: Help (P22) | Nick Foy | Danish Hassan | 3.25 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5877 | 3 | -0.25 | 104 | 278.1119
__export__.project_task_2111_856c2d94 | Multiple People not seeing PWX PS Support Helpdesk | Sprint 2102 | 2021-01-04 | Bug Fix | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 4 | 100 |  |  |  | Complete | EquityTeam | 6094 | 3.5 | -0.5 | 0 | 122.9314
__export__.project_task_2083_574c120e | freight vendor email: add total weight | Sprint 2102 | 2021-01-04 | Development | KMI: Help (P41) | Levi Barnes | Danish Hassan | 2.42 | 100 |  |  |  | Complete | KMI Zeolite | 6192 | 2.4167 | -0.0033333 | 0 | 138.9303
__export__.project_task_1884_43b1dd64 | Test Connection to Hydrofarm API | Sprint 2051 | 2020-12-14 | Development | Dialed Supply: Help (P21) | Muhammad Afzaal | Raheel Aslam | 2.25 | 100 |  |  |  | Complete | Dialed Supply | 6584 | 0.66667 | -1.5833 | 0 | 80
__export__.project_task_1550_35e0064f | Connect to AV-IQ Product Search API | Sprint 2105 | 2021-01-25 | Development | Continuant: Quotation Management / Automation (P31) | Kaesi Lee | Raheel Aslam | 17.25 | 100 |  |  |  | Complete | Continuant | 7559 | 17.25 | 0 | 0 | 464
__export__.project_task_1276_7c177588 | Release Plan:Listview for buyers | Sprint 32 | 2020-09-21 | Configuration | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8581 | 0 | 0 | 0 | 23.7414
__export__.project_task_2827_41cc6f3a | User group config | Sprint 2112 | 2021-03-15 | Development | Moln: 3 New Portal Websites (P62) | Levi Barnes | Danish Hassan | 5.5 | 100 |  |  |  | Complete | Moln Solutions, LLC | 4732 | 4 | -1.5 | 0 | 111.3629
__export__.project_task_2784_8d197481 | FW: uninstall apps | Sprint 2110 | 2021-03-01 | Development | PWX: app cleanup (P67) | Levi Barnes | Danish Hassan | 4.42 | 100 |  |  |  | Complete | EquityTeam | 5017 | 4 | -0.42 | 0 | 96
__export__.project_task_2617_4eb25939 | Go Live: Introductions discounts | Sprint 2107 | 2021-02-01 | Configuration | Mid-America: Help (P37) | Levi Barnes | Levi Barnes | 0.5 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 5521 | 0 | -0.5 | 0 | 190.3111
__export__.project_task_2606_521dda32 | Test the Whole functionality on both local and staging | Sprint 2108 | 2021-02-08 | Development | Wild Leaf: Helcim Integration (P38) | Nick Foy | Wajahat Ali | 16.33 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5548 | 2.5 | -13.83 | 24.0436 | 198.4622
__export__.project_task_2412_28581db7 | Phase 1: Create a CSV file export module: Create a Filter option | Sprint 2108 | 2021-02-08 | Development | Cellpoint: ecoATM API (P50) | Nick Foy | Raheel Aslam | 4.17 | 100 |  |  |  | Complete | Cellpoint Corporation | 5619 | 3 | -1.17 | 0 | 287.3208
__export__.project_task_2336_9bb505c8 | Send to Pick Window: Filter Delivery Order Selection | Sprint 2104 | 2021-01-18 | Development | Continuant: AV Warehouse (P34) | Nick Foy | Danish Hassan | 2.08 | 100 |  |  |  | Complete | Continuant | 5837 | 1.75 | -0.33 | 88.9985 | 263.0093
__export__.project_task_2255_4b97c5ab | Create AV Item Button Confirmation Message | Sprint 2104 | 2021-01-18 | Development | Continuant: AV Warehouse (P34) | Nick Foy | Danish Hassan | 6.58 | 100 |  | NF Review |  | Complete | Continuant | 5926 | 4.8333 | -1.7467 | 120 | 294.0122
__export__.project_task_2233_53d95857 | Record Views - Contacts>Units: Other | Sprint 2103 | 2021-01-11 | Development | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 2.83 | 100 |  |  |  | Complete | EquityTeam | 5932 | 1.5 | -1.33 | 0 | 71.0325
__export__.project_task_2165_77866dbf | Dashboard for CSRs Requirements |  |  | Requirements Collection | Wild Leaf: Dashboard for CSRs (P173) | Abdul Hameed | Abdul Hameed | 0 | 0 | Gather requirements from the Client |  |  | Planning | Wild Leaf Beverage | 6029 | 3 | 3 | 1335.8876 | 0
__export__.project_task_2142_7b798f28 | Default link is set, should be blank | Sprint 2102 | 2021-01-04 | Bug Fix | Silverdale: Help (P12) | Nick Foy | Muzher Siddique | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 6070 | 1 | 1 | 0 | 114.9292
__export__.project_task_2140_880fa8d4 | Build function to auto-create a Project and Analytic Account for any new Building or Unit |  |  | Development | PWX: Field Service to Invoicing (P47) | Levi Barnes | Raheel Aslam | 11 | 100 |  | Difficulty 2 |  | Complete | EquityTeam | 6071 | 21 | -0.91 | 0 | 391.4522
__export__.project_task_2099_c1306d7f | Security Audits |  |  | Configuration | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 1 | 0 |  |  |  | Complete | Silverdale Technology LLC | 6104 | 0 | -2.83 | 0 | 66.7834
__export__.project_task_2001_280daa06 | Backup setup | Sprint 2102 | 2021-01-04 | Configuration | KMI: Help (P41) | Levi Barnes | Levi Barnes | 0.75 | 0 |  |  |  | Complete | KMI Zeolite | 6506 | 0 | -0.75 | 0 | 210.9203
__export__.project_task_1829_3c33f406 | Auto-assign the Project Manager to Tasks | Sprint 2051 | 2020-12-14 | Development | Silverdale: Help (P12) | Nick Foy | Danish Hassan | 2.5 | 98.84 |  |  |  | Complete | Silverdale Technology LLC | 6750 | 3.1667 | 0.036667 | 0 | 117.6196
__export__.project_task_1272_92e487c1 | Release Plan: Android Manual Release | Sprint 32 | 2020-09-21 | Configuration | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8581 | 0 | 0 | 0 | 23.8195
__export__.project_task_4590_cdf9bf50 | Consignment additional Changes After Demo | Sprint 2136 | 2021-08-30 | Development | Wild Leaf: Consignment and Sales Improvements (P112) | Naseeb Razaq | Muhammad Bilal | 11.75 | 100 |  | SPLN |  | Complete | Wild Leaf Beverage | 797 | 0.083333 | -11.6667 | 102.9823 | 164.4037
__export__.project_task_4548_fa074076 | Pre-deployment QA-2133 |  |  | Development | Silverdale: SDET (P132) | Muhammad Afzaal |  | 0.58 | 0 |  |  |  | Complete | Silverdale Technology LLC | 800 | 0 | -0.58 | 0 | 60
__export__.project_task_4543_8a49ffeb | WildLeaf Deploy To Deployment + Production(2133) | Sprint 2133 | 2021-08-09 | Deployment | Wild Leaf: Help (P22) | Mir Muhammad Muzammil |  | 6.75 | 100 |  |  |  | Complete | Wild Leaf Beverage | 802 | 6.75 | 0 | 0 | 89.0436
__export__.project_task_4526_38e05ee0 | Customer still able to see all invoices, need to only see open invoices | Sprint 2135 | 2021-08-23 | Bug Fix | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Raheel Aslam | 4.75 | 100 |  | SPLN |  | Complete | Continuant | 842 | 4.75 | 0 | 0 | 145.4206
__export__.project_task_4525_8953926c | Pay now button is gone on INV/2021/25652 | Sprint 2135 | 2021-08-23 | Bug Fix | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Fahad Hussain Malik | 0.25 | 25 |  | SPLN |  | Complete | Continuant | 842 | 1 | 0.75 | 0 | 145.4206
__export__.project_task_4524_ee4aa842 | Unable to pay multiple invoices | Sprint 2136 | 2021-08-30 | Bug Fix | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Raheel Aslam | 9.42 | 94.2 |  | SPLN |  | Complete | Continuant | 842 | 10 | 0.58 | 0 | 145.4206
__export__.project_task_4523_976337dc | Search bar is not available on portal | Sprint 2135 | 2021-08-23 | Bug Fix | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Raheel Aslam | 4 | 53.33 |  | SPLN |  | Complete | Continuant | 842 | 7.5 | 3.5 | 0 | 145.4206
__export__.project_task_4522_12b01594 | Scale Continuant logo to fit portal dimensions | Sprint 2135 | 2021-08-23 | Configuration | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  | SPLN |  | Complete | Continuant | 842 | 0.5 | 0.5 | 0 | 113.4208
__export__.project_task_4521_8761bede | Unable to print PDF for credit | Sprint 2135 | 2021-08-23 | Bug Fix | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Raheel Aslam | 5.5 | 100 |  | SPLN |  | Complete | Continuant | 842 | 5.5 | 0 | 0 | 145.4208
__export__.project_task_4487_4bbf550d | Credits showing as SI's on portal | Sprint 2135 | 2021-08-23 | Bug Fix | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Raheel Aslam | 0.67 | 8.38 |  | SPLN |  | Complete | Continuant | 892 | 8 | 7.33 | 1.9473e-05 | 131.5153
__export__.project_task_4370_0a268776 | suplus sale configuration | Sprint 2133 | 2021-08-09 | Configuration | Mid-America: Help (P37) | Naseeb Razaq |  | 8 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 1201 | 8 | 0 | 0 | 108.6453
__export__.project_task_3894_67400212 | Job Position: job website modifications | Sprint 2127 | 2021-06-28 | Development | PWX: HR (P61) | Farman Ahmad Cheema | Raheel Aslam | 6.5 | 100 |  | SPLN | 2 | Complete | EquityTeam | 2477 | 5 | -1.5 | 170.9534 | 201.1692
__export__.project_task_3893_0c0ae42c | Job Position: Job Posting field | Sprint 2127 | 2021-06-28 | Development | PWX: HR (P61) | Farman Ahmad Cheema | Raheel Aslam | 3.33 | 83.25 |  | SPLN | 2 | Complete | EquityTeam | 2477 | 4 | 0.67 | 170.9706 | 201.1809
__export__.project_task_3842_e59cdaf6 | Do a full set of critical test script PDQA on Wildleaf | Sprint 2122 | 2021-05-24 | Configuration | Wild Leaf: Accounting (P64) | Muhammad Afzaal | Muhammad Saqlain Alam | 7.83 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2669 | 0 | -7.83 | 0.019098 | 8.9447
__export__.project_task_3575_71beabc6 | Add Manufactured Quantity to the Sales Order | Sprint 2120 | 2021-05-10 | Development | Wild Leaf: Help (P22) | Muhammad Afzaal | Aleem khan | 5.2 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 3240 | 3 | -2.2 | 0 | 55.3897
__export__.project_task_3357_4068e32d | Job Position form fix:2 | Sprint 2117 | 2021-04-19 | Bug Fix | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 2.75 | 100 |  |  | 1 | Complete | EquityTeam | 3675 | 1 | -1.75 | 0 | 95.5186
__export__.project_task_3348_c729fb11 | PWX: Job selection field on employee form should be a multi selection field:Make another function to make first selected job as Main job | Sprint 2118 | 2021-04-26 | Development | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 6.75 | 100 |  |  | 2 | Complete | EquityTeam | 3720 | 3 | -3.75 | 0 | 136
__export__.project_task_3313_e3a0fb3c | Deployement 07-04-2021:Mid-America | Sprint 2116 | 2021-04-12 | Configuration | Mid-America: Help (P37) | Levi Barnes | Wajahat Ali | 2.25 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 3870 | 0 | -2.25 | 0.0092883 | 2.059
__export__.project_task_3308_14772dce | WildLeaf: Add customer number field and vendor number field | Sprint 2118 | 2021-04-26 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Fahad Hassan | 2.42 | 100 |  |  | 1 | Complete | Wild Leaf Beverage | 3877 | 1 | -1.42 | 0 | 71.6508
__export__.project_task_3298_7b4ed7bf | Continuant: Picklist is filling out done quantity instead of reserved quantity | Sprint 2116 | 2021-04-12 | Development | Continuant: AV Warehouse (P34) | Jeff Gross |  | 4.08 | 74.18 |  |  | 3 | Complete | Continuant | 3915 | 5.5 | 1.42 | 0 | 96
__export__.project_task_3297_0823a205 | Continuant: Invoice ready still ready when invoice is open | Sprint 2116 | 2021-04-12 | Development | Continuant: Quotation Management / Automation (P31) | Jeff Gross | Muhammad Bilal | 3.42 | 85.5 |  |  | 2 | Complete | Continuant | 3915 | 4 | 0.58 | 0 | 72
__export__.project_task_3296_fd8456a0 | Continuant: Make serial numbers non-mandatory when drop shipping | Sprint 2116 | 2021-04-12 | Development | Continuant: AV Warehouse (P34) | Jeff Gross | Muhammad Bilal | 2.92 | 62.57 |  |  | 3 | Complete | Continuant | 3916 | 4.6667 | 1.7467 | 0 | 96
__export__.project_task_3286_7da02891 | Invoice is not getting confirmed | Sprint 2115 | 2021-04-05 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 0 | 0 |  |  |  | Cancelled | Mid-America Gardens, LLC | 4016 | 0 | 0 | 0 | 0
__export__.project_task_3274_335476a8 | Deployment Wednesday: Wildleaf |  |  | Configuration | Wild Leaf: Accounting (P64) | Jeff Gross | Wajahat Ali | 2.83 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4041 | 0 | -2.83 | 0 | 3.6103
__export__.project_task_3247_21d32b3a | Add the print pdf option under the action drop down menu in Picklist | Sprint 2114 | 2021-03-29 | Development | Continuant: AV Warehouse (P34) | Jeff Gross | Muhammad Bilal | 3.42 | 85.5 |  |  | 2 | Complete | Continuant | 4162 | 4 | 0.58 | 0 | 124.8717
__export__.project_task_3212_dd06633b | Donors Management System | Sprint 2117 | 2021-04-19 | Development | Heronswood: Network for Good transition to Odoo (P78) | Jeff Gross | Danish Hassan | 6.92 | 100 |  |  | 3 | Complete | Port Gamble Sâ€™Klallam Foundation | 4232 | 5 | -1.92 | 1.718e-05 | 195.6047
__export__.project_task_3205_ae8cea18 | Wildleaf: Customer accept and sign on portal should not confirm sales order | Sprint 2114 | 2021-03-29 | Development | Wild Leaf: Help (P22) | Jeff Gross | Danish Hassan | 3.83 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 4233 | 3.5 | -0.33 | 0 | 68.0531
__export__.project_task_3202_d5faf249 | Change the Scan IMEI Inbound target field | Sprint 2114 | 2021-03-29 | Development | Cellpoint: ecoATM API (P50) | Nick Foy |  | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 4245 | 0 | 0 | 0 | 0
__export__.project_task_3188_2caaf438 | Continuant: Customer portal preferred delivery method overrides existing preferred invoice delivery method | Sprint 2115 | 2021-04-05 | Development | Continuant: Customer Portal AR (P32) | Jeff Gross | Muhammad Bilal | 21.42 | 100 |  |  | 2 | Complete | Continuant | 4331 | 14 | -7.42 | 1.4339e-05 | 165.5445
__export__.project_task_2988_8a556fc0 | Phase 2: Create a CSV Import module (eco specific): change to import field contents | Sprint 2112 | 2021-03-15 | Development | Cellpoint: ecoATM API (P50) | Nick Foy | Muzher Siddique | 1.83 | 100 |  |  | 2 | Complete | Cellpoint Corporation | 4494 | 0.5 | -1.33 | 0 | 87.2514
__export__.project_task_2868_03b3bd85 | Add new fields to the x_shipments table | Sprint 2112 | 2021-03-15 | Development | Cellpoint: ecoATM API (P50) | Nick Foy | Danish Hassan | 2.58 | 100 |  |  | 2 | Complete | Cellpoint Corporation | 4655 | 1.1667 | -1.4133 | 0 | 125.3286
__export__.project_task_2778_4d872f52 | deployment incorrect |  |  | Bug Fix | PWX: HR (P61) | Levi Barnes | Kaleem Khan | 3 | 0 |  |  |  | Complete | EquityTeam | 5041 | 0 | -3 | 0 | 96
__export__.project_task_2773_2262767e | singleton bug |  |  | Bug Fix | Dialed Supply: Help (P21) | Levi Barnes | Kaleem Khan | 7.5 | 0 |  |  |  | Complete | Dialed Supply | 5066 | 0 | -7.5 | 0 | 191.2072
__export__.project_task_2723_44a4d7be | Evalon circle of death |  |  | Bug Fix | Mid-America: Help (P37) | Levi Barnes | Fahad Hassan | 4.83 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 5187 | 0 | -4.83 | 0 | 128
__export__.project_task_2722_d00746b6 | Demo | Sprint 2109 | 2021-02-15 | Development | Dialed Supply: Help (P21) | Levi Barnes | Raheel Aslam | 1.58 | 79 |  |  |  | Complete | Dialed Supply | 5187 | 2 | 0.42 | 0 | 38.6911
__export__.project_task_2700_3401d814 | Fwd: Error Message when creating sales quote |  |  | Bug Fix | PWX: Help (P23) | Levi Barnes | Danish Hassan | 5 | 0 |  |  |  | Complete | EquityTeam | 5329 | 0 | -5 | 0 | 160
__export__.project_task_2678_d0c11c7c | FW: 3 Modules Deployed Today |  |  | Bug Fix | Continuant: Unit Testing (P51) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Continuant | 5349 | 0 | 0 | 0 | 7.2617
__export__.project_task_2609_0cb0ab4b | Associate the Sale Order with created Transection | Sprint 2107 | 2021-02-01 | Development | Wild Leaf: Helcim Integration (P38) | Nick Foy | Wajahat Ali | 7.58 | 94.75 |  |  |  | Complete | Wild Leaf Beverage | 5546 | 8 | 0.42 | 24 | 198.3103
__export__.project_task_2407_d116f269 | Unit Testing: Quotation Management / Automation |  |  |  | Continuant: Quotation Management / Automation (P31) | Kaesi Lee |  | 0.5 | 0 |  |  |  | Cancelled | Continuant | 5661 | 0 | -0.5 | 0 | 40
__export__.project_task_2397_215840a3 | Finding exact root cause of error |  |  | Bug Fix | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 0.83 | 99.6 |  |  |  | Complete | Wild Leaf Beverage | 5690 | 0.83333 | 0.0033333 | 0 | 0
__export__.project_task_2304_8109490c | Connect Postgress database to PowerBI | Sprint 2103 | 2021-01-11 | Configuration | Silverdale: Help (P12) | Nick Foy | Danish Hassan | 4.17 | 100 |  |  |  | Complete | Silverdale Technology LLC | 5885 | 5 | -3.17 | 0 | 22.5716
__export__.project_task_2253_450d6491 | By default display Room on List and Form View | Sprint 2104 | 2021-01-18 | Development | Continuant: AV Warehouse (P34) | Nick Foy | Danish Hassan | 3 | 100 |  | Difficulty 1 |  | Complete | Continuant | 5927 | 3 | 0 | 120 | 294.0111
NF Review
__export__.project_task_2170_c7b47f27 | Use Related Contract Field | Sprint 2104 | 2021-01-18 | Development | Continuant: AV Warehouse (P34) | Nick Foy | Danish Hassan | 3.5 | 100 |  | Difficulty 1 |  | Complete | Continuant | 6024 | 3.5 | 0 | 136 | 310.0103
__export__.project_task_2157_3bffa69f | Purchase Order Form View: Move Deliver To field to under Vendor. |  |  | Studio | Wild Leaf: Help (P22) | Kaesi Lee |  | 0.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6053 | 0 | -0.25 | 0 | 120.5819
__export__.project_task_2153_f6b6cf2c | Sales Orders: Form View: Small Changes |  |  | Studio | Wild Leaf: Help (P22) | Kaesi Lee | Kaesi Lee | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6053 | 0 | 0 | 0.02561 | 32.6773
__export__.project_task_2152_2ac9a892 | Update work center names to include location |  |  | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 0.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6053 | 0 | -0.25 | 0.02585 | 120.7106
__export__.project_task_2145_02ef20e6 | CPBids Belmont Azure Incorrect Mapping | Sprint 2102 | 2021-01-04 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Fahad Hassan | 2.5 | 100 |  |  |  | Complete | Cellpoint Corporation | 6067 | 2.5 | 0 | 0 | 114.9283
__export__.project_task_2126_08426920 | Client Reference Field for Tasks | Sprint 2103 | 2021-01-11 | Development | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 2.42 | 100 |  | Difficulty 1 |  | Complete | Silverdale Technology LLC | 6074 | 2.4167 | -0.0033333 | 0 | 144
__export__.project_task_2105_14cbf658 | Create a new tab(QA) in Project Task |  |  |  | Silverdale: Help (P12) | Muhammad Afzaal | Kaleem Khan | 2.08 | 100 |  |  |  | Cancelled | Silverdale Technology LLC | 6103 | 2 | -0.08 | 0.06936 | 155.2363
__export__.project_task_2006_0ffce0d4 | Inventory Import - Production CAL Counts | Sprint 2052 | 2020-12-21 | Development | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 4.33 | 100 |  |  |  | Complete | Wild Leaf Beverage | 6438 | 4 | -0.33 | 0 | 94.4786
__export__.project_task_1788_32537ab1 | Increment Rule not showing as a tag | Sprint 2050 | 2020-12-07 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 2.17 | 100 |  |  |  | Complete | Cellpoint Corporation | 6836 | 2 | -0.17 | 0 | 102.5614
__export__.project_task_1268_80fd0942 | Buyer List View for APP Version | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8582 | 0 | 0 | 0 | 24
__export__.project_task_3218_d5a4cc92 | Wildleaf: Resize the location barcode | Sprint 2117 | 2021-04-19 | Development | Wild Leaf: Help (P22) | Jeff Gross | Muhammad Bilal | 12.75 | 98.08 |  |  | 3 | Complete | Wild Leaf Beverage | 4208 | 13 | 0.25 | 0 | 172
__export__.project_task_2602_c8d1a2bf | Create & Validate transaction | Sprint 2107 | 2021-02-01 | Development | Wild Leaf: Helcim Integration (P38) | Nick Foy | Wajahat Ali | 5.58 | 69.75 |  |  |  | Complete | Wild Leaf Beverage | 5548 | 8 | 2.42 | 24.2319 | 198.5413
__export__.project_task_2426_8b4199a6 | av_iq_product unit testing | Sprint 2107 | 2021-02-01 | Development | Continuant: Unit Testing (P51) | Nick Foy | Fahad Hassan | 10.17 | 100 |  |  |  | Complete | Continuant | 5589 | 8 | -2.17 | 40 | 214.3106
__export__.project_task_2366_ecc02dd3 | Internal: Project UX Review: strip error |  |  | Bug Fix | Dialed Supply: Help (P21) | Levi Barnes | Raheel Aslam | 1.97 | 100 |  |  |  | Complete | Dialed Supply | 5762 | 0.66667 | -1.3033 | 0 | 272
__export__.project_task_2313_005939af | Research the API Documentation available on the website | Sprint 2104 | 2021-01-18 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 3.83 | 95.75 |  | Difficulty 3 |  | Complete | Mid-America Gardens, LLC | 5866 | 4 | 0.17 | 0 | 59.6264
MA Review
__export__.project_task_2175_10bd6b01 | Create Sales Orders and Invoices for previous Deerfield donations (305) | Sprint 2103 | 2021-01-11 | Configuration | PWX: Help (P23) | Levi Barnes | Nick Foy | 2.5 | 83.33 |  |  |  | Complete | EquityTeam | 6020 | 3 | 0.5 | 0 | 102.7253
__export__.project_task_2154_1f0ff5a8 | Unconfirmed event attendees receiving Event: Reminder email | Sprint 2102 | 2021-01-04 | Bug Fix | Heronswood: Events (P3) | Nick Foy | Danish Hassan | 2.5 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 6053 | 0 | -13.75 | 0 | 107.5808
__export__.project_task_2082_abbe87d3 | Mapping Table for Vendor Fields: config | Sprint 2104 | 2021-01-18 | Configuration | Dialed Supply: Help (P21) | Levi Barnes | Raheel Aslam | 9.67 | 100 |  | Difficulty 2 |  | Complete | Dialed Supply | 6193 | 9.3333 | -0.33667 | 0 | 168
__export__.project_task_1731_6a219a36 | Add Lot Ref as the default in Search | Sprint 2049 | 2020-11-30 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 3.17 | 100 |  |  |  | Complete | Cellpoint Corporation | 6869 | 3 | -2.34 | 0 | 9.3155
__export__.project_task_1158_e5de5ca1 | Relist and Duplicate | Sprint 31 | 2020-09-14 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9202 | 0 | 0 | 0 | 140.5272
__export__.project_task_2946_bd5900d3 | Wildleaf Unit of measures issue | Sprint 2116 | 2021-04-12 | Development | Wild Leaf: Help (P22) | Jeff Gross | Aleem khan | 15.5 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 4538 | 8 | -7.5 | 0 | 216
__export__.project_task_2250_e248a477 | Fields Missing as an option in Menu | Sprint 2103 | 2021-01-11 | Bug Fix | Continuant: Power BI Integration (P30) | Kaesi Lee | Muzher Siddique | 0 | 0 |  | Difficulty 2 |  | Complete | Continuant | 5928 | 0 | 0 | 0 | 8
__export__.project_task_2155_ced412c1 | Sales Order: Customer Preview: Add Warehouse location on the customer preview | Sprint 2102 | 2021-01-04 | Development | Wild Leaf: Help (P22) | Kaesi Lee | Muzher Siddique | 0.75 | 100 |  |  |  | Complete | Wild Leaf Beverage | 6053 | 0.75 | 0 | 0 | 107.5689
__export__.project_task_2087_5ef66b52 | FW: You have been assigned to Deerfield Contacts Import (305) |  |  | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 1.25 | 0 |  |  |  | Complete | EquityTeam | 6190 | 0 | -4.83 | 0 | 142.7286
__export__.project_task_1853_83bda1da | create website draft | Sprint 2051 | 2020-12-14 | Development | Mid-America: Help (P37) | Levi Barnes | Danish Hassan | 6.25 | 78.12 |  | Website |  | Complete | Mid-America Gardens, LLC | 6724 | 8 | 1.75 | 0 | 108
SPriority
__export__.project_task_965_a3d7e44e | Buyers Update | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9637 | 0.5 | 0.5 | 75.3537 | 0
__export__.project_task_3311_a54eebdb | Mobile View "Print Product Labels" button to Transfers page | Sprint 2116 | 2021-04-12 | Development | Wild Leaf: Help (P22) | Jeff Gross | Muhammad Bilal | 5 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 3872 | 3 | -2 | 0 | 60
__export__.project_task_2605_624d63d0 | Create Page for API Settings (AV IQ) | Sprint 2107 | 2021-02-01 | Development | Continuant: Quotation Management / Automation (P31) | Nick Foy | Muzher Siddique | 2 | 80 |  |  |  | Complete | Continuant | 5548 | 2.5 | 0.5 | 24.103 | 198.4116
__export__.project_task_2371_dac97ff5 | propertyware api: add unit fields | Sprint 2107 | 2021-02-01 | Development | PWX: Property (P58) | Levi Barnes | Muzher Siddique | 4.33 | 96.22 |  |  |  | Complete | EquityTeam | 5757 | 4.5 | 0.17 | 0 | 254.3069
__export__.project_task_2353_3ca467b3 | Button Visibility | Sprint 2104 | 2021-01-18 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 1.17 | 100 |  |  |  | Complete | Cellpoint Corporation | 5766 | 1 | -0.17 | 5.9179e-05 | 73.592
__export__.project_task_2156_d053fd40 | CRM Warehouse Selection | Sprint 2102 | 2021-01-04 | Development | Wild Leaf: Help (P22) | Kaesi Lee | Muzher Siddique | 1.67 | 100 |  |  |  | Complete | Wild Leaf Beverage | 6053 | 1.6667 | -0.0033333 | 0 | 107.542
__export__.project_task_2032_b6c79012 | Remove the "CI Pattern Type" Field | Sprint 2052 | 2020-12-21 | Bug Fix | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 3.55 | 0 |  |  |  | Complete | EquityTeam | 6389 | 0 | -3.55 | 0 | 77.6793
__export__.project_task_1981_75396ff4 | Assign Product Pictures to Products | Sprint 2102 | 2021-01-04 | Configuration | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 1.67 | 55.67 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 3 | 1.33 | 0 | 218.9228
__export__.project_task_1847_30034dc8 | Module Upgrading issue | Sprint 2050 | 2020-12-07 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 3.75 | 100 |  |  |  | Complete | Cellpoint Corporation | 6726 | 3 | -0.75 | 0.15896 | 80.5351
__export__.project_task_963_ca7ec9d9 | Lot Updates | Sprint 28 | 2020-08-24 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9637 | 4 | 4 | 75.5572 | 0
__export__.project_task_3204_57ff95d8 | Show total count, total amount and delivery number on RFQ, Delivery order and Invoicing Slip | Sprint 2115 | 2021-04-05 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 18.55 | 100 |  |  | 2 | Complete | Mid-America Gardens, LLC | 4233 | 16 | -2.55 | 0 | 148.2317
__export__.project_task_2429_dda2cb64 | auto_close_order unit testing | Sprint 2107 | 2021-02-01 | Development | Continuant: Unit Testing (P51) | Nick Foy | Danish Hassan | 11.83 | 100 |  |  |  | Complete | Continuant | 5589 | 2.5 | -9.33 | 40 | 214.3025
__export__.project_task_2419_84258e47 | Create Invoice on Quotation Stage | Sprint 2107 | 2021-02-01 | Development | Wild Leaf: Help (P22) | Nick Foy | Danish Hassan | 12.87 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5592 | 3 | -9.87 | 40 | 214.3067
__export__.project_task_2351_4e759adc | Build function to auto-create a Project and Analytic Account for any new Building or Unit: new Unit property | Sprint 2104 | 2021-01-18 | Development | PWX: Field Service to Invoicing (P47) | Levi Barnes | Raheel Aslam | 4.33 | 100 |  |  |  | Complete | EquityTeam | 5773 | 3.8333 | -0.49667 | 0 | 79.6933
__export__.project_task_2026_fce79bcf | FW: John Walko not seeing tickets (#43) | Sprint 2052 | 2020-12-21 | Bug Fix | PWX: Help (P23) | Levi Barnes | Kaleem Khan | 2.08 | 100 |  |  |  | Complete | EquityTeam | 6414 | 1.5 | -0.58 | 0 | 86.2244
__export__.project_task_1726_e8cb219b | New Buyer Signup | Sprint 2050 | 2020-12-07 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 5.25 | 100 |  |  |  | Complete | Cellpoint Corporation | 6870 | 2 | -3.25 | 0 | 112.2202
__export__.project_task_960_ff234064 | Web Auctions Update | Sprint 27 | 2020-08-17 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9637 | 4 | 4 | 0 | 0
__export__.project_task_3200_25356306 | Wildleaf: Pallet Specification tab should appear on Manufacturing Order for all operations | Sprint 2114 | 2021-03-29 | Development | Wild Leaf: Help (P22) | Jeff Gross | Danish Hassan | 3.17 | 100 |  |  | 1 | Complete | Wild Leaf Beverage | 4280 | 1.6667 | -1.5033 | 0 | 160
__export__.project_task_2603_9ce5f589 | Handle the Transaction to Create Invoice and Payment in Odoo | Sprint 2107 | 2021-02-01 | Development | Wild Leaf: Helcim Integration (P38) | Nick Foy | Wajahat Ali | 8.5 | 85 |  |  |  | Complete | Wild Leaf Beverage | 5548 | 10 | 1.5 | 24.1638 | 198.468
__export__.project_task_2350_e836202c | Build function to auto-create a Project and Analytic Account for any new Building or Unit: new Building | Sprint 2104 | 2021-01-18 | Development | PWX: Field Service to Invoicing (P47) | Levi Barnes | Raheel Aslam | 3.33 | 100 |  |  |  | Complete | EquityTeam | 5773 | 2.8333 | -0.49667 | 0 | 79.7054
__export__.project_task_2174_818b358c | Create digital products for Deerfield donations (305) | Sprint 2102 | 2021-01-04 | Configuration | PWX: Help (P23) | Levi Barnes | Nick Foy | 0.5 | 100 |  |  |  | Complete | EquityTeam | 6020 | 0.5 | 0 | 0 | 98.9239
__export__.project_task_2104_93e28991 | elavon payment acquirer:Convert from V13 to V14 | Sprint 2104 | 2021-01-18 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 8.08 | 99.96 |  | Difficulty 3 |  | Complete | Mid-America Gardens, LLC | 6103 | 8.0833 | 0.0033333 | 2.5203e-05 | 155.2992
NF Review
__export__.project_task_1735_9cf70fdb | Check the email template for New tasks | Sprint 2051 | 2020-12-14 | Bug Fix | Silverdale: Help (P12) | Nick Foy | Fahad Hassan | 4 | 100 |  |  |  | Complete | Silverdale Technology LLC | 6867 | 3 | -1 | 0 | 140
__export__.project_task_1547_51b0dfea | Customer Invoice Portal: Online Payment |  |  | Development | Continuant: Customer Portal AR (P32) | Jeff Gross | Kaleem Khan | 2.67 | 100 |  |  |  | Complete | Continuant | 7559 | 2.5 | -0.17 | 696 | 712
__export__.project_task_1281_ce52cb5c | Release Plan:Sellers Profile | Sprint 32 | 2020-09-21 | Configuration | Cellpoint: Odoo Back-End (P8) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8573 | 0 | 0 | 0.016669 | 7.3606
__export__.project_task_3195_7e3fecc4 | Customizations on the Quotation/ Order Pdf and Customer preview | Sprint 2114 | 2021-03-29 | Development | Wild Leaf: Help (P22) | Jeff Gross | Danish Hassan | 3.75 | 93.75 |  |  | 1 | Complete | Wild Leaf Beverage | 4304 | 4 | 0.25 | 0 | 160
__export__.project_task_2436_a993b2c5 | payment_cash_on_delivery unit testing | Sprint 2107 | 2021-02-01 | Development | Continuant: Unit Testing (P51) | Nick Foy | Fahad Hassan | 14.92 | 100 |  |  |  | Complete | Continuant | 5589 | 6 | -8.92 | 40 | 214.2972
__export__.project_task_2349_d9665461 | Build function to auto-create a Project and Analytic Account for any new Building or Unit: add required field type to property tag | Sprint 2104 | 2021-01-18 | Studio | PWX: Field Service to Invoicing (P47) | Levi Barnes | Raheel Aslam | 2.25 | 100 |  |  |  | Complete | EquityTeam | 5773 | 1.5833 | -0.66667 | 0 | 79.7162
__export__.project_task_1980_8ee443b3 | Import Product Pictures | Sprint 2102 | 2021-01-04 | Configuration | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 4.17 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 2.1667 | -2.0033 | 14.4117 | 218.9133
__export__.project_task_1842_19525b77 | add scheduled Activity to chatter | Sprint 2051 | 2020-12-14 | Development | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 6.17 | 100 |  | SPriority |  | Complete | EquityTeam | 6740 | 6 | -0.17 | 0 | 116
__export__.project_task_1780_7e9fa441 | Auction Save & Confirm | Sprint 2102 | 2021-01-04 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 2.83 | 94.33 |  |  |  | Complete | Cellpoint Corporation | 6836 | 3 | 0.17 | 0 | 290.9214
__export__.project_task_1702_b87813f6 | Bid Category Missing | Sprint 2050 | 2020-12-07 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 13.42 | 100 |  |  |  | Complete | Cellpoint Corporation | 6895 | 13 | -0.42 | 0 | 121.3828
__export__.project_task_1271_4fbbf523 | Web Bids are not updating APPs | Sprint 31 | 2020-09-14 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8581 | 0 | 0 | 0 | 11.9229
__export__.project_task_3199_c60df58f | Addition of delivery date field on quotation/order pdf and customer preview | Sprint 2114 | 2021-03-29 | Development | Wild Leaf: Help (P22) | Jeff Gross | Kaleem Khan | 6.83 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4281 | 6 | -0.83 | 0 | 160
__export__.project_task_2604_229dcc2f | Handle Success and Failure | Sprint 2107 | 2021-02-01 | Development | Wild Leaf: Helcim Integration (P38) | Nick Foy | Wajahat Ali | 7.5 | 93.75 |  |  |  | Complete | Wild Leaf Beverage | 5548 | 8 | 0.5 | 24.1071 | 198.4085
__export__.project_task_2289_863b4f8b | Unconfirmed event attendees receiving Event: Reminder email: happened a 2nd time | Sprint 2104 | 2021-01-18 | Development | Heronswood: Events (P3) | Nick Foy | Muzher Siddique | 11.25 | 100 |  | Potential Silverdale App |  | Complete | Port Gamble Sâ€™Klallam Foundation | 5898 | 11.25 | 0 | 0 | 104
NF Review
MA Review
__export__.project_task_1969_640ce90e | Import Customer Primary Address | Sprint 2053 | 2020-12-28 | Configuration | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 6.17 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 4 | -2.17 | 14.4119 | 148
__export__.project_task_1906_311a8072 | Duplicate Lines in Transmitted data | Sprint 2102 | 2021-01-04 | Bug Fix | Continuant: Power BI Integration (P30) | Kaesi Lee | Kaleem Khan | 11.68 | 83.43 |  | SPriority |  | Complete | Continuant | 6551 | 14 | 2.32 | 0 | 184
__export__.project_task_1883_14b2da2f | CPBids Seller Account Marked as Invite Only | Sprint 2051 | 2020-12-14 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 6594 | 0 | 0 | 0 | 40
__export__.project_task_1859_fb288e43 | chatter default minimized: Message and activity content | Sprint 2051 | 2020-12-14 | Development | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 4.17 | 100 |  | SPriority |  | Complete | EquityTeam | 6700 | 4 | -0.17 | 0 | 100
__export__.project_task_1161_6cb4a0e5 | Turn Off Webkul Emails | Sprint 28 | 2020-08-24 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9199 | 0 | 0 | 0 | 0
__export__.project_task_3273_334263b9 | Pricelist on POS |  |  | Configuration | MMH: Help (P83) | Jeff Gross | Aleem khan | 23.83 | 100 |  |  | 4 | Complete | Mountain Meadow Herbs | 4060 | 5 | -18.83 | 0 | 104
__export__.project_task_2638_738ed203 | Change the 10x bid limit rule to 5x:On WEB | Sprint 2107 | 2021-02-01 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 4.67 | 100 |  |  |  | Complete | Cellpoint Corporation | 5427 | 4.5 | -0.17 | 0 | 174.2992
__export__.project_task_2231_8bebe05d | Record Views - Contacts>Units: Contacts & Addresses | Sprint 2104 | 2021-01-18 | Development | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 4.75 | 95 |  |  |  | Complete | EquityTeam | 5932 | 5 | 0.25 | 0 | 112.1304
__export__.project_task_1852_623110e0 | migrate contacts | Sprint 2051 | 2020-12-14 | Development | Mid-America: Help (P37) | Levi Barnes | Danish Hassan | 9.92 | 100 |  | SPriority |  | Complete | Mid-America Gardens, LLC | 6724 | 5 | -4.92 | 0 | 108
__export__.project_task_1796_3b44c980 | Add Lot Ref as the default in Search: | Sprint 2050 | 2020-12-07 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 2.17 | 0 |  |  |  | Complete | Cellpoint Corporation | 6836 | 0 | -2.17 | 0 | 8
__export__.project_task_1153_fdc3bfe7 | GFK Catalog Management Web Service: Add Product | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9218 | 0 | 0 | 0 | 0
__export__.project_task_961_fedd4812 | Seller Update | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9637 | 3 | 3 | 73.875 | 0
__export__.project_task_3333_1f9e73ce | Add a new state("Closed") in Sales order | Sprint 2117 | 2021-04-19 | Development | Wild Leaf: Help (P22) | Jeff Gross | Muhammad Bilal | 2.5 | 100 |  | Potential Silverdale App | 1 | Complete | Wild Leaf Beverage | 3749 | 1.75 | -0.75 | 0.01975 | 64.9914
__export__.project_task_2445_73b02f48 | shipping price by zone | Sprint 2107 | 2021-02-01 | Configuration | Mid-America: Help (P37) | Levi Barnes | Fahad Hussain Malik | 1.5 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 5568 | 0 | -1.5 | 0 | 189.8769
__export__.project_task_2040_faef20f4 | FW: Project selection not available on Timesheets Mobile app | Sprint 2053 | 2020-12-28 | Bug Fix | PWX: Help (P23) | Levi Barnes | Kaleem Khan | 3 | 0 |  |  |  | Complete | EquityTeam | 6381 | 0 | -3 | 0 | 116
__export__.project_task_579_9461791c | Setup Staging | Sprint 23 | 2020-07-20 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 10114 | 10 | 10 | 0 | 0
__export__.project_task_198_00a10564 | Unify Credentials | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10783 | 2 | 2 | 98.5701 | 0
__export__.project_task_3295_c2441927 | Discount in the invoices is not counting correctly | Sprint 2116 | 2021-04-12 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 16.58 | 100 |  |  | 4 | Complete | Mid-America Gardens, LLC | 3918 | 16 | -0.58 | 0 | 74.2755
__export__.project_task_2845_65db1c64 | New Buyer Signup automation:Auto assign all marketplaces on Android and IOS. | Sprint 2118 | 2021-04-26 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 10.25 | 100 |  |  | 3 | Complete | Cellpoint Corporation | 4687 | 6 | -4.25 | 0 | 338.6997
__export__.project_task_2661_b52b2f60 | Record Views - Contacts>Portfolios:Part2 | Sprint 2107 | 2021-02-01 | Development | PWX: Property (P58) | Levi Barnes | Raheel Aslam | 5.92 | 100 |  |  |  | Complete | EquityTeam | 5363 | 5.1667 | -0.75333 | 0 | 155.721
__export__.project_task_2230_5b02b4c1 | Record Views - Contacts>Units: Description Tab | Sprint 2104 | 2021-01-18 | Development | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 4.25 | 94.44 |  |  |  | Complete | EquityTeam | 5932 | 4.5 | 0.25 | 0 | 112.1402
__export__.project_task_1895_8a4fe3dc | migrate photos: automate photo download | Sprint 2102 | 2021-01-04 | Development | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 3.92 | 78.4 |  |  |  | Complete | Mid-America Gardens, LLC | 6579 | 5 | 1.08 | 0 | 143.965
__export__.project_task_1889_9843aafc | Fwd: error when trying to edit Studio in project task | Sprint 2051 | 2020-12-14 | Bug Fix | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 1.83 | 0 |  |  |  | Complete | EquityTeam | 6582 | 0 | -1.83 | 0.026727 | 77.8156
__export__.project_task_1263_d6918d97 | New registrations not entering Buyer username | Sprint 32 | 2020-09-21 | Bug Fix | Cellpoint: Odoo Back-End (P8) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8616 | 0 | 0 | 0 | 18.3861
__export__.project_task_976_bfce9f3b | Add Product Details Tab: Gallery | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9576 | 0 | 0 | 0 | 0
__export__.project_task_3293_88e64a7b | Notes on the sales order should be on the printed sales order slip | Sprint 2115 | 2021-04-05 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 2.92 | 100 |  |  | 1 | Complete | Mid-America Gardens, LLC | 3992 | 2.8333 | -0.086667 | 0 | 84
__export__.project_task_2293_761b04a1 | Create Working Hours Open on Task | Sprint 2104 | 2021-01-18 | Development | Silverdale: Help (P12) | Nick Foy | Muzher Siddique | 1.33 | 66.5 |  | Difficulty 1 |  | Complete | Silverdale Technology LLC | 5888 | 2 | 0.67 | 0 | 100
__export__.project_task_2108_0e94b640 | Belmont Azure Client Feedback | Sprint 2102 | 2021-01-04 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Fahad Hassan | 14.33 | 100 |  |  |  | Complete | Cellpoint Corporation | 6096 | 9 | -9.83 | 0 | 122.9308
__export__.project_task_2048_f3beaadc | FW: SITE DOWN, URGENT HELP NEEDED | Sprint 2053 | 2020-12-28 | Bug Fix | PWX: Help (P23) | Levi Barnes |  | 1 | 0 |  |  |  | Complete | EquityTeam | 6265 | 0 | -1 | 0 | 92
__export__.project_task_1238_93d181e2 | Email Sends from CPBids | Sprint 31 | 2020-09-14 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8716 | 0 | 0 | 24 | 36
__export__.project_task_300_f811e452 | Tax: Test Avalara Functionality | Sprint 24 | 2020-07-27 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 10247 | 0 | 0 | 56 | 0
__export__.project_task_3291_015a6708 | Deployment Friday: Mid-America | Sprint 2115 | 2021-04-05 | Configuration | Mid-America: Help (P37) | Levi Barnes | Wajahat Ali | 2.92 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 3994 | 0 | -2.92 | 0.111 | 84.6488
__export__.project_task_2141_12bd0686 | Default link is set, should be blank | Sprint 2102 | 2021-01-04 | Bug Fix | Silverdale: Help (P12) | Nick Foy | Muzher Siddique | 0.42 | 84 |  |  |  | Complete | Silverdale Technology LLC | 6070 | 0.5 | 0.08 | 0 | 114.93
__export__.project_task_1824_21841411 | Google Calendar sync:not working correctly | Sprint 2050 | 2020-12-07 | Bug Fix | PWX: Help (P23) | Levi Barnes | Danish Hassan | 3 | 100 |  |  |  | Complete | EquityTeam | 6755 | 2 | -1 | 0 | 92.9068
__export__.project_task_1065_108a5d9f | Get Catalog Data: Bypass Save | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9575 | 0 | 0 | 0 | 0
__export__.project_task_1038_ba6c3da4 | Seller Permissions Group: Remove Conversations | Sprint 28 | 2020-08-24 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 52 | 0
__export__.project_task_3287_aecaceb5 | Printed sales order slip must have delivery order number | Sprint 2115 | 2021-04-05 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 1.67 | 66.8 |  |  | 2 | Complete | Mid-America Gardens, LLC | 4016 | 2.5 | 0.83 | 0 | 92
__export__.project_task_2084_2bee15c0 | FW: You have been assigned to Online meeting with Daniel Reminder (#50) | Sprint 2102 | 2021-01-04 | Bug Fix | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 4.58 | 100 |  |  |  | Complete | EquityTeam | 6190 | 3.8333 | -0.74667 | 0 | 138.9108
__export__.project_task_2050_7e3eb762 | Email Set-Up: Wildleaf outbound email issue | Sprint 2053 | 2020-12-28 | Bug Fix | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 3.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6261 | 0 | -3.25 | 0 | 92
__export__.project_task_962_8c3b0c72 | Seller Dashboard Layout | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9637 | 4 | 4 | 73.8586 | 0
__export__.project_task_952_86ec10cc | Integration GFK Catalog: Import Product Name | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9697 | 0 | 0 | 0 | 0
__export__.project_task_3285_10d165ba | FW: Chart of Accounts auto creation from bank | Sprint 2115 | 2021-04-05 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Fahad Hassan | 5.03 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4017 | 2.5 | -2.53 | 0 | 92
__export__.project_task_2161_2c60ce95 | FW: Error when trying to add Contact | Sprint 2102 | 2021-01-04 | Bug Fix | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 2.83 | 100 |  |  |  | Complete | EquityTeam | 6048 | 2.6667 | -0.16333 | 0 | 106.9106
__export__.project_task_2065_2e54b653 | Install Project Default Stages module | Sprint 2053 | 2020-12-28 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Muzher Siddique | 1.02 | 100 |  |  |  | Complete | Wild Leaf Beverage | 6220 | 1 | -0.02 | 0 | 76
__export__.project_task_1795_e53f65d7 | Can we deploy List View Manager on CPBids? | Sprint 2050 | 2020-12-07 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Fahad Hassan | 3.67 | 0 |  |  |  | Complete | Cellpoint Corporation | 6836 | 0 | -15 | 0 | 102.5581
__export__.project_task_971_d77064d1 | Default Product Tax Code | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9605 | 0 | 0 | 0 | 0
__export__.project_task_964_1ce06955 | Create Auction Update | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9637 | 3 | 3 | 73.6047 | 0
__export__.project_task_3281_2da43af7 | On Mobile App view for Products, add a "Print Label" button | Sprint 2115 | 2021-04-05 | Development | Wild Leaf: Help (P22) | Jeff Gross | Danish Hassan | 3 | 100 |  |  | 1 | Complete | Wild Leaf Beverage | 4019 | 2 | -1 | 0 | 93.6037
__export__.project_task_2660_2aeb924e | Record Views - Contacts>Portfolios: Part1 | Sprint 2107 | 2021-02-01 | Development | PWX: Property (P58) | Levi Barnes | Raheel Aslam | 5.08 | 78.15 |  |  |  | Complete | EquityTeam | 5363 | 6.5 | 1.42 | 0 | 155.753
__export__.project_task_2074_361f2940 | Change default to NOT show time on new projects | Sprint 2053 | 2020-12-28 | Development | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 2.62 | 0 |  |  |  | Complete | Silverdale Technology LLC | 6212 | 0 | -2.62 | 0 | 76
__export__.project_task_1983_1d22c393 | Create a field in Project > Task for "Reference #" | Sprint 2051 | 2020-12-14 | Development | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 0.52 | 52 |  |  |  | Complete | EquityTeam | 6509 | 1 | 0.48 | 0 | 52.4002
__export__.project_task_1779_e34a1467 | Save and Create Single Action | Sprint 2102 | 2021-01-04 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 4.08 | 100 |  |  |  | Complete | Cellpoint Corporation | 6836 | 3 | -1.08 | 0 | 290.9103
__export__.project_task_1066_b09641a0 | New Product Bug | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9575 | 0 | 0 | 0 | 0
__export__.project_task_3279_065c9efc | Widlleaf: Make the "Hold Delivery Until Payment" read only except for Accounting Users | Sprint 2115 | 2021-04-05 | Development | Wild Leaf: Help (P22) | Jeff Gross | Osama Khalid | 4.67 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4019 | 4 | -0.67 | 0 | 93.7165
__export__.project_task_1900_eea3d262 | FW: modify ci survey options to chose from (#12) | Sprint 2051 | 2020-12-14 | Bug Fix | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 1 | 0 |  | Post-Deployment Issue |  | Complete | EquityTeam | 6558 | 0 | -1 | 0 | 70.2586
__export__.project_task_1896_18ffbd6a | CPBids to Azure Alternative | Sprint 2053 | 2020-12-28 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Fahad Hassan | 15.17 | 100 |  | SPriority |  | Complete | Cellpoint Corporation | 6578 | 14 | -19.67 | 0 | 84.2186
__export__.project_task_953_5459e6c4 | Integration GFK Catalog: Import Manufacturer | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9697 | 0 | 0 | 0 | 0
__export__.project_task_3256_108c1b5b | Wildleaf: Group Action "Confirm" for assets | Sprint 2115 | 2021-04-05 | Development | Wild Leaf: Help (P22) | Jeff Gross | Osama Khalid | 2.08 | 52 |  |  | 1 | Complete | Wild Leaf Beverage | 4089 | 4 | 1.92 | 0 | 116
__export__.project_task_3000_070003cf | Personality Survey -> Personality | Sprint 2117 | 2021-04-19 | Development | PWX: Survey (P70) | Levi Barnes | Wajahat Ali | 11.25 | 100 |  |  | 2 | Complete | EquityTeam | 4428 | 4.5 | -6.75 | 0 | 286.4126
__export__.project_task_2622_b3d7f0d1 | CPbids Support | Sprint 2107 | 2021-02-01 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 1.83 | 22.88 |  |  |  | Complete | Cellpoint Corporation | 5500 | 8 | 6.17 | 0.015079 | 27.2223
__export__.project_task_2389_114f3ab5 | Change the 10x bid limit rule to 5x |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 0.5 | 0 |  |  |  | Complete | Cellpoint Corporation | 5732 | 0 | -8.01 | 0 | 311.4564
__export__.project_task_2159_7130082e | Deploy the module | Sprint 2102 | 2021-01-04 | Configuration | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 0.42 | 84 |  |  |  | Complete | EquityTeam | 6052 | 0.5 | 0.08 | 0 | 0.20266
__export__.project_task_2138_d800ece7 | Create Analytic Accounts for each Unit and Building | Sprint 2102 | 2021-01-04 | Configuration | PWX: Field Service to Invoicing (P47) | Levi Barnes | Nick Foy | 0.67 | 67 |  |  |  | Complete | EquityTeam | 6071 | 1 | 0.33 | 0 | 114.9097
__export__.project_task_1903_8ec6e188 | Email Template Title incorrect | Sprint 2051 | 2020-12-14 | Bug Fix | Silverdale: Help (P12) | Nick Foy | Muzher Siddique | 0.63 | 0 |  |  |  | Complete | Silverdale Technology LLC | 6556 | 0 | -0.63 | 0 | 68
__export__.project_task_1744_55c2b8d5 | Online Payments for Wild Leaf: Connect to Helcim API | Sprint 2053 | 2020-12-28 | Development | Wild Leaf: Helcim Integration (P38) | Kaesi Lee | Fahad Hassan | 14.92 | 100 |  |  |  | Complete | Wild Leaf Beverage | 6844 | 6 | -8.92 | 0 | 168
__export__.project_task_1067_1339909d | Product Details Page: Remove Pricing | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9575 | 0 | 0 | 0 | 0
__export__.project_task_3251_b6b4414e | WildLeaf: New status "Signed" for sales order signed by customer | Sprint 2115 | 2021-04-05 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Danish Hassan | 3.5 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4154 | 3.5 | 0 | 0 | 120
__export__.project_task_1909_52baf7d0 | CI Survey: update in Recruiting to correct order | Sprint 2051 | 2020-12-14 | Bug Fix | PWX: Help (P23) | Levi Barnes | Danish Hassan | 1.42 | 0 |  | Post-Deployment Issue |  | Complete | EquityTeam | 6525 | 0 | -1.42 | 0 | 60
__export__.project_task_1849_53556b7a | Add the option to remove time tracking on Portal by Project | Sprint 2053 | 2020-12-28 | Development | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 4.33 | 100 |  |  |  | Complete | Silverdale Technology LLC | 6725 | 4 | -2.95 | 0 | 196.4582
__export__.project_task_1443_7a664ba9 | Data migration from AWS to Odoo:Bids | Sprint 2047 | 2020-11-16 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Raheel Aslam | 61 | 0 |  |  |  | Complete | Cellpoint Corporation | 7997 | 0 | -61 | 0 | 199.1958
__export__.project_task_1069_1a22099d | Product Details Page: Remove Warranty | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9558 | 0 | 0 | 0 | 0
__export__.project_task_3234_fd557662 | WIldleaf: Default Bank configuration on Receipts/Payments | Sprint 2114 | 2021-03-29 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Danish Hassan | 5.42 | 100 |  |  | 1 | Complete | Wild Leaf Beverage | 4183 | 3.5 | -1.92 | 0 | 130.7834
__export__.project_task_2070_17688490 | Replenishment Location mismatch | Sprint 2053 | 2020-12-28 | Bug Fix | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 3.17 | 79.25 |  |  |  | Complete | Wild Leaf Beverage | 6218 | 4 | 0.83 | 0 | 16
__export__.project_task_1738_831b5a41 | user role error | Sprint 2050 | 2020-12-07 | Bug Fix | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 11.83 | 0 |  |  |  | Complete | EquityTeam | 6867 | 0 | -11.83 | 0 | 110.5622
__export__.project_task_1430_255e887a | Web Enabled Bidding: 500: Internal Server Error | Sprint 2044 | 2020-10-26 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 5 | 0 |  |  |  | Complete | Cellpoint Corporation | 8020 | 0 | -5 | 0 | 70.4391
__export__.project_task_967_661fd317 | Shop: Remove Pricing | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9625 | 0 | 0 | 0 | 0
__export__.project_task_3219_cd27f9e9 | Wildleaf: Odoo should directly create the barcode if not exist in the system for packs | Sprint 2114 | 2021-03-29 | Development | Wild Leaf: Help (P22) | Jeff Gross | Fahad Hassan | 16.83 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4208 | 14 | -2.83 | 0 | 139.9093
__export__.project_task_2067_9408d2bc | Belmont User can see too many modules | Sprint 2053 | 2020-12-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 2.08 | 0 |  | P1 |  | Complete | Cellpoint Corporation | 6219 | 0 | -2.08 | 0 | 36.6719
__export__.project_task_1739_883db6a4 | Timesheet error | Sprint 2050 | 2020-12-07 | Bug Fix | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 7.63 | 95.38 |  |  |  | Complete | EquityTeam | 6863 | 8 | 0.37 | 0 | 110.5681
__export__.project_task_968_7e5197d5 | Correct Duplicate Photo Bug | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9624 | 0 | 0 | 0 | 0
__export__.project_task_3217_7255d151 | Wildleaf: Mandatory Lot number on work orders on MO | Sprint 2114 | 2021-03-29 | Development | Wild Leaf: Help (P22) | Jeff Gross | Osama Khalid | 3.05 | 76.25 |  |  | 1 | Complete | Wild Leaf Beverage | 4209 | 4 | 0.95 | 0 | 140
__export__.project_task_2056_ae36e4e6 | Scoping and Requirements | Sprint 2102 | 2021-01-04 | Configuration | PWX: Field Service to Invoicing (P47) | Levi Barnes |  | 1 | 100 |  |  |  | Complete | EquityTeam | 6236 | 1 | 0 | 0 | 56
__export__.project_task_2052_a66d6fd3 | CPBids to Azure Alternative: Transfer Data From Excel Files | Sprint 2053 | 2020-12-28 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Fahad Hassan | 18.5 | 0 |  |  |  | Complete | Cellpoint Corporation | 6249 | 0 | -18.5 | 0 | 26.103
__export__.project_task_1836_43b3fcb1 | employee card error | Sprint 2050 | 2020-12-07 | Bug Fix | PWX: Help (P23) | Levi Barnes |  | 0.5 | 0 |  |  |  | Complete | EquityTeam | 6747 | 0 | -0.5 | 0 | 86.5861
__export__.project_task_1412_482e77e1 | Soonest closing auctions should be on top | Sprint 2042 | 2020-10-12 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 8 | 0 |  |  |  | Complete | Cellpoint Corporation | 8094 | 0 | -8 | 0 | 32.1731
__export__.project_task_1126_aea2ea9b | Integration GFK Catalog: Pull Synnex Product ID from GFK | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9415 | 0 | 0 | 0 | 0
__export__.project_task_3216_bab22f58 | Wildleaf: Modification of Terms and conditions field nature | Sprint 2114 | 2021-03-29 | Development | Wild Leaf: Help (P22) | Jeff Gross | Osama Khalid | 10.33 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4209 | 2 | -8.33 | 0 | 140
__export__.project_task_1835_28b66ac5 | CPBids Transition 2053 | Sprint 2053 | 2020-12-28 | Configuration | Cellpoint CPBids: Help (P7) | Muzher Siddique | Wajahat Ali | 1 | 0 |  |  |  | Complete | Cellpoint Corporation | 6748 | 0 | -1 | 0 | 108.7554
__export__.project_task_1701_0895a426 | google oauth | Sprint 2050 | 2020-12-07 | Bug Fix | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 2 | 0 |  |  |  | Complete | EquityTeam | 6900 | 0 | -2 | 0 | 125.3919
__export__.project_task_1345_544ff1b6 | Banner notificationsÂ | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8398 | 0 | 0 | 0 | 59.8783
__export__.project_task_339_511c4b4e | Carrier: set-up sending of tracking info to customers | Sprint 32 | 2020-09-21 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 417.7145 | 417.7145
__export__.project_task_3208_4af469fc | Add Correct Count on Invoice and Report | Sprint 2114 | 2021-03-29 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 3.83 | 99.91 |  |  | 2 | Complete | Mid-America Gardens, LLC | 4233 | 3.8333 | 0.0033333 | 0 | 148
__export__.project_task_1733_1541ec31 | FW: Odoo Error Message | Sprint 2049 | 2020-11-30 | Bug Fix | PWX: Help (P23) | Levi Barnes | Fahad Hassan | 2.5 | 0 |  |  |  | Complete | EquityTeam | 6868 | 0 | -2.5 | 0.023655 | 24.1212
__export__.project_task_1312_a60c78bf | Change Increment to simple field | Sprint 2041 | 2020-10-05 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8431 | 40 | 40 | 0.072205 | 86.7119
__export__.project_task_955_7e8fd8f3 | Product Details: Check Availability | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9696 | 0 | 0 | 0 | 0
__export__.project_task_3203_2f38a733 | Wildleaf: Pallet build specs and manufacturing notes on MO PDF | Sprint 2114 | 2021-03-29 | Development | Wild Leaf: Help (P22) | Jeff Gross | Fahad Hassan | 4.58 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4234 | 3.1667 | -1.4133 | 0 | 148.5607
__export__.project_task_1686_c4b693e2 | chatter bug | Sprint 2049 | 2020-11-30 | Bug Fix | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 2.92 | 100 |  |  |  | Complete | EquityTeam | 6916 | 2.9167 | -0.0033333 | 0 | 40.1062
__export__.project_task_3037_409e034a | Missing lot description on web | Sprint 2115 | 2021-04-05 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 4.5 | 100 |  |  | 2 | Complete | Cellpoint Corporation | 4372 | 3 | -1.5 | 1.8428e-05 | 176.3239
__export__.project_task_1306_cd1863c5 | Cannot move Buyers to Invited Status | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8446 | 0 | 0 | 0 | 6.4281
__export__.project_task_1732_1043b9c5 | Tax cloud error | Sprint 2050 | 2020-12-07 | Bug Fix | Moln: Help (P16) | Levi Barnes | Fahad Hassan | 7 | 0 |  |  |  | Complete | Moln Solutions, LLC | 6869 | 0 | -7 | 0 | 111.4198
__export__.project_task_1245_46ab8067 | Gucci website: user cannot change shipping address | Sprint 2041 | 2020-10-05 | Development | Moln: Help (P16) | Muhammad Afzaal | Gadha Continuant | 5 | 31.25 |  | Website |  | Complete | Moln Solutions, LLC | 8694 | 16 | 11 | 81.7733 | 121.7733
__export__.project_task_1586_798d241e | URGENT: Why are invite emails saying ***TEST ORDER DO NOT SHIP*** ? | Sprint 2046 | 2020-11-09 | Bug Fix | Moln: Help (P16) | Kaesi Lee | Fahad Hassan | 2.42 | 0 |  |  |  | Complete | Moln Solutions, LLC | 7415 | 0 | -2.42 | 24 | 71.2058
__export__.project_task_581_d99a9565 | BGIUM: Notification Record Issue | Sprint 24 | 2020-07-27 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10109 | 0 | 0 | 37.7343 | 0
__export__.project_task_180_44a4d108 | Winner Status in Admin and Seller Portal | Sprint 28 | 2020-08-24 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10809 | 0 | 0 | 0 | 0
__export__.project_task_1484_72bf8f6d | iOS: Auction Extensions Not Visible | Sprint 2045 | 2020-11-02 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 0 | 0 |  | P0 |  | Complete | Cellpoint Corporation | 7899 | 0 | 0 | 0 | 144
__export__.project_task_1481_54ca1070 | Remove CPBids Marketplace from Web Bidding | Sprint 2044 | 2020-10-26 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 7910 | 2 | 2 | 0 | 38.2058
__export__.project_task_1419_4d62d0be | Web Enabled Bidding: Time Remaining Display Issue | Sprint 2042 | 2020-10-12 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Deepak Krishnan | 8 | 0 |  |  |  | Complete | Cellpoint Corporation | 8070 | 0 | -8 | 0 | 24.0316
__export__.project_task_1380_87c10144 | Auctions Visible Before Start Time | Sprint 2041 | 2020-10-05 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 6 | 0 |  |  |  | Complete | Cellpoint Corporation | 8256 | 0 | -6 | 0 | 40
__export__.project_task_1301_3ac8f01b | Cannot email @qq.com | Sprint 2043 | 2020-10-19 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8453 | 0 | 0 | 72.2528 | 136.4881
__export__.project_task_1194_39324949 | override product title | Sprint 32 | 2020-09-21 | Configuration | Moln: Help (P16) | Muhammad Afzaal |  | 18 | 100 |  | eCommerce |  | Complete | Moln Solutions, LLC | 8880 | 4 | -14 | 48 | 168
Inventory
__export__.project_task_1487_8bb5dbf2 | Non-Belmont Approved Buyers can see and bid on Belmont lots | Sprint 2043 | 2020-10-19 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Security |  | Complete | Cellpoint Corporation | 7894 | 0 | 0 | 0 | 24
__export__.project_task_1408_bf8dc1ef | Buyers cannot register through the app | Sprint 2041 | 2020-10-05 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8108 | 0 | 0 | 0 | 32
__export__.project_task_1383_ee664108 | sell bv case on following products | Sprint 33 | 2020-09-28 | Configuration | Moln: Help (P16) | Nick Foy |  | 5 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8253 | 0 | -5 | 0 | 16
__export__.project_task_1154_9930e94a | Move from Odoo Cloud to Odoo.sh | Sprint 30 | 2020-09-07 | Development | Moln: Help (P16) | Muhammad Afzaal |  | 5.5 | 68.75 |  |  |  | Complete | Moln Solutions, LLC | 9215 | 8 | 2.5 | 24 | 0
__export__.project_task_1353_908e3f08 | Notifications Display Error | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8381 | 0 | 0 | 0 | 13.6085
__export__.project_task_1196_b88d021a | login required landing page for gucci | Sprint 33 | 2020-09-28 | Configuration | Moln: Help (P16) | Gadha Continuant |  | 18.25 | 45.62 |  | Website |  | Complete | Moln Solutions, LLC | 8857 | 40 | 21.75 | 94.9325 | 142.3442
__export__.project_task_182_923e4a77 | 2 New Sellers | Sprint 22 | 2020-07-12 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10809 | 0 | 0 | 0 | 0
__export__.project_task_1864_482b7181 | gucci - unable to place orders - neverending loop | Sprint 2050 | 2020-12-07 | Bug Fix | Moln: Help (P16) | Levi Barnes | Muzher Siddique | 0.33 | 0 |  |  |  | Complete | Moln Solutions, LLC | 6676 | 0 | -0.33 | 0.032154 | 62.7672
__export__.project_task_958_dd426655 | Select All Buyers Error Message | Sprint 26 | 2020-08-10 | Bug Fix | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9694 | 0 | 0 | 0 | 0
__export__.project_task_1696_b86d4031 | Inventory Import - Production | Sprint 2049 | 2020-11-30 | Development | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 4 | 100 |  |  |  | Complete | Wild Leaf Beverage | 6913 | 4 | 0 | 0 | 39.8842
__export__.project_task_1385_880cb990 | Website Product Variant - remove module | Sprint 33 | 2020-09-28 | Bug Fix | Moln: Help (P16) | Muhammad Afzaal |  | 2 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8239 | 0 | -2 | 0.4411 | 18.1244
__export__.project_task_1806_4a0dba01 | Inventory Import - Production (2nd File) | Sprint 2050 | 2020-12-07 | Development | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 2 | 100 |  |  |  | Complete | Wild Leaf Beverage | 6770 | 2 | 0 | 0 | 94.5861
__export__.project_task_181_5905278c | Auto Refresh | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10809 | 0 | 0 | 103.8814 | 0
__export__.project_task_1805_0210d079 | Default Public Price based on Category | Sprint 2050 | 2020-12-07 | Development | Wild Leaf: Help (P22) | Kaesi Lee | Danish Hassan | 8.5 | 100 |  |  |  | Complete | Wild Leaf Beverage | 6772 | 8 | -0.5 | 0 | 94.5861
__export__.project_task_1264_0cfd4df4 | CPBids App Outage Sep 21 | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8609 | 0 | 0 | 9.3442 | 32
__export__.project_task_1406_9e127d59 | Incoming emails not working | Sprint 2041 | 2020-10-05 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8118 | 0 | 0 | 0.52812 | 16.1126
__export__.project_task_1291_64d6c399 | User cannot see Belmont lots | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Nick Foy |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8492 | 0 | 0 | 0 | 2.7308
__export__.project_task_1727_5396cd32 | Cloud to SH migration | Sprint 2049 | 2020-11-30 | Configuration | Heronswood: Events (P3) | Nick Foy | Danish Hassan | 2.67 | 100 |  | Odoo.sh Migration |  | Complete | Port Gamble Sâ€™Klallam Foundation | 6870 | 2 | -0.67 | 0 | 25.5117
__export__.project_task_1265_ca2584f5 | Hold Non-Electronic Payment Orders | Sprint 2043 | 2020-10-19 | Development | Moln: Help (P16) | Muhammad Afzaal | Gadha Continuant | 13 | 54.17 |  | Inventory |  | Complete | Moln Solutions, LLC | 8592 | 24 | 11 | 102.7911 | 208.6517
Sales
Invoicing
__export__.project_task_1670_89045483 | Scheduled Action:2049 | Sprint 2049 | 2020-11-30 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Raheel Aslam | 17.08 | 100 |  | 3.0.5 |  | Complete | Cellpoint Corporation | 7011 | 11.4167 | -5.6633 | 0 | 55.8803
__export__.project_task_1247_64c382d2 | website content updates | Sprint 2043 | 2020-10-19 | Configuration | Moln: Help (P16) | Kaesi Lee | Anusha | 9.75 | 0 |  | Website |  | Complete | Moln Solutions, LLC | 8692 | 0 | -9.75 | 125.8642 | 175.9747
__export__.project_task_1674_0a391c96 | Auction Relist Original End Time Error | Sprint 2049 | 2020-11-30 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 6942 | 0 | 0 | 0 | 49.9157
__export__.project_task_1477_1af2c3d7 | Bids not accepted even though higher than current highest bid | Sprint 2046 | 2020-11-09 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 174.5 | 0 |  | P0 |  | Complete | Cellpoint Corporation | 7939 | 0 | -174.5 | 0 | 200
__export__.project_task_1442_ffe800f2 | Data migration from AWS to Odoo: Manifests | Sprint 2047 | 2020-11-16 | Configuration | Cellpoint CPBids: Help (P7) | Kaesi Lee | Kaleem Khan | 15 | 0 |  |  |  | Complete | Cellpoint Corporation | 7997 | 0 | -15 | 0 | 246.9231
__export__.project_task_1257_743d8258 | Variant visibility by website (required for Gucci) | Sprint 33 | 2020-09-28 | Development | Moln: Help (P16) | Gadha Continuant |  | 20 | 83.33 |  | Website |  | Complete | Moln Solutions, LLC | 8667 | 24 | 4 | 23.165 | 102.2553
eCommerce
__export__.project_task_966_a2d941a7 | Test Lot Showing to buyers | Sprint 26 | 2020-08-10 | Bug Fix | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9637 | 0 | 0 | 0 | 0
__export__.project_task_1409_f181d54e | New registration email confirmation - no link | Sprint 2041 | 2020-10-05 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8108 | 0 | 0 | 0 | 8
__export__.project_task_1368_660aa4c4 | taxes not being charged to authorize.net | Sprint 2044 | 2020-10-26 | Development | Moln: Help (P16) | Nick Foy | Anusha | 38 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8307 | 0 | -38 | 8 | 142.8586
__export__.project_task_1300_d693ff65 | Invite emails being sent | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8454 | 0 | 0 | 0.033098 | 1.6331
__export__.project_task_1298_d3a35e5c | New buyer registrations - name is incorrect | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8469 | 0 | 0 | 0 | 46.5333
__export__.project_task_269_7b6d9e7b | Auto Update - Delayed | Sprint 22 | 2020-07-12 | Bug Fix | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10262 | 0 | 0 | 0 | 0
__export__.project_task_1659_483ce9cc | Migrate Dialed Supply to Odoo.sh: Sub-Task | Sprint 2049 | 2020-11-30 | Configuration | Dialed Supply: Help (P21) | Levi Barnes | Danish Hassan | 2.67 | 89 |  |  |  | Complete | Dialed Supply | 7065 | 3 | 0.33 | 0 | 76.0365
__export__.project_task_1530_de540f81 | gucci checkout process not working as per requirements | Sprint 2045 | 2020-11-02 | Bug Fix | Moln: Help (P16) | Kaesi Lee | Muzher Siddique | 1 | 0 |  | Website |  | Complete | Moln Solutions, LLC | 7587 | 0 | -1 | 0 | 32
__export__.project_task_1299_a155d786 | Missing AWS Buyers | Sprint 33 | 2020-09-28 | Configuration | Cellpoint CPBids: Help (P7) | Roshan Mecoth |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8460 | 0 | 0 | 0 | 43.0082
__export__.project_task_1201_b175850e | Forefront landing page | Sprint 31 | 2020-09-14 | Configuration | Moln: Help (P16) | Kaesi Lee |  | 1 | 100 |  |  |  | Complete | Moln Solutions, LLC | 8833 | 1 | 0 | 8 | 0
__export__.project_task_1491_094b05bf | Incorrect Notifications and Win/Lose Status on Auctions | Sprint 2046 | 2020-11-09 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 0 | 100 |  | P1 |  | Complete | Cellpoint Corporation | 7878 | 5 | -4.5 | 0.144 | 177.7704
__export__.project_task_1303_2b53ede6 | Data migration from AWS to Odoo |  |  | Configuration | Cellpoint CPBids: Help (P7) | Kaesi Lee | Faizan Zia Malik | 11 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8452 | 0 | -87 | 0 | 358.997
P1
__export__.project_task_1144_20e7b4cc | integrate with 3PL warehouse - Part 2/3 | Sprint 2043 | 2020-10-19 | Development | Moln: Help (P16) | Kaesi Lee | Gadha Continuant | 39.5 | 0 |  | API |  | Complete | Moln Solutions, LLC | 9240 | 0 | -39.5 | 272 | 360.6667
Inventory
Sales
__export__.project_task_1420_1f089ac0 | Auction Form View: Relist and Duplicate Actions Unavailable to Sellers | Sprint 2045 | 2020-11-02 | Bug Fix | Cellpoint CPBids: Help (P7) | Kaesi Lee | Gadha Continuant | 11 | 0 |  |  |  | Complete | Cellpoint Corporation | 8068 | 0 | -11 | 93.439 | 135.1684
__export__.project_task_1388_a330e7d8 | Gucci: Landing page after checkout | Sprint 33 | 2020-09-28 | Bug Fix | Moln: Help (P16) | Muhammad Afzaal | Gadha Continuant | 1 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8229 | 0 | -1 | 0 | 16
__export__.project_task_1343_71bd8d8e | Auto Refresh is not working for detail view as well | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8398 | 0 | 0 | 0 | 22.5511
__export__.project_task_1338_d9c89f5b | Dashboard for monitoring CPbids | Sprint 2043 | 2020-10-19 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8398 | 0 | 0 | 0 | 110.2586
__export__.project_task_1588_1cc4f873 | error message when loading products on aao.drprotect.com | Sprint 2046 | 2020-11-09 | Bug Fix | Moln: Help (P16) | Levi Barnes | Muzher Siddique | 4.5 | 0 |  |  |  | Complete | Moln Solutions, LLC | 7412 | 0 | -4.5 | 48 | 72
__export__.project_task_1361_918cf3cd | in stock notification appearing twice | Sprint 2041 | 2020-10-05 | Development | Moln: Help (P16) | Nick Foy | Gadha Continuant | 5 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8354 | 0 | -5 | 12.0344 | 40
__export__.project_task_228_c8ab9525 | Duplicate List for Buyer name | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10589 | 0 | 0 | 44.6991 | 0
__export__.project_task_1743_50cd1394 | Online Payments for Wild Leaf: Research Helcim API | Sprint 2052 | 2020-12-21 | Development | Wild Leaf: Helcim Integration (P38) | Kaesi Lee | Fahad Hassan | 11.33 | 100 |  |  |  | Complete | Wild Leaf Beverage | 6845 | 5 | -6.33 | 0 | 125.2517
__export__.project_task_1377_7751fb3a | integrate with 3PL warehouse Part 1 | Sprint 2043 | 2020-10-19 | Development | Moln: Help (P16) | Kaesi Lee | Gadha Continuant | 12 | 0 |  | API |  | Complete | Moln Solutions, LLC | 8263 | 0 | -12 | 25.5102 | 131.4816
Inventory
Sales
__export__.project_task_1423_2e5dc3ef | gucci invitation email ready to be sent | Sprint 2041 | 2020-10-05 | Configuration | Moln: Help (P16) | Nick Foy | Gadha Continuant | 10 | 0 |  | Email Configuration |  | Complete | Moln Solutions, LLC | 8062 | 0 | -10 | 0 | 144
__export__.project_task_1292_4f7ac1ca | CPBids User Cannot Grant Portal Access | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Roshan Mecoth |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8477 | 0 | 0 | 1.3583 | 2.1119
__export__.project_task_1237_5223f9d1 | Odoo Audit | Sprint 32 | 2020-09-21 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 2.5 | 62.5 |  |  |  | Complete | Wild Leaf Beverage | 8716 | 4 | 1.5 | 22.8843 | 48.3312
__export__.project_task_1261_b259e751 | orders placed on drprotect.com is routing to weshield.us | Sprint 32 | 2020-09-21 | Bug Fix | Moln: Help (P16) | Kaesi Lee |  | 2 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8660 | 0 | -2 | 23.0678 | 40
__export__.project_task_1294_e43b2b12 | Manifest emails not being received | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Roshan Mecoth |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8472 | 0 | 0 | 1.1411 | 1.3244
__export__.project_task_4916_38a58c52 | show Delivery contact name, phone number and email address | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 | Follow Up | 2016-09-01 |  | Backlog | Zuma Sales LLC | 51 | 1 | 1 | 0 | 0
Fahad
__export__.project_task_4915_de6d4fac | Setup Tax Cloud Category for Products | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0.5 | 100 |  | 2014-09-01 |  | Complete | Zuma Sales LLC | 51 | 0.5 | 0 | 0 | 9.5759
Asfand
__export__.project_task_4898_37b47db7 | Install URL module for T&Cs on SOs layout | Sprint 2138 | 2021-09-13 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Muzher Siddique | 1.92 | 96 | This task missed the deadline! | 2015-09-01 | 1 | Integrated Testing | Zuma Sales LLC | 69 | 2 | 0.08 | 0 | 0
Your task missed the deadline!
Integrated Testing
Fahad
__export__.project_task_4882_428a1ec6 | Create demo for different Ship to and billed to use cases | Sprint 2138 | 2021-09-13 | Demo to the client | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 125 | 1 | 1 | 4.3267e-05 | 18.925
__export__.project_task_4861_2cbbb37a | Estimate Continuant Database Upgradation |  |  | Development | Continuant: Update Odoo to V14/15 (P211) | Fahad Hussain Malik | Muzher Siddique | 2.17 | 100 | PM Review this task | 2015-09-01 |  | PM Review | Continuant | 147 | 2.1667 | -0.0033333 | 0 | 0
__export__.project_task_4858_51bdcfb2 | Configure Email Templates | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0.83 | 41.5 |  | 2014-09-01 |  | ELS | Zuma Sales LLC | 148 | 2 | 1.17 | 0 | 0
Client Set-up
Fahad
__export__.project_task_4857_beedb1e6 | Demo the in-stock versus dropship routing | Sprint 2138 | 2021-09-13 | Client Meetings | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 1.75 | 43.75 | Followup | 2015-09-01 |  | In Progress | Zuma Sales LLC | 149 | 4 | 2.25 | 0 | 0
Asfand
__export__.project_task_4856_b29ac49b | Install and set-up the user roles module | Sprint 2137 | 2021-09-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 2.5 | 83.33 |  | SPLN |  | ELS | Zuma Sales LLC | 149 | 3 | 0.5 | 3.3864e-05 | 0
__export__.project_task_4818_f8bb53ab | Setup Authorize.net and Paypal Payflow | Sprint 2137 | 2021-09-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0.33 | 16.5 |  | 2021-10-09 |  | Complete | Zuma Sales LLC | 171 | 2 | 1.67 | 5.6918e-05 | 19.3014
Client Set-up
__export__.project_task_4802_a2fe5fdf | Validation Script error | Sprint 2137 | 2021-09-06 | Bug Fix | Wild Pack Help (SOR-17586) | Naseeb Razaq | Aleem khan | 1.17 | 100 |  | SPLN |  | ELS | Wild Leaf Beverage | 196 | 1.1667 | -0.0033333 | 29.5917 | 0
__export__.project_task_4780_c65af954 | Email Release Notes and Why they should opt for Odoo 15 as Mass Email |  |  | Creative | Odoo Experience 2021 (P208) | Muhammad Zubair | Erin Olson | 0 | 0 | Discuss | Marketing |  | Planning | Silverdale Technology LLC | 293 | 0 | 0 | 0 | 0
__export__.project_task_4779_b8b78d78 | Create and Apply Email Signatures for Silverdale Employees - Odoo Experience 2021 | Sprint 2137 | 2021-09-06 | Creative | Odoo Experience 2021 (P208) | Muhammad Zubair | Shehroz Faiq | 3.67 | 91.75 |  |  |  | Complete | Silverdale Technology LLC | 293 | 4 | 0.33 | 0 | 46.8118
__export__.project_task_4768_f421c764 | Change wording on Congratulations message | Sprint 2138 | 2021-09-13 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Sajjad Hussain | 3.25 | 69.64 | PM Review this task | 2015-09-01 |  | PM Review | Cellpoint Corporation | 296 | 4.6667 | 1.4167 | 40 | 0
2016-09-01
__export__.project_task_4751_bba3ca08 | R & D for 2,850 Estimate | Sprint 2137 | 2021-09-06 | Development | Improvements for Belmont (P213) | Farman Ahmad Cheema | Wajahat Ali | 5.83 | 97.17 |  |  |  | Complete | Cellpoint Corporation | 322 | 6 | 0.17 | 48 | 48.7664
__export__.project_task_4729_25589e64 | Process Documentation - Silverdale Cares Representative Job Description | Sprint 2136 | 2021-08-30 | Documentation | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 387 | 0 | 0 | 1.3448e-05 | 5.2978
__export__.project_task_4724_d228f482 | Set up Tools - Cares Representative A-Player 3x5 KPIs Dashboard |  |  | Configuration | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Create Dashboard | Dashboard |  | Planning | Silverdale Technology LLC | 390 | 2 | 2 | 0 | 0
Development Dependent
__export__.project_task_4719_86851daa | Process Documentation - Cares Representative A-Player 3x5 | Sprint 2137 | 2021-09-06 | Documentation | Silverdale Cares 24/7 (P188) | Muhammad Zubair | Muhammad Zubair | 0 | 0 |  | SPLN |  | Complete | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 88.3911
__export__.project_task_4701_4a9c83fe | Process Documentation - Root Cause Analysis and Correction of Error | Sprint 2138 | 2021-09-13 | Documentation | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 88.3911
__export__.project_task_4697_cbfab5f7 | Process Documentation - Client Ticket Journey | Sprint 2137 | 2021-09-06 | Documentation | Silverdale Cares 24/7 (P188) | Muhammad Zubair | Muhammad Zubair | 1 | 25 |  | SPLN |  | Complete | Silverdale Technology LLC | 391 | 4 | 3 | 0 | 88.3911
__export__.project_task_4650_df51fb73 | Set-Up SLAs | Sprint 2136 | 2021-08-30 | Configuration | Wild Leaf: Implement Helpdesk (P184) | Naseeb Razaq | Naseeb Razaq | 0.5 | 50 |  | SPLN |  | Complete | Wild Leaf Beverage | 529 | 1 | 0.5 | 23.7685 | 88.851
__export__.project_task_4648_64e59944 | Track Shipped not billed with filter on Journal Items | Sprint 2138 | 2021-09-13 | Development | Wild Leaf: Automatic Identification of Shipped Not Billed Account Difference (P195) | Naseeb Razaq | Raheel Aslam | 8.17 | 74.27 | Please add next activity | 2015-09-01 |  | PM Review | Wild Leaf Beverage | 533 | 11 | 2.83 | 57.4409 | 0
PM Review this task
__export__.project_task_4643_57f8a104 | Break + Meetings |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Zubair | Muzher Siddique | 109.92 | 0 |  |  |  | Complete | Silverdale Technology LLC | 556 | 0 | -109.92 | 6.1502 | 34.1068
__export__.project_task_4594_44ec6ffc | Propagate Dates - Schedule Date on MO to Pick and Store | Sprint 2136 | 2021-08-30 | Development | Wild Leaf: Help (P22) | Naseeb Razaq | Raheel Aslam | 12.92 | 100 |  | SPLN |  | Complete | Wild Leaf Beverage | 793 | 12.5 | -0.42 | 99.4583 | 155.4583
__export__.project_task_4578_89d7460d | Custom Modules have all been installed and configured | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.5 | 25 | Follow Up | 2016-09-01 |  | Deployment | Zuma Sales LLC | 799 | 2 | 1.5 | 0 | 0
Fahad
__export__.project_task_4562_71d09da2 | Set a Bank Reconciliation threshold date to define when bank reconciliation will start. | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  | 2015-09-01 |  | Cancelled | Zuma Sales LLC | 799 | 1 | 1 | 0 | 176.3064
Meeting w/Bonnie
Asfand
__export__.project_task_4500_e3fd9088 | MMH Email Agent Link Expiry | Sprint 2135 | 2021-08-23 | Development | MMH: Affiliate Program Setup (P96) | Naseeb Razaq | Muhammad Bilal | 5.83 | 97.17 |  | SPLN |  | Complete | Mountain Meadow Herbs | 873 | 6 | 0.17 | 0 | 149.4208
__export__.project_task_4415_eed802d9 | Deploy to Deployment+Production(2131) | Sprint 2132 | 2021-08-02 | Deployment | MMH: Affiliate Program Setup (P96) | Naseeb Razaq | Fahad Hassan | 9 | 100 |  | SADL | 2 | Complete | Mountain Meadow Herbs | 1068 | 5 | -4 | 0 | 54.0659
__export__.project_task_4409_ca3a300e | Tasks and Tickets | Sprint 2133 | 2021-08-09 | Internal Time Tracking | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema |  | 194.33 | 0 |  |  |  | Complete | Cellpoint Corporation | 1128 | 0 | -194.33 | 0 | 94.3833
__export__.project_task_4347_507deb86 | Filtering on SOs for the unavailable items | Sprint 2131 | 2021-07-26 | Development | Mid-America: Help (P37) | Naseeb Razaq | Danish Hassan | 7.33 | 91.62 |  | SPLN | 1 | Complete | Mid-America Gardens, LLC | 1423 | 8 | 0.67 | 0 | 104.0192
__export__.project_task_4344_a2b9844a | Formats for Export Files | Sprint 2131 | 2021-07-26 | Configuration | Cellpoint: Odoo for Boost Files (P165) | Nick Foy | Nick Foy | 0 | 0 |  | SPLN |  | Complete | Cellpoint Corporation | 1466 | 1 | 1 | 5.6255e-05 | 72.5951
__export__.project_task_4337_3154b33d | Critical Functionality Testing(2129+Deployment on Production) | Sprint 2131 | 2021-07-26 | Development | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Fahad Hassan | 8 | 88.89 |  |  | 2 | Complete | Continuant | 1470 | 9 | 1 | 0.038322 | 54.27
__export__.project_task_4307_6766b2ab | CPBids Modules Upgradation |  |  | Development | Cellpoint: CPBids Upgrade to v14 (P161) | Farman Ahmad Cheema | Wajahat Ali | 30.67 | 61.34 | Plan it in a sprint |  | 3 | Backlog | Cellpoint Corporation | 1517 | 50 | 19.33 | 318.3909 | 0
__export__.project_task_4286_edc8d28f | Customer should have option to view invoice PDF on portal, Part2 | Sprint 2131 | 2021-07-26 | Development | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Muhammad Bilal | 6.33 | 100 |  | SPLN | 3 | Complete | Continuant | 1643 | 6 | -0.33 | 50.2866 | 142.0466
__export__.project_task_4279_11dbd717 | Complete Review of Affiliate Link | Sprint 2131 | 2021-07-26 | Configuration | MMH: Affiliate Program Setup (P96) | Naseeb Razaq | Naseeb Razaq | 5 | 100 |  | SPLN |  | Complete | Mountain Meadow Herbs | 1657 | 5 | 0 | 0 | 152.0192
__export__.project_task_4240_23123c91 | Schedule Report | Sprint 2131 | 2021-07-26 | Development | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Aleem khan | 7.92 | 66 |  | SPLN | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 1661 | 12 | 4.08 | 0 | 201.2943
__export__.project_task_4236_dfb81208 | nginx routing |  |  | Configuration | DGS: Server Consolidation (P158) | Levi Barnes | Fahad Hussain Malik | 3 | 75 |  |  |  | Complete | DG Solutions Inc. | 1662 | 4 | 1 | 0 | 74.0936
__export__.project_task_4231_3b29dbae | Fix AWS transfer via TSQL |  |  | Development | DGS: ETL 2 (P156) | Levi Barnes |  | 3.5 | 70 |  |  |  | Complete | DG Solutions Inc. | 1680 | 5 | 1.5 | 0 | 167.1406
__export__.project_task_4195_84192c2d | Conduct Custom Code Standards Review | Sprint 2132 | 2021-08-02 | Other | CraftAG: Odoo Audit (P147) | Fahad Hussain Malik | Danish Hassan | 7.83 | 65.25 |  |  |  | Complete | CraftAG | 1798 | 12 | 4.17 | 143.3328 | 232.0192
__export__.project_task_4154_28bbd579 | Upgrade to v14 (copy) | Sprint 2125 | 2021-06-14 | Other | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  | Odoo Migration |  | Cancelled | Zuma Sales LLC | 1829 | 8.5 | 8.5 | 94.145 | 0.051428
__export__.project_task_4153_415c37ab | Estimate to do Configurations after version upgrade | Sprint 2128 | 2021-07-05 | Configuration | DGS: Odoo Audit and v14 Upgrade Estimate (P136) | Jeff Gross | Fahad Hussain Malik | 2 | 40 |  | Odoo Migration |  | Complete | DG Solutions Inc. | 1829 | 5 | 3 | 0.0081425 | 41.1612
__export__.project_task_4125_68810959 | Lead Generation from Website Form | Sprint 2128 | 2021-07-05 | Configuration | MMH: Website Edits June 2021 (P120) | Naseeb Razaq |  | 2 | 100 |  | SADL |  | Complete | Mountain Meadow Herbs | 1901 | 2 | 0 | 0 | 45.1452
__export__.project_task_4088_86e2f1f5 | Compare the Donations uploaded for Friend Membership |  |  | Configuration | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq |  | 3.5 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 2040 | 0 | -3.5 | 0 | 149.0147
__export__.project_task_4058_ab22c2da | Sponsor Call |  |  | Internal Time Tracking | Heronswood: Help (P54) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 2065 | 0 | 0 | 0.0049245 | 348.0385
__export__.project_task_4043_5acd2a5b | Change Location Names of new Routes setups / Staging |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 0.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2144 | 0 | -0.5 | 0 | 3.546
__export__.project_task_4032_d0eed514 | Inventory Adjustment for all products to 0/ Staging |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 1.83 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2144 | 0 | -1.83 | 0 | 4
__export__.project_task_4016_f3404cd2 | Sponsor Call Meeting |  |  | Other | MMH: Help (P83) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Mountain Meadow Herbs | 2168 | 0 | 0 | 0 | 115.427
__export__.project_task_4006_57cda6c7 | Matt To Provide Categories for Consignee |  |  | Other | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2191 | 0 | 0 | 0 | 19.296
__export__.project_task_3999_f2838b2e | Database Setup Configuration | Sprint 2129 | 2021-07-12 | Development | Continuant: Customer Invoice Portal (P118) | Umer Farooq | Muhammad Bilal | 6.5 | 92.86 |  |  | 2 | Complete | Continuant | 2210 | 7 | 0.5 | 0 | 164.2231
__export__.project_task_3995_f19afdb2 | Allow customers to pay multiple invoices at once, or one, depending on the outstanding invoices they have | Sprint 2131 | 2021-07-26 | Development | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Muhammad Bilal | 16.33 | 81.65 |  | SPLN | 4 | Complete | Continuant | 2210 | 20 | 3.67 | 189.4636 | 312.0192
__export__.project_task_3974_336a28f0 | Affiliate link on the Agent Portal | Sprint 2131 | 2021-07-26 | Development | MMH: Affiliate Program Setup (P96) | Naseeb Razaq | Danish Hassan | 6.5 | 100 |  | SPLN | 1 | Complete | Mountain Meadow Herbs | 2233 | 4.5 | -2 | 0 | 344.0192
__export__.project_task_3971_c402bfa0 | New Routes Demonstration to Operations Team |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 4.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2234 | 0 | -4.5 | 0 | 29.5678
__export__.project_task_3969_d32b3f81 | Affiliate link work for the new customer | Sprint 2131 | 2021-07-26 | Development | MMH: Affiliate Program Setup (P96) | Naseeb Razaq | Muhammad Bilal | 16.58 | 92.11 |  | SPLN | 3 | Complete | Mountain Meadow Herbs | 2234 | 18 | 1.42 | 0 | 344.0192
__export__.project_task_3960_ffb74429 | Apply Credits when selecting invoices for payment | Sprint 2125 | 2021-06-14 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Aleem khan | 31.67 | 83.34 |  |  | 3 | Complete | Wild Leaf Beverage | 2242 | 38 | 6.33 | 2.1931e-05 | 93.2567
__export__.project_task_3952_c0636cc4 | Apply Credits when selecting invoices for payment |  |  | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Aleem khan | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 2312 | 0 | 0 | 0 | 0.26627
__export__.project_task_3935_25bdafdb | Set categories for the blogs | Sprint 2125 | 2021-06-14 | Development | MMH: Website Edits June 2021 (P120) | Naseeb Razaq | Muhammad Bilal | 6.25 | 34.72 |  |  | 2 | Complete | Mountain Meadow Herbs | 2329 | 18 | 11.75 | 0 | 80
__export__.project_task_3922_59fad581 | Deployment Wildleaf (11-06-21) | Sprint 2124 | 2021-06-07 | Other | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair |  | 18.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2335 | 0 | -18.25 | 0.0078461 | 25.2798
__export__.project_task_3889_ea67130b | Create a link for Affiliate partners to share with prospects for buying | Sprint 2131 | 2021-07-26 | Development | MMH: Affiliate Program Setup (P96) | Naseeb Razaq | Muhammad Bilal | 5 | 100 |  | SADL | 2 | Complete | Mountain Meadow Herbs | 2478 | 3 | -2 | 0 | 393.7293
__export__.project_task_3883_450b3a61 | Klaviyo or other campaign management integration |  |  | Development | MMH: E-Commerce Functionality (P101) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Mountain Meadow Herbs | 2496 | 0 | 0 | 0 | 567.4377
__export__.project_task_3845_fce650c2 | Dashboard shows in first place |  |  | Development | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Danish Hassan | 4.12 | 100 |  |  | 1 | Complete | Port Gamble Sâ€™Klallam Foundation | 2666 | 3 | -1.12 | 0 | 79.2658
__export__.project_task_3830_2adb4842 | Credit Note for Refund after Insurance check | Sprint 2124 | 2021-06-07 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Raheel Aslam | 12.75 | 98.08 |  |  | 3 | Complete | Perfect Golf Event | 2741 | 13 | 0.25 | 0 | 144.666
__export__.project_task_3827_cbc26dd3 | When split MO, it asks for the date and quantity for each backorder | Sprint 2124 | 2021-06-07 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Aleem khan | 25.08 | 99.99 |  |  | 3 | Complete | Wild Leaf Beverage | 2743 | 25.0833 | 0.0033333 | 88.107 | 130.5598
__export__.project_task_3801_b629c406 | Change Pick > Pack > Ship Behavior | Sprint 2125 | 2021-06-14 | Configuration | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Mir Muhammad Muzammil | 2.58 | 43 |  |  |  | Complete | Wild Leaf Beverage | 2886 | 6 | 3.42 | 119.2226 | 233.6754
__export__.project_task_3700_07becec8 | Zoho query |  |  | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Perfect Golf Event | 2905 | 0 | 0 | 0 | 112
__export__.project_task_3660_0de2b61a | Refining the Modules & codes | Sprint 2126 | 2021-06-21 | Development | Wild Leaf: Help (P22) | Muhammad Zubair | Wajahat Ali | 15.5 | 100 |  | SADL | 1 | Complete | Wild Leaf Beverage | 3168 | 8 | -7.5 | 313.8011 | 288
__export__.project_task_3650_35edf515 | Incorporate client feedback | Sprint 2127 | 2021-06-28 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 5 | 100 |  | SPLN |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 1 | -4 | 0.00052273 | 345.9839
__export__.project_task_3647_6d95ce10 | Upload graphics to Odoo | Sprint 2120 | 2021-05-10 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 0.42 | 84 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.5 | 0.08 | 0.00024495 | 201.9839
__export__.project_task_3638_60d78970 | Create any new fields required in Odoo | Sprint 2120 | 2021-05-10 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 0.17 | 34 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.5 | 0.33 | 0 | 17.9839
__export__.project_task_3555_2d9ebc22 | email template link color change | Sprint 2125 | 2021-06-14 | Development | PWX: Help (P23) | Muhammad Afzaal | Danish Hassan | 5.5 | 100 |  |  | 1 | Complete | EquityTeam | 3319 | 5 | -0.5 | 1.475e-05 | 306.4011
__export__.project_task_3503_c157ece6 | Add Donations types and donation products |  |  | Configuration | Heronswood: Network for Good transition to Odoo (P78) | Jeff Gross | Farman Ahmad Cheema | 2.33 | 93.2 |  | MA Review |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3410 | 2.5 | 0.17 | 0 | 144
__export__.project_task_3392_f7f7e8a1 | For Tools For Healing Create Transactions the company deals in |  |  | Functionality Test | MMH: Odoo Audit (P100) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Mountain Meadow Herbs | 3531 | 0 | 0 | 0 | 168
__export__.project_task_3326_1f6f48a1 | internal 500 server error | Sprint 2117 | 2021-04-19 | Bug Fix | MMH Unity Research: Help (P108) | Jeff Gross | Muhammad Bilal | 9 | 0 |  |  | 4 | Complete | Mountain Meadow Herbs | 3846 | 0 | -9 | 0 | 97.4562
__export__.project_task_3011_f6a2e2cc | docker e-learning | Sprint 2126 | 2021-06-21 | Configuration | Silverdale: Devops (P84) | Muzher Siddique | Muzher Siddique | 5.5 | 61.11 | Please add next activity |  |  | Backlog | Silverdale Technology LLC | 4414 | 9 | 3.5 | 1002.4521 | 0
__export__.project_task_3005_c26fa0f6 | Demo: Maintenance Module |  |  | Demo to the client | Wild Leaf: Help (P22) | Jeff Gross | Bilal Ahmad Khan | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4422 | 0 | 0 | 0 | 36.9689
__export__.project_task_2995_8023f9de | application survey | Sprint 2114 | 2021-03-29 | Configuration | PWX: Survey (P70) | Levi Barnes | Umer Farooq | 0 | 0 |  |  |  | Complete | EquityTeam | 4430 | 3 | 3 | 0 | 83.6392
__export__.project_task_2919_a8604e40 | Plan and set-up design workshops for the processes |  |  |  | DESIGN (P77) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1049.801
__export__.project_task_2847_4b102d7e | Install and Set-up Dashboard Ninja | Sprint 2112 | 2021-03-15 | Development | Wild Leaf: Help (P22) | Jeff Gross |  | 0 | 0 |  |  | 1 | Complete | Wild Leaf Beverage | 4687 | 0 | 0 | 10.4456 | 250.4456
__export__.project_task_2779_833f941f | Payment process surcharge - 3% Fee for Credit Card Transactions: Part-1 | Sprint 2110 | 2021-02-22 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Danish Hassan | 3.83 | 95.75 |  |  |  | Complete | Wild Leaf Beverage | 5020 | 4 | 0.17 | 88 | 135.4025
__export__.project_task_2729_c9708acb | Employee: Rewards | Sprint 2113 | 2021-03-22 | Development | PWX: HR (P61) | Levi Barnes | Osama Khalid | 1.63 | 100 |  |  | 1 | Complete | EquityTeam | 5182 | 1 | -0.63 | 0 | 368
__export__.project_task_2710_57ca1e78 | Project Planning |  |  | Internal Time Tracking | Moln: 3 New Portal Websites (P62) | Levi Barnes | Levi Barnes | 0.5 | 0 |  |  |  | Complete | Moln Solutions, LLC | 5260 | 0 | -0.5 | 0 | 120.0167
__export__.project_task_2699_4680b6c1 | 207:Watchlist - Mybids Web: Create controller to get watchlist Data | Sprint 2108 | 2021-02-08 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Muhammad Bilal | 5.25 | 100 |  |  |  | Complete | Cellpoint Corporation | 5330 | 5 | -0.25 | 0 | 207.3236
__export__.project_task_2651_c87d5f55 | Fw: Example files for VAR SFTP | Sprint 2113 | 2021-03-22 | Development | Cellpoint: ecoATM API (P50) | Nick Foy |  | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 5406 | 0 | 0 | 8.1009e-05 | 417.9304
__export__.project_task_2395_f25c0d3c | Recruitment Planning. |  |  | Configuration | Silverdale: Help (P12) | Nick Foy | Faisal Huda Khan | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5711 | 0 | 0 | 0 | 24
__export__.project_task_2380_be79b880 | Job Post Error |  |  | Bug Fix | Silverdale: Help (P12) | Faisal Huda Khan | Fahad Hassan | 2.17 | 0 |  | WK |  | Complete | Silverdale Technology LLC | 5740 | 0 | -2.17 | 0 | 55.5269
__export__.project_task_2295_bf7cf16e | Placeholder Work Orders Planning Requirements |  |  | Requirements Collection | Wild Leaf: Placeholder Work Orders Planning Requirements (P153) | Naseeb Razaq |  | 0 | 0 |  |  |  | New | Wild Leaf Beverage | 5888 | 0 | 0 | 1344 | 0
__export__.project_task_2093_381c912a | General Time |  |  | Configuration | Wild Leaf: Help (P22) | Nick Foy | Nick Foy | 31.67 | 100 |  |  |  | Complete | Wild Leaf Beverage | 6190 | 31.1667 | -0.50333 | 176 | 208
__export__.project_task_2092_ef8f4999 | FW: You have been assigned to Edits to Recruitment Module (#45) |  |  | Development | PWX: Help (P23) | Levi Barnes |  | 0 | 100 |  |  |  | Complete | EquityTeam | 6190 | 13.5 | -2.74 | 0 | 415.4586
__export__.project_task_2073_7c3fa23d | Quotation for Belmont BTMI functionality | Sprint 2103 | 2021-01-11 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Nick Foy | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 6212 | 0 | 0 | 0 | 104
__export__.project_task_2004_a77cd0ae | Product -> vendor match |  |  | Configuration | KMI: Help (P41) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | KMI Zeolite | 6506 | 0 | 0 | 0 | 360
__export__.project_task_1872_88097867 | not able to take orders - site still looks broken | Sprint 2051 | 2020-12-14 | Bug Fix | Moln: Help (P16) | Levi Barnes |  | 0.25 | 0 |  |  |  | Complete | Moln Solutions, LLC | 6601 | 0 | -0.25 | 0 | 78.6889
__export__.project_task_1823_58d5b1f1 | CPBids to Azure for Belmont: Restrict to Belmont Auctions |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0.25 | 7.69 |  |  |  | Complete | Cellpoint Corporation | 6764 | 3.25 | 3 | 0 | 212.6069
__export__.project_task_1819_84340ba3 | CPBids to Azure for Belmont |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 17.17 | 100 |  |  |  | Complete | Cellpoint Corporation | 6765 | 3.6667 | -18.6733 | 0 | 264
__export__.project_task_1695_412ffbca | Create Outstanding Purchase Orders | Sprint 2049 | 2020-11-30 | Development | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 11.67 | 100 |  |  |  | Complete | Wild Leaf Beverage | 6915 | 8 | -3.67 | 0 | 72
__export__.project_task_1678_b8655da8 | Fwd: 2021 Tour Schedule | Sprint 2049 | 2020-11-30 | Configuration | Albers Vista (P20) | Levi Barnes | Fahad Hassan | 1.67 | 100 |  |  |  | Complete | Albers Marcovina Vista Gardens | 6933 | 1 | -0.67 | 8 | 47.8919
__export__.project_task_1635_d47fad89 | Lot Ref. QUFEK Enter Bids | Sprint 2048 | 2020-11-23 | Bug Fix | Cellpoint CPBids: Help (P7) | Kaesi Lee | Anusha | 0.5 | 0 |  |  |  | Complete | Cellpoint Corporation | 7179 | 0 | -0.5 | 0 | 15.885
__export__.project_task_1504_30bd2c8b | Gucci: No Check Out Button | Sprint 2045 | 2020-11-02 | Bug Fix | Moln: Help (P16) | Kaesi Lee | Muzher Siddique | 2.25 | 0 |  | Website |  | Complete | Moln Solutions, LLC | 7729 | 0 | -2.25 | 0 | 64
__export__.project_task_1499_398b814d | Complete Product Category Configuration | Sprint 2044 | 2020-10-26 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 4 | 0 |  |  |  | Complete | Wild Leaf Beverage | 7780 | 0 | -4 | 0 | 24
__export__.project_task_1495_35991aed | Windows Security Software | Sprint 2044 | 2020-10-26 | Configuration | Silverdale: Help (P12) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 7855 | 0 | 0 | 0.31315 | 26.5657
__export__.project_task_1436_922c8bb8 | Inventory Migration |  |  | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 0.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 8019 | 0 | -20.5 | 0 | 460.7367
__export__.project_task_1417_8ee44c14 | Construction Management |  |  |  | PWX: Help (P23) | Levi Barnes |  | 0.33 | 0 |  |  |  | Cancelled | EquityTeam | 8088 | 0 | -0.33 | 111.5092 | 624
__export__.project_task_1410_b9a13f78 | category with no products - please hide from commerce front-end | Sprint 2045 | 2020-11-02 | Bug Fix | Moln: Help (P16) | Kaesi Lee | Muzher Siddique | 37.28 | 100 |  | Website |  | Complete | Moln Solutions, LLC | 8107 | 16 | -21.28 | 8 | 200
eCommerce
__export__.project_task_1371_6ced452b | Urgent: drprotect not loading | Sprint 2041 | 2020-10-05 | Bug Fix | Moln: Help (P16) | Kaesi Lee |  | 0.25 | 0 |  | Website |  | Complete | Moln Solutions, LLC | 8287 | 0 | -0.25 | 6.6834 | 6.6834
__export__.project_task_1367_1221aa03 | Contact Import | Sprint 2041 | 2020-10-05 | Configuration | Wild Leaf: Help (P22) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 8332 | 0 | 0 | 0 | 40
__export__.project_task_1365_fe9c10b6 | Invoicing walkthrough | Sprint 2041 | 2020-10-05 | Configuration | Wild Leaf: Help (P22) | Nick Foy |  | 5 | 100 |  |  |  | Complete | Wild Leaf Beverage | 8348 | 2 | -3 | 0 | 80
__export__.project_task_1317_99ce3168 | FW: Missing product names | Sprint 33 | 2020-09-28 | Bug Fix | Moln: Help (P16) | Gadha Continuant |  | 0 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8428 | 0 | 0 | 0 | 24
__export__.project_task_1297_9313e50f | Deploy audit best practice | Sprint 2041 | 2020-10-05 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 4 | 0 |  |  |  | Complete | Wild Leaf Beverage | 8470 | 0 | -4 | 0 | 120
__export__.project_task_1183_9097872f | Authorize.net payment capture form |  |  |  | Moln: Help (P16) | Levi Barnes |  | 7 | 0 |  |  |  | Cancelled | Moln Solutions, LLC | 8998 | 0 | -7 | 432 | 840
__export__.project_task_1170_c0a636a5 | AOA Landing Page | Sprint 30 | 2020-09-07 | Configuration | Moln: Help (P16) | Kaesi Lee |  | 1 | 100 |  |  |  | Complete | Moln Solutions, LLC | 9096 | 1 | 0 | 4.8314 | 0
__export__.project_task_242_78a1faac | Access to Deepak (Github) | Sprint 28 | 2020-08-24 | Development | Silverdale: Help (P12) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 10445 | 0 | 0 | 0 | 0
__export__.project_task_171_26d4f547 | Maintain Status |  |  |  | Cellpoint: Belmont Manifest API Integration (P6) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11310 | 0 | 0 | 0 | 0
__export__.project_task_4929_4e383f9e | Odoo Direct Print Set-Up & Configuration (One-Time Fee) |  |  |  | Cellpoint: Direct Print Set-up and Config (P224) | Public user |  | 0 | 0 | Please add next activity |  |  | New | Cellpoint Corporation | 21 | 1 | 1 | 0 | 0
__export__.project_task_4918_f1a30ea3 | SO Contact & Company Information Setup | Sprint 2139 | 2021-09-20 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Aleem khan | 3.08 | 77 | This task missed the deadline! | 2015-09-01 |  | Integrated Testing | Zuma Sales LLC | 33 | 4 | 0.92 | 0 | 0
Your task missed the deadline!
Code push & Integration Testing
fahad hasan
__export__.project_task_4896_dab81551 | Set up Costing Methods | Sprint 2137 | 2021-09-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 118 | 0.083333 | 0.083333 | 1.9629e-05 | 0.014186
__export__.project_task_4862_73af56e3 | FIX: Bill to & Ship to Addresses to Reflect on Contact | Sprint 2138 | 2021-09-13 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Aleem khan | 9.17 | 85.97 | This task missed the deadline! | 2015-09-01 |  | QA | Zuma Sales LLC | 145 | 10.6667 | 1.4967 | 0.12779 | 0
Your task missed the deadline!
Quality check this task
fahad hasan
__export__.project_task_4839_57077ceb | Share Assets with Odoo for Sponsorship Showcase | Sprint 2138 | 2021-09-13 | Creative | Odoo Experience 2021 (P208) | Muhammad Zubair | Shehroz Faiq | 17 | 85 | This task missed the deadline! |  |  | In Progress | Silverdale Technology LLC | 169 | 20 | 3 | 0 | 0
Your task missed the deadline!
Please Review Task
Voice over
__export__.project_task_4822_c9ed3fea | Purchasing Training | Sprint 2138 | 2021-09-13 | Client Meetings | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 1 | 100 |  | 2013-09-01 |  | Complete | Zuma Sales LLC | 171 | 1 | 0 | 5.1486e-05 | 24.6367
__export__.project_task_4816_df6f46d2 | Import auction file format | Sprint 2137 | 2021-09-06 | Configuration | Improvements for Belmont (P213) | Farman Ahmad Cheema | Wajahat Ali | 1.42 | 94.67 |  |  |  | Complete | Cellpoint Corporation | 175 | 1.5 | 0.08 | 0 | 16.8372
__export__.project_task_4800_f28c79c8 | Estimate for Odoo upgrade |  |  | Configuration | Continuant: Update Odoo to V14/15 (P211) | Fahad Hussain Malik | Fahad Hussain Malik | 1 | 0 | Follow-up | 2015-09-01 |  | Planning | Continuant | 198 | 0 | -1 | 0 | 0
__export__.project_task_4781_18d99a07 | Schedule Client Demos for v15 Functionality (depending on interest levels) |  |  | Client Meetings | Odoo Experience 2021 (P208) | Muhammad Zubair | Erin Olson | 0 | 0 | Plan Demos |  |  | Planning | Silverdale Technology LLC | 293 | 0 | 0 | 0 | 0
__export__.project_task_4774_fd4cade2 | 7x Blog Posts about the Odoo 15 Release and Odoo Experience |  |  | Creative | Odoo Experience 2021 (P208) | Muhammad Zubair | Erin Olson | 0 | 0 | Discuss | Marketing |  | Backlog | Silverdale Technology LLC | 293 | 0 | 0 | 0 | 0
__export__.project_task_4767_0b9d183a | Change wording on auction finished message | Sprint 2138 | 2021-09-13 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Sajjad Hussain | 4.42 | 94.71 | Assign to a developer | 2015-09-01 |  | QA | Cellpoint Corporation | 297 | 4.6667 | 0.24667 | 40 | 0
2016-09-01
__export__.project_task_4733_4ba2f9b3 | Process Documentation - Cares Representative A-Player Agreement | Sprint 2137 | 2021-09-06 | Documentation | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 |  | SPLN |  | Complete | Silverdale Technology LLC | 383 | 0 | 0 | 0 | 82.5912
__export__.project_task_4722_d438c7f0 | Activity - Add Client Phone numbers |  |  | Improvements | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Plan the activity |  |  | Planning | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 0
__export__.project_task_4721_021cf866 | Process Documentation - Client and Internal Awareness | Sprint 2138 | 2021-09-13 | Documentation | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 88.3911
__export__.project_task_4698_3fbc2a3b | Process Documentation - Helpdesk Ticket Escalation | Sprint 2137 | 2021-09-06 | Documentation | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 |  | SPLN |  | Complete | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 88.3911
__export__.project_task_4662_a96ffc83 | Add Analytic Account from Rules if Set on Accounting Head |  |  | Development | Wild Leaf: Analytic Account Clean Up (P199) | Abdul Hameed | Raheel Aslam | 12 | 100 |  |  |  | Complete | Wild Leaf Beverage | 516 | 10.1667 | -1.8333 | 16 | 80
__export__.project_task_4651_b8f72db4 | Set-Up Ticket Types | Sprint 2136 | 2021-08-30 | Configuration | Wild Leaf: Implement Helpdesk (P184) | Nick Foy | Naseeb Razaq | 0.5 | 100 |  | SPLN |  | Complete | Wild Leaf Beverage | 529 | 0.5 | 0 | 0.0053248 | 88.8264
__export__.project_task_4549_eea02db3 | Define any Bank Reconciliation Models | Sprint 2137 | 2021-09-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.5 | 100 |  | SPLN |  | ELS | Zuma Sales LLC | 799 | 0.5 | 0 | 0 | 0
__export__.project_task_4520_d55ba73b | All Customers already defined Agent the affiliate link should be work for them | Sprint 2135 | 2021-08-23 | Development | MMH: Affiliate Program Setup (P96) | Naseeb Razaq | Muhammad Bilal | 5.92 | 71.04 |  | SPLN |  | Complete | Mountain Meadow Herbs | 844 | 8.3333 | 2.4133 | 0.020498 | 139.4133
__export__.project_task_4477_d106b5d7 | Deploy to Deployment + Production (2132) | Sprint 2133 | 2021-08-09 | Deployment | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Fahad Hassan | 5.08 | 72.57 |  |  | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 894 | 7 | 1.92 | 0 | 9.4498
__export__.project_task_4475_af08ebd8 | Deploy to Deployment +Production (2132) | Sprint 2133 | 2021-08-09 | Deployment | PWX: Help (P23) | Farman Ahmad Cheema | Fahad Hassan | 4.75 | 100 |  |  | 2 | Complete | EquityTeam | 894 | 4 | -0.75 | 0 | 9.4647
__export__.project_task_4453_1afac806 | Unit price without VAT changes by increasing quantity more than one on manual invoice creation | Sprint 2136 | 2021-08-30 | Bug Fix | MMH Dr. Clark: Help (P106) | Naseeb Razaq | Wajahat Ali | 10.42 | 96.93 |  | SPLN |  | Complete | Mountain Meadow Herbs | 968 | 10.75 | 0.33 | 0 | 200
__export__.project_task_4424_753b03ed | Revise The negative quantity validation message | Sprint 2135 | 2021-08-23 | Development | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Danish Hassan | 3.42 | 78.92 |  | SPLN |  | Complete | Wild Leaf Beverage | 1056 | 4.3333 | 0.91333 | 1.3253e-05 | 192.4681
__export__.project_task_4413_40a7a809 | Training Videos | Sprint 2133 | 2021-08-09 | Configuration | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Farman Ahmad Cheema | 0 | 0 |  | SPLN |  | Cancelled | Cellpoint Corporation | 1082 | 2 | 2 | 0 | 94.4072
__export__.project_task_4350_8d1ca411 | Project Meetings and Calls | Sprint 2133 | 2021-08-09 | Internal Time Tracking | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema |  | 147.22 | 0 |  |  |  | Complete | Cellpoint Corporation | 1392 | 0 | -147.22 | 0 | 152.0192
__export__.project_task_4343_6e3242bb | Process Mapping | Sprint 2132 | 2021-08-02 | Configuration | Cellpoint: Odoo for Boost Files (P165) | Nick Foy | Farman Ahmad Cheema | 10 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 1466 | 10 | 0 | 0 | 106.5453
__export__.project_task_4332_27029e60 | Shift Tracker Demo | Sprint 2131 | 2021-07-26 | Configuration | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Naseeb Razaq | 2 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 1472 | 2 | 0 | 0 | 76.0109
__export__.project_task_4329_774e3c82 | Deploy to Deployment+Production(WildLeaf+2129) | Sprint 2131 | 2021-07-26 | Deployment | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Fahad Hassan | 7.58 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 1475 | 5 | -2.58 | 11.9169 | 47.6527
__export__.project_task_4328_f47db423 | Deploy to Deployment + Production (2129) | Sprint 2132 | 2021-08-02 | Deployment | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Fahad Hassan | 3.5 | 50 |  |  | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 1475 | 7 | 3.5 | 0 | 99.4332
__export__.project_task_4327_7bf34e68 | Deploy to Deployment +Production (PWX+2129) | Sprint 2131 | 2021-07-26 | Deployment | PWX: Survey (P70) | Naseeb Razaq | Fahad Hassan | 4.42 | 100 |  | SPLN | 2 | Complete | EquityTeam | 1476 | 4 | -0.42 | 0 | 126.4083
__export__.project_task_4306_423e2dbb | Collectors Databases | Sprint 2135 | 2021-08-23 | Development | Heronswood: Collectors Database Phase 1 (P142) | Naseeb Razaq | Danish Hassan | 4.75 | 100 |  | SPLN |  | Complete | Port Gamble Sâ€™Klallam Foundation | 1517 | 4 | -0.75 | 0 | 292.6259
__export__.project_task_4287_6c818b78 | Customer should have option to view invoice PDF on portal, Part3 | Sprint 2131 | 2021-07-26 | Development | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Muhammad Bilal | 0.33 | 4.71 |  | SPLN | 3 | Complete | Continuant | 1643 | 7 | 6.67 | 51.4605 | 142.0207
__export__.project_task_4253_2c649c60 | On the Contact form need to add Informal Greeting field | Sprint 2129 | 2021-07-12 | Development | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq |  | 0 | 0 |  |  | 1 | Cancelled | Port Gamble Sâ€™Klallam Foundation | 1660 | 3 | 3 | 0 | 40
__export__.project_task_4243_91d165e6 | Scheduler for creating employees for volunteers | Sprint 2131 | 2021-07-26 | Development | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Aleem khan | 4.67 | 46.7 |  | SPLN | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 1661 | 10 | 5.33 | 2.9799e-05 | 185.2048
__export__.project_task_4242_03f6cd00 | Kiosk Changes | Sprint 2131 | 2021-07-26 | Development | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Raheel Aslam | 15.33 | 100 |  | SPLN | 3 | Complete | Port Gamble Sâ€™Klallam Foundation | 1661 | 15 | -0.33 | 0 | 201.2455
__export__.project_task_4233_9c6c9651 | Send email with file info on success |  |  | Development | DGS: ETL 2 (P156) | Levi Barnes |  | 1.25 | 100 |  |  |  | Complete | DG Solutions Inc. | 1680 | 1 | -0.25 | 0 | 167.1422
__export__.project_task_4212_ec28bba7 | Survey End Page Changes | Sprint 2129 | 2021-07-12 | Development | PWX: Survey (P70) | Naseeb Razaq | Aleem khan | 6.17 | 88.14 |  | SPLN | 2 | Complete | EquityTeam | 1733 | 7 | 0.83 | 0 | 185.3009
__export__.project_task_4197_d2cd5ad9 | Conduct Feature Usage Review | Sprint 2132 | 2021-08-02 | Other | CraftAG: Odoo Audit (P147) | Fahad Hussain Malik | Fahad Hussain Malik | 1.5 | 50 |  |  |  | Complete | CraftAG | 1798 | 3 | 1.5 | 143.3078 | 204.1653
__export__.project_task_4126_e60b4641 | Rework on Front End Website Changes | Sprint 2127 | 2021-06-28 | Development | MMH: Website Edits June 2021 (P120) | Naseeb Razaq |  | 0 | 0 |  | SADL |  | Cancelled | Mountain Meadow Herbs | 1901 | 0 | 0 | 0 | 21.595
__export__.project_task_4124_09ad5cd3 | Demo Videos for Training | Sprint 2131 | 2021-07-26 | Configuration | MMH: Affiliate Program Setup (P96) | Naseeb Razaq | Naseeb Razaq | 3.67 | 100 |  | SPLN |  | Complete | Mountain Meadow Herbs | 1901 | 3 | -0.67 | 0 | 264.8992
__export__.project_task_4099_36587d88 | Condition of Auto stage change to Customer Paid | Sprint 2127 | 2021-06-28 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 4 | 100 |  | SPLN | 2 | Complete | Perfect Golf Event | 1992 | 3 | -1 | 0 | 64
__export__.project_task_4087_2f463be4 | Donation Notes to upload | Sprint 2127 | 2021-06-28 | Configuration | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq |  | 6.75 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 2040 | 0 | -6.75 | 0 | 61.3611
__export__.project_task_4047_e6015980 | Set 0 Cost Per unit on all products on Production where category under finished goods |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 2 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2136 | 0 | -2 | 0 | 0
__export__.project_task_4042_f09a1961 | Set Semi-finish routes settings on product categories / Staging |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 2.83 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2144 | 0 | -2.83 | 0 | 3.5785
__export__.project_task_4036_65d3e82b | Change Costing Method on Product Categories / Staging |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 0.17 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2144 | 0 | -0.17 | 0 | 4
__export__.project_task_3994_779dc8c4 | Customer should be able to attach a document when paying an invoice | Sprint 2131 | 2021-07-26 | Development | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Muhammad Bilal | 21.08 | 100 |  | SPLN | 3 | Complete | Continuant | 2210 | 12 | -9.08 | 188.2897 | 312.0192
__export__.project_task_3992_ec7ab047 | Link the customer portal to the email that is sent out to customers | Sprint 2131 | 2021-07-26 | Configuration | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Fahad Hussain Malik | 2.5 | 100 |  | SPLN |  | Complete | Continuant | 2210 | 2 | -0.5 | 189.4811 | 304.0192
__export__.project_task_3972_7d2d43d6 | Portal User for Agents | Sprint 2131 | 2021-07-26 | Development | MMH: Affiliate Program Setup (P96) | Naseeb Razaq | Danish Hassan | 14.5 | 100 |  | SPLN | 3 | Complete | Mountain Meadow Herbs | 2234 | 13 | -1.5 | 0 | 344.0192
__export__.project_task_3970_b83badec | Email send to Agents on expiry the link | Sprint 2131 | 2021-07-26 | Development | MMH: Affiliate Program Setup (P96) | Naseeb Razaq | Danish Hassan | 5 | 100 |  | SPLN | 2 | Complete | Mountain Meadow Herbs | 2234 | 4.5 | -0.5 | 0 | 344.0192
__export__.project_task_3962_7e38aa59 | Graphic Designing |  |  | Creative | Silverdale Time Tracking (P56) | Muhammad Zubair |  | 5 | 100 |  |  |  | Complete | Silverdale Technology LLC | 2239 | 5 | 0 | 392 | 499.6178
__export__.project_task_3906_77600add | Review Functionality of Code against Requirements | Sprint 2125 | 2021-06-14 | Other | MMH: Affiliate Program Setup (P96) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Mountain Meadow Herbs | 2399 | 0 | 0 | 0 | 40
__export__.project_task_3904_04bd4712 | Cut Over plan for donation |  |  | Configuration | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Port Gamble Sâ€™Klallam Foundation | 2400 | 0 | 0 | 0 | 287.1583
__export__.project_task_3902_bad6999e | when invoicing the invoice qty is not always updating the Sales order. Pull from Invoice to SO if the Invoice line is removed/added againâ€‹ | Sprint 2125 | 2021-06-14 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Raheel Aslam | 22.5 | 100 |  |  | 4 | Complete | Wild Leaf Beverage | 2402 | 20 | -2.5 | 5.5472 | 128
__export__.project_task_3879_93c0d50c | moving search and opt-in email up higher on the homepage | Sprint 2125 | 2021-06-14 | Development | MMH: Website Edits June 2021 (P120) | Naseeb Razaq | Danish Hassan | 4.42 | 98.22 |  |  | 2 | Complete | Mountain Meadow Herbs | 2496 | 4.5 | 0.08 | 0 | 152
__export__.project_task_3878_9d5490d3 | Parent task for June 3rd Requests |  |  | Development | MMH: Website Edits June 2021 (P120) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Mountain Meadow Herbs | 2496 | 0 | -20.59 | 0 | 120
__export__.project_task_3870_d965f3c6 | Fwd: Color code for Prospect vs Customer Opportunities in CRM? | Sprint 2124 | 2021-06-07 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Fahad Hassan | 10.47 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 2525 | 5 | -5.47 | 30.5564 | 113.0092
__export__.project_task_3838_13303f0c | Crone job for the sequence number on donations order to set |  |  | Development | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Raheel Aslam | 2.67 | 66.75 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 2670 | 4 | 1.33 | 0.024277 | 23.7909
__export__.project_task_3832_e4e833d5 | Customer Credit Limits | Sprint 2128 | 2021-07-05 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Muhammad Bilal | 148.83 | 100 |  | SPLN | 3 | Complete | Wild Leaf Beverage | 2720 | 103 | -45.83 | 81.2958 | 283.7486
__export__.project_task_3828_a5e42f74 | TC-236-242 | Sprint 2129 | 2021-07-12 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 10 | 100 |  |  |  | Complete | Silverdale Technology LLC | 2741 | 8 | -2 | 0 | 361.2432
__export__.project_task_3782_106e9809 | Sending Signage document proofs to customer with PDF | Sprint 2122 | 2021-05-24 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 3.83 | 95.75 |  |  | 2 | Complete | Perfect Golf Event | 2886 | 4 | 0.17 | 18.0504 | 162.0504
__export__.project_task_3701_d9d6ea5c | Refining the Modules & codes Mid-America | Sprint 2121 | 2021-05-17 | Development | Mid-America: Help (P37) | Naseeb Razaq | Danish Hassan | 7.25 | 100 |  |  | 2 | Complete | Mid-America Gardens, LLC | 2904 | 5 | -2.25 | 0 | 80
__export__.project_task_3691_223ef14a | Import contact list into Odoo | Sprint 2121 | 2021-05-17 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 2.25 | 90 |  |  | 2 | Complete | Perfect Golf Event | 2998 | 2.5 | 0.25 | 0 | 152
__export__.project_task_3655_65449249 | Close the project with the client | Sprint 2127 | 2021-06-28 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 0 | 0 |  | SPLN |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.5 | 0.5 | 0.00052273 | 345.9839
__export__.project_task_3646_447af670 | Download graphics from Constant Contact | Sprint 2124 | 2021-06-07 | Development | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq | Aleem khan | 8 | 94.12 |  |  | 3 | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 8.5 | 0.5 | 0.00024495 | 177.27
__export__.project_task_3639_e48cdabb | Remove any duplicates from the source data | Sprint 2120 | 2021-05-10 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 0.08 | 24 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.33333 | 0.25333 | 0 | 24.6539
__export__.project_task_3589_8b3bbaeb | PWX-Critical functions automation(SalesModule) |  |  | Development | Silverdale: Devops (P84) | Levi Barnes | Muhammad Saqlain Alam | 9.95 | 99.5 |  |  | 4 | Cancelled | Silverdale Technology LLC | 3195 | 10 | 0.05 | 0 | 159.1322
__export__.project_task_3559_50307276 | applicant scorecard tab |  |  | Studio | PWX: Survey (P70) | Muhammad Afzaal | Levi Barnes | 2 | 100 |  |  |  | Complete | EquityTeam | 3317 | 2 | 0 | 0 | 40.5983
__export__.project_task_3492_233421ab | Heronswood Meeting |  |  | Internal Time Tracking | Heronswood: Help (P54) | Naseeb Razaq |  | 5.7 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3479 | 0 | -5.7 | 461.1792 | 461.1811
__export__.project_task_3391_81aae2f3 | For The Wolf Clinic Create Transactions the company deals in |  |  | Functionality Test | MMH: Odoo Audit (P100) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Mountain Meadow Herbs | 3531 | 0 | 0 | 0 | 168
__export__.project_task_3310_bee3199b | Setup Github for internal versioning control | Sprint 2116 | 2021-04-12 | Configuration | Silverdale: Devops (P84) | Levi Barnes | Wajahat Ali | 7.83 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3872 | 0 | -7.83 | 0 | 60
__export__.project_task_3029_478abb7a | Clean up Volunteer CSV Files | Sprint 2113 | 2021-03-22 | Other | Heronswood: Volunteer On-boarding (P79) | Jeff Gross | Muzher Siddique | 0.75 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 4395 | 0 | -0.75 | 0 | 184
__export__.project_task_3028_03477e84 | Deployment 2111: ecoatm | Sprint 2113 | 2021-03-22 | Configuration | Cellpoint: ecoATM API (P50) | Nick Foy | Wajahat Ali | 1 | 0 |  |  |  | Complete | Cellpoint Corporation | 4396 | 0 | -1 | 0.0086551 | 24.0092
__export__.project_task_3020_a79e5859 | The untaxed amount in sales orders must be without subtracting discounts | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Muhammad Bilal | 2.42 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 4402 | 1.75 | -0.67 | 7.83e-06 | 74.3242
__export__.project_task_2996_7c5aecc8 | interview surveys | Sprint 2113 | 2021-03-22 | Configuration | PWX: Survey (P70) | Levi Barnes | Umer Farooq | 0 | 0 |  |  |  | Complete | EquityTeam | 4430 | 3 | 3 | 0 | 83.7625
__export__.project_task_2987_d21ab9e0 | duplicate website 3 | Sprint 2112 | 2021-03-15 | Development | Moln: 3 New Portal Websites (P62) | Levi Barnes | Danish Hassan | 4.75 | 100 |  |  | 2 | Complete | Moln Solutions, LLC | 4497 | 3.5 | -1.25 | 0 | 204.298
__export__.project_task_2892_3ab73586 | Set-Up Weekly Sponsor Reviews |  |  |  | DISCOVERY (P76) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1050.1385
__export__.project_task_2884_ea3a086e | Deployment : Continuant | Sprint 2112 | 2021-03-15 | Configuration | Continuant: Quotation Management / Automation (P31) | Jeff Gross | Wajahat Ali | 0.42 | 0 |  |  |  | Complete | Continuant | 4586 | 0 | -0.42 | 0 | 32
__export__.project_task_2792_f5ff69cb | Helcim: Field validation | Sprint 2110 | 2021-03-01 | Development | Wild Leaf: Helcim Integration (P38) | Jeff Gross | Danish Hassan | 4.33 | 100 |  |  |  | Complete | Wild Leaf Beverage | 4921 | 4 | -0.33 | 72 | 159.0808
__export__.project_task_2783_922e9a84 | please remove these logos on AOA - keeps coming back |  |  | Configuration | Moln: 3 New Portal Websites (P62) | Levi Barnes |  | 0.25 | 0 |  |  |  | Complete | Moln Solutions, LLC | 5019 | 0 | -0.25 | 0 | 56
__export__.project_task_2781_0143204c | Payment process surcharge - 3% Fee for Credit Card Transactions:Part-3 | Sprint 2110 | 2021-02-22 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Raheel Aslam | 7.67 | 95.88 |  |  |  | Complete | Wild Leaf Beverage | 5020 | 8 | 0.33 | 88 | 135.4047
__export__.project_task_2765_ccf55f9d | Belmont Invoice API:R &D for api response | Sprint 2109 | 2021-02-15 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 5.67 | 100 |  |  |  | Complete | Cellpoint Corporation | 5076 | 4 | -1.67 | 1.8974e-05 | 158.1828
__export__.project_task_2757_33ebb907 | Goals: SMART | Sprint 2109 | 2021-02-15 | Development | PWX: Strategic Planning (P43) | Levi Barnes | Raheel Aslam | 2.5 | 83.33 |  |  |  | Complete | EquityTeam | 5094 | 3 | 0.5 | 0 | 96.736
__export__.project_task_2753_96d4d0d1 | CPBids Web: Language switcher is not working | Sprint 2112 | 2021-03-15 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Danish Hassan | 8 | 100 |  |  |  | Complete | Cellpoint Corporation | 5136 | 8 | 0 | 0 | 245.3339
__export__.project_task_2736_e124708c | Add functionality to manage US 1099 reporting | Sprint 2112 | 2021-03-15 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Wajahat Ali | 1.58 | 86.18 |  |  |  | Complete | Wild Leaf Beverage | 5180 | 1.8333 | 0.25333 | 128 | 253.3381
__export__.project_task_2733_1db943d8 | When creating an Asset, select an existing Asset Model | Sprint 2110 | 2021-02-22 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Raheel Aslam | 5.95 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5181 | 4.5 | -1.45 | 128 | 175.4072
__export__.project_task_2721_526a9a06 | Alert messaging:Needs to be from configuration not code. | Sprint 2110 | 2021-03-01 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 18.17 | 100 |  | 3.0.6 |  | Complete | Cellpoint Corporation | 5187 | 13.5 | -4.67 | 0 | 253.3064
__export__.project_task_2718_6b311e00 | General 2107 |  |  | Internal Time Tracking | PWX: Help (P23) | Levi Barnes | Levi Barnes | 3 | 0 |  |  |  | Complete | EquityTeam | 5228 | 0 | -3 | 0 | 55.7744
__export__.project_task_2698_725bd455 | 207:Watchlist - Mybids Web: Add Watchlish tab on website and enable /disable data base on option | Sprint 2108 | 2021-02-08 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Muhammad Bilal | 4.33 | 86.6 |  |  |  | Complete | Cellpoint Corporation | 5331 | 5 | 0.67 | 0 | 207.3261
__export__.project_task_2600_03175e3c | Authenticate the Heclim Provide Credentials from Odoo. |  |  | Development | Wild Leaf: Helcim Integration (P38) | Jeff Gross | Wajahat Ali | 2.58 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5549 | 2 | -0.58 | 216.971 | 304.1293
__export__.project_task_2335_466c1776 | Send to Pick Window: Added Fields | Sprint 2104 | 2021-01-18 | Development | Continuant: AV Warehouse (P34) | Nick Foy | Danish Hassan | 2.4 | 100 |  |  |  | Complete | Continuant | 5837 | 2 | -0.4 | 89.0686 | 263.0864
__export__.project_task_2268_d8af40fb | Sales | Sprint 2103 | 2021-01-11 | Configuration | Silverdale: Help (P12) | Faisal Huda Khan | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5910 | 0 | 0 | 0.14534 | 22.1128
__export__.project_task_2247_626a894e | Manufacturing operations in multiple BoMs - change to many2many: Configure New Operations |  |  | Configuration | Wild Leaf: Help (P22) | Nick Foy | Nick Foy | 1.5 | 100 |  | 2014-01-01 |  | Cancelled | Wild Leaf Beverage | 5931 | 1.5 | 0 | 120 | 128
__export__.project_task_2224_c9e80ded | Review preferred routes for Products as there are several k without a route preventing replenishment from working | Sprint 2103 | 2021-01-11 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Kaesi Lee | 0.75 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5972 | 0 | -0.75 | 0 | 40
__export__.project_task_2206_710ce966 | Create locations in new Warehouses | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy |  | 1 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5998 | 0 | -1 | 0 | 90.9667
__export__.project_task_2158_39ca09ce | Configure dropship correctly | Sprint 2103 | 2021-01-11 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Kaesi Lee | 0 | 0 |  | 2014-01-01 |  | Complete | Wild Leaf Beverage | 6053 | 0 | 0 | 0 | 120.574
__export__.project_task_2037_5bdf17b7 | Ability to add related fields on Odoo Side |  |  | Development | Continuant: Power BI Integration (P30) | Kaesi Lee | Raheel Aslam | 0.58 | 19.33 |  | Difficulty 2 |  | Complete | Continuant | 6384 | 3 | 2.42 | 0 | 152
__export__.project_task_2021_64500c39 | For Rent Page error on embed code for listings |  |  | Bug Fix | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 29.08 | 100 |  | Difficulty 4 |  | Complete | EquityTeam | 6434 | 9 | -20.08 | 0 | 413.5403
__export__.project_task_1992_2c140afc | freight vendor email |  |  | Development | KMI: Help (P41) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | KMI Zeolite | 6506 | 0 | -48.35 | 0 | 360
__export__.project_task_1985_3aa6f8a2 | Add Shipping Methods |  |  | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 1 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6508 | 0 | -1 | 0 | 100.7408
__export__.project_task_1894_8d661270 | migrate photos: automate imports into odoo | Sprint 2102 | 2021-01-04 |  | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 4.17 | 92.67 |  |  |  | Cancelled | Mid-America Gardens, LLC | 6580 | 4.5 | 0.33 | 0 | 264
__export__.project_task_1851_2489b53c | migrate photos |  |  |  | Mid-America: Help (P37) | Levi Barnes |  | 0 | 0 |  |  |  | Cancelled | Mid-America Gardens, LLC | 6724 | 0 | -8.09 | 0 | 296
__export__.project_task_1821_a67be7d8 | CPBids to Azure for Belmont: Create Azure database structure | Sprint 2053 | 2020-12-28 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 4.33 | 100 |  |  |  | Complete | Cellpoint Corporation | 6765 | 3 | -1.33 | 0 | 216
__export__.project_task_1820_1fc16304 | CPBids to Azure for Belmont: Deploy the app |  |  | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0.17 | 51 |  |  |  | Complete | Cellpoint Corporation | 6765 | 0.33333 | 0.16333 | 0 | 212.6092
__export__.project_task_1813_a74afd79 | Set-Up Google Maps | Sprint 2109 | 2021-02-15 | Development | Heronswood: Events (P3) | Nick Foy | Fahad Hassan | 2.17 | 86.8 |  | SPriority |  | Complete | Port Gamble Sâ€™Klallam Foundation | 6767 | 2.5 | 0.33 | 0 | 488
__export__.project_task_1801_7b368189 | Plan Transition |  |  | Configuration | Cellpoint CPBids: Help (P7) | Muzher Siddique | Wajahat Ali | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 6777 | 0 | -25.59 | 0 | 159.0164
__export__.project_task_1799_f8ea68b7 | gucci portal user invitation resend |  |  | Configuration | Moln: Help (P16) | Levi Barnes |  | 0.33 | 0 |  |  |  | Complete | Moln Solutions, LLC | 6811 | 0 | -0.33 | 14.3464 | 126.6892
__export__.project_task_1782_bea2d30a | Confirmation for Start Now | Sprint 2053 | 2020-12-28 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 1.25 | 41.67 |  |  |  | Complete | Cellpoint Corporation | 6836 | 3 | 1.75 | 0 | 220
__export__.project_task_1717_f076c64c | Investigate Fiscal Positions Effect on Cost Accounts in Standard Odoo | Sprint 2053 | 2020-12-28 |  | Continuant: Quotation Management / Automation (P31) | Kaesi Lee | Danish Hassan | 2 | 50 |  |  |  | Cancelled | Continuant | 6886 | 4 | 2 | 0 | 336
__export__.project_task_1707_63969ccf | Online Payments for Wild Leaf: Research and Connect |  |  | Configuration | Wild Leaf: Helcim Integration (P38) | Kaesi Lee | Fahad Hassan | 0.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6894 | 0 | -26.5 | 0.012408 | 241.5624
__export__.project_task_1691_4f9353c7 | FW: webpage needs to be update | Sprint 2049 | 2020-11-30 | Configuration | Albers Vista (P20) | Levi Barnes | Fahad Hassan | 0.67 | 33.5 |  |  |  | Complete | Albers Marcovina Vista Gardens | 6915 | 2 | 1.33 | 0 | 39.8819
__export__.project_task_1660_8dc2d4e4 | [Quick Fix] CPBids.com | Sprint 2048 | 2020-11-23 | Bug Fix | Cellpoint CPBids: Help (P7) | Faizan Zia Malik | Muzher Siddique | 0.33 | 66 |  | Website |  | Complete | Cellpoint Corporation | 7062 | 0.5 | 0.17 | 0.20063 | 66.012
__export__.project_task_1590_1a47c59c | Helpdesk & Misc Assigned Tasks (For Timesheets) |  |  | Configuration | Cellpoint CPBids: Help (P7) | Faizan Zia Malik | Faizan Zia Malik | 300.5 | 0 |  |  |  | Complete | Cellpoint Corporation | 7399 | 0 | -300.5 | 0 | 375.8079
__export__.project_task_1535_df38d50a | Monday |  |  | Configuration | Silverdale: Help (P12) | Muzher Siddique |  | 114.92 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 7568 | 0 | -114.92 | 0 | 504.8567
__export__.project_task_1494_ae6d9077 | Continuant: Change Passwords |  |  | Configuration | Silverdale: Help (P12) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 7855 | 0 | 0 | 0 | 146.3607
__export__.project_task_1439_7fe0947d | BoMs: Test Import of Bill of Materials | Sprint 2044 | 2020-10-26 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 8019 | 0 | 0 | 0 | 128
__export__.project_task_1435_6a2a850c | Product / Vendor Match | Sprint 2044 | 2020-10-26 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 4.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 8019 | 0 | -4.5 | 0 | 72
__export__.project_task_1384_fbb5c551 | Gucci: Need to change products to case size variations only | Sprint 2041 | 2020-10-05 | Configuration | Moln: Help (P16) | Nick Foy |  | 3 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8253 | 0 | -3 | 0 | 8
__export__.project_task_1348_71497f88 | Customer Import | Sprint 2041 | 2020-10-05 | Configuration | Wild Leaf: Help (P22) | Nick Foy |  | 2 | 100 |  |  |  | Complete | Wild Leaf Beverage | 8398 | 1 | -1 | 0 | 56
__export__.project_task_1347_963105c5 | Vendor Import | Sprint 2041 | 2020-10-05 | Configuration | Wild Leaf: Help (P22) | Nick Foy |  | 2 | 100 |  |  |  | Complete | Wild Leaf Beverage | 8398 | 1 | -1 | 0 | 56
__export__.project_task_1323_7b5e62e6 | FW: hard to read | Sprint 2042 | 2020-10-12 | Development | Silverdale: Help (P12) | Nick Foy | Anusha | 4 | 0 |  |  |  | Complete | Silverdale Technology LLC | 8408 | 0 | -4 | 75.7108 | 145.7066
__export__.project_task_1295_581dd458 | Move PowerBI sources to Odoo | Sprint 2051 | 2020-12-14 | Configuration | Cellpoint CPBids: Help (P7) | Kaesi Lee |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8472 | 2 | 2 | 0 | 487.5339
__export__.project_task_1266_8f2600d7 | remove mention of we shield from footer on AOA page | Sprint 32 | 2020-09-21 | Configuration | Moln: Help (P16) | Kaesi Lee |  | 0.25 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8591 | 0 | -0.25 | 7.4783 | 16
__export__.project_task_1225_7873fb11 | clone drprotect.com -> ShieldUs.com | Sprint 32 | 2020-09-21 | Configuration | Moln: Help (P16) | Kaesi Lee |  | 1.25 | 0 |  | Website |  | Complete | Moln Solutions, LLC | 8760 | 0 | -1.25 | 0 | 64
eCommerce
__export__.project_task_1214_36451f90 | getting subscription notice | Sprint 31 | 2020-09-14 | Configuration | Moln: Help (P16) | Nick Foy |  | 0.25 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8785 | 0 | -0.25 | 0 | 0
__export__.project_task_1145_2b57c0c3 | Amazon Integration |  |  |  | Moln: Help (P16) | Levi Barnes |  | 1 | 33.33 |  | Amazon Connector |  | Cancelled | Moln Solutions, LLC | 9240 | 3 | 2 | 488 | 896
__export__.project_task_1022_65aaa8be | Add Field to View: Auction ID | Sprint 28 | 2020-08-24 | Development | CPBids Migration AWS->odoo (P5) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 88.8228 | 0
__export__.project_task_192_030be375 | Live - Data Validate for a Week |  |  |  | Cellpoint: Belmont Manifest API Integration (P6) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10806 | 0 | 0 | 0 | 0
__export__.project_task_4859_58f91aed | Continuant: Modules Upgradation |  |  | Research | Continuant: Update Odoo to V14/15 (P211) | Fahad Hussain Malik | Muzher Siddique | 6.5 | 0 | Follow-up | 2015-09-01 |  | Planning | Continuant | 147 | 0 | -6.5 | 0 | 0
__export__.project_task_4855_943f961c | Complete the Shopify de-duplication on Shopify |  |  | Configuration | Zuma: Odoo Implementation Phase 2 (P204) | Asfand Yaar | Asfand Yaar | 0 | 0 |  | Client Set-up |  | Planning | Zuma Sales LLC | 149 | 2 | 2 | 8.6904 | 0
2016-09-01
__export__.project_task_4852_45ffb5b3 | Set-up products as drop-ship | Sprint 2137 | 2021-09-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.25 | 100 |  | SPLN |  | ELS | Zuma Sales LLC | 149 | 0.25 | 0 | 0 | 0
__export__.project_task_4823_f13e4693 | Import final list of contacts | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 2.83 | 70.75 | Follow-up | 2015-09-01 |  | Deployment | Zuma Sales LLC | 171 | 4 | 1.17 | 0 | 0
Asfand
__export__.project_task_4821_bff1f025 | CRM to Sales training | Sprint 2138 | 2021-09-13 | Client Meetings | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  | 2013-09-01 |  | Complete | Zuma Sales LLC | 171 | 1 | 1 | 0 | 24.6429
__export__.project_task_4778_0d16fddd | Create Silverdale Release Notes for Odoo 15 |  |  | Documentation | Odoo Experience 2021 (P208) | Muhammad Zubair |  | 0 | 0 | Create Release Notes | Marketing |  | Planning | Silverdale Technology LLC | 293 | 0 | 0 | 0 | 0
__export__.project_task_4731_aea86e43 | Process Documenation - Silverdale Cares Shift Management to enable 24x7 support | Sprint 2137 | 2021-09-06 | Documentation | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 |  | SPLN |  | Complete | Silverdale Technology LLC | 386 | 0 | 0 | 0 | 84.3911
__export__.project_task_4723_90b8dc37 | Set up Tools - Automated Ringers for Non-Response |  |  | Development | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Add Requirements | Add Requirements |  | Planning | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 0
__export__.project_task_4720_2cce3770 | Activity - Client and Internal Awareness |  |  | Configuration | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Plan |  |  | New | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 0
__export__.project_task_4694_0b247d36 | Deploy to Production(2135) | Sprint 2136 | 2021-08-30 | Deployment | PWX: Survey (P70) | Farman Ahmad Cheema | Muzher Siddique | 2.92 | 97.33 |  |  | 2 | Complete | EquityTeam | 395 | 3 | 0.08 | 0 | 32
__export__.project_task_4693_41164210 | Deploy to Production(2135) | Sprint 2136 | 2021-08-30 | Deployment | Heronswood: Help (P54) | Naseeb Razaq | Muzher Siddique | 3.08 | 61.6 |  |  | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 395 | 5 | 1.92 | 0 | 8
__export__.project_task_4692_e22cec89 | Deploy to Production(2135) | Sprint 2136 | 2021-08-30 | Deployment | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Muzher Siddique | 1.58 | 31.6 |  |  | 2 | Complete | Wild Leaf Beverage | 396 | 5 | 3.42 | 0 | 45.4208
__export__.project_task_4672_d25df1dd | DSM Meetings 2135 | Sprint 2135 | 2021-08-23 | Internal Time Tracking | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 1 | 0 |  |  |  | Complete | Wild Leaf Beverage | 513 | 0 | -1 | 0 | 17.335
__export__.project_task_4669_bb5d9e02 | Deploy to Deployment+Production(2135) | Sprint 2136 | 2021-08-30 | Deployment | MMH: Affiliate Program Setup (P96) | Naseeb Razaq | Muzher Siddique | 2.83 | 56.6 |  |  | 2 | Complete | Mountain Meadow Herbs | 514 | 5 | 2.17 | 0 | 24.8525
__export__.project_task_4661_5e7fceec | Analytic Account on Entries (All Entry Types) make mandatory | Sprint 2135 | 2021-08-23 | Development | Wild Leaf: Analytic Account Clean Up (P199) | Abdul Hameed | Danish Hassan | 6.67 | 95.29 |  |  |  | Complete | Wild Leaf Beverage | 516 | 7 | 0.33 | 0 | 56
__export__.project_task_4649_1ba2ad48 | Complete inbound email set-up and testing | Sprint 2137 | 2021-09-06 | Configuration | Wild Leaf: Implement Helpdesk (P184) | Naseeb Razaq | Naseeb Razaq | 2 | 100 |  | SPLN |  | ELS | Wild Leaf Beverage | 529 | 2 | 0 | 0 | 0
__export__.project_task_4639_057fdc8a | Customer Portal: Add a filter by priority for helpdesk tickets | Sprint 2136 | 2021-08-30 | Development | Silverdale: Help (P12) | Muhammad Zubair | Aleem khan | 5.67 | 100 |  | SPLN |  | Complete | Silverdale Technology LLC | 564 | 5.6667 | -0.0033333 | 8 | 117.4197
__export__.project_task_4626_b695e926 | Deployment cellpoint(P165) | Sprint 2133 | 2021-08-09 | Configuration | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 5 | 0 |  |  |  | Complete | Cellpoint Corporation | 708 | 0 | -5 | 0.0090108 | 5.5535
__export__.project_task_4580_e7aa4d0e | Test Run on Opening Balances | Sprint 2138 | 2021-09-13 | Demo to the client | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 | Close ticket | 2015-09-01 |  | Backlog | Zuma Sales LLC | 799 | 1 | 1 | 0 | 0
Meeting w/Bonnie
Asfand
__export__.project_task_4536_62c8a4d5 | Time format in Schedule to be AM/PM | Sprint 2135 | 2021-08-23 | Development | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Danish Hassan | 9 | 100 |  | SPLN |  | Complete | Port Gamble Sâ€™Klallam Foundation | 824 | 9 | 0 | 0 | 133.4208
__export__.project_task_4505_94fe5247 | Export Purchase Orders to SFTP |  |  | Development | Zuma: Odoo Implementation Phase 2 (P204) | Asfand Yaar | Aleem khan | 9 | 94.74 |  |  |  | QA | Zuma Sales LLC | 871 | 9.5 | 0.5 | 113.3375 | 0
__export__.project_task_4429_ed226449 | Re-Work for glitches | Sprint 2132 | 2021-08-02 | Development | MMH: Affiliate Program Setup (P96) | Naseeb Razaq | Muhammad Bilal | 6.67 | 83.38 |  |  |  | Complete | Mountain Meadow Herbs | 1037 | 8 | 1.33 | 0 | 64.9733
__export__.project_task_4421_e8b6c5b4 | Check IN/OUT time to correct | Sprint 2132 | 2021-08-02 | Development | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Aleem khan | 5 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 1060 | 4 | -1 | 0 | 72
__export__.project_task_4376_f74aea7c | Add Product information In Product Barcode Screen Transfers | Sprint 2136 | 2021-08-30 | Development | Wild Leaf: Help (P22) | Naseeb Razaq | Aleem khan | 14 | 100 |  | SPLN |  | Complete | Wild Leaf Beverage | 1176 | 13.75 | -0.25 | 195.2068 | 251.2068
__export__.project_task_4311_35cbe115 | Customer IP to share with Authorize.net | Sprint 2138 | 2021-09-13 | Development | MMH: Customer IP for Authorize.net (P174) | Naseeb Razaq | Muhammad Bilal | 9.25 | 30.83 | Gather requirements from the Client | 2015-09-01 |  | In Progress | Mountain Meadow Herbs | 1497 | 30 | 20.75 | 0 | 0
To Do
__export__.project_task_4294_d9e41773 | CPbids Upgrade (Odoo) |  |  | Development | Cellpoint: CPBids Upgrade to v14 (P161) | Farman Ahmad Cheema | Wajahat Ali | 14.5 | 48.33 | Add in a sprint |  |  | Backlog | Cellpoint Corporation | 1635 | 30 | 15.5 | 341.1093 | 0
__export__.project_task_4241_9462d5d7 | Screen for schedule registration on portal | Sprint 2129 | 2021-07-12 | Development | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Aleem khan | 8.25 | 55 |  | SPLN | 3 | Complete | Port Gamble Sâ€™Klallam Foundation | 1661 | 15 | 6.75 | 0 | 185.2783
__export__.project_task_4235_e7b44aee | nginx consolidation |  |  | Configuration | DGS: Server Consolidation (P158) | Levi Barnes | Fahad Hussain Malik | 0.25 | 50 |  |  |  | Complete | DG Solutions Inc. | 1662 | 0.5 | 0.25 | 0 | 74.0956
__export__.project_task_4232_40de74f1 | Send email if transfer fails |  |  | Development | DGS: ETL 2 (P156) | Levi Barnes |  | 0.75 | 75 |  |  |  | Complete | DG Solutions Inc. | 1680 | 1 | 0.25 | 0 | 167.1433
__export__.project_task_4084_e15157e7 | Make all volunteers as employees |  |  | Configuration | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Port Gamble Sâ€™Klallam Foundation | 2048 | 0 | 0 | 0 | 98.4827
__export__.project_task_4031_9f42bd55 | Routes Settings Semi-finish for all warehouses/ Staging |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 2 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2145 | 0 | -2 | 0 | 4
__export__.project_task_4028_5bd88ab6 | Upload Data from Network For Good |  |  | Configuration | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Farman Ahmad Cheema | 2.83 | 35.38 |  |  |  | Cancelled | Port Gamble Sâ€™Klallam Foundation | 2160 | 8 | 5.17 | 0 | 223.1617
__export__.project_task_4024_e197ec41 | Customer Scripts(Test Plan): viewable from portal | Sprint 2134 | 2021-08-16 | Development | Silverdale: SDET (P132) | Levi Barnes | Aleem khan | 5.42 | 67.75 |  |  | 2 | Complete | Silverdale Technology LLC | 2164 | 8 | 2.58 | 0 | 402.9317
__export__.project_task_3998_beb93120 | Customer should have the options to pay via credit card, bank debits, bank transfers and check. | Sprint 2131 | 2021-07-26 | Configuration | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Fahad Hussain Malik | 2.33 | 100 |  | SPLN |  | Complete | Continuant | 2210 | 2 | -0.33 | 189.4847 | 304.0192
__export__.project_task_3997_b29eb78f | Customer should have option to view invoice PDF on portal Part1 | Sprint 2131 | 2021-07-26 | Development | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Muhammad Bilal | 6 | 85.71 |  | SPLN | 3 | Complete | Continuant | 2210 | 7 | 1 | 189.4686 | 280.0192
__export__.project_task_3993_37fc5498 | Require customers to enter name and email address when paying | Sprint 2131 | 2021-07-26 | Development | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Muhammad Bilal | 8.58 | 71.5 |  | SPLN | 3 | Complete | Continuant | 2210 | 12 | 3.42 | 189.4661 | 312.0192
__export__.project_task_3968_952b1643 | Link Creation | Sprint 2131 | 2021-07-26 | Development | MMH: Affiliate Program Setup (P96) | Naseeb Razaq | Danish Hassan | 5.33 | 100 |  | SPLN | 1 | Complete | Mountain Meadow Herbs | 2234 | 5 | -0.33 | 0 | 251.7872
__export__.project_task_3948_b26f2336 | Product Export from SFTP to odoo | Sprint 2126 | 2021-06-21 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 4.92 | 98.4 |  | reuse | 1 | Complete | Zuma Sales LLC | 2312 | 5 | 0.08 | 208.4956 | 99.5395
SADL
__export__.project_task_3920_3270897a | Show Contact ID on Contact form |  |  | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 0.5 | 50 |  |  | 1 | Complete | Perfect Golf Event | 2352 | 1 | 0.5 | 0 | 64
__export__.project_task_3912_c328893f | Wildleaf-Critical functions automation(Inventory) |  |  | Development | Silverdale: Devops (P84) | Muzher Siddique | Muhammad Saqlain Alam | 54.2 | 0 |  |  |  | Complete | Silverdale Technology LLC | 2381 | 0 | -54.2 | 534.9916 | 542.9916
__export__.project_task_3910_07a66416 | Delivered or Manufactured not Billed Report | Sprint 2124 | 2021-06-07 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Danish Hassan | 6.42 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 2381 | 4 | -2.42 | 0.00010222 | 81.2468
__export__.project_task_3897_3eb701a6 | Release notes (Audit of All modules) |  |  | Improvements | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair |  | 9.17 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2474 | 0 | -9.17 | 24 | 70.2978
__export__.project_task_3892_20d11b99 | important requirements for lead generation |  |  | Development | MMH: E-Commerce Functionality (P101) | Naseeb Razaq |  | 0 | 0 | Please add next activity |  |  | Planning | Mountain Meadow Herbs | 2478 | 0 | 0 | 0 | 0
__export__.project_task_3886_e8d493a6 | WildLeaf: Want to show lots and lot units attached to invoices | Sprint 2126 | 2021-06-21 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Fahad Hassan | 25 | 100 |  | SADL | 3 | Complete | Wild Leaf Beverage | 2479 | 16 | -9 | 16.7327 | 139.1852
__export__.project_task_3884_de0dc7cd | Deployment 2021-06-04 |  |  | Other | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair |  | 28.83 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2483 | 0 | -28.83 | 19.0112 | 61.464
__export__.project_task_3858_a594e617 | Individual Auction open in a new tab | Sprint 2138 | 2021-09-13 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Sajjad Hussain | 3.58 | 61.37 | Code push | 2015-09-01 |  | Integrated Testing | Cellpoint Corporation | 2576 | 5.8333 | 2.2533 | 472.05 | 0
integrated testing
__export__.project_task_3846_bd5cb86a | Add third party module |  |  | Configuration | Heronswood: Help (P54) | Naseeb Razaq | Danish Hassan | 0.75 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 2666 | 0 | -0.75 | 0 | 8
__export__.project_task_3702_18d14b4f | Create an estimate | Sprint 2121 | 2021-05-17 | Other | Continuant: Customer Invoice Portal (P118) | Jeff Gross |  | 1.17 | 0 |  |  |  | Complete | Continuant | 2904 | 0 | -1.17 | 0 | 128
__export__.project_task_3690_ceb2f318 | recruitment view modifications |  |  | Development | PWX: Survey (P70) | Muhammad Afzaal | Levi Barnes | 2.25 | 100 |  |  | 2 | Complete | EquityTeam | 2999 | 2 | -0.25 | 0 | 224
__export__.project_task_3683_94dbf76b | TC-285 | Sprint 2123 | 2021-05-31 | Improvements | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 4.17 | 100 |  |  |  | Complete | Silverdale Technology LLC | 3042 | 3.5 | -0.67 | 0 | 22.8644
__export__.project_task_3645_7e9c65ae | Create email campaigns in Odoo | Sprint 2127 | 2021-06-28 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 1 | 100 |  | SPLN |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.16667 | -0.83333 | 0.00024495 | 305.1152
__export__.project_task_3570_fb9b7864 | Train Heronswood users on how to use new module | Sprint 2125 | 2021-06-14 | Demo to the client | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq |  | 4 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3243 | 0 | -4 | 0 | 288
__export__.project_task_3557_1a41e053 | Job specific gwc |  |  | Studio | PWX: Survey (P70) | Muhammad Afzaal | Levi Barnes | 2 | 100 |  |  |  | Complete | EquityTeam | 3317 | 2 | 0 | 0 | 57.0308
__export__.project_task_3495_b13c7000 | Command Center | Sprint 2120 | 2021-05-10 | Other | Silverdale: Devops (P84) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3477 | 0 | 0 | 0 | 110.7708
__export__.project_task_3493_5ef00577 | Silverdale Meeting |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 722.23 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3477 | 0 | -722.23 | 0.0051905 | 634.8594
__export__.project_task_3384_e4b852c2 | For Dr. Clark Create Transactions the company deals in |  |  | Functionality Test | MMH: Odoo Audit (P100) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Mountain Meadow Herbs | 3531 | 0 | 0 | 0 | 168
__export__.project_task_3358_08a36b72 | Mid America Gardens Web Site Automation | Sprint 2116 | 2021-04-12 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 4.5 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3673 | 0 | -4.5 | 0 | 8
__export__.project_task_3337_360aa5d1 | Transfer Donation Balances Into Odoo | Sprint 2121 | 2021-05-17 | Configuration | Heronswood: Network for Good transition to Odoo (P78) | Jeff Gross | Danish Hassan | 11.25 | 100 |  |  | 3 | Complete | Port Gamble Sâ€™Klallam Foundation | 3727 | 7.5 | -3.75 | 2.4994e-05 | 232.5839
__export__.project_task_3224_178adf52 | Calendar for volunteer activities management |  |  |  | Heronswood: Volunteer On-boarding (P79) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 4205 | 0 | 0 | 0 | 160.7158
__export__.project_task_3018_8220caec | Some products have tag "In stock" some don't have | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Osama Khalid | 7.75 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 4402 | 2 | -5.75 | 0 | 74.5497
__export__.project_task_2885_2d3d0853 | Plan Kick-Off Session with Client |  |  |  | DISCOVERY (P76) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1050.1741
__export__.project_task_2878_ba87e717 | applicant evaluation | Sprint 2113 | 2021-03-22 | Development | PWX: Survey (P70) | Levi Barnes | Raheel Aslam | 6.97 | 99.57 |  |  | 3 | Complete | EquityTeam | 4589 | 7 | 0.03 | 0 | 233.0666
__export__.project_task_2867_ae7fadd8 | Add new field in shipment SHIPPING_CHARGE | Sprint 2112 | 2021-03-15 | Development | Cellpoint: ecoATM API (P50) | Nick Foy | Danish Hassan | 1.33 | 100 |  |  | 1 | Complete | Cellpoint Corporation | 4655 | 1 | -0.33 | 0 | 240
__export__.project_task_2809_73eb575f | Remove the Chat button from CPBids apps | Sprint 2110 | 2021-03-01 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0.83 | 0 |  | 3.0.6 |  | Complete | Cellpoint Corporation | 4849 | 0 | -0.83 | 0 | 173.3083
__export__.project_task_2808_4fe1bc04 | cpbids test scripts and Android and IOS builds testing | Sprint 2110 | 2021-02-22 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 4 | 0 |  |  |  | Complete | Cellpoint Corporation | 4854 | 0 | -4 | 0.0076353 | 20.1157
__export__.project_task_2787_5e2ef4db | modify modules | Sprint 2110 | 2021-02-22 | Development | Moln: 3 New Portal Websites (P62) | Levi Barnes | Danish Hassan | 3.5 | 87.5 |  |  |  | Complete | Moln Solutions, LLC | 5007 | 4 | 0.5 | 0 | 135.4097
__export__.project_task_2780_6c819763 | Payment process surcharge - 3% Fee for Credit Card Transactions:Part-2 | Sprint 2110 | 2021-02-22 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Raheel Aslam | 11.13 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5020 | 8 | -3.13 | 88 | 135.4119
__export__.project_task_2760_0bfcd8d6 | Plan: Main | Sprint 2109 | 2021-02-15 | Development | PWX: Strategic Planning (P43) | Levi Barnes | Raheel Aslam | 1.67 | 41.75 |  |  |  | Complete | EquityTeam | 5094 | 4 | 2.33 | 0 | 96.7248
__export__.project_task_2623_8645dd47 | Remaining hours - Kanban view | Sprint 2110 | 2021-03-01 | Development | Silverdale: Help (P12) | Nick Foy | Raheel Aslam | 3.17 | 100 |  |  |  | Complete | Silverdale Technology LLC | 5500 | 3 | -0.17 | 0 | 250.535
__export__.project_task_2382_ab283628 | Startex Meeting (Timesheet) |  |  | Development | Silverdale: Help (P12) | Muhammad Afzaal | Faizan Zia Malik | 4 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 5738 | 0 | -4 | 0 | 72
__export__.project_task_2334_9d47b09c | Picklist Status | Sprint 2104 | 2021-01-18 | Development | Continuant: AV Warehouse (P34) | Nick Foy | Danish Hassan | 2.17 | 100 |  |  |  | Complete | Continuant | 5837 | 1.5 | -0.67 | 89.0862 | 263.1032
__export__.project_task_2286_ec9563e2 | Drop Down Values (Selection) Not being Transfered |  |  | Bug Fix | Continuant: Power BI Integration (P30) | Kaesi Lee | Muzher Siddique | 1.5 | 50 |  |  |  | Complete | Continuant | 5902 | 3 | 1.5 | 0 | 40
__export__.project_task_2267_448fcf24 | Introduction | Sprint 2103 | 2021-01-11 | Configuration | Silverdale: Help (P12) | Faisal Huda Khan | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5910 | 0 | 0 | 0.1567 | 22.1264
__export__.project_task_2151_95e03747 | Buyer Emails sent Incorrectly |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 11.5 | 88.46 |  | Difficulty 3 |  | Cancelled | Cellpoint Corporation | 6054 | 13 | 1.5 | 0 | 336.6299
NF Review
__export__.project_task_2130_afcaf018 | FW: You have been assigned to Edits to Recruitment Module (#45): CI survey link | Sprint 2107 | 2021-02-01 | Studio | PWX: Help (P23) | Levi Barnes | Levi Barnes | 0.25 | 0 |  |  |  | Complete | EquityTeam | 6072 | 0 | -0.25 | 0 | 326.3342
__export__.project_task_2127_55f2d4ba | Enable MRP | Sprint 2105 | 2021-01-25 | Configuration | Wild Leaf: Help (P22) | Nick Foy | Nick Foy | 1.67 | 0 |  | 2018-01-01 |  | Cancelled | Wild Leaf Beverage | 6073 | 0 | -1.67 | 152 | 160
__export__.project_task_2003_ff557dab | B.o.Ms |  |  | Configuration | KMI: Help (P41) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | KMI Zeolite | 6506 | 0 | 0 | 0 | 360
__export__.project_task_1886_469181af | Heronswood Deployment 2050 | Sprint 2050 | 2020-12-07 | Configuration | Heronswood: Events (P3) | Muzher Siddique | Muzher Siddique | 0.42 | 42 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 6583 | 1 | 0.58 | 4.9094e-06 | 1.6533
__export__.project_task_1649_4e463433 | API performance improvement |  |  |  | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Shajahan | 10 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 7072 | 0 | -10 | 0 | 384
__export__.project_task_1563_0975e0fa | Drprotect.com Redesign |  |  |  | Moln: Help (P16) | Levi Barnes | Fahad Hassan | 2 | 4.55 |  |  |  | Cancelled | Moln Solutions, LLC | 7513 | 44 | 42 | 72 | 480
__export__.project_task_1552_18b559bd | Website Content Updates | Sprint 2046 | 2020-11-09 | Configuration | Albers Vista (P20) | Levi Barnes |  | 0.17 | 0 |  |  |  | Complete | Albers Marcovina Vista Gardens | 7540 | 0 | -0.17 | 0.28181 | 62.3149
__export__.project_task_1493_8579b49a | staging server email | Sprint 2044 | 2020-10-26 | Configuration | Moln: Help (P16) | Kaesi Lee |  | 0.25 | 0 |  |  |  | Complete | Moln Solutions, LLC | 7876 | 0 | -0.25 | 6.7906 | 46.2542
__export__.project_task_1394_e4c42ba7 | Gucci: text update | Sprint 2041 | 2020-10-05 | Configuration | Moln: Help (P16) | Nick Foy |  | 0.25 | 100 |  |  |  | Complete | Moln Solutions, LLC | 8210 | 0.25 | 0 | 0 | 0
__export__.project_task_1386_998e030f | Gucci: Inventory by website | Sprint 2041 | 2020-10-05 | Development | Moln: Help (P16) | Gadha Continuant |  | 2 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8238 | 0 | -2 | 2.0481 | 18.0481
__export__.project_task_1374_bef32700 | Website looks broken on mobile |  |  |  | Moln: Help (P16) | Kaesi Lee | Gadha Continuant | 8 | 0 |  | Website |  | Cancelled | Moln Solutions, LLC | 8274 | 0 | -8 | 48 | 672
__export__.project_task_1255_51e2ab02 | AOA Website: Initial messaging change | Sprint 32 | 2020-09-21 | Configuration | Moln: Help (P16) | Kaesi Lee |  | 0.25 | 100 |  | Website |  | Complete | Moln Solutions, LLC | 8667 | 0.25 | 0 | 0 | 32
__export__.project_task_1249_33c59fa4 | old transactions showing up in authorize.net | Sprint 32 | 2020-09-21 | Bug Fix | Moln: Help (P16) | Kaesi Lee |  | 0.75 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8690 | 0 | -0.75 | 0 | 29.1064
__export__.project_task_1105_0ac04245 | Setup New Staging Server | Sprint 27 | 2020-08-17 | Configuration | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9469 | 0 | 0 | 0 | 0
__export__.project_task_252_89011e56 | Add Estimated Hours for Project | Sprint 28 | 2020-08-24 | Development | Silverdale: Help (P12) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 10396 | 0 | 0 | 0 | 0
__export__.project_task_208_929e4d85 | Auto Refresh - Web | Sprint 2042 | 2020-10-12 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10783 | 8 | 8 | 426.4342 | 642.4342
__export__.project_task_178_f7e6a039 | Scaleability Test |  |  |  | Cellpoint: Belmont Manifest API Integration (P6) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10809 | 0 | 0 | 0 | 0
__export__.project_task_4860_07a46b05 | Continuant Upgrade (Odoo) |  |  | Development | Continuant: Update Odoo to V14/15 (P211) | Fahad Hussain Malik | Muzher Siddique | 0 | 0 | Follow-up | 2015-09-01 |  | Planning | Continuant | 147 | 0 | 0 | 0 | 0
__export__.project_task_4851_b6b61fd7 | Product / Vendor set-up | Sprint 2137 | 2021-09-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 9 | 100 |  | SPLN |  | ELS | Zuma Sales LLC | 149 | 9 | 0 | 0 | 0
2021-09-09
__export__.project_task_4838_182bd6d6 | Share Data with Odoo for Sponsorship Showcase | Sprint 2138 | 2021-09-13 | Creative | Odoo Experience 2021 (P208) | Muhammad Zubair | Erin Olson | 0 | 0 | Get approval from Nick |  |  | In Progress | Silverdale Technology LLC | 169 | 0 | 0 | 0 | 0
__export__.project_task_4836_5cd0ea7d | Go-live day check in | Sprint 2138 | 2021-09-13 | Client Meetings | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 | Followup | 2020-09-01 |  | Backlog | Zuma Sales LLC | 170 | 1 | 1 | 0 | 0
Asfand
__export__.project_task_4834_7b6c80e4 | Master data confirmation run through | Sprint 2138 | 2021-09-13 | Demo to the client | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 | This task missed the deadline! | 2015-09-01 |  | In Progress | Zuma Sales LLC | 170 | 1 | 1 | 0 | 0
Your task missed the deadline!
Close ticket after demo
Asfand
__export__.project_task_4829_267b04bc | Remove Odoo standard COAs | Sprint 2137 | 2021-09-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0.5 | 100 |  | SPLN |  | ELS | Zuma Sales LLC | 171 | 0.5 | 0 | 0 | 0
__export__.project_task_4777_d1d96d9b | Internal Presentations for new features to have a hands on on October 9th |  |  | Internal Time Tracking | Odoo Experience 2021 (P208) | Muhammad Zubair |  | 0 | 0 | Plan Event |  |  | Planning | Silverdale Technology LLC | 293 | 0 | 0 | 6.0178e-06 | 0
__export__.project_task_4712_88f76949 | Activity - Helpdesk Process Review - Existing |  |  | Internal Meetings | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Close after review |  |  | In Progress | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 0
__export__.project_task_4710_b6a647aa | Process Documentation - Client Helpdesk Onboarding | Sprint 2137 | 2021-09-06 | Documentation | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 |  | SPLN |  | Complete | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 88.3911
__export__.project_task_4646_831063ea | Landed Cost Demo |  |  | Demo to the client | Wild Leaf: Help (P22) | Mir Muhammad Muzammil |  | 1 | 100 |  |  |  | Complete | Wild Leaf Beverage | 537 | 1 | 0 | 0 | 25.1678
__export__.project_task_4635_4d67fe6b | create new menu for user server action that will be visible without debug mode | Sprint 2135 | 2021-08-23 | Development | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Danish Hassan | 4 | 100 |  | SPLN |  | Complete | Wild Leaf Beverage | 634 | 4 | 0 | 0 | 93.4208
__export__.project_task_4541_45377ff5 | Change domain for Sales Order selection in Project module | Sprint 2134 | 2021-08-16 | Development | Silverdale: Help (P12) | Muhammad Zubair | Muzher Siddique | 3 | 85.71 |  | SPLN |  | Complete | Silverdale Technology LLC | 804 | 3.5 | 0.5 | 48.0011 | 85.4242
__export__.project_task_4390_7003e668 | Print Master Carton label and attach to carton | Sprint 2132 | 2021-08-02 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Muhammad Bilal | 8.67 | 86.7 |  |  | 3 | Complete | Cellpoint Corporation | 1154 | 10 | 1.33 | 0 | 88
__export__.project_task_4316_2f84b4e5 | Upload Data of trip collection from Excel | Sprint 2136 | 2021-08-30 | Configuration | Heronswood: Collectors Database Phase 1 (P142) | Naseeb Razaq | Farman Ahmad Cheema | 8.25 | 100 |  | SPLN |  | Complete | Port Gamble Sâ€™Klallam Foundation | 1489 | 7 | -1.25 | 0 | 320.9458
__export__.project_task_4200_5009b4a0 | Internal Review of Results | Sprint 2132 | 2021-08-02 | Other | CraftAG: Odoo Audit (P147) | Fahad Hussain Malik | Fahad Hussain Malik | 2 | 100 |  |  |  | Complete | CraftAG | 1798 | 2 | 0 | 143.2536 | 204.1728
__export__.project_task_4196_e24024e6 | Conduct Master Data Coverage Review | Sprint 2132 | 2021-08-02 | Other | CraftAG: Odoo Audit (P147) | Fahad Hussain Malik | Asfand Yaar | 3 | 100 |  |  |  | Complete | CraftAG | 1798 | 3 | 0 | 143.3231 | 232.0192
__export__.project_task_4107_3438db4f | TC-250-256 Purchase Module | Sprint 2131 | 2021-07-26 | Development | Silverdale: Devops (P84) | Muzher Siddique | Wishal Nasir | 5 | 71.43 | Decide validity | SPLN |  | Backlog | Silverdale Technology LLC | 1974 | 7 | 2 | 441.0932 | 0
__export__.project_task_4083_3df8ca9d | Set up Employee module | Sprint 2129 | 2021-07-12 | Configuration | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Naseeb Razaq | 0.25 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 2048 | 0.25 | 0 | 0 | 113.4621
__export__.project_task_4035_92e18555 | Upload Costs on Product Master/ Staging |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 0.67 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2144 | 0 | -0.67 | 0 | 4
__export__.project_task_4034_438df078 | Export Current Inventories with Location, Lots, Package and Owner/ Staging |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 0.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2144 | 0 | -0.25 | 0 | 4
__export__.project_task_4023_b4860dc5 | Customer Scripts(Test Plan): Add server field |  |  | Development | Silverdale: SDET (P132) | Levi Barnes | Aleem khan | 0.75 | 75 |  |  | 1 | Complete | Silverdale Technology LLC | 2164 | 1 | 0.25 | 0 | 377.5102
__export__.project_task_3973_db35f7d8 | Modify the Existing Portal Account format for Agents | Sprint 2131 | 2021-07-26 | Development | MMH: Affiliate Program Setup (P96) | Naseeb Razaq | Danish Hassan | 6.75 | 100 |  | SPLN | 2 | Complete | Mountain Meadow Herbs | 2234 | 6 | -0.75 | 0 | 344.0192
__export__.project_task_3929_b32d39cd | Get credentials for DNS setup | Sprint 2123 | 2021-05-31 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  | Odoo.sh Migration |  | Complete | Zuma Sales LLC | 2333 | 0 | 0 | 214.1225 | 35.17
__export__.project_task_3913_b7e7dd31 | Wishlist alphabetized | Sprint 2126 | 2021-06-21 | Development | Mid-America: Help (P37) | Naseeb Razaq | Raheel Aslam | 6.25 | 100 |  | SPLN | 2 | Complete | Mid-America Gardens, LLC | 2364 | 4 | -2.25 | 0 | 118.6594
__export__.project_task_3903_0468bdc7 | Apply Down Payment on Multiple invoices | Sprint 2129 | 2021-07-12 | Development | Wild Leaf: Partial Deposits and Partial Credit Reconciliation (P139) | Mir Muhammad Muzammil | Raheel Aslam | 44.75 | 100 |  | SPLN | 4 | Complete | Wild Leaf Beverage | 2402 | 31 | -13.75 | 236.885 | 320.0192
__export__.project_task_3899_f7cbc068 | Upload multiple approved design in Sales Order ¦ Insurance details in Purchase Order | Sprint 2124 | 2021-06-07 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 4.75 | 95 |  |  | 2 | Complete | Perfect Golf Event | 2407 | 5 | 0.25 | 0 | 82.9344
__export__.project_task_3882_ff8c9428 | making sure we have a search bar in or near the header on every page | Sprint 2125 | 2021-06-14 | Development | MMH: Website Edits June 2021 (P120) | Naseeb Razaq | Muhammad Bilal | 6.67 | 95.29 |  |  | 2 | Complete | Mountain Meadow Herbs | 2496 | 7 | 0.33 | 0 | 152
__export__.project_task_3873_b01ec143 | Sales Order Lines Analytical Accounts | Sprint 2124 | 2021-06-07 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair |  | 10.97 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 2525 | 8.8333 | -2.1367 | 30.1152 | 112.5677
__export__.project_task_3869_8fd21e40 | R & D: web based buyer notifications don't have any pop up or count. |  |  | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Kaleem Khan | 19 | 79.17 | Please add next activity |  | 3 | Backlog | Cellpoint Corporation | 2531 | 24 | 5 | 456 | 0
__export__.project_task_3840_4746da35 | Transactions ID to show on invoices report | Sprint 2124 | 2021-06-07 | Development | Heronswood: Help (P54) | Naseeb Razaq | Danish Hassan | 9.5 | 100 |  |  | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 2669 | 7.5 | -2 | 0.032948 | 121.1085
__export__.project_task_3819_e44efa0f | Wildleaf critical functionalities automation |  |  | Development | Silverdale: Devops (P84) | Levi Barnes | Muhammad Saqlain Alam | 25.17 | 0 |  |  |  | Complete | Silverdale Technology LLC | 2831 | 0 | -25.17 | 0 | 102.9764
__export__.project_task_3696_60395d2e | Whenever priority gets changed, it should be visible in chatter | Sprint 2121 | 2021-05-17 | Development | Silverdale: Help (P12) | Muhammad Afzaal | Danish Hassan | 1.92 | 76.8 |  |  | 1 | Complete | Silverdale Technology LLC | 2908 | 2.5 | 0.58 | 0 | 56
__export__.project_task_3654_f100530f | Check email logs on email send statistics and share with client | Sprint 2124 | 2021-06-07 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 1.5 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.16667 | -1.3333 | 0.00052273 | 169.9839
__export__.project_task_3491_d5b023a7 | Perfect Golf Meeting |  |  | Internal Time Tracking | Perfect Golf: Help (P99) | Naseeb Razaq |  | 16.37 | 0 |  |  |  | Complete | Perfect Golf Event | 3480 | 0 | -16.37 | 461.1844 | 461.1861
__export__.project_task_3437_a9a8ab39 | Add chart of accounts |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3484 | 0 | 0 | 461.1711 | 520.1997
__export__.project_task_3387_577c0844 | For MMHerbs Create Transactions the company deals in |  |  | Functionality Test | MMH: Odoo Audit (P100) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Mountain Meadow Herbs | 3531 | 0 | 0 | 0 | 168
__export__.project_task_3343_57e57706 | Upload the data for Vendor and Customer numbers | Sprint 2117 | 2021-04-19 | Development | Wild Leaf: Help (P22) | Jeff Gross |  | 0.25 | 3.12 |  |  |  | Cancelled | Wild Leaf Beverage | 3722 | 8 | 7.75 | 0 | 8
__export__.project_task_3335_6c8e48f4 | create vendor registration web form |  |  |  | PWX: HR (P61) | Levi Barnes |  | 0 | 0 |  |  |  | Cancelled | EquityTeam | 3749 | 0 | 0 | 0 | 48.3992
__export__.project_task_3221_912ee909 | Icon alignment and font size should be uniform | Sprint 2116 | 2021-04-12 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 5.17 | 100 |  |  | 2 | Complete | Cellpoint Corporation | 4206 | 4 | -1.17 | 0.059807 | 138.2037
__export__.project_task_3021_2c2bc4de | The description of products in invoice should be visible or hide using radio button | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Muhammad Bilal | 0.75 | 75 |  |  |  | Complete | Mid-America Gardens, LLC | 4402 | 1 | 0.25 | 0 | 73.9718
__export__.project_task_2999_1088325a | Add Evaluate button on Application form and attach URL link | Sprint 2113 | 2021-03-22 | Development | PWX: Survey (P70) | Levi Barnes | Raheel Aslam | 7.25 | 100 |  |  | 3 | Complete | EquityTeam | 4428 | 6 | -1.25 | 0 | 198.9687
__export__.project_task_2887_c6cf4e42 | Kick-Off Run Through Session |  |  |  | DISCOVERY (P76) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1050.1624
__export__.project_task_2761_e5a295ac | Themes: Main | Sprint 2109 | 2021-02-15 | Development | PWX: Strategic Planning (P43) | Levi Barnes | Raheel Aslam | 2.67 | 61.62 |  |  |  | Complete | EquityTeam | 5094 | 4.3333 | 1.6633 | 0 | 96.7261
__export__.project_task_2437_60429ffa | PO forecast Setup Requirements |  |  | Requirements Collection | Wild Leaf: PO Forecast Setup Requirements (P175) | Naseeb Razaq |  | 0 | 0 |  |  |  | New | Wild Leaf Beverage | 5589 | 0 | 0 | 1272.6968 | 0
__export__.project_task_2357_da63c9ac | Startex Daily Requirements Review / Writing (Timesheet) |  |  | Development | Silverdale: Help (P12) | Muhammad Afzaal | Faizan Zia Malik | 8 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 5763 | 0 | -8 | 0 | 80
__export__.project_task_2332_fbb4ac07 | Create Room from Pick List Form View | Sprint 2108 | 2021-02-08 | Development | Continuant: AV Warehouse (P34) | Nick Foy | Danish Hassan | 0.5 | 75 |  |  |  | Cancelled | Continuant | 5837 | 0.66667 | 0.16667 | 89.1589 | 135.6781
__export__.project_task_2272_a3e1fc17 | eCommerce |  |  | Internal Training | Silverdale: Help (P12) | Faisal Huda Khan | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5910 | 0 | 0 | 0.0028365 | 366.067
__export__.project_task_2222_0c0d39c6 | Record Views - Contacts>Units: unit main | Sprint 2107 | 2021-02-01 | Development | PWX: Property (P58) | Levi Barnes | Raheel Aslam | 10.75 | 100 |  |  |  | Complete | EquityTeam | 5996 | 8.3333 | -2.4167 | 0 | 302.3339
__export__.project_task_2219_97fccb88 | Use Export / Import to change the company of operations | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy |  | 0.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5998 | 0 | -0.25 | 0 | 90.9642
__export__.project_task_2088_aa026d0f | FW: You have been assigned to KPI Balance Scorecard App or Develop? (copy) | Sprint 2103 | 2021-01-11 | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 0 | 0 |  |  |  | Complete | EquityTeam | 6190 | 0 | 0 | 0 | 181.59
__export__.project_task_1856_45980437 | Android and IOS Builds for testing |  |  | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 2 | 0 |  |  |  | Complete | Cellpoint Corporation | 6702 | 0 | -2 | 0 | 169.861
__export__.project_task_1822_d2b9ba9b | CPBids to Azure for Belmont: Create and Test Connection |  |  | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0.42 | 84 |  |  |  | Complete | Cellpoint Corporation | 6764 | 0.5 | 0.08 | 0 | 173.4408
__export__.project_task_1793_33c61e5c | Add Planned End DateTime as a Filter option | Sprint 2103 | 2021-01-11 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 1.75 | 100 |  |  |  | Complete | Cellpoint Corporation | 6836 | 1.5 | -0.25 | 0 | 320
__export__.project_task_1781_af6d7331 | Drag and Drop Pictures | Sprint 2052 | 2020-12-21 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 5 | 100 |  |  |  | Complete | Cellpoint Corporation | 6836 | 0.5 | -4.5 | 0 | 180.7586
__export__.project_task_1716_aba74eb2 | R2 Yes/No and R2 Expiry Date Fields |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 0.5 | 100 |  |  |  | Complete | Cellpoint Corporation | 6887 | 3.5 | -10.17 | 0 | 196.7667
__export__.project_task_1714_1f46904f | Overdue Filter should only show overdue Activities | Sprint 2110 | 2021-03-01 | Development | Silverdale: Help (P12) | Muzher Siddique | Raheel Aslam | 2.58 | 100 |  |  |  | Complete | Silverdale Technology LLC | 6890 | 2.5 | -0.08 | 0 | 586.5431
__export__.project_task_1697_4fe69cdb | Create WLB Filling Products | Sprint 2050 | 2020-12-07 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 0.5 | 50 |  |  |  | Complete | Wild Leaf Beverage | 6910 | 1 | 0.5 | 0 | 71.5278
__export__.project_task_1621_6d7bf383 | New Seller Onboarding: EcoATM: Buyer Set-Up | Sprint 2048 | 2020-11-23 | Configuration | CPBids: ecoATM Onboarding (P35) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 7223 | 0 | 0 | 0 | 656
__export__.project_task_1558_00fb07b3 | Website links go to mambotango | Sprint 2045 | 2020-11-02 | Bug Fix | Albers Vista (P20) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Albers Marcovina Vista Gardens | 7533 | 0 | 0 | 0 | 16
__export__.project_task_1432_7410ea55 | emails going to spam | Sprint 2043 | 2020-10-19 | Configuration | Moln: Help (P16) | Levi Barnes |  | 1.5 | 0 |  | Email Configuration |  | Complete | Moln Solutions, LLC | 8020 | 0 | -1.5 | 32.0721 | 63.8152
__export__.project_task_1369_d480ed20 | Showing wrong thumbail when shared | Sprint 2041 | 2020-10-05 | Configuration | Moln: Help (P16) | Kaesi Lee |  | 0.5 | 0 |  | Website |  | Complete | Moln Solutions, LLC | 8287 | 0 | -0.5 | 7.0931 | 10.7161
__export__.project_task_1349_4380ca38 | Product Import | Sprint 2041 | 2020-10-05 | Configuration | Wild Leaf: Help (P22) | Nick Foy |  | 5 | 100 |  |  |  | Complete | Wild Leaf Beverage | 8398 | 2 | -3 | 0 | 72
__export__.project_task_1284_7c2a7f3f | Remove Winning Bid: PKYNR | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Kaesi Lee | Apps Maven | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8548 | 0 | 0 | 93.8964 | 93.8931
__export__.project_task_1223_a14aecc7 | New Product Creation: Default Websites Selection | Sprint 31 | 2020-09-14 | Development | Moln: Help (P16) | Kaesi Lee |  | 1 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8765 | 0 | -1 | 8.6269 | 24.6269
__export__.project_task_1217_d4d838ba | enable blog for AOA | Sprint 32 | 2020-09-21 | Configuration | Moln: Help (P16) | Gadha Continuant |  | 6 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8781 | 0 | -6 | 48 | 64
__export__.project_task_1171_5cb9187e | google analytics + tags | Sprint 31 | 2020-09-14 | Development | Moln: Help (P16) | Gadha Continuant |  | 1.5 | 100 |  |  |  | Complete | Moln Solutions, LLC | 9096 | 0.5 | -1 | 83.2786 | 0
__export__.project_task_1143_1be410f1 | Clone website and point new DNS settings to it | Sprint 28 | 2020-08-24 | Development | Moln: Help (P16) | Nick Foy |  | 8 | 100 |  |  |  | Complete | Moln Solutions, LLC | 9240 | 8 | 0 | 0 | 0
__export__.project_task_1040_054597a3 | Change title to "All Lots" | Sprint 28 | 2020-08-24 | Development | CPBids Migration AWS->odoo (P5) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 88.8531 | 0
__export__.project_task_168_a8ea4fd4 | Initial Document |  |  |  | Cellpoint: Belmont Manifest API Integration (P6) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11553 | 0 | 0 | 0 | 0
__export__.project_task_4837_5b576011 | Set up Casselton Warehouse | Sprint 2137 | 2021-09-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0.25 | 100 |  | SPLN |  | ELS | Zuma Sales LLC | 170 | 0.25 | 0 | 0 | 0
__export__.project_task_4820_839a1805 | Inventory Training | Sprint 2138 | 2021-09-13 | Client Meetings | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 2 | 100 | Close ticket | 2014-09-01 |  | Complete | Zuma Sales LLC | 171 | 2 | 0 | 0 | 32.9543
Asfand
__export__.project_task_4776_6434e798 | Attend Odoo Experience 2021 on October 6th and 7th |  |  | Internal Time Tracking | Odoo Experience 2021 (P208) | Muhammad Zubair |  | 0 | 0 | Create Calendar Entries |  |  | Planning | Silverdale Technology LLC | 293 | 0 | 0 | 0 | 0
__export__.project_task_4713_37e059cb | Set up Tools - Making helpdesk phone ready |  |  | Internal Training | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Do a test run of phone process. |  |  | Planning | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 0
__export__.project_task_4709_bf435065 | Process Documentation - Customer Touch Points - Helpdesk | Sprint 2137 | 2021-09-06 | Documentation | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 |  | SPLN |  | Complete | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 88.3911
__export__.project_task_4633_a4f0885a | Activity Types and Task types Means |  |  | Internal Time Tracking | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair |  | 1.5 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 701 | 0 | -1.5 | 31.3039 | 0
__export__.project_task_4504_ef868ebb | Export Customer(Sales) Orders to SFTP |  |  | Development | Zuma: Odoo Implementation Phase 2 (P204) | Asfand Yaar | Aleem khan | 3 | 42.86 |  |  |  | QA | Zuma Sales LLC | 871 | 7 | 4 | 113.3408 | 0
__export__.project_task_4431_c0b6dc50 | Allow Changing state of Sale order after Confirmation | Sprint 2135 | 2021-08-23 | Development | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Danish Hassan | 7.92 | 100 |  | SPLN |  | Complete | Wild Leaf Beverage | 1017 | 7.9167 | -0.0033333 | 0 | 181.4208
__export__.project_task_4430_2877e560 | Rippling Integration Requirements |  |  | Configuration | Wild Leaf: Rippling Payroll Integration (P39) | Naseeb Razaq | Naseeb Razaq | 0 | 0 | Please add next activity |  |  | Backlog | Wild Leaf Beverage | 1032 | 2 | 2 | 162.6577 | 0
__export__.project_task_4276_fcb5b7ef | Amazon Connector Testing |  |  | Development | MMH: Amazon Module Automation (P102) | Naseeb Razaq | Fahad Hassan | 0.67 | 3.35 | Please add next activity |  |  | Backlog | Mountain Meadow Herbs | 1657 | 20 | 19.33 | 0 | 0
__export__.project_task_4239_ce1a9f8f | Create a Schedule Model in Attendance (Day Based) - Name + Date + Working Schedule Connection to Attendance Records | Sprint 2129 | 2021-07-12 | Development | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Aleem khan | 9.25 | 44.05 |  | SPLN | 3 | Complete | Port Gamble Sâ€™Klallam Foundation | 1661 | 21 | 11.75 | 0 | 185.3716
__export__.project_task_4199_c43ae700 | Review With Client | Sprint 2135 | 2021-08-23 | Configuration | CraftAG: Odoo Audit (P147) | Fahad Hussain Malik | Naseeb Razaq | 0 | 0 |  | SPLN |  | Cancelled | CraftAG | 1798 | 1 | 1 | 137.7745 | 361.2062
__export__.project_task_4114_59916136 | Contact us and About us Migration | Sprint 2127 | 2021-06-28 | Development | DGS: Odoo Website Migration (P126) | Fahad Hussain Malik | Danish Hassan | 1.33 | 44.33 |  | SPLN | 2 | Complete | DG Solutions Inc. | 1973 | 3 | 1.67 | 0.72678 | 88.7268
__export__.project_task_4091_6e2c66ab | Analyse the code quality in custom modules | Sprint 2128 | 2021-07-05 | Improvements | DGS: Odoo Audit and v14 Upgrade Estimate (P136) | Fahad Hussain Malik | Fahad Hussain Malik | 6 | 75 |  | SPLN |  | Complete | DG Solutions Inc. | 2021 | 8 | 2 | 46.0665 | 72.4462
__export__.project_task_4067_73c59c11 | Woocommerce Connector for buying |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 | Request Andrew for buying this connector |  |  | Backlog | Mountain Meadow Herbs | 2048 | 0 | 0 | 0 | 0
__export__.project_task_4020_611b20f1 | Master Script: add module field |  |  | Development | Silverdale: SDET (P132) | Levi Barnes | Aleem khan | 1.33 | 33.25 |  |  | 1 | Complete | Silverdale Technology LLC | 2164 | 4 | 2.67 | 0 | 377.5578
__export__.project_task_3991_6c137c3c | Continuant Brand the Portal (have their colors in the top bar) | Sprint 2131 | 2021-07-26 | Development | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Aleem khan | 4.33 | 86.6 |  | SPLN | 1 | Complete | Continuant | 2210 | 5 | 0.67 | 189.4731 | 312.0192
__export__.project_task_3921_721613b0 | Apply Partial Reconciliation Amount on Invoices | Sprint 2129 | 2021-07-12 | Development | Wild Leaf: Partial Deposits and Partial Credit Reconciliation (P139) | Muhammad Zubair | Raheel Aslam | 25.6 | 85.33 |  | SPLN | 4 | Complete | Wild Leaf Beverage | 2351 | 30 | 4.4 | 126 | 261
__export__.project_task_3917_49fd8729 | Upgrade to v14 | Sprint 2125 | 2021-06-14 | Other | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Aleem khan | 7.58 | 89.18 | COE | Odoo Migration |  | Complete | Zuma Sales LLC | 2356 | 8.5 | 0.92 | 221.0725 | 80.065
__export__.project_task_3881_5d4d00ce | moving the social media icons to the footer section. We also need to add some like Pinterest and Tik Tok | Sprint 2125 | 2021-06-14 | Development | MMH: Website Edits June 2021 (P120) | Naseeb Razaq | Danish Hassan | 6.5 | 92.86 |  |  | 2 | Complete | Mountain Meadow Herbs | 2496 | 7 | 0.5 | 0 | 152
__export__.project_task_3874_02ca2ce4 | New Stage for Approved Design |  |  | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 4 | 100 |  |  | 2 | Complete | Perfect Golf Event | 2520 | 4 | 0 | 0 | 104
__export__.project_task_3872_a5e63122 | New inventory valuation view | Sprint 2124 | 2021-06-07 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Raheel Aslam | 9.67 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 2525 | 7 | -2.67 | 30.1572 | 120.6097
__export__.project_task_3867_cbbb0740 | Add Event Details on Sales Quotation | Sprint 2122 | 2021-05-24 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 4.58 | 100 |  |  | 1 | Complete | Perfect Golf Event | 2569 | 4.5 | -0.08 | 0 | 24
__export__.project_task_3856_f612fbd1 | Export Button, ListView Table Header, Display Issue and Typo-Fix | Sprint 2138 | 2021-09-13 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Sajjad Hussain | 4.33 | 86.6 | review | 2015-09-01 |  | Peer Review | Cellpoint Corporation | 2576 | 5 | 0.67 | 472.0483 | 0
__export__.project_task_3697_7454fd6f | Install Modules needed from Workstream Module Plan | Sprint 2121 | 2021-05-17 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Perfect Golf Event | 2906 | 0 | 0 | 0 | 0
__export__.project_task_3656_51ad05d3 | Check on Client email sending service (smtp) | Sprint 2124 | 2021-06-07 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq | Muhammad Bilal | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.5 | 0.5 | 0 | 153.8116
__export__.project_task_3436_f491d70e | Add finance companies |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3484 | 0 | 0 | 461.1772 | 520.2058
__export__.project_task_3413_d348467f | R & D Group By filter in Cash Flow Statement, Trail Balance and General Ledger |  |  | Development | Wild Leaf: Financial statement pivot views and filters (P116) | Naseeb Razaq | Muhammad Bilal | 12.5 | 100 |  |  | 4 | New | Wild Leaf Beverage | 3504 | 12.5 | 0 | 770.8457 | 0
__export__.project_task_3403_6448900c | A Player Agreement | Sprint 2123 | 2021-05-31 | Other | Silverdale: Help (P12) | Muhammad Afzaal | Muhammad Afzaal | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3507 | 0 | 0 | 0 | 344
__export__.project_task_3401_99893b8a | Create training video for volunteers with portal access | Sprint 2117 | 2021-04-19 | Demo to the client | Heronswood: Volunteer On-boarding (P79) | Jeff Gross |  | 13.33 | 100 |  | MA Review |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3510 | 6 | -7.33 | 0 | 153.4646
__export__.project_task_3388_6aa1c56e | For Unity Research Create Transactions the company deals in |  |  | Functionality Test | MMH: Odoo Audit (P100) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Mountain Meadow Herbs | 3531 | 0 | 0 | 0 | 168
__export__.project_task_3372_b86212bd | Business Processes and the modules used by every company |  |  | Improvements | MMH: Odoo Audit (P100) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Mountain Meadow Herbs | 3574 | 0 | 0 | 0 | 184
__export__.project_task_3327_ebc5ca64 | On-Site Support |  |  | Internal Time Tracking | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 77 | 0 |  |  |  | Complete | Wild Leaf Beverage | 3841 | 0 | -77 | 0 | 80
__export__.project_task_3225_ea4c1630 | WildLeaf Daily Meeting |  |  | Other | Wild Leaf: Help (P22) | Umer Farooq |  | 164.73 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 4202 | 0 | -164.73 | 0 | 568
__export__.project_task_3033_8c3d7997 | Invoice Status Paid/Unpaid on Sales Order |  |  | Development | Mid-America: Help (P37) | Levi Barnes | Muhammad Bilal | 1.92 | 48 |  |  |  | Complete | Mid-America Gardens, LLC | 4378 | 4 | 2.08 | 0 | 66.7976
__export__.project_task_2889_2d735070 | Send Kick-Off Invite |  |  |  | DISCOVERY (P76) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1050.1568
__export__.project_task_2875_c691db95 | Relate applicant and surveys | Sprint 2113 | 2021-03-22 | Development | PWX: Survey (P70) | Levi Barnes | Raheel Aslam | 6.08 | 100 |  |  | 3 | Complete | EquityTeam | 4589 | 5 | -1.08 | 0 | 233.1178
__export__.project_task_2846_492f319f | Add RCA(Root Case Analysis) On Helpdesk Ticket | Sprint 2110 | 2021-03-01 | Development | Silverdale: Help (P12) | Nick Foy | Danish Hassan | 2.33 | 77.67 |  |  |  | Complete | Silverdale Technology LLC | 4687 | 3 | 0.67 | 0.011679 | 61.0381
__export__.project_task_2829_8faf1b49 | Add R2 Certified to Belmont Buyer View | Sprint 2110 | 2021-03-01 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 3.33 | 100 |  | 3.0.6 |  | Complete | Cellpoint Corporation | 4723 | 1.3333 | -1.9967 | 0 | 111.0856
__export__.project_task_2786_62f81582 | duplicate website | Sprint 2110 | 2021-02-22 | Development | Moln: 3 New Portal Websites (P62) | Levi Barnes | Danish Hassan | 8.5 | 100 |  |  |  | Complete | Moln Solutions, LLC | 5007 | 6 | -7.25 | 0 | 135.4156
__export__.project_task_2752_5f3444be | CPBids Web: CPBIDS Bot Menu should be hidden for non-login users | Sprint 2110 | 2021-03-01 | Improvements | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Muhammad Bilal | 3 | 42.86 |  |  |  | Complete | Cellpoint Corporation | 5136 | 7 | 4 | 0 | 168
__export__.project_task_2738_07b18a04 | Create an Activity type of "Create Deposit Invoice" | Sprint 2109 | 2021-02-15 | Development | Wild Leaf: Accounting (P64) | Nick Foy | Danish Hassan | 0.5 | 66.67 |  |  |  | Complete | Wild Leaf Beverage | 5180 | 0.75 | 0.25 | 0 | 110.4764
__export__.project_task_2633_db53d8f5 | Change the Belmont Invoice API check for Lot References |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 8.33 | 100 |  |  |  | Complete | Cellpoint Corporation | 5469 | 5.5 | -8.5 | 0 | 287.1614
__export__.project_task_2345_a5130ba1 | Internal: Project UX Review |  |  | Other | Continuant: Quotation Management / Automation (P31) | Nick Foy | Nick Foy | 1.17 | 100 |  |  |  | Cancelled | Continuant | 5809 | 1.1667 | -0.0033333 | 88 | 160
__export__.project_task_2210_e0ea96b2 | Move open Sales orders to OpCo and relevant warehouse | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy |  | 2 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5998 | 0 | -2 | 0 | 90.9628
__export__.project_task_2147_0e65a150 | 2106: Test Scripts/QA: Tasks Result |  |  | Development | Silverdale: Help (P12) | Muhammad Afzaal | Danish Hassan | 2 | 100 |  |  |  | Cancelled | Silverdale Technology LLC | 6056 | 2 | 0 | 3.1367 | 353.8586
__export__.project_task_2091_3ecf19fa | FW: You have been assigned to remove "login as Odoo" from ALL SITES (#46) |  |  | Configuration | PWX: Help (P23) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | EquityTeam | 6190 | 0 | 0 | 0 | 181.5889
__export__.project_task_2062_1aff0733 | FW: Issue with GUI Editor Marketing Automation |  |  | Bug Fix | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 3.08 | 100 |  |  |  | Complete | EquityTeam | 6224 | 3 | -0.08 | 0 | 466.9229
__export__.project_task_2059_fda33019 | How to link Purchase Orders and Sales Orders through Replenishment Requirements |  |  | Configuration | Wild Leaf: Help (P22) | Nick Foy | Nick Foy | 0 | 0 |  | Difficulty 2 |  | Cancelled | Wild Leaf Beverage | 6236 | 0 | 0 | 192 | 200
__export__.project_task_2038_c224e024 | Manufacturing Orders |  |  | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 1 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6382 | 0 | -1 | 0 | 119.3492
__export__.project_task_1874_d9966ea4 | Filter by Tag | Sprint 2103 | 2021-01-11 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 2.5 | 100 |  |  |  | Complete | Cellpoint Corporation | 6600 | 2.5 | 0 | 0 | 272
__export__.project_task_1613_08a69123 | Tuesday |  |  | Configuration | Silverdale: Help (P12) | Muzher Siddique |  | 125.98 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 7243 | 0 | -125.98 | 0 | 428.8889
__export__.project_task_1441_5402385a | Data migration from AWS to Odoo: Lots | Sprint 2043 | 2020-10-19 | Configuration | Cellpoint CPBids: Help (P7) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 7997 | 0 | 0 | 0 | 40
__export__.project_task_1437_2e26839b | BoMs |  |  | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 14.58 | 0 |  |  |  | Complete | Wild Leaf Beverage | 8019 | 0 | -22.75 | 0 | 404
__export__.project_task_1376_0d3fefad | Change website image for Gucci.weshield.us | Sprint 2041 | 2020-10-05 | Configuration | Moln: Help (P16) | Nick Foy |  | 0.25 | 100 |  | Website |  | Complete | Moln Solutions, LLC | 8264 | 0.25 | 0 | 0 | 4
__export__.project_task_1324_46358d21 | clone AOA to AAO | Sprint 2041 | 2020-10-05 | Configuration | Moln: Help (P16) | Kaesi Lee |  | 1 | 100 |  |  |  | Complete | Moln Solutions, LLC | 8402 | 1 | 0 | 14.8456 | 53.8142
__export__.project_task_1289_fe1b7925 | Inventory in packsizes | Sprint 2041 | 2020-10-05 | Configuration | Moln: Help (P16) | Nick Foy |  | 2 | 0 |  | Inventory |  | Complete | Moln Solutions, LLC | 8523 | 0 | -2 | 0 | 62.5456
__export__.project_task_1256_a7ff918f | AOA Website: Add Special Pricing Available language | Sprint 32 | 2020-09-21 | Configuration | Moln: Help (P16) | Kaesi Lee |  | 0.25 | 6.25 |  | Website |  | Complete | Moln Solutions, LLC | 8667 | 4 | 3.75 | 0 | 32
__export__.project_task_1216_f37132ba | can we use different payment acquirers across different sites? | Sprint 31 | 2020-09-14 | Configuration | Moln: Help (P16) | Nick Foy |  | 0.25 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8782 | 0 | -0.25 | 0 | 0
__export__.project_task_1203_beb94e3d | Manifest for Web and Mobile Auctions | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8799 | 0 | 0 | 0 | 88
__export__.project_task_1043_cbed939a | Remove Information tab "Lot Category" Field | Sprint 28 | 2020-08-24 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 1064
__export__.project_task_245_89c4ced6 | Send Emails to Buyers | Sprint 27 | 2020-08-17 | Development | Silverdale: Help (P12) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 10427 | 0 | 0 | 4.5506 | 0
__export__.project_task_191_81405e90 | odoo-> PowerBI data transfer |  |  |  | Cellpoint: Belmont Manifest API Integration (P6) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10806 | 2 | 2 | 113.6369 | 0
__export__.project_task_166_58497448 | 1.6.2 lot reference#(30 Minutes) | Sprint 27 | 2020-08-17 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 0
__export__.project_task_4824_07d5a882 | Import final list of vendors | Sprint 2137 | 2021-09-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 2 | 100 |  | SPLN |  | ELS | Zuma Sales LLC | 171 | 2 | 0 | 0 | 0
__export__.project_task_4775_b0ee899c | 300x Social Media Posts about Odoo 15 Release and Odoo Experience |  |  | Creative | Odoo Experience 2021 (P208) | Muhammad Zubair | Erin Olson | 0 | 0 | Discuss | Marketing |  | Planning | Silverdale Technology LLC | 293 | 0 | 0 | 0 | 0
__export__.project_task_4714_f7b241a1 | Activity - Cares Team Email Signatures |  |  | Creative | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 82.7436
__export__.project_task_4576_17892bda | Signoff on UAT/Training for all modules | Sprint 2138 | 2021-09-13 | Client Meetings | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 4.83 | 48.3 | Schedule meeting | 2016-09-01 |  | Backlog | Zuma Sales LLC | 799 | 10 | 5.17 | 0 | 0
Close ticket
__export__.project_task_4502_235f529c | Export SKU/Part Master to SFTP |  |  | Development | Zuma: Odoo Implementation Phase 2 (P204) | Asfand Yaar | Aleem khan | 2.33 | 33.29 |  |  |  | QA | Zuma Sales LLC | 871 | 7 | 4.67 | 113.3506 | 0
__export__.project_task_4403_e46cef7b | Print Pallet Label and attach to Pallet | Sprint 2132 | 2021-08-02 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Muhammad Bilal | 3.5 | 43.75 |  |  | 3 | Complete | Cellpoint Corporation | 1154 | 8 | 4.5 | 0 | 78.5825
__export__.project_task_4373_5346b9e8 | Contact us form submission error | Sprint 2133 | 2021-08-09 | Bug Fix | MMH Unity Research: Help (P108) | Naseeb Razaq | Danish Hassan | 7.67 | 85.22 |  | SPLN |  | Complete | Mountain Meadow Herbs | 1184 | 9 | 1.33 | 0 | 185.0436
__export__.project_task_4298_bfbbf826 | Deploy to Production (WildLeaf - 2128) | Sprint 2129 | 2021-07-12 | Development | Wild Leaf: Help (P22) | Muhammad Zubair | Fahad Hassan | 2.17 | 43.4 |  |  |  | Complete | Wild Leaf Beverage | 1548 | 5 | 2.83 | 0.024908 | 10.9902
__export__.project_task_4217_8872664b | Deploy to Deployment + Production (MMherbs - 2129) | Sprint 2129 | 2021-07-12 | Configuration | MMH Dr. Clark: Help (P106) | Naseeb Razaq | Fahad Hassan | 10.58 | 100 |  |  |  | Complete | Mountain Meadow Herbs | 1715 | 5 | -5.58 | 0.044644 | 69.5449
__export__.project_task_4194_ff6ac4ef | Conduct Settings and Configuraton Review | Sprint 2132 | 2021-08-02 | Other | CraftAG: Odoo Audit (P147) | Fahad Hussain Malik | Asfand Yaar | 1.33 | 44.33 |  |  |  | Complete | CraftAG | 1798 | 3 | 1.67 | 143.3403 | 204.1753
__export__.project_task_4163_c2f50a54 | Briefing Developer | Sprint 2128 | 2021-07-05 | Internal Time Tracking | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Naseeb Razaq | 1 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 1829 | 1 | 0 | 0 | 46.9991
__export__.project_task_4151_6d009444 | USPS Integration |  |  | Configuration | Zuma: Odoo Implementation Phase 2 (P204) | Asfand Yaar | Fahad Hussain Malik | 1.17 | 58.5 |  |  |  | Cancelled | Zuma Sales LLC | 1830 | 2 | 0.83 | 378.8224 | 412.4552
__export__.project_task_4122_df2ec640 | Add New Fields on Projects, Tasks and Tickets | Sprint 2137 | 2021-09-06 | Development | Silverdale: Help (P12) | Muhammad Zubair | Aleem khan | 6 | 75 |  | SPLN |  | ELS | Silverdale Technology LLC | 1901 | 8 | 2 | 311.1943 | 0
__export__.project_task_4085_978dfdb8 | Configurations after version upgrade (copy) | Sprint 2126 | 2021-06-21 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  | Odoo Migration |  | Cancelled | Zuma Sales LLC | 2041 | 0 | 0 | 149.0078 | 24
__export__.project_task_4055_1578d97b | Setup Attendance module | Sprint 2129 | 2021-07-12 | Configuration | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Naseeb Razaq | 0.5 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 2066 | 0.5 | 0 | 0 | 128
__export__.project_task_4030_56227fbe | Pytest Odoo Pom library |  |  | Development | Silverdale: SDET (P132) | Muhammad Afzaal | Wishal Nasir | 4 | 66.67 |  |  |  | Complete | Silverdale Technology LLC | 2160 | 6 | 2 | 370.4321 | 410.4321
__export__.project_task_4022_1662192e | Master Script(test specification): Change Description to HTML Widget |  |  | Development | Silverdale: SDET (P132) | Levi Barnes | Aleem khan | 0.75 | 37.5 |  |  | 1 | Complete | Silverdale Technology LLC | 2164 | 2 | 1.25 | 0 | 377.5359
__export__.project_task_4009_6359a2a6 | Setting up Canada for Zuma |  |  | Configuration | Zuma: Odoo Implementation Phase 2 (P204) | Asfand Yaar | Fahad Hussain Malik | 0 | 0 | Initiate project |  | 2 | New | Zuma Sales LLC | 2188 | 16 | 16 | 502.897 | 0
__export__.project_task_3996_79872e01 | A search feature on the portal to allow the customer | Sprint 2131 | 2021-07-26 | Development | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Muhammad Bilal | 8.67 | 36.12 |  | SPLN | 2 | Complete | Continuant | 2210 | 24 | 15.33 | 189.4772 | 312.0192
__export__.project_task_3797_fbd10fa0 | Add event details for Insurance Company | Sprint 2122 | 2021-05-24 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 3.75 | 93.75 |  |  | 2 | Complete | Perfect Golf Event | 2886 | 4 | 0.25 | 18.0504 | 194.0504
__export__.project_task_3682_72867f67 | Create a new user group for Read Only access to Customer Invoices | Sprint 2121 | 2021-05-17 | Development | Wild Leaf: Help (P22) | Muhammad Afzaal | Raheel Aslam | 7 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 3048 | 5.5 | -1.5 | 0 | 64
__export__.project_task_3578_830d4b36 | Contacts Titles | Sprint 2120 | 2021-05-10 | Configuration | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq |  | 0.5 | 50 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3228 | 1 | 0.5 | 0.03861 | 71.1592
__export__.project_task_3501_58a56daa | First Transfer over their database from AWS hosted server | Sprint 2124 | 2021-06-07 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 4.63 | 92.6 |  | Odoo.sh Migration | 3 | Complete | Zuma Sales LLC | 3412 | 5 | 0.37 | 453.0075 | 296
__export__.project_task_3498_317ec1e6 | Sprint Meetings |  |  | Internal Time Tracking | Silverdale: Biz Dev (P63) | Muhammad Afzaal | Muhammad Saqlain Alam | 79.57 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3475 | 0 | -79.57 | 29.6733 | 760
__export__.project_task_3472_fc1c0610 | Review credit limit + Inform sales agents of any changes to credit limits from entry into Odoo |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.9583 | 520.0192
__export__.project_task_3389_afeac852 | For Hard Rock Road Holding Create Transactions the company deals in |  |  | Functionality Test | MMH: Odoo Audit (P100) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Mountain Meadow Herbs | 3531 | 0 | 0 | 0 | 168
__export__.project_task_3226_25a6834f | Integrate Volunteer Release Form with Volunteer contacts | Sprint 2118 | 2021-04-26 | Configuration | Heronswood: Volunteer On-boarding (P79) | Naseeb Razaq | Naseeb Razaq | 0.5 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 4196 | 0.5 | 0 | 0 | 223.5189
__export__.project_task_3193_285c8e85 | shipping charging on gift/catalog | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 4.08 | 68 |  |  | 3 | Complete | Mid-America Gardens, LLC | 4326 | 6 | 1.92 | 0 | 162.0956
__export__.project_task_3007_32aab668 | show customer email and cell no on invoice and quotation | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 3.08 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 4420 | 2.5 | -0.58 | 0 | 77.5663
__export__.project_task_2890_4152ca4f | Get list of Kick-Off attendees from Client |  |  |  | DISCOVERY (P76) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1050.1524
__export__.project_task_2820_3b3b3cb7 | cpbids test scripts and Android, IOS builds testing | Sprint 2112 | 2021-03-15 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 8.33 | 0 |  |  |  | Complete | Cellpoint Corporation | 4739 | 0 | -8.33 | 4.919e-05 | 69.4184
__export__.project_task_2744_9ae4c610 | add gift/product button: modified behavior | Sprint 2110 | 2021-02-22 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 10.53 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 5168 | 8 | -2.53 | 0 | 139.4738
__export__.project_task_2732_ab894a75 | On Assets, analytic account should be populated from the vendor bill | Sprint 2109 | 2021-02-15 | Development | Wild Leaf: Accounting (P64) | Nick Foy | Muhammad Bilal | 5.5 | 84.62 |  |  |  | Complete | Wild Leaf Beverage | 5181 | 6.5 | 1 | 0 | 110.4789
__export__.project_task_2401_ef111e47 | Update Proposal PDF |  |  | Configuration | Continuant: Quotation Management / Automation (P31) | Jeff Gross | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Continuant | 5686 | 0 | 0 | 248 | 288
__export__.project_task_2229_a1989f78 | Recruitment Stages and responsible | Sprint 2110 | 2021-03-01 | Development | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 2.75 | 100 |  | Difficulty 2 |  | Complete | Silverdale Technology LLC | 5936 | 2 | -0.75 | 0 | 366.3257
__export__.project_task_2216_2d30cf99 | Change Company of Products with specified company to no company | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy |  | 0.08 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5998 | 0 | -0.08 | 0 | 90.9622
__export__.project_task_2110_75ad2f31 | sort alpha | Sprint 2103 | 2021-01-11 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 2.92 | 97.33 |  | Difficulty 1 |  | Complete | EquityTeam | 6094 | 3 | 0.08 | 0 | 165.5875
__export__.project_task_2043_1d3f78e9 | Create a module named Employee Evaluation: Configuration | Sprint 2053 | 2020-12-28 | Configuration | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 1.33 | 66.5 |  |  |  | Complete | Silverdale Technology LLC | 6272 | 2 | 0.67 | 0 | 96
__export__.project_task_1792_9b66191e | Create an Active Field for Buyers | Sprint 2103 | 2021-01-11 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 4.83 | 96.6 |  |  |  | Complete | Cellpoint Corporation | 6836 | 5 | 0.17 | 0 | 320
__export__.project_task_1706_489cd31c | Bank Statement Import and Reconciliation | Sprint 2103 | 2021-01-11 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Kaesi Lee | 0.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6894 | 0 | -0.25 | 0.025058 | 256.9773
__export__.project_task_1415_784d1b8d | Detail page lot title is too large | Sprint 2044 | 2020-10-26 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 1 | 0 |  |  |  | Complete | Cellpoint Corporation | 8092 | 0 | -1 | 0 | 38.6514
__export__.project_task_1399_db637947 | Create deployment plan for Wild Leaf | Sprint 2041 | 2020-10-05 | Configuration | Wild Leaf: Help (P22) | Nick Foy |  | 2 | 100 |  |  |  | Complete | Wild Leaf Beverage | 8184 | 1 | -1 | 0 | 40
__export__.project_task_1392_ec4ef25c | WeShield.us 10/08 Feedback | Sprint 2043 | 2020-10-19 | Development | Moln: Help (P16) | Kaesi Lee | Faizan Zia Malik | 0 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8215 | 0 | 0 | 0 | 67.084
__export__.project_task_1373_7090a7ca | Shutdown AWS for CPbids | Sprint 2041 | 2020-10-05 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8286 | 0 | 0 | 24.557 | 41.6576
__export__.project_task_1337_7774bc9a | Dashboards Ascending order | Sprint 2041 | 2020-10-05 | Bug Fix | Cellpoint CPBids: Help (P7) | Roshan Mecoth |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8398 | 0 | 0 | 16 | 72
__export__.project_task_1302_1b50782b | Make end date time field editable except for Closed lots | Sprint 33 | 2020-09-28 | Studio | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8452 | 0 | 0 | 0 | 5.8296
__export__.project_task_1280_c4075de2 | Delete Duplicate Auction BSHJX | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8575 | 0 | 0 | 0 | 42.7621
__export__.project_task_1242_650ffdf0 | Gucci website: multiple emails for order confirmation | Sprint 32 | 2020-09-21 | Configuration | Moln: Help (P16) | Nick Foy |  | 0.25 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8694 | 0 | -0.25 | 17.7879 | 17.7879
__export__.project_task_1218_c28f5264 | AOA Navigation | Sprint 31 | 2020-09-14 | Configuration | Moln: Help (P16) | Kaesi Lee |  | 0.5 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8781 | 0 | -0.5 | 0 | 0
__export__.project_task_1202_38f6b09e | remove this text | Sprint 31 | 2020-09-14 | Configuration | Moln: Help (P16) | Nick Foy |  | 0.5 | 100 |  |  |  | Complete | Moln Solutions, LLC | 8828 | 0.5 | 0 | 8 | 0
__export__.project_task_1058_99ba37bf | Investigate Send Invitation Button | Sprint 28 | 2020-08-24 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_608_17eeece8 | Backend Rollout | Sprint 27 | 2020-08-17 | Configuration | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9949 | 2 | 2 | 0 | 0
__export__.project_task_276_abb4cc51 | Task ID | Sprint 22 | 2020-07-12 | Development | Silverdale: Help (P12) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 10254 | 0.33333 | 0.33333 | 0 | 0
__export__.project_task_187_b6ea1bfd | Validate data |  |  |  | Cellpoint: Belmont Manifest API Integration (P6) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10806 | 0 | 0 | 0 | 0
__export__.project_task_4819_41bd64fb | Data Cleanup - Contacts | Sprint 2137 | 2021-09-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 3.5 | 77.78 |  | SPLN |  | ELS | Zuma Sales LLC | 171 | 4.5 | 1 | 1.8524e-05 | 0
__export__.project_task_4711_24275085 | Set up Tools - Client Helpdesk Onboarding - Making sure everything is set up and ready to go |  |  | Configuration | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Set up Automation on testing and production | Automation |  | Planning | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 0
__export__.project_task_4699_3b8aa466 | Process Documentation - Helpdesk Priorities Management | Sprint 2138 | 2021-09-13 | Documentation | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 88.3911
__export__.project_task_4577_95ddbde0 | Critical Test Cases completed | Sprint 2134 | 2021-08-16 | Configuration | CraftAG: Help (P138) | Fahad Hussain Malik | Fahad Hassan | 4 | 57.14 |  | SPLN |  | Complete | CraftAG | 799 | 7 | 3 | 40 | 40
__export__.project_task_4474_93497124 | Import Leads from NewLiftParts.com |  |  | Development | Zuma: Help (P97) | Fahad Hussain Malik | Raheel Aslam | 6.33 | 90.43 | Follow-up |  |  | Backlog | Zuma Sales LLC | 896 | 7 | 0.67 | 0 | 0
__export__.project_task_4396_837e5203 | Attach FedEx label and add to Odoo | Sprint 2133 | 2021-08-09 | Configuration | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Muhammad Bilal | 0 | 0 |  | SPLN |  | Complete | Cellpoint Corporation | 1154 | 0 | 0 | 0 | 88
__export__.project_task_4209_0155e52e | Deploy to Deployment & Production (MidAmerica - PDQA - 2127) | Sprint 2128 | 2021-07-05 | Development | Mid-America: Help (P37) | Naseeb Razaq | Fahad Hassan | 5.92 | 98.67 |  |  |  | Complete | Mid-America Gardens, LLC | 1740 | 6 | 0.08 | 0.018968 | 24.6951
__export__.project_task_4162_b3f10431 | Task Creation | Sprint 2128 | 2021-07-05 | Configuration | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Naseeb Razaq | 0.5 | 50 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 1829 | 1 | 0.5 | 0 | 39.8131
__export__.project_task_4142_6cb60594 | To Install the 3rd party connector |  |  | Deployment | MMH: Amazon Module Automation (P102) | Naseeb Razaq | Muzher Siddique | 1.67 | 47.71 | Please add next activity |  |  | Backlog | Mountain Meadow Herbs | 1832 | 3.5 | 1.83 | 0 | 0
__export__.project_task_4111_c294b009 | Problem Changing Schedule Date |  |  | Development | Wild Leaf: Help (P22) | Muhammad Zubair |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 1973 | 0 | 0 | 0 | 56.0283
__export__.project_task_4092_707ad598 | Business Processes and the modules used by every company | Sprint 2128 | 2021-07-05 | Configuration | DGS: Odoo Audit and v14 Upgrade Estimate (P136) | Jeff Gross |  | 9 | 75 |  | SPLN |  | Complete | DG Solutions Inc. | 2021 | 12 | 3 | 0 | 72.4116
__export__.project_task_3880_29dd0502 | having expanded opt-in flexibility... may need an app for this sequence? | Sprint 2128 | 2021-07-05 | Configuration | MMH: Website Edits June 2021 (P120) | Naseeb Razaq |  | 3 | 100 |  |  |  | Complete | Mountain Meadow Herbs | 2496 | 3 | 0 | 0 | 192
__export__.project_task_3875_9dcbb1d5 | back out the function that is blocking our ability to close MOs without stock | Sprint 2124 | 2021-06-07 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Raheel Aslam | 3.25 | 97.01 |  |  | 1 | Complete | Wild Leaf Beverage | 2502 | 3.35 | 0.1 | 23.4661 | 73.9189
__export__.project_task_3796_557d211c | Sending the terms and condition document in Sales Order | Sprint 2122 | 2021-05-24 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Fahad Hassan | 6.08 | 100 |  |  | 2 | Complete | Perfect Golf Event | 2886 | 5.5 | -0.58 | 18.0504 | 194.0504
__export__.project_task_3695_41c04336 | Configure payment methods for customers | Sprint 2121 | 2021-05-17 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 2.5 | 0 |  |  |  | Complete | Perfect Golf Event | 2909 | 0 | -2.5 | 0 | 169.2432
__export__.project_task_3530_3fbc86f2 | Demo.silverdale.com |  |  | Improvements | Silverdale: Help (P12) | Muhammad Zubair | Sanaullah Khan | 0 | 0 | Evaluate if needed |  |  | Planning | Silverdale Technology LLC | 3405 | 0 | 0 | 640.0292 | 0
__export__.project_task_3390_eccd0fa4 | For Phytovation Create Transactions the company deals in |  |  | Functionality Test | MMH: Odoo Audit (P100) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Mountain Meadow Herbs | 3531 | 0 | 0 | 0 | 168
__export__.project_task_3378_cde4a6d1 | Zuma Meeting |  |  | Internal Time Tracking | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 21.33 | 96.95 |  |  |  | Complete | Zuma Sales LLC | 3551 | 22 | 0.67 | 481.4851 | 741.0428
__export__.project_task_3278_65212ef5 | MM Herbs Meeting |  |  | Internal Time Tracking | MMH: Help (P83) | Naseeb Razaq |  | 33.48 | 0 |  |  |  | Complete | Mountain Meadow Herbs | 4034 | 0 | -33.48 | 597.1892 | 597.1903
__export__.project_task_3211_50dcaa90 | Portal User for Volunteers | Sprint 2118 | 2021-04-26 | Development | Heronswood: Volunteer On-boarding (P79) | Jeff Gross | Danish Hassan | 13.17 | 100 |  |  | 3 | Complete | Port Gamble Sâ€™Klallam Foundation | 4232 | 10 | -3.17 | 0 | 235.1342
__export__.project_task_3055_be94efd30 | Declare the new Odoo system live |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0.00061774 | 206.1934
__export__.project_task_2994_8f093ce4 | Personality traits score calculation | Sprint 2113 | 2021-03-22 | Development | PWX: Survey (P70) | Levi Barnes | Danish Hassan | 11.33 | 100 |  |  | 2 | Complete | EquityTeam | 4430 | 6 | -5.33 | 0 | 200
__export__.project_task_2990_65db2ce3 | Picking report: picking operations & delivery slip | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Danish Hassan | 6 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4491 | 0 | -6 | 0 | 85.3664
__export__.project_task_2911_522af380 | Identify key players in the client for each work stream |  |  |  | DESIGN (P77) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1049.8109
__export__.project_task_2881_82f7339b | Accept service requests |  |  | Development | PWX: Field Service to Invoicing (P47) | Naseeb Razaq |  | 0 | 0 | Bring this up with Mark and Estimate the Effort for Fixed Price |  |  | Planning | EquityTeam | 4589 | 0 | 0 | 1039.867 | 0
__export__.project_task_2836_cda79a92 | Send Shipment Details to IL2000 | Sprint 2119 | 2021-05-03 | Development | Wild Leaf: IL2000 Integration (P40) | Jeff Gross | Fahad Hassan | 42.58 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 4700 | 8 | -34.58 | 16 | 456
__export__.project_task_2785_ff32984d | gucci configuration | Sprint 2110 | 2021-02-22 | Development | Moln: 3 New Portal Websites (P62) | Levi Barnes | Danish Hassan | 3.67 | 100 |  |  |  | Complete | Moln Solutions, LLC | 5007 | 3 | -0.67 | 0 | 135.4183
__export__.project_task_2716_277f33f7 | Deployment: 2105 | Sprint 2108 | 2021-02-08 | Configuration | PWX: Property (P58) | Levi Barnes | Wajahat Ali | 1 | 0 |  |  |  | Complete | EquityTeam | 5240 | 0 | -1 | 0 | 8
__export__.project_task_2677_e8015975 | Kevin Morris: Process walkthrough in Odoo | Sprint 2107 | 2021-02-01 | Internal Time Tracking | Silverdale: Biz Dev (P63) | Nick Foy | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5351 | 0 | 0 | 0 | 167.4489
__export__.project_task_2632_42ecf4f4 | Odoo x Ramp Requirements |  |  | Requirements Collection | Wild Leaf: Ramp Integration (P75) | Naseeb Razaq | Naseeb Razaq | 0 | 0 |  |  |  | New | Wild Leaf Beverage | 5493 | 0 | 0 | 1241.0951 | 0
__export__.project_task_2422_e831d595 | Scheduling | Sprint 2105 | 2021-01-25 | Configuration | Wild Leaf: Help (P22) | Nick Foy | Nick Foy | 2 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 5591 | 0 | -2 | 40 | 198.8542
__export__.project_task_2182_8fc85727 | 2106: Task Test Script |  |  | Development | Silverdale: Help (P12) | Muhammad Afzaal | Danish Hassan | 2 | 66.67 |  |  |  | Cancelled | Silverdale Technology LLC | 6004 | 3 | 1 | 0 | 334.1689
__export__.project_task_2143_76a4a20e | Default Customer to Project Customer for emailed in tasks | Sprint 2110 | 2021-03-01 | Development | Silverdale: Help (P12) | Nick Foy | Raheel Aslam | 2.67 | 100 |  | Potential Silverdale App |  | Complete | Silverdale Technology LLC | 6068 | 2 | -0.67 | 0 | 394.5667
__export__.project_task_2132_5e7b1e32 | FW: You have been assigned to Edits to Recruitment Module (#45): email template |  |  | Development | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 1.33 | 4.16 |  |  |  | Cancelled | EquityTeam | 6072 | 32 | 30.67 | 0 | 264
__export__.project_task_2123_1f420d82 | re-install/update sprint module |  |  | Configuration | PWX: Help (P23) | Levi Barnes |  | 0.25 | 0 |  |  |  | Complete | EquityTeam | 6077 | 0 | -0.25 | 0 | 158.5629
__export__.project_task_2058_f66d6c2b | Set defaults on product expiry date fields | Sprint 2053 | 2020-12-28 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Muzher Siddique | 0.5 | 100 |  |  |  | Complete | Wild Leaf Beverage | 6236 | 0.5 | 0 | 0 | 84
__export__.project_task_2055_4d56ffb2 | Restrict purchase order items to product/vendor list | Sprint 2102 | 2021-01-04 | Development | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 5.92 | 98.67 |  |  |  | Complete | Wild Leaf Beverage | 6239 | 6 | 0.08 | 0 | 154.9614
__export__.project_task_1898_101bf529 | Sacramento Training |  |  | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 3 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6572 | 0 | -3 | 0 | 167.5178
__export__.project_task_1831_c2d17626 | Step-up Help Desk app on Silverdale server |  |  | Configuration | Silverdale: Help (P12) | Muzher Siddique | Kaleem Khan | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 6750 | 0 | -0.17 | 0 | 505.3733
__export__.project_task_1785_c03ddca6 | Add Date Only Fields | Sprint 2103 | 2021-01-11 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 3.83 | 95.75 |  |  |  | Complete | Cellpoint Corporation | 6836 | 4 | 0.17 | 0 | 320
__export__.project_task_1615_36aa1808 | Wednesday |  |  | Configuration | Silverdale: Help (P12) | Muzher Siddique |  | 139.73 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 7233 | 0 | -139.73 | 0 | 425.0466
__export__.project_task_1502_88416610 | Disabling Increment Rules Affects My Bid Display | Sprint 2047 | 2020-11-16 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 7 | 0 |  |  |  | Complete | Cellpoint Corporation | 7734 | 0 | -7 | 0.037145 | 210.1699
__export__.project_task_1414_2c56c176 | Fonts and text sizes on details page | Sprint 2044 | 2020-10-26 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 3 | 0 |  |  |  | Complete | Cellpoint Corporation | 8092 | 0 | -3 | 0 | 38.6634
__export__.project_task_1375_ea2c9f40 | text updates to gucci site | Sprint 2041 | 2020-10-05 | Configuration | Moln: Help (P16) | Nick Foy |  | 0.25 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8274 | 0 | -0.25 | 4 | 8
__export__.project_task_1372_ffd18a03 | Product Display Issue | Sprint 2041 | 2020-10-05 | Bug Fix | Moln: Help (P16) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8286 | 0 | 0 | 7.035 | 41.1061
__export__.project_task_1193_574969c2 | 3rd Party Module for Enhanced Product Listing | Sprint 31 | 2020-09-14 | Configuration | Moln: Help (P16) | Kaesi Lee |  | 0.25 | 6.25 |  |  |  | Complete | Moln Solutions, LLC | 8880 | 4 | 3.75 | 0 | 0
__export__.project_task_1068_de67e342 | Clean Buyer Data | Sprint 27 | 2020-08-17 | Configuration | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9560 | 0 | 0 | 0 | 0
__export__.project_task_270_d9f73703 | Setup lastpass | Sprint 22 | 2020-07-12 | Development | Silverdale: Help (P12) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 10261 | 0 | 0 | 0.0077691 | 0
__export__.project_task_177_297fbc93 | Add Check on IMEI |  |  |  | Cellpoint: Belmont Manifest API Integration (P6) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10809 | 0 | 0 | 0 | 0
__export__.project_task_4828_7cbcc701 | Set up sales quote template for equipment | Sprint 2137 | 2021-09-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0.5 | 50 |  | 2021-10-09 |  | Complete | Zuma Sales LLC | 171 | 1 | 0.5 | 0 | 18.6601
Client Set-up
__export__.project_task_4718_64c242d3 | Activity - Install Floor Screens | Sprint 2139 | 2021-09-20 | Improvements | Silverdale Cares 24/7 (P188) | Muhammad Zubair | Faisal Huda Khan | 0 | 0 | Close when completed |  |  | In Progress | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 0
__export__.project_task_4717_6676d21f | Activity - Training |  |  | Internal Training | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Plan Training for team. |  |  | New | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 0
__export__.project_task_4700_a7fd1c3a | Process Documentation - Helpdesk Knowledge Management | Sprint 2138 | 2021-09-13 | Documentation | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 88.3911
__export__.project_task_4581_c83ee02c | User Roles have been defined and set up as groups in Odoo | Sprint 2137 | 2021-09-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  | SPLN |  | ELS | Zuma Sales LLC | 799 | 2 | 2 | 0 | 0
__export__.project_task_4471_d7c3bb41 | Task Estimations Mechanism |  |  | Improvements | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair | Muzher Siddique | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 897 | 0 | 0 | 80 | 0
__export__.project_task_4387_e6eb3aab | Print POS Label and attach to device | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Muhammad Bilal | 10 | 80 |  | SPLN | 3 | Complete | Cellpoint Corporation | 1154 | 12.5 | 2.5 | 0 | 78.5994
Priority
__export__.project_task_4372_894a1649 | Lock the invoices, remove the cancelled invoices and change the invoice view | Sprint 2132 | 2021-08-02 | Development | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Muhammad Bilal | 9.25 | 100 |  |  | 2 | Complete | Continuant | 1184 | 9 | -0.25 | 0 | 76
__export__.project_task_4355_03cd91dc | Warehouse Setup | Sprint 2133 | 2021-08-09 | Configuration | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Farman Ahmad Cheema | 0 | 0 |  | SPLN |  | Complete | Cellpoint Corporation | 1230 | 0 | 0 | 0 | 114.2857
__export__.project_task_4216_892f1e82 | Deploy To Production (Wildleaf - 2127) | Sprint 2128 | 2021-07-05 | Development | Wild Leaf: Help (P22) | Muhammad Zubair | Fahad Hassan | 1.53 | 12.75 |  |  | 3 | Complete | Wild Leaf Beverage | 1716 | 12 | 10.47 | 0 | 4.895
__export__.project_task_4187_a144b544 | Deploy To Deployment (Wildleaf - PDQA - 2127) | Sprint 2128 | 2021-07-05 | Development | Wild Leaf: Help (P22) | Muhammad Zubair | Fahad Hassan | 3.83 | 31.92 |  |  | 3 | Complete | Wild Leaf Beverage | 1810 | 12 | 8.17 | 0.00020654 | 14.9433
__export__.project_task_4160_5d010cd8 | Discussions for finalization | Sprint 2128 | 2021-07-05 | Internal Time Tracking | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Naseeb Razaq | 0.5 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 1829 | 0.5 | 0 | 0 | 47.0977
__export__.project_task_4128_e6a70d4e | Additional Sales Order Statuses | Sprint 2137 | 2021-09-06 | Development | Wild Leaf: Sales Improvements (P150) | Naseeb Razaq | Aleem khan | 29.25 | 100 |  | SPLN | 3 | ELS | Wild Leaf Beverage | 1897 | 29.25 | 0 | 364 | 0
__export__.project_task_4082_7f5ee8c0 | Import Customer Data |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 | Plan for the sprint |  |  | Planning | Mountain Meadow Herbs | 2048 | 5 | 5 | 0 | 0
__export__.project_task_4019_882fdad2 | Master Script: name change |  |  | Development | Silverdale: SDET (P132) | Levi Barnes | Aleem khan | 0.83 | 83 |  |  | 1 | Complete | Silverdale Technology LLC | 2164 | 1 | 0.17 | 0 | 377.5626
__export__.project_task_3876_3ebe8e81 | Product Category Group By and Filter on Forecast Report | Sprint 2129 | 2021-07-12 | Development | Wild Leaf: Burn Down Report (P117) | Muhammad Zubair | Aleem khan | 10.25 | 85.42 |  | SPLN | 3 | Complete | Wild Leaf Beverage | 2499 | 12 | 1.75 | 21.5472 | 264
__export__.project_task_3871_5c784503 | Change default response to log note on team items |  |  | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Raheel Aslam | 1.33 | 66.5 |  |  | 4 | Complete | Wild Leaf Beverage | 2525 | 2 | 0.67 | 30.4959 | 72.9487
__export__.project_task_3694_1eddb2bf | Set up products (Hole in one, closest to pin, etc. | Sprint 2124 | 2021-06-07 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0.25 | 0 |  |  |  | Complete | Perfect Golf Event | 2910 | 0 | -0.25 | 0 | 121.4379
__export__.project_task_3685_37a4f8a3 | WildLeaf: Remove unnecessary payment steps from Las Vegas and Sacramento warehouses | Sprint 2121 | 2021-05-17 | Configuration | Wild Leaf: Help (P22) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 3026 | 0 | 0 | 0 | 116.9872
__export__.project_task_3496_5d4d22fa | P112: Wildleaf Consignment Requirements Discussion |  |  | Improvements | Wild Leaf: Consignment and Sales Improvements (P112) | Muhammad Afzaal | Muhammad Bilal | 22.17 | 96.39 |  | MA Review |  | Cancelled | Wild Leaf Beverage | 3476 | 23 | 0.83 | 0 | 88
__export__.project_task_3416_37409edc | Leadership Meeting |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Muzher Siddique | 17.38 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3501 | 0 | -17.38 | 0 | 632
__export__.project_task_3215_87e521b6 | Wildleaf: Installation of 3rd party module to manage substitute products on MO | Sprint 2114 | 2021-03-29 | Configuration | Wild Leaf: Help (P22) | Jeff Gross | Danish Hassan | 4.83 | 100 |  |  | 1 | Complete | Wild Leaf Beverage | 4213 | 3.5 | -1.33 | 0 | 143.9532
__export__.project_task_3054_be94efd29 | Confirm that all components of the new Odoo system are operational |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0.00061774 | 206.1934
__export__.project_task_2893_bd304b79 | Create Client Email Address |  |  |  | DISCOVERY (P76) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1050.1351
__export__.project_task_2873_8882a686 | Change all client Odoo account logins | Sprint 2118 | 2021-04-26 | Configuration | Silverdale: Help (P12) | Nick Foy | Muzher Siddique | 0 | 0 |  |  | 1 | Complete | Silverdale Technology LLC | 4591 | 0 | 0 | 0 | 266.5148
__export__.project_task_2855_991531cf | general | Sprint 2112 | 2021-03-15 | Internal Time Tracking | Mid-America: Help (P37) | Levi Barnes | Levi Barnes | 2.5 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4681 | 0 | -2.5 | 0 | 32
__export__.project_task_2840_d8308e6e | Add Shipping Quote to Customer Sales Order | Sprint 2119 | 2021-05-03 | Development | Wild Leaf: IL2000 Integration (P40) | Jeff Gross | Raheel Aslam | 7.92 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4700 | 7 | -0.92 | 16 | 456
__export__.project_task_2751_e6e7c62d | CPBids Web: Remove Admin bar for non-login users | Sprint 2110 | 2021-03-01 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Muhammad Bilal | 11.5 | 100 |  |  |  | Complete | Cellpoint Corporation | 5136 | 10 | -1.5 | 0 | 207.0889
__export__.project_task_2598_6699c7ee | Send the alert messaging to Philip for translation | Sprint 2107 | 2021-02-01 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 1.17 | 100 |  |  |  | Complete | Cellpoint Corporation | 5564 | 1.5 | -3.34 | 0 | 206.3281
__export__.project_task_2376_848bd7b3 | Task Difficulty | Sprint 2110 | 2021-02-22 | Development | Silverdale: Help (P12) | Muhammad Afzaal | Danish Hassan | 4.75 | 95 |  | WK | 1 | Complete | Silverdale Technology LLC | 5742 | 5 | 0.25 | 0.010377 | 390.8073
__export__.project_task_2275_1373cff7 | Human Resources | Sprint 2110 | 2021-03-01 | Configuration | Silverdale: Help (P12) | Faisal Huda Khan | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5910 | 0 | 0 | 0.067317 | 328.4673
__export__.project_task_1794_163ad95d | Add a column chooser to all Lot views | Sprint 2050 | 2020-12-07 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Fahad Hassan | 0.33 | 0 |  |  |  | Complete | Cellpoint Corporation | 6836 | 0 | -0.33 | 0 | 102.5861
__export__.project_task_1786_1b35e2c0 | On Lot Views - add related Company | Sprint 2108 | 2021-02-08 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 4.52 | 100 |  |  |  | Complete | Cellpoint Corporation | 6836 | 3.5 | -1.02 | 0 | 502.415
__export__.project_task_1642_b092bc86 | sales order email not in email log |  |  | Configuration | Moln: Help (P16) | Levi Barnes |  | 0.25 | 0 |  |  |  | Complete | Moln Solutions, LLC | 7101 | 0 | -0.25 | 8 | 87.9031
__export__.project_task_1525_a3cc3710 | Reviews Forms | Sprint 2045 | 2020-11-02 | Development | PWX: Reviews Module (P53) | Levi Barnes | Raheel Aslam | 4.58 | 100 |  |  |  | Complete | EquityTeam | 7588 | 3 | -1.58 | 0 | 72
__export__.project_task_1433_91e6a2d9 | logo missing on quotations | Sprint 2043 | 2020-10-19 | Bug Fix | Moln: Help (P16) | Kaesi Lee |  | 0.25 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8020 | 0 | -0.25 | 16 | 31.3933
__export__.project_task_1341_c25ee732 | Winner and Loser donâ€™t need watchlist notifications | Sprint 2043 | 2020-10-19 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 5 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8398 | 0 | -5 | 0 | 72
__export__.project_task_1315_84c972ff | wrong site loading - can we fix this asap? | Sprint 2041 | 2020-10-05 | Configuration | Moln: Help (P16) | Kaesi Lee |  | 0.25 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8429 | 0 | -0.25 | 48.3534 | 64.3534
__export__.project_task_1246_50789cce | Gucci website: 5. Can we add a flat processing fee of $6.00 per order? | Sprint 32 | 2020-09-21 | Configuration | Moln: Help (P16) | Kaesi Lee |  | 0.5 | 100 |  | Website |  | Complete | Moln Solutions, LLC | 8694 | 0.5 | 0 | 0.012592 | 57.7673
eCommerce
__export__.project_task_1166_5cab34ed | Add 2 new Task Types | Sprint 29 | 2020-08-31 | Development | Silverdale: Help (P12) | Tung Nguyen |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 9119 | 0 | 0 | 14.4989 | 0
__export__.project_task_1165_150d6e60 | custom product page | Sprint 29 | 2020-08-31 | Development | Moln: Help (P16) | Kaesi Lee |  | 1.25 | 100 |  |  |  | Complete | Moln Solutions, LLC | 9119 | 0.5 | -0.75 | 0 | 0
__export__.project_task_1131_c296b6f5 | Test Production odoo APP | Sprint 27 | 2020-08-17 | Configuration | CPBids Migration AWS->odoo (P5) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9374 | 0 | 0 | 0 | 0
__export__.project_task_1054_7a0ae674 | Conditional Hide: If Status is Draft, don't show bidding information or offers tab | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_559_918d2e70 | API:Buy it now(Live ) | Sprint 2047 | 2020-11-16 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 10.33 | 100 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 5 | -5.33 | 69.8808 | 792
__export__.project_task_307_e33ca74d | RCA - iOS Notification Issue | Sprint 22 | 2020-07-12 | Bug Fix | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10231 | 0 | 0 | 0.03901 | 0
__export__.project_task_244_87d3403b | Incorrect Status On Won Bid | Sprint 27 | 2020-08-17 | Development | Cellpoint CPBids: Help (P7) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10444 | 0 | 0 | 0 | 0
__export__.project_task_188_ac09d769 | Move to Production |  |  |  | Cellpoint: Belmont Manifest API Integration (P6) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10806 | 0 | 0 | 0 | 0
__export__.project_task_4853_16d9e2ae | De-Duplication of Contacts | Sprint 2137 | 2021-09-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.5 | 33.33 |  | 2021-10-09 |  | ELS | Zuma Sales LLC | 149 | 1.5 | 1 | 0 | 0
Meeting w/Bonnie
Asfand
__export__.project_task_4716_85651c03 | Activity - Rollout - External |  |  | Improvements | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Plan |  |  | New | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 0
__export__.project_task_4705_88c863f1 | Process Documentation - Turn Around Times | Sprint 2138 | 2021-09-13 | Documentation | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 88.3911
__export__.project_task_4366_ca070d8a | Data pop-up to "Bill to" as well | Sprint 2132 | 2021-08-02 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 5.83 | 100 |  |  | 2 | Complete | Zuma Sales LLC | 1209 | 4 | -1.83 | 0 | 108
__export__.project_task_4093_747f9235 | Audit of the best Practices, Features, and Master Data used by the client | Sprint 2128 | 2021-07-05 | Configuration | DGS: Odoo Audit and v14 Upgrade Estimate (P136) | Jeff Gross |  | 5 | 100 |  | SPLN |  | Complete | DG Solutions Inc. | 2021 | 5 | 0 | 0 | 72.401
__export__.project_task_4081_a41e8ad1 | Import Product Categories, tags & coupons |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 | Plan it for sprint |  |  | Planning | Mountain Meadow Herbs | 2048 | 4 | 4 | 0 | 0
__export__.project_task_3890_6afffc1d | Helpdesk Non-Billable tick box to be unticked when ticket type is not Issue - Internal | Sprint 2135 | 2021-08-23 | Development | Silverdale: Help (P12) | Muhammad Zubair | Raheel Aslam | 5 | 100 |  | SPLN | 2 | Complete | Silverdale Technology LLC | 2478 | 5 | 0 | 439.6691 | 477.0935
__export__.project_task_3885_134ec638 | Wrong error pop up on lot expiry |  |  | Development | Wild Pack Help (SOR-17586) | Naseeb Razaq |  | 20.67 | 79.5 | Please add next activity |  | 3 | Backlog | Wild Leaf Beverage | 2481 | 26 | 5.33 | 552 | 0
__export__.project_task_3823_2c5f399a | Wildleaf Tickets |  |  | Internal Time Tracking | Wild Leaf: Help (P22) | Muhammad Afzaal |  | 182.67 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 2745 | 0 | -182.67 | 0.006026 | 252.0674
__export__.project_task_3693_963e511c | Set up terms and conditions, make them available to sign online | Sprint 2121 | 2021-05-17 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Perfect Golf Event | 2910 | 0 | 0 | 0 | 65.6015
__export__.project_task_3544_abf77be5 | Set up E-Learning Module | Sprint 2123 | 2021-05-31 | Configuration | MMH: Help (P83) | Jeff Gross |  | 13.58 | 100 |  |  |  | Complete | Mountain Meadow Herbs | 3361 | 2 | -11.58 | 0 | 189.3461
__export__.project_task_3053_be94efd28 | Initiate support |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0.00061774 | 206.1934
__export__.project_task_2922_784a44b3 | Send Shipment Details to IL2000: Research for developer | Sprint 2114 | 2021-03-29 | Development | Wild Leaf: IL2000 Integration (P40) | Jeff Gross | Raheel Aslam | 5.5 | 68.75 |  |  | 2 | Complete | Wild Leaf Beverage | 4570 | 8 | 2.5 | 0 | 72.7382
__export__.project_task_2895_3ef923f4 | Finalize Deliverables |  |  |  | DISCOVERY (P76) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1050.1252
__export__.project_task_2813_14874059 | Inventory |  |  | Internal Time Tracking | Silverdale: Help (P12) | Fahad Hussain Malik | Bilal Ahmad Khan | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4762 | 0 | 0 | 0.087734 | 308.7055
__export__.project_task_2748_0968554e | Consumable Items that can be sold |  |  | Requirements Collection | Wild Leaf: Consumable Items that can be sold (P152) | Naseeb Razaq |  | 0 | 0 | Please add next activity |  |  | Planning | Wild Leaf Beverage | 5137 | 0 | 0 | 1160 | 0
__export__.project_task_2726_78b6dce3 | Employee: Security | Sprint 2110 | 2021-02-22 | Development | PWX: HR (P61) | Levi Barnes | Danish Hassan | 4.33 | 100 |  |  |  | Complete | EquityTeam | 5182 | 4 | -0.33 | 0 | 175.4211
__export__.project_task_2688_19e29b58 | Monitor Helpdesk Tickets QA tasks |  |  | Other | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 25 | 0 |  |  |  | Complete | Cellpoint Corporation | 5337 | 0 | -25 | 0.0095423 | 204.2918
__export__.project_task_2280_59bdbf6b | ELS stage email confirmation popup | Sprint 2110 | 2021-03-01 | Development | Silverdale: Help (P12) | Nick Foy | Raheel Aslam | 3.33 | 100 |  |  |  | Complete | Silverdale Technology LLC | 5910 | 2 | -1.33 | 0.013561 | 392.8419
__export__.project_task_2273_d0e5e0a3 | Accounting - Part 1 | Sprint 2109 | 2021-02-15 | Configuration | Silverdale: Help (P12) | Faisal Huda Khan | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5910 | 0 | 0 | 0.087559 | 254.4867
__export__.project_task_2044_0e6b617b | Research and Planning |  |  | Configuration | Silverdale: v14 Upgrade (P46) | Muhammad Afzaal | Muzher Siddique | 0 | 100 |  |  |  | Cancelled | Silverdale Technology LLC | 6268 | 3.9 | -13.43 | 392.1173 | 432.1173
__export__.project_task_1878_37ad338b | Google calendar only syncing default calendar to Odoo |  |  | Bug Fix | PWX: Help (P23) | Levi Barnes | Levi Barnes | 13.42 | 100 |  |  |  | Complete | EquityTeam | 6597 | 10 | -3.42 | 0 | 559.2183
__export__.project_task_1791_397df206 | Tidy Up Test Buyer Accounts |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0.33 | 11 |  |  |  | Complete | Cellpoint Corporation | 6836 | 3 | 2.67 | 0 | 180.8003
__export__.project_task_1715_f378aa8d | Bug should be priority task automatically | Sprint 2109 | 2021-02-15 | Development | Silverdale: Help (P12) | Muhammad Afzaal | Raheel Aslam | 2 | 66.67 |  |  |  | Cancelled | Silverdale Technology LLC | 6890 | 3 | 1 | 340.9289 | 517.8919
__export__.project_task_1616_62c95872 | Listview: Bug - Android | Sprint 2047 | 2020-11-16 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0 | 0 |  | P1 |  | Complete | Cellpoint Corporation | 7232 | 0 | 0 | 0 | 91.7041
__export__.project_task_1561_4d021030 | Inventory Migration: Trial Run | Sprint 2046 | 2020-11-09 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 16 | 0 |  | Inventory |  | Complete | Wild Leaf Beverage | 7531 | 0 | -16 | 0 | 80
__export__.project_task_1528_8eefdf63 | Integration with Better Business Bureau | Sprint 2050 | 2020-12-07 | Configuration | PWX: Reviews Module (P53) | Levi Barnes | Danish Hassan | 11.42 | 100 |  |  |  | Complete | EquityTeam | 7587 | 7.5 | -3.92 | 0 | 286.5861
__export__.project_task_1483_609355a4 | Taxcloud API post/response | Sprint 2043 | 2020-10-19 | Configuration | Moln: Help (P16) | Levi Barnes |  | 0.5 | 0 |  |  |  | Complete | Moln Solutions, LLC | 7900 | 0 | -0.5 | 7.315 | 24
__export__.project_task_1313_538a3126 | Web Enabled Bidding Beta Testing | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8429 | 0 | 0 | 0 | 33.1604
__export__.project_task_1262_7bbb8bff | show all CC providers | Sprint 33 | 2020-09-28 | Development | Moln: Help (P16) | Nick Foy |  | 2 | 8.33 |  | eCommerce |  | Complete | Moln Solutions, LLC | 8660 | 24 | 22 | 12 | 96
__export__.project_task_1244_c40c2879 | Gucci website: Bypass fedex integration - free shipping | Sprint 32 | 2020-09-21 | Configuration | Moln: Help (P16) | Kaesi Lee |  | 0.5 | 100 |  | Website |  | Complete | Moln Solutions, LLC | 8694 | 0.5 | 0 | 0.082692 | 57.7771
eCommerce
__export__.project_task_1130_9dce9e3b | Update Production URLs | Sprint 27 | 2020-08-17 | Configuration | CPBids Migration AWS->odoo (P5) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9374 | 0 | 0 | 0 | 0
__export__.project_task_1052_c976ca0f | Investigate "ReList" Field and Function | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_362_d43bb076 | Add Task Type field: Development vs Bug Fix | Sprint 23 | 2020-07-20 | Development | Silverdale: Help (P12) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 10229 | 0.5 | 0.5 | 8.0498 | 0
__export__.project_task_256_96b68701 | Kaesi's Staging Server Login | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10394 | 0 | 0 | 0 | 0
__export__.project_task_189_6f19ff77 | Integration Document |  |  |  | Cellpoint: Belmont Manifest API Integration (P6) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10806 | 0 | 0 | 0 | 0
__export__.project_task_4830_cc85a838 | Connector training w/Sales team | Sprint 2138 | 2021-09-13 | Client Meetings | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  | 2014-09-01 |  | Cancelled | Zuma Sales LLC | 171 | 1 | 1 | 0 | 28.4341
Asfand
__export__.project_task_4808_345983c2 | FW: Things I use in Odoo |  |  |  | MMH: V15 Upgrade (P135) | Naseeb Razaq |  | 0 | 0 |  |  |  | New | Mountain Meadow Herbs | 191 | 0 | 0 | 2.099e-05 | 0
__export__.project_task_4593_69b9f649 | Shopify Connector Testing | Sprint 2136 | 2021-08-30 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hassan | 25.83 | 99.99 |  | SPLN |  | Complete | Zuma Sales LLC | 796 | 25.8333 | 0.0033333 | 0 | 171.223
__export__.project_task_4288_85fde750 | Setup DHL shipping method | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 2.25 | 64.29 |  |  |  | Cancelled | Zuma Sales LLC | 1640 | 3.5 | 1.25 | 0 | 350.2803
__export__.project_task_4158_1699355a | Upgrade Custom modules Estimate | Sprint 2128 | 2021-07-05 | Development | DGS: Odoo Audit and v14 Upgrade Estimate (P136) | Jeff Gross | Muzher Siddique | 2.83 | 100 |  |  | 2 | Complete | DG Solutions Inc. | 1829 | 2.5 | -0.33 | 0 | 44.9465
__export__.project_task_4080_eff22de6 | Import Product Price, Stock levels & Images |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 | Plan it for sprint |  |  | Planning | Mountain Meadow Herbs | 2048 | 4 | 4 | 0 | 0
__export__.project_task_4060_35a28d77 | Documents setup | Sprint 2126 | 2021-06-21 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2065 | 0 | 0 | 157.0075 | 40
__export__.project_task_3868_1ee9ee89 | Home Page Top bar and Main Menu improvements |  |  | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Kaleem Khan | 0.42 | 7 | Please add next activity |  |  | Backlog | Cellpoint Corporation | 2553 | 6 | 5.58 | 464.0133 | 0
__export__.project_task_3841_bac29bd8 | Golf Courses to be added in contacts with a check of "Golf Courses" | Sprint 2123 | 2021-05-31 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 4.92 | 89.45 |  |  | 1 | Complete | Perfect Golf Event | 2669 | 5.5 | 0.58 | 0 | 89.0092
__export__.project_task_3692_f04874c2 | Set up manufacturing partners as vendors | Sprint 2121 | 2021-05-17 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Perfect Golf Event | 2910 | 0 | 0 | 0 | 79.8685
__export__.project_task_3402_10ce2434 | Create training video for sign module | Sprint 2117 | 2021-04-19 | Demo to the client | Heronswood: Volunteer On-boarding (P79) | Jeff Gross | Bilal Ahmad Khan | 3.5 | 87.5 |  | MA Review |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3510 | 4 | 0.5 | 0 | 153.4345
__export__.project_task_3400_c31fdaca | Wildleaf critical functionalities automation |  |  | Development | Wild Leaf: Help (P22) | Levi Barnes |  | 11.07 | 92.25 |  |  | 4 | Cancelled | Wild Leaf Beverage | 3525 | 12 | 0.93 | 0 | 408
__export__.project_task_3329_6e70d76e | General |  |  | Internal Time Tracking | PWX: Help (P23) | Levi Barnes |  | 2.5 | 0 |  |  |  | Complete | EquityTeam | 3821 | 0 | -2.5 | 0 | 112.9653
__export__.project_task_3299_b2a681ae | code merge mid america |  |  | Development | Mid-America: Help (P37) |  |  | 1.5 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 3914 | 0 | -1.5 | 0 | 56
__export__.project_task_3052_be94efd27 | Initiate open issues and create tickets where necessary |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0.00061774 | 206.1934
__export__.project_task_2909_c741e798 | Establish workstreams for the client |  |  |  | DESIGN (P77) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1049.8144
__export__.project_task_2880_048425f0 | schedule appointments |  |  | Development | PWX: Field Service to Invoicing (P47) | Naseeb Razaq |  | 0 | 0 | To bring this thing in weekly meeting with Mark |  |  | Planning | EquityTeam | 4589 | 0 | 0 | 1039.8844 | 0
__export__.project_task_2852_bb5a45ea | Database Transition on AWS | Sprint 2112 | 2021-03-15 | Improvements | Continuant: Quotation Management / Automation (P31) | Jeff Gross | Muzher Siddique | 4.5 | 100 |  |  |  | Complete | Continuant | 4682 | 4.5 | 0 | 8 | 48
__export__.project_task_2837_ea0cfea0 | Receive Shipping Quotes from IL2000 | Sprint 2119 | 2021-05-03 | Development | Wild Leaf: IL2000 Integration (P40) | Jeff Gross | Fahad Hassan | 17.58 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 4700 | 7 | -10.58 | 16 | 456
__export__.project_task_2832_151426c0 | mobile shop view modification | Sprint 2110 | 2021-03-01 | Development | Mid-America: Help (P37) | Levi Barnes | Muhammad Bilal | 4.5 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 4707 | 3 | -1.5 | 0 | 103.0961
__export__.project_task_2640_79ee882f | Helpdesk (For Timesheets) |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Zubair | Faizan Zia Malik | 323.92 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5426 | 0 | -323.92 | 1124.707 | 1152.707
__export__.project_task_2438_e5d38f62 | Silverdale tech : Deployment Sprint 2103 | Sprint 2105 | 2021-01-25 | Configuration | Silverdale: Help (P12) | Muhammad Afzaal | Wajahat Ali | 1 | 85.71 |  |  |  | Complete | Silverdale Technology LLC | 5578 | 1.1667 | 0.16667 | 0.0059258 | 1.8156
__export__.project_task_1986_a9700772 | Configure Payment Methods | Sprint 2103 | 2021-01-11 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Kaesi Lee | 0 | 0 |  | 2014-01-01 |  | Complete | Wild Leaf Beverage | 6508 | 0 | 0 | 0 | 152
__export__.project_task_1848_9f2f57c8 | Move CPBids to a subaccount in SMTP2GO | Sprint 2053 | 2020-12-28 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 0.92 | 46 |  |  |  | Complete | Cellpoint Corporation | 6725 | 2 | 1.08 | 0 | 197.031
__export__.project_task_1505_79b9e79c | Seller Profile: Export Button | Sprint 2047 | 2020-11-16 | Studio | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 10 | 41.67 |  |  |  | Complete | Cellpoint Corporation | 7703 | 24 | 14 | 0 | 200
__export__.project_task_1286_deea6a90 | Customer Carrier Selection | Sprint 2044 | 2020-10-26 | Development | Moln: Help (P16) | Kaesi Lee | Gadha Continuant | 12 | 75 |  | Inventory |  | Complete | Moln Solutions, LLC | 8526 | 16 | 4 | 103.5125 | 197.93
Sales
__export__.project_task_1167_1a858c17 | Update Taxcloud setting for Delivery products | Sprint 29 | 2020-08-31 | Development | Moln: Help (P16) | Kaesi Lee |  | 1.25 | 100 |  |  |  | Complete | Moln Solutions, LLC | 9119 | 0.5 | -0.75 | 8 | 0
__export__.project_task_1129_203894fb | Consolidated Manifest for Buyers |  |  | Development | Cellpoint CPBids: Help (P7) |  |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9390 | 0 | 0 | 0 | 305.4327
__export__.project_task_1071_7f090f20 | Delete Auction RXFCR | Sprint 27 | 2020-08-17 | Configuration | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9554 | 0 | 0 | 0 | 0
__export__.project_task_1039_2e56de01 | Remove Kanban View | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_929_338065bf | 583: Android Release | Sprint 24 | 2020-07-27 | Development | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9924 | 2 | 2 | 0 | 0
__export__.project_task_365_f05fbd22 | Project View: Reverse Sprint Order | Sprint 23 | 2020-07-20 | Development | Silverdale: Help (P12) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 10204 | 6 | 6 | 0 | 0
__export__.project_task_210_782bea43 | Duplicate Updates in odoo app | Sprint 22 | 2020-07-12 |  | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10782 | 10 | 10 | 97.4064 | 1257.4064
__export__.project_task_190_4479baa1 | Setup all Historical Auction in Lot Table |  |  |  | Cellpoint: Belmont Manifest API Integration (P6) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10806 | 0 | 0 | 0 | 0
__export__.project_task_165_40402e6d | Make changes to odoo Module | Sprint 27 | 2020-08-17 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 0
__export__.project_task_4937_22793a98 | Server Action is making issue |  |  | Bug Fix | MMH: Help (SOR-17600) | Naseeb Razaq | Muhammad Bilal | 0 | 0 | Generate an estimate |  |  | Planning | Mountain Meadow Herbs | 0 | 0 | 0 | 0 | 0
__export__.project_task_4936_a4017e77 | Data Proofing |  |  | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 | Please add next activity | 2016-09-01 |  | New | Zuma Sales LLC | 1 | 0 | 0 | 0 | 0
Asfand
__export__.project_task_4935_f4257f9f | Conventional, Economy and Priority Cost | Sprint 2138 | 2021-09-13 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 0 | 0 | Generate an estimate | 2016-09-01 |  | Planning | Zuma Sales LLC | 1 | 0 | 0 | 0.25389 | 0
__export__.project_task_4934_aaab1c1d | Install module for JLG tax dropdown | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 | Check | 2016-09-01 |  | Backlog | Zuma Sales LLC | 3 | 0 | 0 | 2.1353e-06 | 0
Asfand
__export__.project_task_4933_6b435271 | Issue in SO Deposit Calculation in Other Info Part 2 | Sprint 2139 | 2021-09-20 | Development | Wild Pack Help (SOR-17586) | Naseeb Razaq | Raheel Aslam | 0 | 0 | Please add next activity | 2020-09-01 |  | Planning | Wild Leaf Beverage | 3 | 18 | 18 | 0 | 0
__export__.project_task_4932_10584829 | Hide Credit Note Button From Sales & Billing Group | Sprint 2138 | 2021-09-13 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 1.67 | 83.5 | Test on qa-2138 staging | 2017-09-01 |  | QA | Zuma Sales LLC | 8 | 2 | 0.33 | 0 | 0
Review Estimate
Danish
__export__.project_task_4931_d4df5675 | Add Delivery Address & Billing Address To SO Layout | Sprint 2138 | 2021-09-13 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 1.33 | 35.47 |  | 2016-09-01 |  | Complete | Zuma Sales LLC | 11 | 3.75 | 2.42 | 0 | 0
__export__.project_task_4930_cc51ef2b | Hide confirm button from Sales Users & Create Helpdesk Ticket for Wire | Sprint 2138 | 2021-09-13 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Aleem khan | 4.58 | 48.21 | Quality check this task | 2016-09-01 |  | QA | Zuma Sales LLC | 13 | 9.5 | 4.92 | 0 | 0
aleem
__export__.project_task_4928_22dd9843 | Draft Payment Transactions |  |  | Bug Fix | Wild Pack Help (SOR-17586) | Abdul Hameed | Abdul Hameed | 0 | 0 |  |  |  | Planning | Wild Leaf Beverage | 25 | 0 | 0 | 0.010344 | 0
__export__.project_task_4927_868d7b03 | Payment Transaction Error |  |  | Development | Wild Pack Help (SOR-17586) | Abdul Hameed | Aleem khan | 0 | 0 | Generate an estimate |  |  | Planning | Wild Leaf Beverage | 25 | 0 | 0 | 0.012252 | 0
__export__.project_task_4926_42f3c395 | AP Aging Report format | Sprint 2139 | 2021-09-20 | Development | Wild Pack Help (SOR-17586) | Naseeb Razaq | Aleem khan | 1.33 | 0 | Please add next activity |  |  | Planning | Wild Leaf Beverage | 29 | 0 | -1.33 | 3.7251e-05 | 0
Generate an estimate
__export__.project_task_4925_9b96793f | Install password strength module | Sprint 2138 | 2021-09-13 | Configuration | Wild Pack Help (SOR-17586) | Naseeb Razaq | Wajahat Ali | 0 | 0 | Deploy to QA |  |  | QA | Wild Leaf Beverage | 29 | 0 | 0 | 0 | 0
__export__.project_task_4924_3a6a7219 | Add Deliverable, Create Tasks and make them work silverdale way | Sprint 2138 | 2021-09-13 | Internal Time Tracking | Silverdale Technical Training (P115) | Faisal Huda Khan | Muzher Siddique | 0.5 | 1.67 |  |  |  | Complete | Silverdale Technology LLC | 29 | 30 | 29.5 | 0 | 7.3019
__export__.project_task_4923_639f4c27 | Auto refresh on iOS App is not working when lot number search is applied |  |  | Bug Fix | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema |  | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 30 | 4 | 4 | 0 | 1.3527
__export__.project_task_4922_c2b8d1f1 | Auto refresh on iOS App is not working when lot number search is applied | Sprint 2138 | 2021-09-13 | Bug Fix | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Kaleem Khan | 28 | 94.92 | Follow up with Apps Maven, Kaleem and update |  |  | In Progress | Cellpoint Corporation | 30 | 29.5 | 1.5 | 3.1702e-05 | 0
__export__.project_task_4921_99ef33a1 | Auto refresh on iOS App is not working when lot number search is applied |  |  |  | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema |  | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 30 | 0 | 0 | 0 | 1.4182
__export__.project_task_4920_6bc68318 | Trying to create a survey, but the links are not working | Sprint 2138 | 2021-09-13 | Development | Silverdale: Help (P12) | Muzher Siddique | Muzher Siddique | 2 | 66.67 | Please add next activity |  |  | PM Review | Silverdale Technology LLC | 31 | 3 | 1 | 0 | 0
__export__.project_task_4919_5af745aa | Tracking Number Review - Changes | Sprint 2139 | 2021-09-20 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Aleem khan | 5.77 | 72.12 | Review | 2015-09-01 |  | QA | Zuma Sales LLC | 33 | 8 | 2.23 | 0 | 0
fahad hasan
__export__.project_task_4917_15e28e80 | Breaks |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muzher Siddique |  | 24.92 | 83.07 |  |  |  | In Progress | Silverdale Technology LLC | 51 | 30 | 5.08 | 0.01447 | 0
__export__.project_task_4914_82a1b8d6 | Payment terms default to "Due on receipts" |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  | 2014-09-01 |  | Complete | Zuma Sales LLC | 51 | 0 | 0 | 0 | 0.037381
__export__.project_task_4913_42a81108 | Setup correct shipping configuration | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 | To Do | 2015-09-01 |  | Backlog | Zuma Sales LLC | 51 | 1 | 1 | 0.0082619 | 0
Fahad
__export__.project_task_4912_b7e8bb24 | Add demo videos in their eLearning module | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 52 | 1 | 1 | 0 | 13.579
__export__.project_task_4911_b75f242e | Connectors walkthrough | Sprint 2138 | 2021-09-13 | Demo to the client | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 | Please add next activity | 2015-09-01 |  | Backlog | Zuma Sales LLC | 52 | 2 | 2 | 0.0088403 | 0
Asfand
__export__.project_task_4910_d2f00cdf | Silverdale Meetings |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 40.95 | 100 | Please Review Task |  |  | Backlog | Silverdale Technology LLC | 53 | 40.1167 | -0.83333 | 0.0075487 | 0
__export__.project_task_4909_7ca20a45 | Need to show the sales credit view rather than summary invoice view | Sprint 2138 | 2021-09-13 | Development | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Aleem khan | 7.42 | 59.76 | Assign to a developer | 2015-09-01 |  | In Progress | Continuant | 54 | 12.4167 | 4.9967 | 0.024901 | 0
aleem
__export__.project_task_4908_2d6b3f48 | Handle issues from mobile apps after removing seller and location from lot |  |  | Development | Improvements for Belmont (P213) | Farman Ahmad Cheema | Wajahat Ali | 0.17 | 0.68 | Please add next activity |  |  | Planning | Cellpoint Corporation | 54 | 25 | 24.83 | 0 | 0
__export__.project_task_4907_acd6fd56 | Stripe numbers field not showing | Sprint 2138 | 2021-09-13 | Development | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Raheel Aslam | 5.08 | 84.67 | PM Review this task | 2015-09-01 |  | PM Review | Continuant | 54 | 6 | 0.92 | 0 | 0
__export__.project_task_4906_cf9edd02 | SFTP Status Update Issue in odoo | Sprint 2138 | 2021-09-13 | Bug Fix | Cellpoint: ecoATM API (P50) | Farman Ahmad Cheema | Sajjad Hussain | 5.75 | 98.57 | Please add next activity | 2015-09-01 |  | QA | Cellpoint Corporation | 56 | 5.8333 | 0.083333 | 8 | 0
Quality check this task
2016-09-01
__export__.project_task_4905_2cba472b | CPBids Status 7 Notifications are Duplicated | Sprint 2138 | 2021-09-13 | Bug Fix | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Kaleem Khan | 0.17 | 2.12 | Give feedback | 2015-09-01 |  | In Progress | Cellpoint Corporation | 56 | 8 | 7.83 | 8 | 0
__export__.project_task_4903_f551a1f6 | Location on lot view should show auction location not the one selected from location filter | Sprint 2138 | 2021-09-13 | Bug Fix | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Wajahat Ali | 5.12 | 100 | Follow up and Update | 2015-09-01 |  | QA | Cellpoint Corporation | 56 | 5 | -0.12 | 8 | 0
__export__.project_task_4902_44a83acd | CPBids Incorrect Status 8 Notifications to Observers | Sprint 2138 | 2021-09-13 | Bug Fix | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Kaleem Khan | 2.25 | 28.12 |  | 2015-09-01 |  | Complete | Cellpoint Corporation | 56 | 8 | 5.75 | 8 | 16
__export__.project_task_4901_8bea9884 | Location and seller filter on iOS should overwrite marketplace | Sprint 2138 | 2021-09-13 | Bug Fix | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Apps Maven | 2.67 | 76.29 |  |  |  | Complete | Cellpoint Corporation | 57 | 3.5 | 0.83 | 8 | 9.4897
__export__.project_task_4900_cd351b1d | APP Crashing for Search filter | Sprint 2138 | 2021-09-13 | Bug Fix | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Apps Maven | 5 | 71.43 | Follow up from Apps Maven, Kaleem and update this | 2017-09-01 |  | In Progress | Cellpoint Corporation | 57 | 7 | 2 | 8 | 0
__export__.project_task_4899_df55a083 | 500: Internal Server Error On Auction closing in Auction detail view | Sprint 2138 | 2021-09-13 | Bug Fix | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Aleem khan | 14.5 | 96.13 | Code push | 2015-09-01 |  | Integrated Testing | Cellpoint Corporation | 57 | 15.0833 | 0.58333 | 8 | 0
integrated testing
__export__.project_task_4897_0aec047e | Create groups for user roles | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 1.83 | 91.5 |  | 2013-09-01 |  | Complete | Zuma Sales LLC | 118 | 2 | 0.17 | 2.1501e-05 | 14.1367
Asfand
__export__.project_task_4895_4ed80484 | Run a scheduler for adding data from one field to another on a same model | Sprint 2138 | 2021-09-13 | Development | Heronswood: Collectors Database Phase 1 (P142) | Naseeb Razaq | Danish Hassan | 2.67 | 93.68 | Please Review Task |  |  | ELS | Port Gamble Sâ€™Klallam Foundation | 120 | 2.85 | 0.18 | 0 | 0
__export__.project_task_4894_87d67444 | "Preliminary Plant Name" field needed | Sprint 2138 | 2021-09-13 | Development | Heronswood: Collectors Database Phase 1 (P142) | Naseeb Razaq | Danish Hassan | 1.67 | 83.5 | Deploy to deployment |  |  | Integrated Testing | Port Gamble Sâ€™Klallam Foundation | 120 | 2 | 0.33 | 0 | 0
__export__.project_task_4893_c376e112 | Clients Meetings |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 2.67 | 0 |  |  |  | Complete | Silverdale Technology LLC | 121 | 0 | -2.67 | 0.0073081 | 3.429
__export__.project_task_4892_81e33913 | Training Sessions 2138 | Sprint 2138 | 2021-09-13 | Internal Training | Silverdale: Internal Project (P19) | Muhammad Zubair |  | 2.67 | 8.9 | Complete the task and Create Training plan for 2139 |  |  | In Progress | Silverdale Technology LLC | 121 | 30 | 27.33 | 6.2404 | 0
__export__.project_task_4891_ce261b97 | Re: SOR01506 | Sprint 2138 | 2021-09-13 | Configuration | Wild Pack Help (SOR-17586) | Naseeb Razaq | Abdul Hameed | 0.67 | 44.67 | Please add next activity | Checkout Process | 4 | Backlog | Wild Leaf Beverage | 121 | 1.5 | 0.83 | 3.7605 | 0
2015-09-01
__export__.project_task_4890_2bb55632 | Customers Unable to Sign Sales Quotations | Sprint 2138 | 2021-09-13 | Configuration | Wild Pack Help (SOR-17586) | Naseeb Razaq | Abdul Hameed | 0.58 | 38.67 | Please add next activity | 2015-09-01 | 4 | In Progress | Wild Leaf Beverage | 121 | 1.5 | 0.92 | 3.7918 | 0
Please Review Task
__export__.project_task_4889_1f7d0e42 | Routing Orders Through BSW | Sprint 2138 | 2021-09-13 | Configuration | Wild Pack Help (SOR-17586) | Naseeb Razaq | Abdul Hameed | 5.67 | 100 | Please add next activity | 2014-09-01 | 4 | In Progress | Wild Leaf Beverage | 121 | 5.5 | -0.17 | 3.8522 | 0
Please Review Task
2015-09-01
__export__.project_task_4888_41518638 | Scrap negative line item | Sprint 2138 | 2021-09-13 | Bug Fix | Wild Pack Help (SOR-17586) | Naseeb Razaq | Abdul Hameed | 1.42 | 47.33 |  |  |  | ELS | Wild Leaf Beverage | 121 | 3 | 1.58 | 3.9904 | 0
__export__.project_task_4887_98b8d5b9 | "View Sales Order" Link not working | Sprint 2138 | 2021-09-13 | Configuration | Wild Pack Help (SOR-17586) | Naseeb Razaq | Abdul Hameed | 0.5 | 25 | Please add next activity | 2014-09-01 |  | In Progress | Wild Leaf Beverage | 121 | 2 | 1.5 | 4 | 0
Please Review Task
2015-09-01
__export__.project_task_4886_49243a2c | List view as default in Websites | Sprint 2138 | 2021-09-13 | Development | MMH: Help (SOR-17600) | Naseeb Razaq | Danish Hassan | 1.92 | 96 | Please add next activity |  |  | Integrated Testing | Mountain Meadow Herbs | 123 | 2 | 0.08 | 0 | 0
__export__.project_task_4885_5838c38f | Copacking MO Validation error |  |  | Bug Fix | Wild Leaf: Help (P22) | Naseeb Razaq | Raheel Aslam | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 123 | 0 | 0 | 0 | 4.5901
__export__.project_task_4884_4918438a | Train Jeremy on adding equipment. Product configurator | Sprint 2138 | 2021-09-13 | Demo to the client | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 2 | 100 |  | 2014-09-01 |  | Complete | Zuma Sales LLC | 125 | 2 | 0 | 0 | 22.8923
Asfand
__export__.project_task_4883_08715525 | Look through eBay and Amazon contact list for eBay/Amazon email addresses | Sprint 2137 | 2021-09-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  | 2021-10-09 |  | Cancelled | Zuma Sales LLC | 125 | 0 | 0 | 2.4014e-06 | 5.2814
Meeting w/Bonnie
Asfand
__export__.project_task_4881_519a7213 | Demo preparation and Configuration & Testing | Sprint 2138 | 2021-09-13 | Configuration | Wild Leaf: Consignment and Sales Improvements (P112) | Naseeb Razaq |  | 2 | 66.67 | Please Schedule a Demo. |  | 4 | Backlog | Wild Leaf Beverage | 128 | 3 | 1 | 0 | 0
__export__.project_task_4880_181eeeb9 | Handling Tickets | Sprint 2138 | 2021-09-13 | Configuration | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Farman Ahmad Cheema | 8.5 | 85 | Update | 2017-09-01 |  | In Progress | Cellpoint Corporation | 128 | 10 | 1.5 | 16 | 0
__export__.project_task_4879_c2bed004 | cpbids support. | Sprint 2138 | 2021-09-13 | Internal Time Tracking | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema |  | 0 | 0 | Get team to update hours and close this task | 2017-09-01 |  | In Progress | Cellpoint Corporation | 128 | 17 | 17 | 16 | 0
__export__.project_task_4878_f873415f | Demo functionality to client | Sprint 2138 | 2021-09-13 | Client Meetings | Wild Leaf: Vendor Portal - Phase 1 (P49) | Naseeb Razaq | Naseeb Razaq | 0 | 0 | Please add next activity |  |  | Backlog | Wild Leaf Beverage | 141 | 0.5 | 0.5 | 0 | 0
__export__.project_task_4877_27f097a0 | Plan rollout with Matt Koepp | Sprint 2138 | 2021-09-13 | Client Meetings | Wild Leaf: Vendor Portal - Phase 1 (P49) | Naseeb Razaq | Naseeb Razaq | 0 | 0 | To Do |  |  | Backlog | Wild Leaf Beverage | 141 | 0.25 | 0.25 | 0 | 0
__export__.project_task_4876_ba49dbb0 | Configure portal to show open Vendor Bills | Sprint 2138 | 2021-09-13 | Configuration | Wild Leaf: Vendor Portal - Phase 1 (P49) | Naseeb Razaq | Abdul Hameed | 0 | 0 | Your task missed the deadline! | 2016-09-01 | 4 | Backlog | Wild Leaf Beverage | 141 | 0.33333 | 0.33333 | 0 | 0
__export__.project_task_4875_844270e8 | Configure portal to show open POs | Sprint 2138 | 2021-09-13 | Configuration | Wild Leaf: Vendor Portal - Phase 1 (P49) | Naseeb Razaq | Abdul Hameed | 0 | 0 | To Do | 2016-09-01 | 3 | Backlog | Wild Leaf Beverage | 141 | 0.33333 | 0.33333 | 0 | 0
__export__.project_task_4874_5eb18d5d | Create email template for Vendor rollout | Sprint 2138 | 2021-09-13 | Configuration | Wild Leaf: Vendor Portal - Phase 1 (P49) | Naseeb Razaq | Abdul Hameed | 0 | 0 | Please add next activity | 2016-09-01 | 2 | Backlog | Wild Leaf Beverage | 141 | 2 | 2 | 0 | 0
__export__.project_task_4873_69d38761 | Enable customers to make payments on portal | Sprint 2138 | 2021-09-13 | Client Meetings | Wild Leaf: Customer Portal (P125) | Naseeb Razaq | Naseeb Razaq | 0 | 0 | To Do |  |  | Backlog | Wild Leaf Beverage | 141 | 0.33333 | 0.33333 | 0 | 0
__export__.project_task_4872_5f89aa7d | Plan rollout with Matt Koepp | Sprint 2138 | 2021-09-13 | Client Meetings | Wild Leaf: Customer Portal (P125) | Naseeb Razaq | Naseeb Razaq | 0 | 0 | To Do |  |  | Backlog | Wild Leaf Beverage | 141 | 0.5 | 0.5 | 2.7364e-05 | 0
__export__.project_task_4871_b3ffbd11 | Demo functionality to client | Sprint 2138 | 2021-09-13 | Demo to the client | Wild Leaf: Customer Portal (P125) | Naseeb Razaq | Naseeb Razaq | 0 | 0 | To Do |  |  | Backlog | Wild Leaf Beverage | 141 | 0.5 | 0.5 | 0 | 0
__export__.project_task_4870_972bc96b | Configure open SOs for customers | Sprint 2138 | 2021-09-13 | Configuration | Wild Leaf: Customer Portal (P125) | Naseeb Razaq | Naseeb Razaq | 0 | 0 | To Do |  |  | Backlog | Wild Leaf Beverage | 141 | 0.16667 | 0.16667 | 0 | 0
__export__.project_task_4869_50d18df3 | Configure open invoices for customers | Sprint 2138 | 2021-09-13 | Configuration | Wild Leaf: Customer Portal (P125) | Naseeb Razaq | Naseeb Razaq | 0 | 0 | To Do |  |  | Backlog | Wild Leaf Beverage | 141 | 0.5 | 0.5 | 0 | 0
__export__.project_task_4868_ae55d4ce | Configure open invoices on portal | Sprint 2138 | 2021-09-13 | Configuration | Wild Leaf: Customer Portal (P125) | Naseeb Razaq | Naseeb Razaq | 0 | 0 | To Do |  |  | Backlog | Wild Leaf Beverage | 141 | 0.33333 | 0.33333 | 0 | 0
__export__.project_task_4867_4ef8be98 | Create an email template to send to customers | Sprint 2138 | 2021-09-13 | Configuration | Wild Leaf: Customer Portal (P125) | Naseeb Razaq | Abdul Hameed | 0 | 0 | Create Email Template to roll out Customers to get customer portal user access | 2015-09-01 | 2 | In Progress | Wild Leaf Beverage | 142 | 1.5 | 1.5 | 0 | 0
To Do
2016-09-01
__export__.project_task_4866_3ef963ba | Create a client check list for starting a project | Sprint 2138 | 2021-09-13 | Documentation | Silverdale: Sales Team On-Boarding (P201) | Erin Olson |  | 0 | 0 | training material and timeline |  |  | Backlog | Silverdale Technology LLC | 143 | 1 | 1 | 0 | 0
__export__.project_task_4865_65d33a2e | Demo Meetings & Preparation With client | Sprint 2138 | 2021-09-13 | Configuration | Wild Leaf: Marketing Automation Set up (P187) | Abdul Hameed | Abdul Hameed | 3.5 | 100 | Demo With Client |  |  | Complete | Wild Leaf Beverage | 143 | 2.6667 | -0.83333 | 6.4039 | 17.8348
Please Review Task
__export__.project_task_4864_88068a8e | Create Demo Video | Sprint 2138 | 2021-09-13 | Configuration | Wild Leaf: Marketing Automation Set up (P187) | Naseeb Razaq | Abdul Hameed | 0 | 0 | To Do |  |  | Backlog | Wild Leaf Beverage | 143 | 2 | 2 | 0 | 0
__export__.project_task_4863_c87e2bdd | Zuma Meetings (Tickets and Tasks) |  |  | Internal Time Tracking | Zuma: Help (P97) | Fahad Hussain Malik |  | 14.08 | 46.93 | Close Ticket |  |  | Backlog | Zuma Sales LLC | 145 | 30 | 15.92 | 0 | 0
__export__.project_task_4850_98366ab7 | Exclude SLA time until ticket is blocked | Sprint 2137 | 2021-09-06 | Development | Silverdale: Devops (P84) | Muhammad Afzaal | Muzher Siddique | 0 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 150 | 6 | 6 | 0 | 8
__export__.project_task_4849_55f02e01 | Error message: Product Analytical Account is Required | Sprint 2138 | 2021-09-13 | Configuration | Wild Pack Help (SOR-17586) | Naseeb Razaq | Abdul Hameed | 6.67 | 100 |  | 2014-09-01 | 3 | In Progress | Wild Leaf Beverage | 150 | 6 | -0.67 | 16 | 0
__export__.project_task_4848_642b28f5 | Posted Entries Error |  |  | Bug Fix | Wild Pack Help (SOR-17586) | Jeff Gross | Raheel Aslam | 3 | 100 | Provide Update |  |  | PM Review | Wild Leaf Beverage | 151 | 3 | 0 | 16 | 0
__export__.project_task_4847_f1a90132 | Wild Leaf Deployment 2137 | Sprint 2138 | 2021-09-13 | Development | Wild Pack Help (SOR-17586) | Naseeb Razaq |  | 7 | 100 | Your task missed the deadline! |  |  | Complete | Wild Leaf Beverage | 152 | 4.6667 | -2.3333 | 16 | 24
Where is PD Testing Video
Edit the attached video
__export__.project_task_4846_75a74d3e | API testing |  |  | Integration | Wild Leaf: Wildpack Printing (P68) | Naseeb Razaq | Sanaullah Khan | 0 | 0 | Generate an estimate |  |  | Backlog | Wild Leaf Beverage | 152 | 1 | 1 | 0 | 0
To Do
__export__.project_task_4845_6f58735c | Split MO Functionality Review | Sprint 2137 | 2021-09-06 | Development | Wild Pack Help (SOR-17586) | Naseeb Razaq | Aleem khan | 10.42 | 74.43 |  | SPLN |  | ELS | Wild Leaf Beverage | 156 | 14 | 3.58 | 16 | 0
__export__.project_task_4843_7658e4c9 | Meetings |  |  | Client Meetings | Improvements for Belmont (P213) | Farman Ahmad Cheema |  | 0.5 | 0 |  |  |  | Complete | Cellpoint Corporation | 168 | 0 | -0.5 | 0 | 18.7806
__export__.project_task_4842_39cef9ab | Add new vendor and also ASN Vendor format for that vendor | Sprint 2137 | 2021-09-06 | Configuration | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Farman Ahmad Cheema | 0.5 | 100 |  |  |  | Complete | Cellpoint Corporation | 168 | 0.5 | 0 | 3.133 | 3.7125
__export__.project_task_4841_e9167aea | Create products with grade variations |  |  | Development | Improvements for Belmont (P213) | Farman Ahmad Cheema | Wajahat Ali | 0 | 0 | Need images of all the grades (All products) from Belmont team |  |  | Planning | Cellpoint Corporation | 169 | 6 | 6 | 0 | 0
__export__.project_task_4840_f6bffb34 | Products - Applying "Lab tested" filter causing an Odoo error. | Sprint 2138 | 2021-09-13 | Bug Fix | MMH: Help (SOR-17600) | Naseeb Razaq |  | 2.33 | 66.57 | Deploy to production |  |  | Deployment | Mountain Meadow Herbs | 169 | 3.5 | 1.17 | 0 | 0
__export__.project_task_4817_1f246b1e | Accounting - Unrealized Currencies Gains/Losses report accessibility issue. | Sprint 2138 | 2021-09-13 | Bug Fix | PWX: Help (SOR-17593) | Farman Ahmad Cheema | Muzher Siddique | 9 | 85.71 | PM Review this task | 2015-09-01 |  | PM Review | EquityTeam | 174 | 10.5 | 1.5 | 0 | 0
__export__.project_task_4815_23decbe6 | Web notification Code Review and resolve | Sprint 2138 | 2021-09-13 | Bug Fix | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Wajahat Ali | 4.83 | 96.6 | Complete testing with critical function and apps refreshing issue | 2015-09-01 |  | QA | Cellpoint Corporation | 176 | 5 | 0.17 | 24 | 0
__export__.project_task_4814_4bf4d379 | Silverdale Meetings |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 29 | 0 |  |  |  | Complete | Silverdale Technology LLC | 176 | 0 | -29 | 0 | 24
__export__.project_task_4813_d642f52b | Training Session 8th and 9th September 2021 - Consultant Role | Sprint 2137 | 2021-09-06 | Internal Training | Silverdale: Internal Project (P19) | Muhammad Zubair |  | 6.17 | 51.42 |  |  |  | Complete | Silverdale Technology LLC | 176 | 12 | 5.83 | 0 | 20.3392
__export__.project_task_4810_66a9ebb9 | Create a wizard to import file data and create auctions |  |  | Development | Improvements for Belmont (P213) | Farman Ahmad Cheema | Kaleem Khan | 0.17 | 0.71 | Please add next activity |  |  | Planning | Cellpoint Corporation | 178 | 24 | 23.83 | 0 | 0
__export__.project_task_4809_dfd616cd | Create Model for mapping csv file fields |  |  | Development | Improvements for Belmont (P213) | Farman Ahmad Cheema | Kaleem Khan | 0 | 0 | Please add next activity |  |  | Planning | Cellpoint Corporation | 178 | 18 | 18 | 0 | 0
__export__.project_task_4807_41ebff87 | FW: Next week Odoo |  |  |  | MMH: V15 Upgrade (P135) | Naseeb Razaq |  | 0 | 0 | Please add next activity |  |  | Planning | Mountain Meadow Herbs | 191 | 0 | 0 | 0 | 0
__export__.project_task_4806_45eee9b8 | Farman's Video ( P165) |  |  | Creative | Silverdale Time Tracking (P56) | Muhammad Zubair | Shehroz Faiq | 6.92 | 81.41 | Shoot Video |  |  | In Progress | Silverdale Technology LLC | 192 | 8.5 | 1.58 | 26.8495 | 0
__export__.project_task_4805_2a9dceb8 | Customer Quote Email - Change Button | Sprint 2138 | 2021-09-13 | Development | Perfect Golf: Help (SOR-17621) | Farman Ahmad Cheema | Danish Hassan | 2.75 | 78.57 | PM Review this task | 2017-09-01 |  | PM Review | Perfect Golf Event | 193 | 3.5 | 0.75 | 0 | 0
__export__.project_task_4804_75112029 | Change Button in Portal | Sprint 2138 | 2021-09-13 | Development | Perfect Golf: Help (SOR-17621) | Farman Ahmad Cheema | Sajjad Hussain | 5 | 62.5 | Deploy on Deployment for Integrated Testing | SPLN |  | Integrated Testing | Perfect Golf Event | 193 | 8 | 3 | 0 | 0
2017-09-01
__export__.project_task_4803_5a323d06 | Error Processing WLVPRD/00426 |  |  | Bug Fix | Wild Pack Help (SOR-17586) | Naseeb Razaq | Aleem khan | 7.75 | 96.88 |  |  |  | ELS | Wild Leaf Beverage | 194 | 8 | 0.25 | 28.2844 | 0
__export__.project_task_4801_d8f111a2 | Activity - Client Demo Sessions |  |  | Demo to the client | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Plan |  |  | New | Silverdale Technology LLC | 196 | 0 | 0 | 0 | 0
__export__.project_task_4799_6ebe7ac0 | Daily Tasks & Ticket Handling |  |  | Configuration | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 6.5 | 0 |  |  |  | Complete | Silverdale Technology LLC | 200 | 0 | -6.5 | 0 | 40
__export__.project_task_4798_264bb9de | training |  |  | Improvements | Silverdale Time Tracking (P56) | Muhammad Afzaal | Raheel Aslam | 6.17 | 0 |  |  |  | Complete | Silverdale Technology LLC | 201 | 0 | -6.17 | 0 | 8
__export__.project_task_4797_c3f46d6b | Forecasted Negative Date Wise Dashboard | Sprint 2137 | 2021-09-06 | Configuration | Wild Pack Help (SOR-17586) | Naseeb Razaq | Abdul Hameed | 4.83 | 99.93 |  | SPLN |  | ELS | Wild Leaf Beverage | 219 | 4.8333 | 0.0033333 | 36.4334 | 0
__export__.project_task_4796_3421ccb2 | Breaks |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 32.67 | 100 |  |  |  | Complete | Silverdale Technology LLC | 220 | 30 | -2.67 | 0.011889 | 38.3027
__export__.project_task_4795_2ab96cc2 | Deployment MM-Herbs | Sprint 2137 | 2021-09-06 | Deployment | MMH: Help (P83) | Naseeb Razaq |  | 3 | 0 |  |  |  | Complete | Mountain Meadow Herbs | 226 | 0 | -3 | 0 | 8.8422
__export__.project_task_4793_5d2206f4 | Deployment ECO-ATM API-2137 | Sprint 2138 | 2021-09-13 | Deployment | Cellpoint: ecoATM API (P50) | Farman Ahmad Cheema | Kaleem Khan | 17.5 | 97.22 |  |  |  | Complete | Cellpoint Corporation | 288 | 18 | 0.5 | 35.0098 | 43.782
__export__.project_task_4791_f69f40ad | Create Tasks when Project Stage changes | Sprint 2138 | 2021-09-13 | Development | Silverdale: Devops (P84) | Muzher Siddique | Sajjad Hussain | 9.17 | 94.86 | Quality check this task |  |  | QA | Silverdale Technology LLC | 288 | 9.6667 | 0.49667 | 0 | 0
__export__.project_task_4789_bf23ab5d | P&L Reports Totals for Groups - Part 2 |  |  | Development | Wild Leaf: P&L Reports Totals for groups (P193) | Abdul Hameed | Aleem khan | 0 | 0 | When this task gonna complete? |  |  | Planning | Wild Leaf Beverage | 289 | 18 | 18 | 0 | 0
__export__.project_task_4788_940133f3 | Automation: Notify Salesperson / Sales Team When MO Complete | Sprint 2137 | 2021-09-06 | Configuration | Wild Pack Help (SOR-17586) | Naseeb Razaq | Abdul Hameed | 2.25 | 37.5 |  | SPLN |  | ELS | Wild Leaf Beverage | 290 | 6 | 3.75 | 44 | 0
__export__.project_task_4787_3be3f45d | SO & PO Synchronize & Set up |  |  | Configuration | Wild Leaf: Multi-company Set up Phase 1 (P200) | Abdul Hameed | Abdul Hameed | 0 | 0 | What is the progress? Update please. |  |  | In Progress | Wild Leaf Beverage | 290 | 1 | 1 | 0 | 0
__export__.project_task_4786_f2ad3f96 | Demo Preparation |  |  | Internal Time Tracking | Wild Leaf: Multi-company Set up Phase 1 (P200) | Abdul Hameed | Abdul Hameed | 1.33 | 100 |  | 24hrs/update |  | In Progress | Wild Leaf Beverage | 290 | 1 | -0.33 | 0 | 0
__export__.project_task_4785_8904573d | Demo Presentation |  |  | Configuration | Wild Leaf: Multi-company Set up Phase 1 (P200) | Abdul Hameed | Abdul Hameed | 0 | 0 |  | 24hrs/update |  | In Progress | Wild Leaf Beverage | 290 | 1 | 1 | 0 | 0
__export__.project_task_4784_81e3f27e | Reporting based on Analytics in Consolidation |  |  | Configuration | Wild Leaf: Multi-company Set up Phase 1 (P200) | Abdul Hameed | Abdul Hameed | 0 | 0 |  |  |  | Backlog | Wild Leaf Beverage | 290 | 2 | 2 | 0 | 0
__export__.project_task_4783_552b379f | External Email are not receiving into odoo helpdesk ticket | Sprint 2137 | 2021-09-06 | Bug Fix | Wild Leaf: Implement Helpdesk (P184) | Naseeb Razaq | Naseeb Razaq | 0 | 0 |  | SPLN |  | ELS | Wild Leaf Beverage | 291 | 2 | 2 | 0 | 0
__export__.project_task_4782_27ed4e24 | Internal Quiz for v15 with small giveaways |  |  | Internal Training | Odoo Experience 2021 (P208) | Muhammad Zubair | Faisal Huda Khan | 0 | 0 | Design |  |  | Planning | Silverdale Technology LLC | 293 | 0 | 0 | 0 | 0
__export__.project_task_4773_8f52cce5 | Error when using KNow System quick access button (next to Scheduled Activities button) | Sprint 2137 | 2021-09-06 | Bug Fix | Silverdale: Help (P12) | Muhammad Zubair | Aleem khan | 4 | 61.54 |  | SPLN |  | Complete | Silverdale Technology LLC | 294 | 6.5 | 2.5 | 0 | 53.1711
__export__.project_task_4772_9c526b9a | Kishan has to incorporate changes needed |  |  | Bug Fix | MMH Dr. Clark: Help (P106) | Naseeb Razaq | Wajahat Ali | 2.67 | 0 |  |  |  | Complete | Mountain Meadow Herbs | 296 | 0 | -2.67 | 0 | 48
__export__.project_task_4771_54770c58 | cpbids.com/my - dates are in an incorrect format | Sprint 2138 | 2021-09-13 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Sajjad Hussain | 5.33 | 79.95 | Deploy on Deployment for Integrated Testing | SPLN |  | Integrated Testing | Cellpoint Corporation | 296 | 6.6667 | 1.3367 | 48 | 0
2015-09-01
__export__.project_task_4770_e0575ff8 | cpbids.com/my - add Seller to the Won Auctions page | Sprint 2138 | 2021-09-13 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Sajjad Hussain | 5.75 | 100 | Integrated testing | SPLN |  | Integrated Testing | Cellpoint Corporation | 296 | 5.75 | 0 | 48 | 0
Code Push
2017-09-01
__export__.project_task_4769_dd8f1ef4 | cpbids.com/my/auctions - Inconsistent Tab Formats | Sprint 2138 | 2021-09-13 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Kaleem Khan | 4 | 80 | code push | SPLN |  | Integrated Testing | Cellpoint Corporation | 296 | 5 | 1 | 40 | 0
Integrated Testing
2015-09-01
__export__.project_task_4766_54522ed9 | Wildleaf-Deployment 2137 | Sprint 2137 | 2021-09-06 | Deployment | Wild Leaf: Help (P22) | Naseeb Razaq | Muzher Siddique | 5.25 | 100 |  |  |  | Complete | Wild Leaf Beverage | 300 | 4 | -1.25 | 0 | 24
__export__.project_task_4765_6f7aac80 | PWX-Deployment 2136 | Sprint 2137 | 2021-09-06 | Deployment | PWX: Help (P23) | Farman Ahmad Cheema | Muzher Siddique | 5.08 | 100 |  |  |  | Complete | EquityTeam | 300 | 4.5 | -0.58 | 0 | 8
__export__.project_task_4762_da0689a6 | Handling Tickets | Sprint 2137 | 2021-09-06 | Configuration | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Farman Ahmad Cheema | 9.5 | 100 |  |  |  | Complete | Cellpoint Corporation | 313 | 8 | -1.5 | 43.6711 | 47.2161
__export__.project_task_4761_22cc6608 | List out the installed modules which are charging cost | Sprint 2137 | 2021-09-06 | Configuration | PWX: Help (P23) | Farman Ahmad Cheema | Farman Ahmad Cheema | 0.75 | 37.5 |  |  |  | Complete | EquityTeam | 313 | 2 | 1.25 | 3.7612e-05 | 19.7467
__export__.project_task_4760_414ec26b | Solution Design |  |  | Configuration | Wild Leaf: Wildpack Printing (P68) | Naseeb Razaq | Naseeb Razaq | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 313 | 15 | 15 | 0 | 35.8518
__export__.project_task_4759_bee333fd | Information Gathering Session on Consolidation |  |  | Requirements Collection | Wild Leaf: Multi-company Set up Phase 1 (P200) | Abdul Hameed | Abdul Hameed | 0.33 | 66 |  |  |  | Complete | Wild Leaf Beverage | 314 | 0.5 | 0.17 | 0 | 36
__export__.project_task_4758_69fd4aa5 | Adjust inventory to zero | Sprint 2138 | 2021-09-13 | Configuration | Mid-America: Help (P37) | Naseeb Razaq | Naseeb Razaq | 0 | 0 | To Do |  |  | Backlog | Mid-America Gardens, LLC | 314 | 3 | 3 | 0 | 0
__export__.project_task_4757_7131885c | Consolidation for Multi Company Part-2 |  |  | Configuration | Wild Leaf: Multi-company Set up Phase 1 (P200) | Abdul Hameed | Abdul Hameed | 4.5 | 100 |  | 24hrs/update | 3 | In Progress | Wild Leaf Beverage | 314 | 4 | -0.5 | 0 | 0
__export__.project_task_4756_475d13c8 | Run through the whole google calendar setup | Sprint 2138 | 2021-09-13 | Configuration | PWX: Help (SOR-17593) | Farman Ahmad Cheema | Farman Ahmad Cheema | 4 | 40 | To Do | SPLN |  | Backlog | EquityTeam | 315 | 10 | 6 | 0 | 0
2016-09-01
__export__.project_task_4755_709caf33 | Can someone else remotely log into and use my account? |  |  | Development | Wild Leaf: Help (P22) | Naseeb Razaq | Aleem khan | 3.33 | 41.62 |  |  |  | Cancelled | Wild Leaf Beverage | 316 | 8 | 4.67 | 0 | 48.9087
__export__.project_task_4753_34d50faa | Introduction Video | Sprint 2136 | 2021-08-30 | Documentation | Silverdale: Help: Creative (P103) | Faisal Huda Khan | Nick Foy | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 318 | 0 | 0 | 0.1348 | 14.8704
__export__.project_task_4752_d1ec4d5a | 2137 - CPBids Database Upgradation | Sprint 2138 | 2021-09-13 | Development | Cellpoint: CPBids Upgrade to v14 (P161) | Farman Ahmad Cheema | Wajahat Ali | 7.5 | 50 |  | SPLN |  | Complete | Cellpoint Corporation | 321 | 15 | 7.5 | 0 | 56
__export__.project_task_4750_537de66b | Demo Presentation |  |  |  | Wild Leaf: Multi-company Set up Phase 1 (P200) | Abdul Hameed |  | 0.67 | 0 |  |  |  | Complete | Wild Leaf Beverage | 336 | 0 | -0.67 | 0 | 2.6731
__export__.project_task_4749_602b808e | Demo Preparation |  |  |  | Wild Leaf: Multi-company Set up Phase 1 (P200) | Abdul Hameed |  | 1 | 0 |  |  |  | Complete | Wild Leaf Beverage | 336 | 0 | -1 | 0 | 2.6894
__export__.project_task_4748_8aacebe2 | Add Source Document for WLV/WLVOUT/00062 | Sprint 2137 | 2021-09-06 | Improvements | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Raheel Aslam | 2.5 | 100 |  | Need Assistance | 1 | Complete | Wild Leaf Beverage | 343 | 0.66667 | -1.8333 | 0 | 11.7944
__export__.project_task_4747_e379b548 | cpbids support. | Sprint 2137 | 2021-09-06 | Internal Time Tracking | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Kaleem Khan | 17 | 100 |  |  |  | Complete | Cellpoint Corporation | 347 | 17 | 0 | 56 | 56
__export__.project_task_4746_b48bad81 | Timesheet & Planning Enable issue | Sprint 2139 | 2021-09-20 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Raheel Aslam | 5.33 | 59.22 | Follow up | 2027-09-01 |  | Backlog | Zuma Sales LLC | 347 | 9 | 3.67 | 0 | 0
Fahad
__export__.project_task_4745_24d97642 | Timezone conversion | Sprint 2136 | 2021-08-30 | Bug Fix | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Kaleem Khan | 14.25 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 348 | 14.25 | 0 | 0 | 53.4228
__export__.project_task_4744_c5291f8e | Clean data on Production environment | Sprint 2136 | 2021-08-30 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 5.08 | 100 |  |  |  | Complete | Cellpoint Corporation | 348 | 2 | -3.08 | 0 | 0
__export__.project_task_4743_bf9fec30 | Change the Tickets count on Project Kanban card | Sprint 2137 | 2021-09-06 | Development | Silverdale: Help (P12) | Muhammad Zubair | Sajjad Hussain | 6.58 | 85.83 |  | SPLN |  | ELS | Silverdale Technology LLC | 348 | 7.6667 | 1.0867 | 0 | 0
__export__.project_task_4742_099ad035 | Client Dashboard error (#2576) |  |  | Bug Fix | Silverdale: Help (P12) | Muhammad Zubair |  | 3.67 | 91.75 |  |  |  | Complete | Silverdale Technology LLC | 348 | 4 | 0.33 | 0 | 16
__export__.project_task_4741_f14f8180 | Attach Sales Order to Mail Template When DropShip Order is placed | Sprint 2138 | 2021-09-13 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Aleem khan | 4.67 | 77.83 | This task missed the deadline! | SPLN |  | Integrated Testing | Zuma Sales LLC | 363 | 6 | 1.33 | 0 | 0
Your task missed the deadline!
deploy & do Integration Testing
2014-09-01
fahad hasan
__export__.project_task_4740_f355c140 | Setup Client Assignment by Delivery Team | Sprint 2136 | 2021-08-30 | Configuration | Silverdale: Internal Project (P19) | Muhammad Afzaal |  | 0 | 0 |  | SPLN |  | Complete | Silverdale Technology LLC | 363 | 1 | 1 | 0.010139 | 50.614
__export__.project_task_4739_39d2dbab | Consolidation Setup for multi companies - Part 1 |  |  | Configuration | Wild Leaf: Multi-company Set up Phase 1 (P200) | Abdul Hameed |  | 1.5 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 364 | 1.5 | 0 | 0 | 5.4558
__export__.project_task_4738_b5d7b6d5 | Inventory Synchronization & Set up |  |  | Configuration | Wild Leaf: Multi-company Set up Phase 1 (P200) | Abdul Hameed |  | 2 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 364 | 2 | 0 | 9.0492e-06 | 5.482
__export__.project_task_4737_87d3343d | Add Chatter to Projects | Sprint 2136 | 2021-08-30 | Development | Silverdale: Internal Project (P19) | Muhammad Zubair | Aleem khan | 3.83 | 95.75 |  | SPLN |  | Complete | Silverdale Technology LLC | 364 | 4 | 0.17 | 13.922 | 67.3418
__export__.project_task_4736_f404a712 | Timesheet & Planning Enable issue |  |  | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 364 | 0 | 0 | 0 | 25.9949
__export__.project_task_4735_cc5dd7f3 | Create Amazon authorized user | Sprint 2136 | 2021-08-30 | Configuration | MMH: Amazon Module Automation (P102) | Naseeb Razaq | Fahad Hassan | 4 | 100 |  |  |  | Complete | Mountain Meadow Herbs | 369 | 4 | 0 | 0 | 24
__export__.project_task_4734_9cb10a5c | Multi Company Configuration |  |  | Configuration | Wild Leaf: Multi-company Set up Phase 1 (P200) | Abdul Hameed |  | 2.25 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 369 | 2 | -0.25 | 0 | 8
__export__.project_task_4732_fe96f882 | Project Review Meeting |  |  | Requirements Collection | Wild Pack Help (SOR-17586) | Naseeb Razaq | Abdul Hameed | 0.5 | 25 | Please add next activity |  | 3 | Backlog | Wild Leaf Beverage | 384 | 2 | 1.5 | 74.7355 | 0
__export__.project_task_4730_bc55a9ce | google meet link |  |  | Development | PWX: Help (SOR-17593) | Naseeb Razaq |  | 0 | 0 | Add Description and video |  |  | Planning | EquityTeam | 387 | 2 | 2 | 20.3611 | 0
__export__.project_task_4728_8ad6716c | Silverdale Meeting | Sprint 2136 | 2021-08-30 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 58.27 | 100 |  |  |  | Complete | Silverdale Technology LLC | 388 | 49 | -9.27 | 3.6476e-05 | 38.3275
__export__.project_task_4727_e549f559 | Breaks | Sprint 2136 | 2021-08-30 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 38.42 | 100 |  |  |  | Complete | Silverdale Technology LLC | 388 | 31.3333 | -7.0867 | 0.013851 | 35.6608
__export__.project_task_4726_62f3b08b | Conflict Between Deposit & Consignment | Sprint 2136 | 2021-08-30 | Development | Wild Leaf: Help (P22) | Naseeb Razaq | Muzher Siddique | 4.33 | 72.17 |  | SPLN |  | Complete | Wild Leaf Beverage | 389 | 6 | 1.67 | 22.3956 | 78.3956
__export__.project_task_4725_1eb83f04 | Pictures Editing |  |  | Creative | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 389 | 0 | 0 | 0 | 78.5881
__export__.project_task_4696_109cebe5 | Pre-Planning Silverdale Debate Videos |  |  | Creative | Silverdale debate Videos | Faisal Huda Khan | Shehroz Faiq | 8 | 0 | Please add next activity |  |  | Backlog | Silverdale Technology LLC | 392 | 0 | -8 | 80 | 0
__export__.project_task_4695_17cc1dc3 | Create an Automated Action for Leads |  |  | Studio | CraftAG: Help (P138) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Cancelled | CraftAG | 392 | 0 | 0 | 0 | 60
__export__.project_task_4691_5cfb1d6e | Workflow from Chris |  |  | Requirements Collection | Wild Leaf: Wildpack Printing (P68) | Naseeb Razaq | Naseeb Razaq | 0.58 | 58 |  |  |  | Complete | Wild Leaf Beverage | 454 | 1 | 0.42 | 29.1492 | 77.3581
__export__.project_task_4690_7b81b4da | Install user roles module | Sprint 2137 | 2021-09-06 | Configuration | Wild Pack Help (SOR-17586) | Naseeb Razaq | Naseeb Razaq | 1.5 | 75 | Install on production | SPLN |  | Deployment | Wild Leaf Beverage | 458 | 2 | 0.5 | 84.0281 | 0
Day 2 and no updates
__export__.project_task_4689_d18847c4 | Lots and Lot units on invoices based on Production |  |  | Development | Wild Leaf: Lots and Lots Units on Invoices based on Production (P176) | Naseeb Razaq | Raheel Aslam | 5.5 | 34.38 | Please add next activity |  |  | Backlog | Wild Leaf Beverage | 459 | 16 | 10.5 | 84.621 | 0
__export__.project_task_4688_69684cf6 | deployement : cpbid(p7) | Sprint 2135 | 2021-08-23 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 2.17 | 0 |  |  |  | Complete | Cellpoint Corporation | 460 | 0 | -2.17 | 0.017933 | 1.8563
__export__.project_task_4687_14458eca | Split Functionality Required on GRN'S Receipt |  |  | Development | Wild Leaf: Split Functionality Required on Stock Picking (P196) | Naseeb Razaq |  | 0.75 | 0 | Please add next activity |  |  | Planning | Wild Leaf Beverage | 462 | 0 | -0.75 | 88 | 0
__export__.project_task_4686_72fad6db | Customer Prospect Functionality Issue | Sprint 2136 | 2021-08-30 | Bug Fix | Wild Leaf: Sales Improvements (P150) | Naseeb Razaq | Aleem khan | 12.25 | 100 |  | SPLN |  | Complete | Wild Leaf Beverage | 463 | 11.1667 | -1.0833 | 32 | 93.4214
__export__.project_task_4685_4cb14c14 | Pallet Build Info not Carrying over to PRD Order |  |  | Bug Fix | Wild Pack Help (SOR-17586) | Naseeb Razaq | Aleem khan | 0.5 | 50 | Please add next activity |  |  | Backlog | Wild Leaf Beverage | 463 | 1 | 0.5 | 88 | 0
__export__.project_task_4684_928e3ffe | Consignment Configuration on Production | Sprint 2136 | 2021-08-30 | Configuration | Wild Leaf: Consignment and Sales Improvements (P112) | Abdul Hameed |  | 4 | 100 |  | SPLN | 3 | Complete | Wild Leaf Beverage | 463 | 3 | -1 | 24.1528 | 48
__export__.project_task_4683_f866c885 | Fix the 3rd Party module to make it installable | Sprint 2138 | 2021-09-13 | Development | MMH: Amazon Module Automation (P102) | Naseeb Razaq |  | 4.75 | 47.5 | FWU |  |  | In Progress | Mountain Meadow Herbs | 465 | 10 | 5.25 | 0 | 0
__export__.project_task_4682_0141846e | Wildleaf Integrated Testing: 27-08-21 |  |  | Deployment | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Muzher Siddique | 2.08 | 52 |  |  |  | Complete | Wild Leaf Beverage | 467 | 4 | 1.92 | 0 | 8
__export__.project_task_4681_88934f43 | Install Marketing Automation Module | Sprint 2137 | 2021-09-06 | Configuration | Wild Leaf: Marketing Automation Set up (P187) | Naseeb Razaq | Abdul Hameed | 1.17 | 78 | Please add next activity | SPLN |  | ELS | Wild Leaf Beverage | 486 | 1.5 | 0.33 | 2.9739e-06 | 0
__export__.project_task_4680_83dacc6d | Trainings Silverdale Creative |  |  | Creative | Silverdale: Help: Creative (P103) | Muhammad Afzaal | Shehroz Faiq | 72.08 | 0 |  |  |  | Complete | Silverdale Technology LLC | 487 | 0 | -72.08 | 0 | 12
__export__.project_task_4679_efb13d72 | Issue in Applied Deposit amount |  |  | Development | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Raheel Aslam | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 487 | 0 | 0 | 0 | 8
__export__.project_task_4678_e9d9c045 | Issue in SO Deposit Calculation in Other Info | Sprint 2138 | 2021-09-13 | Development | Wild Pack Help (SOR-17586) | Naseeb Razaq | Raheel Aslam | 20.08 | 100 |  | 2015-09-01 |  | In Progress | Wild Leaf Beverage | 505 | 18 | -2.08 | 100 | 0
2016-09-01
__export__.project_task_4676_b496abf9 | Add LOE-C, LOE-D, LOE-Q fields in Tasks | Sprint 2135 | 2021-08-23 | Development | Silverdale: Devops (P84) | Muzher Siddique | Aleem khan | 5.83 | 97.17 |  |  |  | Complete | Silverdale Technology LLC | 510 | 6 | 0.17 | 34.8533 | 85.4214
__export__.project_task_4675_13742907 | Closed Status on Sales Order |  |  | Development | CraftAG: Help (P138) | Fahad Hussain Malik | Aleem khan | 8.25 | 91.67 |  |  |  | Cancelled | CraftAG | 511 | 9 | 0.75 | 0 | 84
__export__.project_task_4673_01b20540 | Landed Cost Demo | Sprint 2135 | 2021-08-23 | Internal Time Tracking | Wild Leaf: Help (P22) | Mir Muhammad Muzammil |  | 2 | 0 |  |  |  | Complete | Wild Leaf Beverage | 512 | 0 | -2 | 0 | 0
__export__.project_task_4671_8f8e9b1a | Operations Meeting 2135 | Sprint 2135 | 2021-08-23 | Internal Time Tracking | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 1.5 | 0 |  | SPLN |  | Complete | Wild Leaf Beverage | 513 | 0 | -1.5 | 0 | 17.3314
__export__.project_task_4670_d798ea81 | Sponsor Deck Meeting | Sprint 2135 | 2021-08-23 | Internal Time Tracking | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 2 | 0 |  |  |  | Complete | Wild Leaf Beverage | 513 | 0 | -2 | 0 | 0
__export__.project_task_4667_903c46f3 | Wildleaf Manufacturing order not linked with Sales order |  |  | Bug Fix | Wild Pack Help (SOR-17586) | Naseeb Razaq | Muzher Siddique | 21.83 | 84.5 | Follow-up |  |  | Backlog | Wild Leaf Beverage | 514 | 25.8333 | 4.0033 | 104 | 0
__export__.project_task_4666_e991be95 | UEDF and NMS run numbers issue | Sprint 2135 | 2021-08-23 | Bug Fix | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 2.5 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 515 | 2.5 | 0 | 0 | 53.4236
__export__.project_task_4665_e11f70c5 | Exception State of IMEIs issue | Sprint 2135 | 2021-08-23 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 1.75 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 515 | 1.75 | 0 | 0 | 53.4236
__export__.project_task_4664_bd72bc1b | Logo is not correct in Email Template | Sprint 2136 | 2021-08-30 | Development | PWX: Help (P23) | Farman Ahmad Cheema | Raheel Aslam | 14.58 | 91.12 |  | SPLN |  | Complete | EquityTeam | 515 | 16 | 1.42 | 0 | 104
__export__.project_task_4663_34932aa0 | NMS Status and UEDF status changing conditions | Sprint 2135 | 2021-08-23 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 5.58 | 55.8 |  | SPLN |  | Complete | Cellpoint Corporation | 515 | 10 | 4.42 | 0 | 64
__export__.project_task_4660_4e806ad6 | Remove the dropdown | Sprint 2135 | 2021-08-23 | Development | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik |  | 1.67 | 83.5 |  | SPLN |  | Complete | Continuant | 516 | 2 | 0.33 | 0 | 77.4208
__export__.project_task_4659_970e4d37 | Re confirming INV-300307 |  |  | Development | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Muhammad Bilal | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 516 | 0 | 0 | 0 | 0
__export__.project_task_4658_b33afb1f | Make Contact issue in Leads | Sprint 2135 | 2021-08-23 | Bug Fix | Zuma: Help (P97) | Fahad Hussain Malik | Danish Hassan | 4.17 | 92.67 |  | SPLN |  | Complete | Zuma Sales LLC | 516 | 4.5 | 0.33 | 0 | 61.4192
__export__.project_task_4657_bd4614cd | Issues with New Contact in Opportunities | Sprint 2138 | 2021-09-13 | Development | Zuma: Help (P97) | Fahad Hussain Malik | Sajjad Hussain | 9.92 | 95.23 |  | SPLN |  | Cancelled | Zuma Sales LLC | 516 | 10.4167 | 0.49667 | 0 | 120
2015-09-01
__export__.project_task_4656_9d9861f3 | P&L Report by Analytic Account Error | Sprint 2137 | 2021-09-06 | Configuration | Wild Leaf: Analytic Account Clean Up (P199) | Abdul Hameed | Abdul Hameed | 8.17 | 100 |  | SPLN |  | Complete | Wild Leaf Beverage | 516 | 6 | -2.17 | 0 | 112
__export__.project_task_4655_1f66ffb5 | Analytic Accounts - Delivery Orders and Production Orders | Sprint 2136 | 2021-08-30 | Development | Wild Leaf: Analytic Account Clean Up (P199) | Abdul Hameed | Raheel Aslam | 13.92 | 100 |  | SPLN |  | Complete | Wild Leaf Beverage | 516 | 8 | -5.92 | 0 | 109.4214
__export__.project_task_4654_52973c45 | Remove "Sent by EquityTeam using Odoo | Sprint 2136 | 2021-08-30 | Bug Fix | PWX: Help (P23) | Farman Ahmad Cheema | Raheel Aslam | 9.25 | 84.09 |  | SPLN |  | Complete | EquityTeam | 516 | 11 | 1.75 | 0 | 104
__export__.project_task_4653_5e01e088 | Operational Meeting for 2135 |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 1 | 100 |  |  |  | Complete | Silverdale Technology LLC | 528 | 1 | 0 | 0 | 43.0944
__export__.project_task_4647_42a4db00 | Cbpid Android and iOS Apps testing |  |  | Internal Time Tracking | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 9.75 | 0 |  |  |  | Complete | Cellpoint Corporation | 534 | 0 | -9.75 | 0.00011565 | 27.2704
__export__.project_task_4644_9c616dc9 | Analytic Missing for Payment Reconciliation Entries | Sprint 2136 | 2021-08-30 | Development | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Muhammad Bilal | 0 | 0 |  |  | 3 | Cancelled | Wild Leaf Beverage | 552 | 0 | 0 | 1.0084e-05 | 28.4783
__export__.project_task_4641_5e63ce39 | Deploy Third party Modules | Sprint 2135 | 2021-08-23 | Deployment | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Muzher Siddique | 4.67 | 100 |  | SPLN |  | Complete | Wild Leaf Beverage | 558 | 3.8333 | -0.83667 | 0 | 53.4211
__export__.project_task_4640_ef2e8fcf | Re confirming INV-300307 | Sprint 2136 | 2021-08-30 | Development | Wild Leaf: Help (P22) | Naseeb Razaq | Raheel Aslam | 7.42 | 100 |  | SPLN | 3 | Complete | Wild Leaf Beverage | 560 | 7 | -0.42 | 64 | 75.9564
__export__.project_task_4637_da497eaa | Odoo Learning |  |  | Research | Silverdale Technical Training (P115) | Faisal Huda Khan |  | 0.92 | 92 |  |  |  | Cancelled | Silverdale Technology LLC | 626 | 1 | 0.08 | 0 | 140
__export__.project_task_4636_3d336fa2 | Can not edit Existing sales order | Sprint 2135 | 2021-08-23 | Bug Fix | Mid-America: Help (P37) | Naseeb Razaq | Danish Hassan | 0.67 | 67 |  |  |  | Complete | Mid-America Gardens, LLC | 626 | 1 | 0.33 | 0 | 57.4583
__export__.project_task_4634_8c0b1936 | Setup SMTP2GO | Sprint 2134 | 2021-08-16 | Configuration | Mid-America: Help (P37) | Naseeb Razaq |  | 1.5 | 0 |  | SPLN |  | Complete | Mid-America Gardens, LLC | 698 | 0 | -1.5 | 0 | 33.636
__export__.project_task_4625_9fc03777 | Change Github Password |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Muzher Siddique | 4.5 | 0 |  |  |  | Complete | Silverdale Technology LLC | 709 | 0 | -4.5 | 0 | 18.7467
__export__.project_task_4623_e4ca1c4e | Remove Purchase Order Number and Purchase Date Field on Stock Production Lot |  |  | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Kaleem Khan | 1.5 | 50 |  |  |  | Cancelled | Cellpoint Corporation | 719 | 3 | 1.5 | 0 | 6.3147
__export__.project_task_4618_250d5f8f | Same Sequence Required for Pallet and Master Carton |  |  | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 720 | 0 | 0 | 0 | 0
__export__.project_task_4609_401d319d | Create Sales and Purchase Team | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 723 | 0.5 | 0.5 | 0 | 44.406
__export__.project_task_4601_f27e513e | Trip Accession number should be selectable in my collection |  |  | Development | Heronswood: Collectors Database Phase 1 (P142) | Naseeb Razaq | Danish Hassan | 2.5 | 71.43 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 723 | 3.5 | 1 | 0.024456 | 113.93
__export__.project_task_4599_568c4f0c | Plant name to show in selection field | Sprint 2135 | 2021-08-23 | Development | Heronswood: Collectors Database Phase 1 (P142) | Naseeb Razaq | Danish Hassan | 2.75 | 91.67 |  | SPLN |  | Complete | Port Gamble Sâ€™Klallam Foundation | 723 | 3 | 0.25 | 0.027102 | 113.9799
__export__.project_task_4598_0d311749 | Get Warehouse Products Quantity | Sprint 2135 | 2021-08-23 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Aleem khan | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 727 | 0 | 0 | 0 | 24.6036
__export__.project_task_4597_a82b1d3f | P&L Reports Totals for Groups - Part 1 |  |  | Development | Wild Leaf: P&L Reports Totals for groups (P193) | Abdul Hameed | Aleem khan | 5.5 | 30.56 | Aleem Please respond |  |  | Backlog | Wild Leaf Beverage | 728 | 18 | 12.5 | 88 | 0
__export__.project_task_4596_e2edb35d | Delivery Orders and Production Orders should have analytic account | Sprint 2135 | 2021-08-23 | Development | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Muhammad Bilal | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 729 | 0 | 0 | 0 | 48
__export__.project_task_4595_57c34cf8 | Craft Meetings |  |  | Internal Time Tracking | CraftAG: Help (P138) | Fahad Hussain Malik |  | 9.75 | 97.5 |  |  |  | Complete | CraftAG | 730 | 10 | 0.25 | 40 | 108
__export__.project_task_4592_97ea41ce | Ebay Integration | Sprint 2136 | 2021-08-30 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hassan | 25.75 | 100 |  | SPLN |  | Complete | Zuma Sales LLC | 796 | 25.75 | 0 | 0.010967 | 171.2671
__export__.project_task_4591_8aa5796e | dev- test | Sprint 2136 | 2021-08-30 | Development | Silverdale: SDET (P132) | Muhammad Afzaal | Abdul Hameed | 4 | 40 |  |  |  | Cancelled | Silverdale Technology LLC | 797 | 10 | 6 | 0.024254 | 38.3748
__export__.project_task_4589_aa5b75b1 | Add Analytic Account from Rules if Set on Accounting Head | Sprint 2135 | 2021-08-23 | Development | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Aleem khan | 0 | 0 |  | SPLN |  | Cancelled | Wild Leaf Beverage | 799 | 0 | 0 | 0 | 72.9775
__export__.project_task_4586_0efde8f9 | List of known issues created and distributed among users (if any) | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 799 | 1 | 1 | 0 | 40
__export__.project_task_4579_6d09c40d | Opening Balances have been compiled as ready to import | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 799 | 0.5 | 0.5 | 0 | 32.6233
__export__.project_task_4574_ec35a306 | Review the options on the Settings screen for Tax Rounding | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 799 | 0.16667 | 0.16667 | 0 | 32.6472
__export__.project_task_4573_c0ffc726 | Review the options on the Settings screen for Sales Tax Return frequency | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 799 | 1 | 1 | 0 | 32.6494
__export__.project_task_4572_93a731f3 | Review the options on the Settings screen for Margin Analysis | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 799 | 0.75 | 0.75 | 0 | 32.6553
__export__.project_task_4571_9f3d0858 | Review the options on the Settings screen for Interbank Transfer Account | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 799 | 0.16667 | 0.16667 | 0 | 32.6578
__export__.project_task_4570_a0f2a3df | Review the options on the Settings screen for Fiscal Year end date / Fiscal period definitions | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 799 | 0.16667 | 0.16667 | 0 | 32.6611
__export__.project_task_4567_4f7cf990 | Review the options on the Settings screen for Budgets | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 799 | 0.5 | 0.5 | 0 | 40
__export__.project_task_4565_c80b1bde | Review the options on the Settings screen for Analytics | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  | SPLN |  | Cancelled | Zuma Sales LLC | 799 | 1 | 1 | 0 | 68.2275
__export__.project_task_4564_10bdd67a | Customize the follow-up report levels if you plant to send dunning report via email/mail/sms | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.25 | 50 |  | SPLN |  | Cancelled | Zuma Sales LLC | 799 | 0.5 | 0.25 | 0 | 68.0578
__export__.project_task_4563_7fb16d0c | Review group assignments (permissions) to enable/disable access to financial information and/or functionality. | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.5 | 33.33 |  | SPLN |  | Cancelled | Zuma Sales LLC | 799 | 1.5 | 1 | 0 | 68.0533
__export__.project_task_4560_9b48940e | Setup any Automatic Transfers you need. | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 799 | 0.16667 | 0.16667 | 0 | 56
__export__.project_task_4559_aaead0b1 | Create/Import any ongoing deferred revenues or deferred expenses and/or models. | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 799 | 1 | 1 | 0 | 32.6839
__export__.project_task_4558_6312db18 | Create/Import Assets and/or Asset models. | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 799 | 1 | 1 | 0 | 32.6861
__export__.project_task_4555_1d1a55e1 | Import your Trial Balance via a Journal Entry, making sure to use a clearing/suspense account for AR, AP and Inventory. | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 799 | 1 | 1 | 0 | 32.6958
__export__.project_task_4553_bcf96bae | Define income, expense and cost of revenue accounts on your Product categories. (copy) | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  | SPLN |  | Cancelled | Zuma Sales LLC | 799 | 0.25 | 0.25 | 0 | 68.1278
__export__.project_task_4550_a75cb12b | Make sure a time zone is setup for each user you have created. | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 799 | 0.5 | 0.5 | 0 | 32.7111
__export__.project_task_4544_41b5cc36 | CraftAG Meetings |  |  | Internal Time Tracking | CraftAG: Help (P138) | Jeff Gross |  | 1.25 | 0 |  |  |  | Complete | CraftAG | 801 | 0 | -1.25 | 8.2661e-06 | 4.2992
__export__.project_task_4540_e0aa9d62 | Meetings, PM, Discussion | Sprint 2133 | 2021-08-09 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 33.83 | 100 |  |  |  | Complete | Silverdale Technology LLC | 819 | 21 | -12.83 | 0 | 21.79
__export__.project_task_4537_f67f86ca | From and To date need to add in Schedule | Sprint 2135 | 2021-08-23 | Development | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Danish Hassan | 4.17 | 92.67 |  | SPLN |  | Complete | Port Gamble Sâ€™Klallam Foundation | 824 | 4.5 | 0.33 | 0 | 133.4208
__export__.project_task_4529_3c4555da | Increased font size on web survey form | Sprint 2135 | 2021-08-23 | Development | PWX: Survey (P70) | Farman Ahmad Cheema | Danish Hassan | 3.17 | 70.44 |  | SPLN |  | Complete | EquityTeam | 841 | 4.5 | 1.33 | 0.016449 | 137.3578
__export__.project_task_4519_498563ee | Commission should not be calculated on shipping charges for Agent | Sprint 2134 | 2021-08-16 | Development | MMH: Affiliate Program Setup (P96) | Naseeb Razaq | Danish Hassan | 4.67 | 58.38 |  | SPLN |  | Complete | Mountain Meadow Herbs | 844 | 8 | 3.33 | 0.011893 | 91.4461
__export__.project_task_4517_17a2a85d | Successor Handover Mechanism |  |  |  | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 849 | 0 | 0 | 0 | 0
__export__.project_task_4516_6d7d74d0 | Accounts & Operations Meeting 2133 | Sprint 2133 | 2021-08-09 | Client Meetings | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 8.83 | 98.11 |  |  |  | Complete | Wild Leaf Beverage | 851 | 9 | 0.17 | 1.0835e-05 | 26.1561
__export__.project_task_4514_78737d15 | Qualifying Survey in Applications |  |  | Development | PWX: Help Desk (P65) | Farman Ahmad Cheema |  | 0 | 0 |  |  |  | Complete | EquityTeam | 865 | 0 | 0 | 0 | 40.7879
__export__.project_task_4513_e8756aa5 | Add city and state fields on Application form | Sprint 2133 | 2021-08-09 | Development | PWX: Survey (P70) | Farman Ahmad Cheema | Danish Hassan | 3.25 | 81.25 |  |  |  | Complete | EquityTeam | 866 | 4 | 0.75 | 0 | 109.0436
__export__.project_task_4512_3913ae9b | Personality tab Changes | Sprint 2133 | 2021-08-09 | Development | PWX: Survey (P70) | Farman Ahmad Cheema | Danish Hassan | 3.25 | 81.25 |  |  |  | Complete | EquityTeam | 866 | 4 | 0.75 | 6.6576 | 109.3863
__export__.project_task_4509_b4ce5b64 | Consignment additional Changes Demo | Sprint 2133 | 2021-08-09 | Development | Wild Leaf: Consignment and Sales Improvements (P112) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 2 | 100 |  | SPLN |  | Complete | Wild Leaf Beverage | 869 | 2 | 0 | 0 | 26.7239
__export__.project_task_4507_f1ccf0b2 | Create Purchase Order in ODOO |  |  | Development | Zuma: Odoo Implementation Phase 2 (P204) | Asfand Yaar | Danish Hassan | 0.42 | 4.94 |  |  |  | Backlog | Zuma Sales LLC | 871 | 8.5 | 8.08 | 113.3331 | 0
__export__.project_task_4506_eaa228e3 | Receive order from CDI (SFTP) |  |  | Configuration | Zuma: Odoo Implementation Phase 2 (P204) | Asfand Yaar | Asfand Yaar | 0.12 | 36 |  |  |  | Backlog | Zuma Sales LLC | 871 | 0.33333 | 0.21333 | 155.0678 | 0
__export__.project_task_4499_3e6de77f | DSM Meetings | Sprint 2133 | 2021-08-09 | Configuration | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 3 | 0 |  |  |  | Complete | Wild Leaf Beverage | 873 | 0 | -3 | 0 | 29.8321
__export__.project_task_4498_06526455 | Sponsor Deck Meeting and Document | Sprint 2133 | 2021-08-09 | Configuration | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 3.33 | 100 |  |  |  | Complete | Wild Leaf Beverage | 873 | 2 | -1.33 | 0 | 6.0357
__export__.project_task_4497_2ab26490 | DSM Review Meetings 2133 | Sprint 2133 | 2021-08-09 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Mir Muhammad Muzammil | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 873 | 0 | 0 | 0 | 58.9219
__export__.project_task_4496_a227bb9c | New Project Requirements Meetings 2133 | Sprint 2133 | 2021-08-09 | Internal Time Tracking | Silverdale Time Tracking (P56) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 0 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 873 | 0 | 0 | 0 | 72
__export__.project_task_4495_e41f3d27 | DSM Meetings Wildleaf |  |  | Internal Time Tracking | Wild Leaf: Help (P22) | Mir Muhammad Muzammil |  | 2.17 | 0 |  |  |  | Complete | Wild Leaf Beverage | 874 | 0 | -2.17 | 0 | 72
__export__.project_task_4494_b90cfe38 | Sprint Planning 2133 | Sprint 2133 | 2021-08-09 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Mir Muhammad Muzammil | 1.5 | 100 |  |  |  | Complete | Silverdale Technology LLC | 874 | 1.5 | 0 | 0 | 0.014111
__export__.project_task_4493_8f59215b | A-Player Agreement for IT Specialist | Sprint 2136 | 2021-08-30 | Documentation | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 0.83 | 41.5 |  | SPLN |  | Complete | Silverdale Technology LLC | 875 | 2 | 1.17 | 0 | 184
__export__.project_task_4492_c96a02ba | ASN Import on transfer form (Multiple products in the file) | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 1.5 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 885 | 0 | -1.5 | 0 | 8
__export__.project_task_4490_af44658f | Add vendor ASN formats for all vendors | Sprint 2133 | 2021-08-09 | Configuration | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema |  | 0 | 0 |  | SPLN |  | Cancelled | Cellpoint Corporation | 892 | 0 | 0 | 0 | 46.3519
__export__.project_task_4473_a646815f | On Purchase Order, add a CLOSED status |  |  | Development | CraftAG: Help (P138) | Fahad Hussain Malik | Aleem khan | 6.33 | 79.12 |  |  |  | Cancelled | CraftAG | 897 | 8 | 1.67 | 80 | 172
__export__.project_task_4463_1cd17f24 | Tiles/Charts to create | Sprint 2134 | 2021-08-16 | Configuration | CraftAG: Set-up Dashboard Ninja (P172) | Fahad Hussain Malik |  | 1.5 | 100 |  |  |  | Complete | CraftAG | 961 | 1.5 | 0 | 0 | 71.9262
__export__.project_task_4462_a6d9090e | Add warehouse location to PO Line items | Sprint 2133 | 2021-08-09 | Development | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Danish Hassan | 4.92 | 61.5 |  | SPLN |  | Complete | Wild Leaf Beverage | 965 | 8 | 3.08 | 0 | 127.9216
__export__.project_task_4459_db41045d | Job Applications, send email to multiple Applicants at a time | Sprint 2133 | 2021-08-09 | Development | PWX: Survey (P70) | Farman Ahmad Cheema | Danish Hassan | 7.25 | 100 |  |  |  | Complete | EquityTeam | 967 | 6.5 | -0.75 | 0 | 125.4244
__export__.project_task_4458_db085991 | Job Position, Interviews Menu needed changes | Sprint 2133 | 2021-08-09 | Development | PWX: Survey (P70) | Farman Ahmad Cheema | Danish Hassan | 4.05 | 90 |  |  |  | Complete | EquityTeam | 967 | 4.5 | 0.45 | 0 | 125.4244
__export__.project_task_4457_d450493a | Odoo recruiting issues 8.4.2021 | Sprint 2135 | 2021-08-23 | Development | PWX: Survey (P70) | Farman Ahmad Cheema | Danish Hassan | 0 | 0 |  | SPLN |  | Complete | EquityTeam | 967 | 0 | 0 | 0 | 120
__export__.project_task_4445_4861637f | Review Sales Document create tiles | Sprint 2134 | 2021-08-16 | Configuration | CraftAG: Set-up Dashboard Ninja (P172) | Fahad Hussain Malik |  | 0.75 | 0 |  | SPLN |  | Complete | CraftAG | 986 | 0 | -0.75 | 0 | 129.6802
__export__.project_task_4443_54dd7a08 | Set Analytics to Missing Journal entries of Inventory Adjustment | Sprint 2132 | 2021-08-02 | Development | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Muzher Siddique | 6.67 | 0 |  |  |  | Complete | Wild Leaf Beverage | 992 | 0 | -6.67 | 0 | 51.3988
__export__.project_task_4442_2a7bdb6e | Create IT Contract for Vasanth | Sprint 2132 | 2021-08-02 | Internal Time Tracking | Silverdale: Internal Project (P13) | Muhammad Afzaal | Muhammad Zubair | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 993 | 0 | 0 | 0 | 208
__export__.project_task_4441_2f43f527 | Deployment to Production | Sprint 2133 | 2021-08-09 | Deployment | Wild Leaf: Sales Improvements (P150) | Mir Muhammad Muzammil | Fahad Hassan | 5.83 | 0 |  |  |  | Complete | Wild Leaf Beverage | 996 | 0 | -5.83 | 0 | 30.2408
__export__.project_task_4439_4d889e5f | NMS Export giving error (Training Branch) | Sprint 2133 | 2021-08-09 | Bug Fix | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 9 | 0 |  | SPLN |  | Complete | Cellpoint Corporation | 1008 | 0 | -9 | 0 | 64
Priority
__export__.project_task_4437_c81d9571 | Off Cycle Deployment | Sprint 2132 | 2021-08-02 | Configuration | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 1 | 0 |  |  |  | Complete | Wild Leaf Beverage | 1009 | 0 | -1 | 0 | 26.66
__export__.project_task_4436_583f3101 | Questions or Information required before going live | Sprint 2133 | 2021-08-09 | Other | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Muhammad Zubair | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 1009 | 0 | 0 | 0 | 28
__export__.project_task_4435_6c86d089 | Tax Cloud Calculation on Delivery Address | Sprint 2133 | 2021-08-09 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 1011 | 0 | 0 | 0 | 59.7711
__export__.project_task_4433_12320e0f | Wildleaf Sponsor Meeting and Document 2132 | Sprint 2132 | 2021-08-02 | Client Meetings | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 2.5 | 83.33 |  |  |  | Complete | Wild Leaf Beverage | 1015 | 3 | 0.5 | 0 | 0.029309
__export__.project_task_4432_58fc85a3 | New Projects Requirements Meetings 2132 | Sprint 2134 | 2021-08-16 | Client Meetings | Silverdale Time Tracking (P56) | Muhammad Afzaal | Mir Muhammad Muzammil | 0.67 | 9.57 |  |  |  | Complete | Silverdale Technology LLC | 1015 | 7 | 6.33 | 0 | 104
__export__.project_task_4428_216dd65d | Deployment on Production (2131) | Sprint 2132 | 2021-08-02 | Deployment | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Fahad Hassan | 4.17 | 100 |  |  |  | Complete | Continuant | 1042 | 4 | -0.17 | 0 | 3.9087
__export__.project_task_4427_87ce6e7e | WhatsApp Connector |  |  | Development | Silverdale: Internal Project (P13) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 1043 | 0 | 0 | 224 | 0
__export__.project_task_4426_71de84dc | Accounts & Operations Meeting 2132 | Sprint 2132 | 2021-08-02 | Client Meetings | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 8.17 | 90.78 |  |  |  | Complete | Wild Leaf Beverage | 1055 | 9 | 0.83 | 0 | 42.6042
__export__.project_task_4425_4cf59434 | Sprint Planning 2132 | Sprint 2132 | 2021-08-02 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 1 | 100 |  | SPLN |  | Complete | Silverdale Technology LLC | 1055 | 1 | 0 | 0 | 0
__export__.project_task_4423_0156b1fd | Commission Report - Customization | Sprint 2138 | 2021-09-13 | Development | Wild Leaf: Commission Report (P181) | Naseeb Razaq | Raheel Aslam | 12 | 82.76 | PM Review this task |  |  | PM Review | Wild Leaf Beverage | 1057 | 14.5 | 2.5 | 174.0094 | 0
__export__.project_task_4420_04336933 | Accounting end to end run through | Sprint 2132 | 2021-08-02 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 2.5 | 100 |  |  |  | Complete | Zuma Sales LLC | 1065 | 1 | -1.5 | 0 | 44
__export__.project_task_4419_daad994a | overwrite the functionality of field in Customer CRM Prospect Selection | Sprint 2132 | 2021-08-02 | Development | Wild Leaf: Sales Improvements (P150) | Mir Muhammad Muzammil | Danish Hassan | 10.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 1065 | 0 | -10.5 | 0 | 76.2854
__export__.project_task_4418_44fb0ba9 | Deploy Ninja Dashboard On Craft AG | Sprint 2134 | 2021-08-16 | Deployment | CraftAG: Set-up Dashboard Ninja (P172) | Fahad Hussain Malik | Danish Hassan | 1.75 | 100 |  | SPLN |  | Complete | CraftAG | 1067 | 1 | -0.75 | 120 | 125.4233
__export__.project_task_4414_2307c8ca | Demo to Client | Sprint 2132 | 2021-08-02 | Demo to the client | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Farman Ahmad Cheema | 4 | 100 |  |  |  | Complete | Cellpoint Corporation | 1082 | 4 | 0 | 0 | 40
__export__.project_task_4412_aa585b35 | Sprint 2132 Sponsor Call - Perfect Golf | Sprint 2132 | 2021-08-02 | Internal Time Tracking | Perfect Golf: Help (P99) | Farman Ahmad Cheema | Farman Ahmad Cheema | 0 | 0 |  |  |  | Complete | Perfect Golf Event | 1083 | 0.5 | 0.5 | 0 | 80
__export__.project_task_4410_46300e84 | test |  |  | Other | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 1113 | 0 | 0 | 0 | 0
__export__.project_task_4408_9c164502 | Allow Changing Scheduled date of back orders if bigger than Deadline date of Parent MO | Sprint 2137 | 2021-09-06 | Development | Wild Pack Help (SOR-17586) | Naseeb Razaq | Aleem khan | 5.58 | 74.4 |  | SPLN |  | ELS | Wild Leaf Beverage | 1130 | 7.5 | 1.92 | 236 | 0
__export__.project_task_4405_cc92bb69 | Deploy to Deployment + Production (2131) | Sprint 2132 | 2021-08-02 | Deployment | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hassan | 8.42 | 100 |  |  |  | Complete | Zuma Sales LLC | 1137 | 7.5 | -0.92 | 0 | 19.6213
__export__.project_task_4402_1e6f56ac | Meetings, PM, Discussion | Sprint 2132 | 2021-08-02 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Fahad Hussain Malik | 23 | 100 |  |  |  | Complete | Silverdale Technology LLC | 1154 | 21 | -2 | 0 | 59.2314
__export__.project_task_4401_42a97d58 | Buy Ninja Dashboard | Sprint 2132 | 2021-08-02 | Integration | CraftAG: Set-up Dashboard Ninja (P172) | Jeff Gross | Asfand Yaar | 0 | 0 |  |  |  | Complete | CraftAG | 1154 | 4 | 4 | 0 | 35.1772
__export__.project_task_4400_747d3fb3 | Integrate module for 2 level approval for purchase order | Sprint 2134 | 2021-08-16 | Integration | CraftAG: Purchase Orders - 2 Levels of Approval (P164) | Fahad Hussain Malik | Asfand Yaar | 4 | 100 |  | SPLN |  | Complete | CraftAG | 1154 | 4 | 0 | 0 | 137.4233
__export__.project_task_4399_b7388843 | Integrate Custom Credit Limits Module | Sprint 2136 | 2021-08-30 | Integration | CraftAG: Customer Credit Limits (P166) | Fahad Hussain Malik | Aleem khan | 8.08 | 99.96 |  | SPLN |  | Complete | CraftAG | 1154 | 8.0833 | 0.0033333 | 0 | 217.4208
__export__.project_task_4398_1b014499 | Ship to Dish (Customer) | Sprint 2132 | 2021-08-02 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 1154 | 0 | 0 | 0 | 20.8214
__export__.project_task_4392_044b10ed | Scan Pallet Temp Label to attach to Delivery Order | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema |  | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 1154 | 0 | 0 | 0 | 8
__export__.project_task_4391_db8b1b32 | Go to Delivery Order | Sprint 2133 | 2021-08-09 | Configuration | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema |  | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 1154 | 0 | 0 | 0 | 8
__export__.project_task_4389_e834892a | Scan Master Carton temp label | Sprint 2132 | 2021-08-02 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 1154 | 0 | 0 | 0 | 8
__export__.project_task_4386_b80c3d17 | Shopify, eBay and Amazon | Sprint 2132 | 2021-08-02 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 28.25 | 100 |  |  |  | Complete | Zuma Sales LLC | 1156 | 20 | -8.25 | 0 | 49.0975
__export__.project_task_4385_c70f36bc | Audit of the best Practices, Features, and Master Data used by the client |  |  | Functionality Test | CraftAG: Odoo Audit (P147) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | CraftAG | 1157 | 7 | 7 | 0 | 0.12819
__export__.project_task_4384_9892cd3e | Business Processes and the modules used by every company |  |  | Functionality Test | CraftAG: Odoo Audit (P147) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | CraftAG | 1157 | 4 | 4 | 0 | 0.15366
__export__.project_task_4383_3509ccf2 | Analyse the code quality in custom modules |  |  | Other | CraftAG: Odoo Audit (P147) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Cancelled | CraftAG | 1157 | 12 | 12 | 0 | 0.19203
__export__.project_task_4382_154cd39a | Hide the fields | Sprint 2132 | 2021-08-02 | Configuration | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Fahad Hussain Malik | 0.33 | 99 |  |  |  | Complete | Continuant | 1160 | 0.33333 | 0.0033333 | 0 | 43.757
__export__.project_task_4381_0a2a0df0 | Hide the fileds |  |  |  | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Cancelled | Continuant | 1160 | 0 | 0 | 0 | 14.6089
__export__.project_task_4379_2f6c63d4 | CraftAG / Silverdale - Lead to Invoicing Process Walkthrough | Sprint 2134 | 2021-08-16 | Documentation | CraftAG: Help (P138) | Fahad Hussain Malik | Asfand Yaar | 2.5 | 100 |  |  |  | Complete | CraftAG | 1173 | 2.5 | 0 | 72 | 124.1194
__export__.project_task_4377_d58f59ca | Project Knowledge Transfer for internal PM | Sprint 2131 | 2021-07-26 | Demo to the client | MMH: Help (P83) | Naseeb Razaq |  | 3.75 | 93.75 |  |  |  | Complete | Mountain Meadow Herbs | 1176 | 4 | 0.25 | 0 | 0
__export__.project_task_4375_94a5d74e | Meeting DG Solutions |  |  | Other | DGS: Help (P131) | Fahad Hussain Malik |  | 0.5 | 0 |  |  |  | Complete | DG Solutions Inc. | 1181 | 0 | -0.5 | 0.018835 | 55.7444
__export__.project_task_4374_d09d849a | Remove the developments | Sprint 2141 | 2021-10-04 | Configuration | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Naseeb Razaq | 0 | 0 | Your task missed the deadline! |  |  | Backlog | Port Gamble Sâ€™Klallam Foundation | 1181 | 4 | 4 | 0 | 0
__export__.project_task_4371_11e4a2d3 | Create JD for IT/Server Administrator Job Positions | Sprint 2134 | 2021-08-16 | Documentation | Silverdale Time Tracking (P56) | Muhammad Afzaal | Muzher Siddique | 1.83 | 91.5 |  |  |  | Cancelled | Silverdale Technology LLC | 1185 | 2 | 0.17 | 0 | 160
__export__.project_task_4368_64a9f294 | JMeter |  |  | Improvements | Silverdale: Devops (P84) | Muzher Siddique | Wishal Nasir | 2 | 0 | Decide validity |  |  | Backlog | Silverdale Technology LLC | 1206 | 0 | -2 | 272.8428 | 0
__export__.project_task_4367_d7dee781 | Create Button on Leads which create the contact on click | Sprint 2132 | 2021-08-02 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 8.5 | 100 |  |  | 2 | Complete | Zuma Sales LLC | 1208 | 4.5 | -4 | 0 | 68
__export__.project_task_4365_f98ed980 | Remove Bill to and Ship to From Leads | Sprint 2132 | 2021-08-02 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 3.08 | 88 |  |  | 1 | Complete | Zuma Sales LLC | 1209 | 3.5 | 0.42 | 0 | 68
__export__.project_task_4359_f31997f2 | Serial Status change from Inbound to Received | Sprint 2131 | 2021-07-26 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 1230 | 0 | 0 | 0 | 12.7912
__export__.project_task_4357_c583312f | Fields Mapping for ASN import (Excel file with existing Odoo fields) | Sprint 2132 | 2021-08-02 | Configuration | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Farman Ahmad Cheema | 0 | 0 |  | SPLN |  | Complete | Cellpoint Corporation | 1230 | 0 | 0 | 0 | 47.6323
__export__.project_task_4354_5e5a5525 | Cellpoint: Setup Odoo.sh instance v14 | Sprint 2132 | 2021-08-02 | Configuration | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 0.5 | 0 |  | SPLN |  | Complete | Cellpoint Corporation | 1230 | 0 | -0.5 | 0 | 106.3105
__export__.project_task_4353_0c506dc0 | Vendor and Customer list import | Sprint 2131 | 2021-07-26 | Configuration | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Farman Ahmad Cheema | 0 | 0 |  | SPLN |  | Complete | Cellpoint Corporation | 1231 | 0 | 0 | 1.3257e-05 | 34.3611
__export__.project_task_4352_2177e585 | Automation: Notify Salesperson / Sales Team When MO Complete |  |  | Development | Wild Leaf: Help (P22) | Mir Muhammad Muzammil |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 1233 | 0 | 0 | 0 | 44
__export__.project_task_4349_9436d5bf | Revise Lucid Chart for Consignment based on Document |  |  | Documentation | Wild Leaf: Consignment and Sales Improvements (P112) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 1397 | 3 | 3 | 1.6503e-05 | 179.3747
__export__.project_task_4348_9da82504 | Add-on in the audit report | Sprint 2131 | 2021-07-26 | Configuration | DGS: Odoo Audit and v14 Upgrade Estimate (P136) | Fahad Hussain Malik | Fahad Hussain Malik | 3 | 100 |  |  |  | Complete | DG Solutions Inc. | 1400 | 3 | 0 | 0 | 56.4231
__export__.project_task_4346_425ddcc9 | Help Desk Tickets Review (2131) | Sprint 2131 | 2021-07-26 | Internal Time Tracking | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 2.33 | 46.6 |  | SPLN |  | Complete | Wild Leaf Beverage | 1465 | 5 | 2.67 | 5.3789 | 80.0192
__export__.project_task_4345_ff2c0432 | Linked invoiced lines to Sale orders line. | Sprint 2131 | 2021-07-26 | Development | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Raheel Aslam | 8.67 | 92.89 |  | SPLN | 4 | Complete | Wild Leaf Beverage | 1466 | 9.3333 | 0.66333 | 5.3044 | 88.0192
__export__.project_task_4342_2749c682 | Create critical test cases for Continuant | Sprint 2131 | 2021-07-26 | Configuration | Continuant: Customer Invoice Portal (P118) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Continuant | 1469 | 5 | 5 | 0 | 36.922
__export__.project_task_4339_0f9f8623 | DSM, Sponsor Review, Sprint, Project Review | Sprint 2131 | 2021-07-26 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Fahad Hussain Malik | 3.25 | 59.09 |  |  |  | Complete | Silverdale Technology LLC | 1470 | 5.5 | 2.25 | 0.12795 | 73.521
__export__.project_task_4334_8ecf7847 | Payment Options show on website | Sprint 2131 | 2021-07-26 | Development | MMH Dr. Clark: Help (P106) | Naseeb Razaq | Danish Hassan | 4.83 | 69 |  |  | 2 | Complete | Mountain Meadow Herbs | 1472 | 7 | 2.17 | 0 | 35.4065
__export__.project_task_4333_01477e72 | Daily Meetings For Lead Consultant | Sprint 2131 | 2021-07-26 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Naseeb Razaq | 6.15 | 47.31 |  | SPLN |  | Complete | Silverdale Technology LLC | 1472 | 13 | 6.85 | 3.584e-05 | 75.7686
__export__.project_task_4331_e220f247 | Sprint Planning | Sprint 2131 | 2021-07-26 | Internal Time Tracking | Silverdale Time Tracking (P56) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 1.5 | 100 |  | SPLN |  | Complete | Silverdale Technology LLC | 1473 | 1 | -0.5 | 9.4161 | 140.0483
__export__.project_task_4330_835ffec8 | Inventory Report | Sprint 2129 | 2021-07-12 | Configuration | Wild Leaf: Help (P22) | Muhammad Zubair | Mir Muhammad Muzammil | 0.33 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 1473 | 0 | -0.33 | 8.5668e-05 | 4.0865
__export__.project_task_4326_a7cd13f1 | Wildleaf Sponsor Meeting 2131 | Sprint 2131 | 2021-07-26 | Client Meetings | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 1.5 | 100 |  |  |  | Complete | Wild Leaf Beverage | 1488 | 1 | -0.5 | 14.3942 | 54.0792
__export__.project_task_4325_2767f1cd | Wildleaf Sponsor Document 2131 | Sprint 2131 | 2021-07-26 | Documentation | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 1 | 100 |  | SPLN |  | Complete | Wild Leaf Beverage | 1488 | 1 | 0 | 14.3992 | 72
__export__.project_task_4324_cbe41800 | Daily Standup Meetings and Prep | Sprint 2131 | 2021-07-26 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Farman Ahmad Cheema | 6.08 | 100 |  |  |  | Complete | Silverdale Technology LLC | 1488 | 2.5 | -3.58 | 0 | 80.0192
__export__.project_task_4323_9f73aa3e | MMH Daily and Weekly Calls | Sprint 2131 | 2021-07-26 | Internal Time Tracking | MMH: Help (P83) | Naseeb Razaq | Farman Ahmad Cheema | 0 | 0 |  |  |  | Complete | Mountain Meadow Herbs | 1488 | 2 | 2 | 0 | 80.0192
__export__.project_task_4322_54e58584 | Sprint Planning Discussion with Developer 2131 | Sprint 2131 | 2021-07-26 | Internal Time Tracking | Silverdale Time Tracking (P56) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 1488 | 3 | 3 | 13.4114 | 80.0192
__export__.project_task_4321_d70eaa82 | Accounts & Operations Meeting 2131 | Sprint 2131 | 2021-07-26 | Client Meetings | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 11.25 | 100 |  |  |  | Complete | Wild Leaf Beverage | 1488 | 9 | -2.25 | 13.4036 | 88.0192
__export__.project_task_4320_b4375176 | Wild Leaf: PM Review of Tasks 2131 | Sprint 2131 | 2021-07-26 | Internal Time Tracking | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 2.5 | 50 |  |  |  | Complete | Wild Leaf Beverage | 1488 | 5 | 2.5 | 14.4453 | 72
__export__.project_task_4319_2a4456bd | Sprint 2132 Planning | Sprint 2131 | 2021-07-26 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Farman Ahmad Cheema | 2 | 100 |  |  |  | Complete | Silverdale Technology LLC | 1488 | 2 | 0 | 0 | 80.0192
__export__.project_task_4318_afbae7fa | Weekly Sponsor Call Heronswood | Sprint 2131 | 2021-07-26 | Internal Time Tracking | Heronswood: Help (P54) | Naseeb Razaq | Farman Ahmad Cheema | 0 | 0 |  |  |  | Cancelled | Port Gamble Sâ€™Klallam Foundation | 1489 | 0.5 | 0.5 | 0 | 80.0192
__export__.project_task_4317_f8b5f56c | Dr. Clark / Silverdale - Weekly Call | Sprint 2131 | 2021-07-26 | Internal Time Tracking | MMH Dr. Clark: Help (P106) | Naseeb Razaq | Farman Ahmad Cheema | 0 | 0 |  |  |  | Cancelled | Mountain Meadow Herbs | 1489 | 0.5 | 0.5 | 0 | 80.0192
__export__.project_task_4315_ab039696 | Auto Fetch Analytic Account on Asset From Bill | Sprint 2131 | 2021-07-26 | Development | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Raheel Aslam | 12.33 | 88.07 |  | SPLN | 3 | Complete | Wild Leaf Beverage | 1489 | 14 | 1.67 | 13.3592 | 96.0192
__export__.project_task_4314_84dc28b9 | Email template report for print on header | Sprint 2132 | 2021-08-02 | Development | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Danish Hassan | 4.75 | 59.38 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 1489 | 8 | 3.25 | 0 | 63.0967
__export__.project_task_4310_2b55bd05 | Import emails sent to ap@pwxusa.com since 6/9/21 into documents module |  |  | Development | PWX: Importing emails from ap@pwxusa.com (P179) | Naseeb Razaq |  | 0 | 0 | Please add next activity |  | 3 | Planning | EquityTeam | 1499 | 25 | 25 | 0 | 0
__export__.project_task_4309_0852e9d8 | Mid-America Gardens Meeting |  |  | Internal Time Tracking | Mid-America: Help (P37) | Naseeb Razaq |  | 1.33 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 1512 | 0 | -1.33 | 0 | 96.0192
__export__.project_task_4302_5aa26b96 | Consignment additional Changes | Sprint 2133 | 2021-08-09 | Development | Wild Leaf: Consignment and Sales Improvements (P112) | Mir Muhammad Muzammil | Muhammad Bilal | 157.58 | 100 |  | SPLN |  | Complete | Wild Leaf Beverage | 1540 | 10 | -147.58 | 29.4333 | 180.0192
__export__.project_task_4301_9edb2014 | Accounts & Operations Meeting | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 8.75 | 97.22 |  |  |  | Complete | Wild Leaf Beverage | 1544 | 9 | 0.25 | 32.5796 | 33.5218
__export__.project_task_4300_a4925429 | Wildleaf Sponsor Document | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Wild Leaf: Help (P22) | Muhammad Zubair | Mir Muhammad Muzammil | 1 | 100 |  |  |  | Complete | Wild Leaf Beverage | 1545 | 1 | 0 | 0.00013531 | 7.6504
__export__.project_task_4293_cfe0706c | Show scheduler on portal | Sprint 2131 | 2021-07-26 | Development | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq | Aleem khan | 4.58 | 45.8 |  | SPLN | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 1637 | 10 | 5.42 | 0 | 112.4338
__export__.project_task_4292_0fe597ff | Credit Limit Over-due Function | Sprint 2129 | 2021-07-12 | Development | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Raheel Aslam | 8.17 | 100 |  | SPLN | 3 | Complete | Wild Leaf Beverage | 1639 | 7 | -1.17 | 47.5575 | 127.9553
__export__.project_task_4291_b89668e1 | Task Creation, Sprint Planning, PM Review, Emails, Helpdesk Buffer | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Fahad Hussain Malik | 18.25 | 100 |  |  |  | Complete | Silverdale Technology LLC | 1640 | 15 | -3.25 | 0.027857 | 44.4959
__export__.project_task_4284_c512354c | Sponsor Call Zuma, DG and Continuant | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Fahad Hussain Malik | 4.5 | 100 |  |  |  | Complete | Silverdale Technology LLC | 1656 | 2.5 | -2 | 0 | 34.5819
__export__.project_task_4283_f325eebb | Silverdale Sprint, Project Reviews , Daily standups, discussion with developers | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Fahad Hussain Malik | 5 | 90.91 |  |  |  | Complete | Silverdale Technology LLC | 1656 | 5.5 | 0.5 | 0 | 52
__export__.project_task_4281_b64ef564 | DG Meetings | Sprint 2129 | 2021-07-12 | Internal Time Tracking | DGS: Help (P131) | Fahad Hussain Malik | Fahad Hussain Malik | 1 | 33.33 |  |  |  | Complete | DG Solutions Inc. | 1656 | 3 | 2 | 0 | 47.1878
__export__.project_task_4280_d7c3b445 | QA Affiliate link program | Sprint 2131 | 2021-07-26 | Configuration | MMH: Affiliate Program Setup (P96) | Naseeb Razaq | Wishal Nasir | 2.08 | 100 |  | SPLN |  | Complete | Mountain Meadow Herbs | 1656 | 2 | -0.08 | 0 | 128.0192
__export__.project_task_4278_4b7c2cb3 | Discussion with Product Team | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Perfect Golf: Odoo Implementation Phase 2 (P155) | Naseeb Razaq | Farman Ahmad Cheema | 0 | 0 |  |  |  | Cancelled | Perfect Golf Event | 1657 | 3 | 3 | 0 | 40
__export__.project_task_4277_af0038d0 | Woo-Commerce Connector Testing |  |  | Quality Assurance | MMH: WooCommerce Integration (P134) | Naseeb Razaq | Wishal Nasir | 0 | 0 | FWU |  |  | Backlog | Mountain Meadow Herbs | 1657 | 5 | 5 | 0 | 0
__export__.project_task_4275_fa3f7c30 | Requirement Mapping |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq | Naseeb Razaq | 0 | 0 | FWU |  |  | Planning | Mountain Meadow Herbs | 1657 | 5 | 5 | 0 | 0
__export__.project_task_4274_655a3175 | Requirements Documentation | Sprint 2132 | 2021-08-02 | Internal Time Tracking | Perfect Golf: Odoo Implementation Phase 2 (P155) | Naseeb Razaq | Farman Ahmad Cheema | 0 | 0 |  |  |  | Complete | Perfect Golf Event | 1657 | 3 | 3 | 0 | 232.0797
__export__.project_task_4273_0243194e | Requirements Gathering Meetings | Sprint 2132 | 2021-08-02 | Internal Time Tracking | Perfect Golf: Odoo Implementation Phase 2 (P155) | Naseeb Razaq | Farman Ahmad Cheema | 0 | 0 |  |  |  | Complete | Perfect Golf Event | 1657 | 2 | 2 | 0 | 232.1349
__export__.project_task_4272_3f55c051 | New Projects Requirement Documentation | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Silverdale Time Tracking (P56) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 1657 | 2 | 2 | 52.2978 | 116.0192
__export__.project_task_4271_5a4a7e4b | New Projects Requirements Meetings | Sprint 2131 | 2021-07-26 | Client Meetings | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 2.83 | 100 |  |  |  | Complete | Wild Leaf Beverage | 1657 | 2 | -0.83 | 53.4422 | 141.2358
__export__.project_task_4270_5406dad8 | Dr. Clark / Silverdale - Weekly Call | Sprint 2129 | 2021-07-12 | Internal Time Tracking | MMH Dr. Clark: Help (P106) | Naseeb Razaq | Farman Ahmad Cheema | 0.5 | 100 |  |  |  | Complete | Mountain Meadow Herbs | 1657 | 0.5 | 0 | 0 | 40
__export__.project_task_4269_364dceae | MMH Daily and Weekly Calls | Sprint 2129 | 2021-07-12 | Internal Time Tracking | MMH: Help (P83) | Naseeb Razaq | Farman Ahmad Cheema | 1.58 | 79 |  |  |  | Complete | Mountain Meadow Herbs | 1657 | 2 | 0.42 | 0 | 48
__export__.project_task_4268_8e3739de | Sprint 2131 Sponsor Call - Perfect Golf | Sprint 2131 | 2021-07-26 | Internal Time Tracking | Perfect Golf: Help (P99) | Naseeb Razaq | Farman Ahmad Cheema | 0 | 0 |  |  |  | Cancelled | Perfect Golf Event | 1657 | 0.5 | 0.5 | 0 | 120.0192
__export__.project_task_4267_ead4705d | Briefing Developer | Sprint 2129 | 2021-07-12 | Other | Heronswood: Collectors Database Phase 1 (P142) | Naseeb Razaq | Naseeb Razaq | 1 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 1657 | 1 | 0 | 0 | 22.9611
__export__.project_task_4266_e10bab8e | Creating Tasks | Sprint 2129 | 2021-07-12 | Configuration | Heronswood: Collectors Database Phase 1 (P142) | Naseeb Razaq | Naseeb Razaq | 0.5 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 1657 | 0.5 | 0 | 0 | 31.9814
__export__.project_task_4265_242cc733 | Weekly Sponsor Call | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Heronswood: Help (P54) | Naseeb Razaq | Farman Ahmad Cheema | 0.33 | 66 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 1657 | 0.5 | 0.17 | 0 | 40
__export__.project_task_4264_63f2fbc1 | Requirement Mapping/Gathering | Sprint 2129 | 2021-07-12 | Configuration | Heronswood: Collectors Database Phase 1 (P142) | Naseeb Razaq | Naseeb Razaq | 1 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 1657 | 1 | 0 | 0 | 40
__export__.project_task_4263_c0897468 | Weekly Project Review Meeting | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Farman Ahmad Cheema | 2.25 | 100 |  |  |  | Complete | Silverdale Technology LLC | 1657 | 1 | -1.25 | 0 | 16
__export__.project_task_4261_5161f583 | Sprint 2131 Planning | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Farman Ahmad Cheema | 3 | 100 |  |  |  | Complete | Silverdale Technology LLC | 1657 | 3 | 0 | 0 | 48
__export__.project_task_4259_9e23a484 | Sprint Review Meeting | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Farman Ahmad Cheema | 0.33 | 66 |  |  |  | Complete | Silverdale Technology LLC | 1657 | 0.5 | 0.17 | 0 | 16
__export__.project_task_4258_2a21f569 | Daily Standup Meetings and Prep | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Farman Ahmad Cheema | 5.42 | 100 |  |  |  | Complete | Silverdale Technology LLC | 1657 | 2.5 | -2.92 | 0 | 48
__export__.project_task_4256_2b177f10 | Deploy module on server |  |  | Configuration | MMH: Available to Promise Quantities (P141) | Naseeb Razaq | Farman Ahmad Cheema | 0 | 0 | Test and update |  |  | Backlog | Mountain Meadow Herbs | 1658 | 5 | 5 | 0 | 0
__export__.project_task_4255_ee915277 | Daily Meetings For Lead Consultant | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Naseeb Razaq | 8.9 | 80.91 |  |  |  | Complete | Silverdale Technology LLC | 1658 | 11 | 2.1 | 0 | 48
__export__.project_task_4254_f301eabc | Sponsor Call | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Perfect Golf: Help (P99) | Naseeb Razaq | Farman Ahmad Cheema | 0.75 | 75 |  |  |  | Complete | Perfect Golf Event | 1659 | 1 | 0.25 | 0 | 28
__export__.project_task_4252_411d9dd9 | Informal Greeting data import from NFGT into Odoo | Sprint 2129 | 2021-07-12 | Configuration | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Farman Ahmad Cheema | 0 | 0 |  |  |  | Cancelled | Port Gamble Sâ€™Klallam Foundation | 1660 | 2 | 2 | 0 | 40
__export__.project_task_4251_33911eeb | Updating Contact mailing List from Constant Contact to Odoo | Sprint 2131 | 2021-07-26 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq | Farman Ahmad Cheema | 2.5 | 83.33 |  | SPLN |  | Complete | Port Gamble Sâ€™Klallam Foundation | 1660 | 3 | 0.5 | 0 | 53.0662
__export__.project_task_4250_ba7c50e9 | Wildleaf Sponsor Meeting | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Wild Leaf: Help (P22) | Muhammad Zubair | Mir Muhammad Muzammil | 0.63 | 94.5 |  |  |  | Complete | Wild Leaf Beverage | 1661 | 0.66667 | 0.036667 | 5.6778 | 20.3317
__export__.project_task_4249_6e23e78f | Project Manager Review of Tasks 2129 | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Wild Leaf: Help (P22) | Muhammad Zubair | Mir Muhammad Muzammil | 2 | 50 |  | SPLN |  | Complete | Wild Leaf Beverage | 1661 | 4 | 2 | 0 | 53.8744
__export__.project_task_4247_e14bd011 | Operations Meetings for Sprint 2129 | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Silverdale Time Tracking (P56) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 1661 | 5 | 5 | 52.8379 | 116.5551
__export__.project_task_4246_3353e4ae | Sprint Planning 2129 | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Silverdale Time Tracking (P56) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 1661 | 1 | 1 | 52.8568 | 53.4129
__export__.project_task_4245_1b2b9ffa | Sprint Planning Discussion with Developer 2129 | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Wild Leaf: Help (P22) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 0.33 | 11 |  |  |  | Complete | Wild Leaf Beverage | 1661 | 3 | 2.67 | 53.8794 | 53.8808
__export__.project_task_4234_2ba1f827 | IL2000 - Validation error not letting the shipping quote to be requested | Sprint 2128 | 2021-07-05 | Development | Wild Leaf: Help (P22) | Muhammad Zubair | Fahad Hassan | 6 | 100 |  | SPLN | 2 | Complete | Wild Leaf Beverage | 1668 | 5 | -1 | 6.3214e-05 | 54.779
__export__.project_task_4230_6dbb203b | To incorporate the modules from Git Hub | Sprint 2138 | 2021-09-13 | Configuration | MMH: Available to Promise Quantities (P141) | Naseeb Razaq | Farman Ahmad Cheema | 8.83 | 94.61 | PM Review this task | 2017-09-01 |  | PM Review | Mountain Meadow Herbs | 1681 | 9.3333 | 0.50333 | 0 | 0
Test and update
__export__.project_task_4228_afbc4689 | Website Loading Issue : DG | Sprint 2128 | 2021-07-05 | Development | DGS: Help (P131) | Fahad Hussain Malik | Muzher Siddique | 8.25 | 63.46 |  | SPLN | 4 | Cancelled | DG Solutions Inc. | 1683 | 13 | 4.75 | 0 | 92.0192
__export__.project_task_4225_123af85c | field service > planning | Sprint 2128 | 2021-07-05 | Development | PWX: Help (P23) | Levi Barnes |  | 4.25 | 85 |  | SPLN | 1 | Complete | EquityTeam | 1691 | 5 | 0.75 | 66.4731 | 214.3365
__export__.project_task_4224_b28e15ff | VAT not reflecting correctly on Online order | Sprint 2128 | 2021-07-05 | Development | MMH Dr. Clark: Help (P106) | Naseeb Razaq | Muhammad Bilal | 10 | 100 |  | SPLN | 3 | Complete | Mountain Meadow Herbs | 1691 | 9.5 | -0.5 | 0 | 86.3665
__export__.project_task_4223_4941f1e3 | Website changes not reflecting on live sites | Sprint 2128 | 2021-07-05 | Development | MMH Tools For Healing: Help (P107) | Naseeb Razaq |  | 5.83 | 89.69 |  | SPLN | 3 | Complete | Mountain Meadow Herbs | 1692 | 6.5 | 0.67 | 0 | 114.4108
__export__.project_task_4222_96f1d014 | Create videos for the Critical Functional test cases | Sprint 2131 | 2021-07-26 | Functionality Test | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Wishal Nasir | 16.25 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 1710 | 11 | -5.25 | 70.4507 | 104.7396
__export__.project_task_4221_49648f75 | Audit Report - Code, Functionality, Master Data and Configurations |  |  | Configuration | DGS: Odoo Audit and v14 Upgrade Estimate (P136) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | DG Solutions Inc. | 1711 | 0 | 0 | 0 | 30.7734
__export__.project_task_4220_abc30cc1 | Downloading content on visiting site after adding info by visitor | Sprint 2128 | 2021-07-05 | Development | MMH: Website Edits June 2021 (P120) | Naseeb Razaq | Danish Hassan | 9.75 | 100 |  | SPLN | 2 | Complete | Mountain Meadow Herbs | 1712 | 8.5 | -1.25 | 0 | 91.6141
__export__.project_task_4219_5e45b6bd | Stop changing Quantity of tickets after registering for tickets | Sprint 2129 | 2021-07-12 | Development | Heronswood: Help (P54) | Naseeb Razaq | Danish Hassan | 7.83 | 100 |  | SPLN | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 1713 | 6 | -1.83 | 0 | 164.2934
__export__.project_task_4215_0606d43a | Trip Video's Selection / Editing |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 1 | 0 |  |  |  | Complete | Silverdale Technology LLC | 1730 | 0 | -1 | 0 | 254.75
__export__.project_task_4214_9f6de584 | Picture's Selection/uploading/Editing |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 4.25 | 0 |  |  |  | Complete | Silverdale Technology LLC | 1730 | 0 | -4.25 | 0 | 254.7558
__export__.project_task_4213_62264955 | Quote to Client |  |  |  | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Mountain Meadow Herbs | 1733 | 0 | 0 | 0 | 144.9704
__export__.project_task_4210_518bcc9e | Upgrade Modules |  |  | Development | Silverdale: v14 Upgrade (P46) | Muhammad Afzaal | Aleem khan | 6.83 | 42.69 |  |  | 2 | Complete | Silverdale Technology LLC | 1740 | 16 | 9.17 | 0.010465 | 150.601
__export__.project_task_4198_5aec0d15 | Create Final Report | Sprint 2137 | 2021-09-06 | Other | CraftAG: Odoo Audit (P147) | Fahad Hussain Malik | Jeff Gross | 0 | 0 |  | SPLN |  | Cancelled | CraftAG | 1798 | 3 | 3 | 137.7915 | 361.2073
__export__.project_task_4193_a993c4a0 | Get access to Client instance |  |  | Other | CraftAG: Odoo Audit (P147) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | CraftAG | 1798 | 0 | 0 | 148.3292 | 148.3306
__export__.project_task_4192_16c15706 | Critical Functional Test Cases Steps after QA first run | Sprint 2129 | 2021-07-12 | Functionality Test | Perfect Golf: Help (P99) | Naseeb Razaq | Wishal Nasir | 6.17 | 100 |  |  |  | Complete | Perfect Golf Event | 1800 | 4 | -2.17 | 0 | 80
__export__.project_task_4191_15e2eebd | Cbpid App support |  |  | Internal Time Tracking | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 23.83 | 0 |  |  |  | Complete | Cellpoint Corporation | 1801 | 0 | -23.83 | 0.028919 | 262.4164
__export__.project_task_4190_5ead5265 | Make the Logos more prominent on all pages |  |  | Development | Cellpoint: Change Color Theme for CPBids (P123) | Muhammad Afzaal | Kaleem Khan | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 1805 | 0 | 0 | 0 | 144.9479
__export__.project_task_4189_af937d63 | Office Video Recording |  |  |  | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 2 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 1806 | 0 | -2 | 0 | 266.7719
__export__.project_task_4188_c09ac441 | Office Video |  |  |  | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 3.5 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 1807 | 0 | -3.5 | 0 | 266.7769
__export__.project_task_4186_4e4bd3ba | Deploy to Production (Cpbids - 2127) | Sprint 2127 | 2021-06-28 | Development | Cellpoint: Change Color Theme for CPBids (P123) | Muhammad Afzaal | Fahad Hassan | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 1811 | 0 | 0 | 0 | 5.2941
__export__.project_task_4185_f7008f4e | Setup Invoicing | Sprint 2128 | 2021-07-05 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 1 | 100 |  | SPLN |  | Complete | Zuma Sales LLC | 1827 | 1 | 0 | 93.0078 | 56
__export__.project_task_4184_3202170a | Connection of Woocommerce |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq | Wajahat Ali | 0 | 0 | FWU |  |  | Planning | Mountain Meadow Herbs | 1827 | 3 | 3 | 0 | 0
__export__.project_task_4183_86fc86cf | Setup Accounting | Sprint 2128 | 2021-07-05 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 1 | 100 |  |  |  | Complete | Zuma Sales LLC | 1827 | 1 | 0 | 93.0078 | 12.9961
__export__.project_task_4182_20864955 | Web application - Move the Meet Us CP Bids information to the bottom of the page | Sprint 2128 | 2021-07-05 | Development | Cellpoint: Meet Us CP Bids information to the bottom of the page (P145) | Muhammad Afzaal | Kaleem Khan | 11.75 | 97.92 |  | SPLN | 2 | Complete | Cellpoint Corporation | 1827 | 12 | 0.25 | 0 | 101.5975
__export__.project_task_4177_fcef2fda | Internal Processes | Sprint 2128 | 2021-07-05 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Fahad Hussain Malik | 7 | 38.89 |  |  |  | Complete | Silverdale Technology LLC | 1829 | 18 | 11 | 0 | 49.768
__export__.project_task_4176_fa988133 | Demo Video for the complete cycle of supply chain | Sprint 2128 | 2021-07-05 | Configuration | MMH: Help (P83) | Naseeb Razaq | Naseeb Razaq | 4 | 100 |  |  |  | Complete | Mountain Meadow Herbs | 1829 | 3 | -1 | 0 | 24.5912
__export__.project_task_4175_03c13c21 | Helpdesk Time | Sprint 2128 | 2021-07-05 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Fahad Hussain Malik | 4 | 80 |  |  |  | Complete | Silverdale Technology LLC | 1829 | 5 | 1 | 0.00010882 | 49.9787
__export__.project_task_4174_c1878f06 | Solution design for the Master location for dispatching items from a single location | Sprint 2128 | 2021-07-05 | Configuration | MMH: Help (P83) | Naseeb Razaq | Naseeb Razaq | 1 | 100 |  |  |  | Complete | Mountain Meadow Herbs | 1829 | 1 | 0 | 2.8027e-05 | 32.6439
__export__.project_task_4173_675650c8 | Planning for Available to Promise Quantities | Sprint 2137 | 2021-09-06 | Configuration | MMH: Available to Promise Quantities (P141) | Naseeb Razaq | Farman Ahmad Cheema | 3.5 | 87.5 |  |  |  | Complete | Mountain Meadow Herbs | 1829 | 4 | 0.5 | 0 | 362.5821
__export__.project_task_4172_81745a36 | Help Desk Tickets Review 2128 | Sprint 2128 | 2021-07-05 | Internal Time Tracking | Wild Leaf: Help (P22) | Muhammad Zubair |  | 5.83 | 41.64 |  |  |  | Complete | Wild Leaf Beverage | 1829 | 14 | 8.17 | 0 | 48.5956
__export__.project_task_4171_2a67df7d | Sprint Planning Discussion with Developer 2128 | Sprint 2128 | 2021-07-05 | Internal Time Tracking | Wild Leaf: Help (P22) | Muhammad Zubair |  | 2 | 50 |  |  |  | Complete | Wild Leaf Beverage | 1829 | 4 | 2 | 0 | 40
__export__.project_task_4170_972c007f | Project Manager Review of Tasks 2128 | Sprint 2128 | 2021-07-05 | Internal Time Tracking | Wild Leaf: Help (P22) | Muhammad Zubair |  | 4.5 | 75 |  |  |  | Complete | Wild Leaf Beverage | 1829 | 6 | 1.5 | 0 | 48.6067
__export__.project_task_4169_9d14cdb4 | Shipping methods configurations correctly to reflect on the MMH websites | Sprint 2128 | 2021-07-05 | Configuration | MMH: Help (P83) | Naseeb Razaq | Naseeb Razaq | 0 | 0 |  |  |  | Complete | Mountain Meadow Herbs | 1829 | 2 | 2 | 0.012857 | 48.7492
__export__.project_task_4168_40b2e425 | Sprint Planning 2128 | Sprint 2128 | 2021-07-05 | Internal Time Tracking | Wild Leaf: Help (P22) | Muhammad Zubair |  | 1.83 | 61 |  |  |  | Complete | Wild Leaf Beverage | 1829 | 3 | 1.17 | 0 | 40
__export__.project_task_4167_f5dfdeb4 | Fahad Meetings for Sprint 2128 | Sprint 2128 | 2021-07-05 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Fahad Hussain Malik | 9.17 | 100 |  |  |  | Complete | Silverdale Technology LLC | 1829 | 5.1667 | -4.0033 | 1.4782e-05 | 40.7781
__export__.project_task_4166_9b664036 | Sponsor Meeting | Sprint 2128 | 2021-07-05 | Internal Time Tracking | Wild Leaf: Help (P22) | Muhammad Zubair |  | 1.67 | 100 |  |  |  | Complete | Wild Leaf Beverage | 1829 | 0.66667 | -1.0033 | 0 | 32
__export__.project_task_4165_1bc1109d | Weekly Sprint Meeting 2129 | Sprint 2129 | 2021-07-12 | Internal Time Tracking | Silverdale Time Tracking (P56) | Mir Muhammad Muzammil | Mir Muhammad Muzammil | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 1829 | 1 | 1 | 93.6849 | 93.6866
__export__.project_task_4164_44337bbc | Operations Meetings for Sprint 2128 | Sprint 2128 | 2021-07-05 | Internal Time Tracking | Wild Leaf: Help (P22) | Muhammad Zubair |  | 0.83 | 23.71 |  |  |  | Complete | Wild Leaf Beverage | 1829 | 3.5 | 2.67 | 0 | 48.6131
__export__.project_task_4161_076efde2 | Accounts Meetings for Sprint 2128 | Sprint 2128 | 2021-07-05 | Internal Time Tracking | Wild Leaf: Help (P22) | Muhammad Zubair |  | 2.67 | 76.29 |  |  |  | Complete | Wild Leaf Beverage | 1829 | 3.5 | 0.83 | 0 | 48.6208
__export__.project_task_4159_296d4af0 | Estimate to Set up email servers | Sprint 2128 | 2021-07-05 | Configuration | DGS: Odoo Audit and v14 Upgrade Estimate (P136) | Jeff Gross | Muzher Siddique | 0 | 0 |  |  |  | Complete | DG Solutions Inc. | 1829 | 0.5 | 0.5 | 0 | 44.9546
__export__.project_task_4157_165054ae | Daily Meetings For Lead Consultant | Sprint 2128 | 2021-07-05 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 5.55 | 74 |  |  |  | Complete | Silverdale Technology LLC | 1829 | 7.5 | 1.95 | 0.11052 | 50.4427
__export__.project_task_4156_3eede1bf | Estimate for First Transfer over their database from AWS hosted server | Sprint 2128 | 2021-07-05 | Development | DGS: Odoo Audit and v14 Upgrade Estimate (P136) | Jeff Gross | Muzher Siddique | 0.17 | 1.13 |  |  | 2 | Complete | DG Solutions Inc. | 1829 | 15 | 14.83 | 2.6931e-05 | 44.9745
__export__.project_task_4155_654d5ed9 | Upgrade to v14 |  |  | Development | DGS: Odoo Audit and v14 Upgrade Estimate (P136) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | DG Solutions Inc. | 1829 | 8 | 8 | 0 | 174.7688
__export__.project_task_4148_7c4ebcf1 | Customs Document Attachment : On invoice views and models | Sprint 2129 | 2021-07-12 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Raheel Aslam | 6.5 | 92.86 |  | SPLN | 3 | Complete | Zuma Sales LLC | 1830 | 7 | 0.5 | 94.8978 | 105.8901
__export__.project_task_4141_00074468 | Customer and CRM Prospects Identification | Sprint 2131 | 2021-07-26 | Development | Wild Leaf: Sales Improvements (P150) | Mir Muhammad Muzammil | Danish Hassan | 11.5 | 95.83 |  | SPLN | 2 | Complete | Wild Leaf Beverage | 1832 | 12 | 0.5 | 97.3658 | 180.0192
__export__.project_task_4140_c40ec70f | Some products MO not generating from Sale order |  |  | Bug Fix | Wild Leaf: Help (P22) | Muhammad Zubair |  | 1 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 1849 | 0 | -1 | 0 | 8
__export__.project_task_4139_cb9e3a07 | Create critical functional test cases | Sprint 2127 | 2021-06-28 | Configuration | Perfect Golf: Help (P99) | Naseeb Razaq |  | 2.5 | 0 |  | SPLN |  | Complete | Perfect Golf Event | 1853 | 0 | -2.5 | 0.0087108 | 16.712
__export__.project_task_4138_f216bb89 | Wildleaf Critical Test Case Run-Post Deployment(Production) |  |  | Internal Time Tracking | Wild Leaf: Help (P22) | Muhammad Zubair |  | 4 | 100 |  |  |  | Complete | Wild Leaf Beverage | 1854 | 4 | 0 | 0 | 33.1376
__export__.project_task_4137_01012cbb | Page Object Model |  |  | Improvements | Silverdale: Devops (P84) | Muzher Siddique | Wishal Nasir | 7.42 | 0 | Decide validity |  |  | Backlog | Silverdale Technology LLC | 1854 | 0 | -7.42 | 417.2947 | 0
__export__.project_task_4136_5b7605af | Create critical functional test cases | Sprint 2127 | 2021-06-28 | Configuration | DGS: Help (P131) | Fahad Hussain Malik |  | 8.08 | 100 |  | SADL |  | Complete | DG Solutions Inc. | 1872 | 2 | -6.08 | 4 | 29.0836
__export__.project_task_4135_ed148428 | Create critical functional test cases | Sprint 2127 | 2021-06-28 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 6 | 100 |  | SADL |  | Complete | Zuma Sales LLC | 1872 | 2 | -4 | 109.0078 | 33.4947
__export__.project_task_4134_65e44c1e | Estimate to Upgrade the instance to V14 | Sprint 2128 | 2021-07-05 | Configuration | DGS: Odoo Audit and v14 Upgrade Estimate (P136) | Fahad Hussain Malik | Muzher Siddique | 2 | 25 |  |  |  | Complete | DG Solutions Inc. | 1879 | 8 | 6 | 0.011889 | 63.2247
__export__.project_task_4133_19c34fd5 | Deploy to Production (PWX - 2126) | Sprint 2127 | 2021-06-28 | Development | PWX: HR (P61) | Naseeb Razaq | Fahad Hassan | 1.58 | 52.67 |  | SPLN |  | Complete | EquityTeam | 1880 | 3 | 1.42 | 0 | 19.7906
__export__.project_task_4132_eade5ddb | Sponsor Review Presentation Sprint 2127 |  |  | Internal Time Tracking | Wild Leaf: Help (P22) | Muhammad Zubair |  | 1.25 | 100 |  |  |  | Complete | Wild Leaf Beverage | 1881 | 1.25 | 0 | 6.485e-06 | 0.011395
__export__.project_task_4131_5fe58e6f | Deploy to Production (PerfectGolf -2126) | Sprint 2127 | 2021-06-28 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Fahad Hassan | 0.42 | 8.4 |  | SPLN |  | Complete | Perfect Golf Event | 1881 | 5 | 4.58 | 2.5216e-05 | 0.073359
__export__.project_task_4129_dbd2128b | Deploy to Production(Wildleaf-Deployment - 2126) | Sprint 2127 | 2021-06-28 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Fahad Hassan | 3.08 | 100 |  | SPLN |  | Complete | Wild Leaf Beverage | 1884 | 2 | -1.08 | 0.00011312 | 1.9184
__export__.project_task_4127_89fee067 | Show 'Stage' of Quotations on Quotations page | Sprint 2127 | 2021-06-28 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0.25 | 0 |  |  |  | Complete | Perfect Golf Event | 1901 | 0 | -0.25 | 0 | 48.3785
__export__.project_task_4123_85a8fd52 | Estimate Effort - Ballpark |  |  | Other | PWX: Accounting for Realtors - Replace Simple Bills (P109) | Levi Barnes |  | 0 | 0 |  |  |  | Cancelled | EquityTeam | 1901 | 0 | 0 | 0.016458 | 265.0351
__export__.project_task_4121_5346dfde | Deploy to Deployment (PerfectGolf - PDQA - 2126) | Sprint 2127 | 2021-06-28 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Fahad Hassan | 2.83 | 56.6 |  | SPLN |  | Complete | Perfect Golf Event | 1903 | 5 | 2.17 | 2.5979e-05 | 6.9956
__export__.project_task_4120_e10ae080 | DG Meeting and Timesheets |  |  | Internal Time Tracking | DGS: Help (P131) | Fahad Hussain Malik |  | 16.83 | 0 |  |  |  | Cancelled | DG Solutions Inc. | 1905 | 0 | -16.83 | 0 | 115.3225
__export__.project_task_4113_12d5c451 | Website Migration - Duplicate Task | Sprint 2127 | 2021-06-28 | Development | DGS: Help (P131) | Umer Farooq | Muzher Siddique | 0 | 0 |  | SPLN |  | Cancelled | DG Solutions Inc. | 1973 | 0 | 0 | 0.18153 | 0.5807
__export__.project_task_4102_f34827f0 | Deploy to Deployment (PWX - PDQA - 2126) | Sprint 2128 | 2021-07-05 | Development | PWX: HR (P61) | Naseeb Razaq | Fahad Hassan | 11.67 | 100 |  | SPLN |  | Complete | EquityTeam | 1978 | 5 | -6.67 | 1.8013e-05 | 45.2142
__export__.project_task_4101_d9eef0fc | Deploy to Deployment (MMHerb - PDQA - 2126) | Sprint 2127 | 2021-06-28 | Development | MMH: Help (P83) | Naseeb Razaq | Fahad Hassan | 0 | 0 |  | SPLN |  | Cancelled | Mountain Meadow Herbs | 1978 | 1 | 1 | 0.61239 | 16.0766
__export__.project_task_4100_9ccdf8ba | Deploy to Deployment (Wildleaf - PDQA - 2126) | Sprint 2127 | 2021-06-28 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Fahad Hassan | 3.92 | 100 |  | SPLN |  | Complete | Wild Leaf Beverage | 1979 | 1 | -2.92 | 3.4017e-05 | 14.9325
__export__.project_task_4097_54edc6f1 | 2126:Cpbids helpdesk tickets developer support | Sprint 2126 | 2021-06-21 | Internal Time Tracking | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 2 | 0 |  |  |  | Complete | Cellpoint Corporation | 2004 | 0 | -2 | 0.00021195 | 14.4252
__export__.project_task_4095_40b1f139 | Training | Sprint 2126 | 2021-06-21 | Other | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 3.5 | 0 |  |  |  | Complete | Perfect Golf Event | 2016 | 0 | -3.5 | 0 | 16
__export__.project_task_4086_f3e6ae0b | Import Newest Membership Date on Donors Profile | Sprint 2127 | 2021-06-28 | Configuration | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq |  | 2.5 | 0 |  | SPLN |  | Complete | Port Gamble Sâ€™Klallam Foundation | 2041 | 0 | -2.5 | 0 | 40
__export__.project_task_4079_78fe2f4f | Import Products along with product variants |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 | Plan it for sprint |  |  | Planning | Mountain Meadow Herbs | 2048 | 1 | 1 | 0 | 0
__export__.project_task_4066_d273910d | Deployment MMHerbs | Sprint 2126 | 2021-06-21 | Development | MMH Dr. Clark: Help (P106) | Naseeb Razaq | Fahad Hassan | 0 | 0 |  |  |  | Complete | Mountain Meadow Herbs | 2049 | 0 | 0 | 0 | 3.9406
__export__.project_task_4065_c67f3717 | Deployment MidAmerica | Sprint 2126 | 2021-06-21 | Development | Mid-America: Help (P37) | Naseeb Razaq | Fahad Hassan | 0.92 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 2050 | 0 | -0.92 | 0 | 4.3363
__export__.project_task_4064_13e8068c | Perfect Golf Deployment | Sprint 2126 | 2021-06-21 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Fahad Hassan | 0 | 0 |  |  |  | Complete | Perfect Golf Event | 2050 | 0 | 0 | 0 | 4.8643
__export__.project_task_4063_b3e2bf7a | Zuma Deployment | Sprint 2126 | 2021-06-21 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 1.75 | 0 |  | SADL |  | Complete | Zuma Sales LLC | 2050 | 0 | -1.75 | 154.351 | 53.3432
__export__.project_task_4062_02b1a6c6 | Deployment WildLeaf | Sprint 2126 | 2021-06-21 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Fahad Hassan | 3.08 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2052 | 0 | -3.08 | 0 | 7.1122
__export__.project_task_4061_70542c39 | Sponsor Call | Sprint 2126 | 2021-06-21 | Other | Perfect Golf: Help (P99) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Perfect Golf Event | 2065 | 0 | 0 | 0 | 32
__export__.project_task_4052_c79fda09 | Set up Projects Module | Sprint 2126 | 2021-06-21 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2068 | 0 | 0 | 156.9908 | 40
__export__.project_task_4051_34850a76 | Inform Client On the Completion of Activity |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2118 | 0 | 0 | 0 | 7.5356
__export__.project_task_4050_a4465396 | Assign Cost & calculate total for each line / Production |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 1 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2118 | 0 | -1 | 0 | 0
__export__.project_task_4049_9be46bd8 | Import Current Inventory Balances / Production |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 2 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2118 | 0 | -2 | 0 | 0
__export__.project_task_4048_fbe120e9 | Import Current Inventory Balances / Staging |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 2 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2118 | 0 | -2 | 0 | 0
__export__.project_task_4046_e86ee11a | Ebay Connection | Sprint 2128 | 2021-07-05 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 2.58 | 100 |  | SPLN | 1 | Complete | Zuma Sales LLC | 2137 | 2 | -0.58 | 165.0075 | 144
__export__.project_task_4041_20461f16 | Set Semi-finish routes settings on product categories / Production |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 1.33 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2144 | 0 | -1.33 | 3.2817e-05 | 3.5798
__export__.project_task_4040_a0be6b77 | Change Location Names of new Routes setups /Production |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 0.17 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2144 | 0 | -0.17 | 0.00014588 | 3.6229
__export__.project_task_4039_9882ab93 | Send COGS totals to Eric for May & June / Production |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 0.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2144 | 0 | -0.5 | 0 | 4
__export__.project_task_4038_107ae056 | Assign Cost and Calculate total for each line/ Production |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 0.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2144 | 0 | -0.5 | 0 | 4
__export__.project_task_4037_239f56ad | Export 0 COGS Invoice lines from Journal Items with Quantities/ Production |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 0.33 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2144 | 0 | -0.33 | 0 | 4
__export__.project_task_4033_7a660112 | Export Current Inventories with Location, Lots, Package and Owner/ Production |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 0.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2144 | 0 | -0.25 | 0 | 4
__export__.project_task_4029_f4c6afda | Routes Settings Semi-finish for all warehouses/ Production |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 2 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2160 | 0 | -2 | 0 | 8
__export__.project_task_4027_0abb101d | 'Stage' Selection Field, Approved Design stage and Is Design Approved | Sprint 2126 | 2021-06-21 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 3.58 | 79.56 |  |  | 2 | Complete | Perfect Golf Event | 2161 | 4.5 | 0.92 | 0 | 21.2094
__export__.project_task_4018_934e4601 | update release notes for Android and iOS new color scheme. | Sprint 2125 | 2021-06-14 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Faizan Zia Malik | 2.17 | 0 |  |  |  | Complete | Cellpoint Corporation | 2167 | 0 | -2.17 | 9.3309e-05 | 131.1018
__export__.project_task_4015_0807cac1 | Remove Payment Reference from Vendor Bill | Sprint 2128 | 2021-07-05 | Development | Wild Leaf: Help (P22) | Muhammad Zubair | Raheel Aslam | 11.08 | 100 |  | SPLN | 2 | Complete | Wild Leaf Beverage | 2169 | 5 | -6.08 | 8.2542e-05 | 155.3698
__export__.project_task_4014_5360b53d | pytest - odoo integration |  |  | Development | Silverdale: SDET (P132) | Levi Barnes | Levi Barnes | 3.58 | 100 |  |  |  | Complete | Silverdale Technology LLC | 2178 | 2.5 | -1.08 | 0 | 232.0192
__export__.project_task_4012_17a620b9 | project planning |  |  | Internal Time Tracking | Silverdale: SDET (P132) | Levi Barnes | Levi Barnes | 0.5 | 0 |  |  |  | Complete | Silverdale Technology LLC | 2184 | 0 | -0.5 | 0 | 8
__export__.project_task_4010_f0e41690 | Toggle for companies so that one user can access only one company at a time. Make this dependent on the user profile. One user can have it one company only at a time. Another can have multiple at a time. |  |  | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 2188 | 0 | 0 | 181.8899 | 385.3526
__export__.project_task_4007_15ba4b0d | ZPL barcode contains "amp;" if product name contains "&" |  |  | Development | Wild Leaf: Labeling (P60) | Muhammad Zubair |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 2191 | 0 | 0 | 0.010762 | 10.2572
__export__.project_task_4005_537d4dae | Inventory Adjustment for all products to 0/ Production |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 2 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2191 | 0 | -2 | 0 | 19.3009
__export__.project_task_4004_b8c212c4 | Change Costing Method on Product Categories / Production |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2192 | 0 | 0 | 0 | 19.4063
__export__.project_task_4002_b325b735 | Upload Costs on Product Master/ Production |  |  | Configuration | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Muhammad Zubair |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2192 | 0 | 0 | 0 | 19.4318
__export__.project_task_4001_902aacdc | Add Costs on Product Master File |  |  | Other | Wild Leaf: Accounting Balances and Inventory Fixes (P133) | Ryan Mason |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2192 | 0 | 0 | 8.4051 | 19.4387
__export__.project_task_4000_e874c235 | SSIS Script error |  |  | Other | DGS: ETL Part 1 (P129) | Levi Barnes |  | 1.25 | 0 |  |  |  | Complete | DG Solutions Inc. | 2207 | 0 | -1.25 | 0 | 0
__export__.project_task_3989_45b8f1be | Sales setup | Sprint 2125 | 2021-06-14 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2216 | 0 | 0 | 192.6961 | 51.6884
__export__.project_task_3967_9941db8b | Share the quote with Customer |  |  |  | MMH: Affiliate Program Setup (P96) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Mountain Meadow Herbs | 2237 | 0 | 0 | 0 | 80.3549
__export__.project_task_3965_3ee756ac | cpbids Android build testing. |  |  | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 10.08 | 0 |  |  |  | Complete | Cellpoint Corporation | 2238 | 0 | -10.08 | 0 | 59.2666
__export__.project_task_3959_4672d41d | Selection field to set on SO/PO | Sprint 2125 | 2021-06-14 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 3.83 | 100 |  |  | 2 | Complete | Perfect Golf Event | 2305 | 3 | -0.83 | 0 | 40
__export__.project_task_3958_7c513f9b | Deployment perfect golf | Sprint 2124 | 2021-06-07 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Wajahat Ali | 5.5 | 0 |  |  |  | Complete | Perfect Golf Event | 2309 | 0 | -5.5 | 0.020923 | 0.40009
__export__.project_task_3956_d23bb7e6 | Change icons color according to marketplace color scheme | Sprint 2125 | 2021-06-14 | Development | Cellpoint: Change Color Theme for CPBids (P123) | Muhammad Afzaal | Kaleem Khan | 4.83 | 100 |  |  | 3 | Complete | Cellpoint Corporation | 2311 | 4 | -0.83 | 4.1289e-05 | 163.2973
__export__.project_task_3955_cf436626 | Change color scheme of buttons and top header menu of detail view | Sprint 2125 | 2021-06-14 | Development | Cellpoint: Change Color Theme for CPBids (P123) | Muhammad Afzaal | Kaleem Khan | 4.83 | 100 |  |  | 2 | Complete | Cellpoint Corporation | 2311 | 4 | -0.83 | 0.00010809 | 163.3432
__export__.project_task_3954_819d5e1d | Change color scheme for top header menu on web list view | Sprint 2125 | 2021-06-14 | Development | Cellpoint: Change Color Theme for CPBids (P123) | Muhammad Afzaal | Kaleem Khan | 4.58 | 100 |  |  | 2 | Complete | Cellpoint Corporation | 2312 | 4 | -0.58 | 0 | 163.3869
__export__.project_task_3953_3bbec403 | Change color scheme for web list view buttons | Sprint 2125 | 2021-06-14 | Development | Cellpoint: Change Color Theme for CPBids (P123) | Muhammad Afzaal | Kaleem Khan | 4.75 | 100 |  |  | 1 | Complete | Cellpoint Corporation | 2312 | 4 | -0.75 | 0 | 163.4591
__export__.project_task_3951_cea1e1bd | Web detail view dynamic marketplace logo | Sprint 2125 | 2021-06-14 | Development | Cellpoint: Change Color Theme for CPBids (P123) | Muhammad Afzaal | Kaleem Khan | 4.75 | 100 |  |  | 2 | Complete | Cellpoint Corporation | 2312 | 4 | -0.75 | 0.00010064 | 163.5004
__export__.project_task_3949_9fd3e484 | Web list view dynamic marketplace logo | Sprint 2125 | 2021-06-14 | Development | Cellpoint: Change Color Theme for CPBids (P123) | Muhammad Afzaal | Kaleem Khan | 5.75 | 100 |  |  | 2 | Complete | Cellpoint Corporation | 2312 | 4 | -1.75 | 6.959e-05 | 163.5231
__export__.project_task_3947_ae8c83ad | Terex SFTP Credentials | Sprint 2126 | 2021-06-21 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 1.17 | 58.5 |  |  |  | Complete | Zuma Sales LLC | 2312 | 2 | 0.83 | 208.549 | 83.5582
__export__.project_task_3945_57abbf39 | Helpdesk setup | Sprint 2125 | 2021-06-14 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2313 | 0 | 0 | 209.0078 | 68
__export__.project_task_3944_b62013bb | Website setup | Sprint 2125 | 2021-06-14 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2313 | 0 | 0 | 209.0078 | 68
__export__.project_task_3943_97245a83 | Perform QA for complete business process and transactional aspects | Sprint 2129 | 2021-07-12 | Quality Assurance | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 9.33 | 93.3 |  | SPLN |  | Complete | Zuma Sales LLC | 2313 | 10 | 0.67 | 209.0765 | 202.2879
__export__.project_task_3942_432b6bb0 | iOS Card View change Color scheme | Sprint 2125 | 2021-06-14 | Development | Cellpoint: Change Color Theme for CPBids (P123) | Muhammad Afzaal | Apps Maven | 3 | 75 |  |  |  | Complete | Cellpoint Corporation | 2324 | 4 | 1 | 0 | 168
__export__.project_task_3941_f452f233 | iOS Detail View change Color scheme | Sprint 2125 | 2021-06-14 | Development | Cellpoint: Change Color Theme for CPBids (P123) | Muhammad Afzaal | Apps Maven | 3.5 | 87.5 |  |  |  | Complete | Cellpoint Corporation | 2324 | 4 | 0.5 | 0 | 168
__export__.project_task_3940_8a577a03 | iOS List View change Color scheme | Sprint 2125 | 2021-06-14 | Development | Cellpoint: Change Color Theme for CPBids (P123) | Muhammad Afzaal | Apps Maven | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 2324 | 4 | 4 | 0 | 168
__export__.project_task_3939_f3ae32b1 | Android Card View change color scheme | Sprint 2125 | 2021-06-14 | Development | Cellpoint: Change Color Theme for CPBids (P123) | Muhammad Afzaal | Apps Maven | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 2324 | 4 | 4 | 0 | 168
__export__.project_task_3938_d71a973f | Android Detail View change color scheme | Sprint 2125 | 2021-06-14 | Development | Cellpoint: Change Color Theme for CPBids (P123) | Muhammad Afzaal | Apps Maven | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 2324 | 4 | 4 | 0 | 168
__export__.project_task_3937_95f553a0 | Android List View change color scheme | Sprint 2125 | 2021-06-14 | Development | Cellpoint: Change Color Theme for CPBids (P123) | Muhammad Afzaal | Apps Maven | 3 | 75 |  |  |  | Complete | Cellpoint Corporation | 2324 | 4 | 1 | 0 | 168
__export__.project_task_3936_cdd8ac9a | CpBids Auctions Automation | Sprint 2126 | 2021-06-21 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 9.83 | 100 |  |  |  | Complete | Silverdale Technology LLC | 2328 | 8 | -1.83 | 0 | 47.1153
__export__.project_task_3918_7af7c7cd | Discuss the Product Master | Sprint 2126 | 2021-06-21 | Other | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2356 | 0 | 0 | 221.0427 | 96.0518
__export__.project_task_3914_1909699c | wishlist product image | Sprint 2125 | 2021-06-14 | Development | Mid-America: Help (P37) | Naseeb Razaq | Raheel Aslam | 3.5 | 87.5 |  |  | 1 | Complete | Mid-America Gardens, LLC | 2364 | 4 | 0.5 | 0 | 118.602
__export__.project_task_3909_77e8699c | ui.constantcontact.com (Image Data) Date 01/05/2021 -- 08/06/2021 | Sprint 2124 | 2021-06-07 | Other | Heronswood: Help (P54) | Naseeb Razaq | Wishal Nasir | 0.5 | 100 |  | Postman |  | Complete | Port Gamble Sâ€™Klallam Foundation | 2387 | 0.5 | 0 | 0.060578 | 21.1386
__export__.project_task_3908_d311fcc5 | Deployment 2021-06-08 |  |  | Other | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 2.83 | 0 |  |  |  | Complete | Perfect Golf Event | 2389 | 0 | -2.83 | 0 | 38.5833
__export__.project_task_3907_949ee277 | Deployment 2021-06-08 |  |  | Other | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq |  | 1.33 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 2389 | 0 | -1.33 | 0 | 37.4251
__export__.project_task_3905_e7a363d9 | survey description by question |  |  | Configuration | PWX: Survey (P70) | Muhammad Afzaal | Levi Barnes | 2 | 0 |  |  |  | Complete | EquityTeam | 2400 | 0 | -2 | 0 | 40
__export__.project_task_3901_229a110d | Can you identify who the Public Users are? Why can't we see their information |  |  |  | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Port Gamble Sâ€™Klallam Foundation | 2405 | 0 | 0 | 0 | 0.13177
__export__.project_task_3900_b79d066b | TC-265-272 Accounting Module | Sprint 2124 | 2021-06-07 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 8 | 100 |  |  |  | Complete | Silverdale Technology LLC | 2405 | 7.5 | -0.5 | 3.9126e-05 | 105.1489
__export__.project_task_3898_a8daea2a | TC-265-272 Accounting Module |  |  | Development | Silverdale: Devops (P84) | Muzher Siddique |  | 2.25 | 60 |  |  |  | Cancelled | Silverdale Technology LLC | 2409 | 3.75 | 1.5 | 544 | 552
__export__.project_task_3896_94f5d895 | Survey: remove retry at the end | Sprint 2127 | 2021-06-28 | Development | PWX: Survey (P70) | Farman Ahmad Cheema | Danish Hassan | 9.58 | 100 |  | SPLN | 2 | Complete | EquityTeam | 2476 | 6 | -3.58 | 169.9586 | 200.1519
__export__.project_task_3895_48694768 | Survey: remove odoo | Sprint 2127 | 2021-06-28 | Development | PWX: Survey (P70) | Farman Ahmad Cheema | Danish Hassan | 2.58 | 81.47 |  | SPLN | 1 | Complete | EquityTeam | 2477 | 3.1667 | 0.58667 | 170.2082 | 200.3965
__export__.project_task_3887_a456de92 | Add Solution to Helpdesk tickets | Sprint 2126 | 2021-06-21 | Development | Silverdale: Help (P12) | Muhammad Afzaal | Muzher Siddique | 3.33 | 100 |  |  | 2 | Complete | Silverdale Technology LLC | 2479 | 3 | -0.33 | 0 | 122.9201
__export__.project_task_3862_7f1b96ab | Business Process Review |  |  |  | MMH: Affiliate Program Setup (P96) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Mountain Meadow Herbs | 2573 | 0 | 0 | 0 | 79.5266
__export__.project_task_3861_adbb51ff | Home Page Improvements | Sprint 2138 | 2021-09-13 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Sajjad Hussain | 0.33 | 9.43 | Please add next activity |  |  | Backlog | Cellpoint Corporation | 2575 | 3.5 | 3.17 | 472.0206 | 0
__export__.project_task_3860_91275716 | Grant Odoo Staging instance Access |  |  | Other | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0.92 | 0 |  |  |  | Complete | Perfect Golf Event | 2575 | 0 | -0.92 | 0 | 0.36312
__export__.project_task_3855_da208b42 | Run critical functionalities on Wildleaf |  |  | Improvements | Wild Leaf: Help (P22) | Muhammad Afzaal |  | 6 | 100 |  |  |  | Complete | Wild Leaf Beverage | 2578 | 6 | 0 | 0 | 155.0761
__export__.project_task_3854_3b9fd29a | Question regarding discrepancy in the September 22nd Heronswood Tour registration data |  |  | Bug Fix | Heronswood: Help (P54) | Naseeb Razaq | Danish Hassan | 4.33 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 2605 | 0 | -4.33 | 0 | 16
__export__.project_task_3853_de641680 | Notes tab should be able to be printed onto Delivery Order slip | Sprint 2122 | 2021-05-24 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Kaleem Khan | 4 | 100 |  |  | 1 | Complete | Wild Leaf Beverage | 2606 | 3 | -1 | 53.5475 | 48
__export__.project_task_3852_25d11417 | Deployment 2021-05-29 | Sprint 2122 | 2021-05-24 | Other | Wild Leaf: Help (P22) | Muhammad Afzaal |  | 6.17 | 0 |  |  |  | Complete | Wild Leaf Beverage | 2624 | 0 | -6.17 | 0 | 10.1422
__export__.project_task_3851_8575924c | Deployment 2021-05-29 | Sprint 2122 | 2021-05-24 | Other | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 2.58 | 0 |  |  |  | Complete | Perfect Golf Event | 2630 | 0 | -2.58 | 0 | 87.0733
__export__.project_task_3850_01c3c0e9 | Hyperlink Sales Order on deposit invoices, final invoices, and hold delivery manufacturing moves | Sprint 2122 | 2021-05-24 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Raheel Aslam | 4.42 | 73.67 |  |  | 2 | Complete | Wild Leaf Beverage | 2631 | 6 | 1.58 | 53.5475 | 48
__export__.project_task_3849_d01ff560 | Add column to invoice page that lists the associated Sales Order # |  |  | Development | Wild Leaf: Help (P22) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 2631 | 3 | 3 | 0 | 0
__export__.project_task_3847_8274d1e1 | MMH Script For Sale 244-249 | Sprint 2122 | 2021-05-24 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 9.42 | 100 |  |  |  | Complete | Silverdale Technology LLC | 2646 | 8 | -1.42 | 0 | 33.3924
__export__.project_task_3844_9c589e3e | Android app release, testing | Sprint 2122 | 2021-05-24 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 6.5 | 0 |  |  |  | Complete | Cellpoint Corporation | 2668 | 0 | -6.5 | 8.7813e-05 | 43.627
__export__.project_task_3843_5a7b3cf0 | Rename fields in Donor Management Module | Sprint 2124 | 2021-06-07 | Development | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Danish Hassan | 2.75 | 78.57 |  |  | 1 | Complete | Port Gamble Sâ€™Klallam Foundation | 2669 | 3.5 | 0.75 | 0 | 93.2526
__export__.project_task_3837_e9b853fc | Bill Reference on Vendor Bills | Sprint 2123 | 2021-05-31 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Raheel Aslam | 5.42 | 67.75 |  |  | 2 | Complete | Wild Leaf Beverage | 2674 | 8 | 2.58 | 66.2477 | 60.7002
__export__.project_task_3836_6a0f5778 | Deployment 2021-05-27 | Sprint 2122 | 2021-05-24 | Other | PWX: Survey (P70) | Muhammad Afzaal | Sanaullah Khan | 4.42 | 0 |  |  |  | Complete | EquityTeam | 2675 | 0 | -4.42 | 0 | 110.5138
__export__.project_task_3835_d0e1364b | Change label "Donor Number" on donation list view as "Donation Number" |  |  | Development | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Danish Hassan | 2.33 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 2694 | 2 | -0.33 | 0.018942 | 17.8612
__export__.project_task_3834_70c7247a | Check margin error |  |  | Development | Wild Leaf: Accounting (P64) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 2698 | 0 | 0 | 0 | 8.5226
__export__.project_task_3833_44b25a47 | Data Driven File Creation & Update Existing PWX Test Scripts | Sprint 2122 | 2021-05-24 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 4 | 100 |  |  |  | Complete | Silverdale Technology LLC | 2700 | 4 | 0 | 0 | 36.3811
__export__.project_task_3831_567f1665 | Perfect Golf Tasks and Tickets |  |  | Internal Time Tracking | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 92.67 | 0 |  |  |  | Complete | Perfect Golf Event | 2735 | 0 | -92.67 | 0 | 308.6206
__export__.project_task_3826_022c1f97 | Need to see more info on when we click on calendar card | Sprint 2122 | 2021-05-24 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Raheel Aslam | 9.17 | 76.42 |  |  | 3 | Complete | Wild Leaf Beverage | 2743 | 12 | 2.83 | 88.1726 | 82.6251
__export__.project_task_3825_84c5f990 | Create crone job for adding address in new contacts created after uploading balances | Sprint 2123 | 2021-05-31 | Development | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Danish Hassan | 4.25 | 100 |  |  | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 2744 | 3.5 | -0.75 | 0.021671 | 24.3403
__export__.project_task_3822_2e394409 | TC-142-152 | Sprint 2122 | 2021-05-24 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 5 | 100 |  |  |  | Complete | Silverdale Technology LLC | 2807 | 5 | 0 | 0 | 16
__export__.project_task_3821_f4a6c813 | Filter Donations on the basis of tag on donors | Sprint 2122 | 2021-05-24 | Development | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Danish Hassan | 3.33 | 100 |  |  | 1 | Complete | Port Gamble Sâ€™Klallam Foundation | 2830 | 3 | -0.33 | 0 | 36.8075
__export__.project_task_3820_57999b3a | Confirm bulk quotations of donations | Sprint 2122 | 2021-05-24 | Development | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Danish Hassan | 3.83 | 100 |  |  | 1 | Complete | Port Gamble Sâ€™Klallam Foundation | 2830 | 3.5 | -0.33 | 0 | 37.0386
__export__.project_task_3818_375c8e7b | Explore v14 ecommerce and make analysis of v13 and v14 |  |  | Functionality Test | MMH: Help (P83) | Naseeb Razaq |  | 2.75 | 0 |  |  |  | Complete | Mountain Meadow Herbs | 2831 | 0 | -2.75 | 0 | 384.0192
__export__.project_task_3817_6ba7df68 | QA on Production and QA on Staging | Sprint 2122 | 2021-05-24 | Other | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 2831 | 0 | 0 | 0 | 208
__export__.project_task_3816_129b4963 | TC-168-181 | Sprint 2122 | 2021-05-24 | Improvements | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 7 | 100 |  |  |  | Complete | Silverdale Technology LLC | 2832 | 7 | 0 | 0 | 24
__export__.project_task_3815_3b78f2f8 | When creating manufacturing order in the sales order, the sales order didn't get linked with the sales order even giving the source | Sprint 2122 | 2021-05-24 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Fahad Hassan | 32.92 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 2832 | 22 | -10.92 | 101.5475 | 96
__export__.project_task_3814_6d9a3905 | Create automation for notifying the sales team whenever a payment is made | Sprint 2122 | 2021-05-24 | Configuration | Wild Leaf: Help (P22) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 2834 | 0 | 0 | 0 | 84.9269
__export__.project_task_3813_35e21a07 | Set domain filter while creation of donation | Sprint 2122 | 2021-05-24 | Development | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Danish Hassan | 2.5 | 100 |  |  | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 2836 | 2.5 | 0 | 0.0080062 | 85.343
__export__.project_task_3812_83edd4df | Subscription Module Exploration |  |  | Improvements | MMH: Help (P83) | Naseeb Razaq | Danish Hassan | 3.5 | 100 |  |  |  | Complete | Mountain Meadow Herbs | 2856 | 3 | -0.5 | 8 | 8
__export__.project_task_3808_98826d09 | Remove/Archive duplication of contacts |  |  | Configuration | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Danish Hassan | 2.5 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 2860 | 2.5 | 0 | 0 | 0
__export__.project_task_3806_3a0610b9 | MM Herbs: Reserved Quantity is not showing up on DO | Sprint 2122 | 2021-05-24 | Bug Fix | MMH: Help (P83) | Naseeb Razaq | Muhammad Bilal | 2.5 | 0 |  |  | 4 | Complete | Mountain Meadow Herbs | 2881 | 0 | -2.5 | 0 | 108.6633
__export__.project_task_3804_61aebec0 | job view modification |  |  | Studio | PWX: HR (P61) | Muhammad Afzaal |  | 1.5 | 100 |  |  |  | Complete | EquityTeam | 2883 | 1.5 | 0 | 0 | 40
__export__.project_task_3800_4c04b729 | Quotation with Insurance coverage on Sales Order | Sprint 2124 | 2021-06-07 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 7.37 | 92.12 |  |  | 2 | Complete | Perfect Golf Event | 2886 | 8 | 0.63 | 18.0504 | 142.9104
__export__.project_task_3799_331d6893 | Insurance coverage confirmation | Sprint 2122 | 2021-05-24 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 2 | 80 |  |  | 1 | Complete | Perfect Golf Event | 2886 | 2.5 | 0.5 | 18.0504 | 54.9968
__export__.project_task_3798_e6c391b7 | Purchase quotation to send to the Insurance Company | Sprint 2122 | 2021-05-24 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 0 | 0 |  |  |  | Cancelled | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 90.0504
__export__.project_task_3795_e77e62d1 | Adding Terms and Condition title in email template | Sprint 2122 | 2021-05-24 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 0.67 | 33.5 |  |  | 1 | Complete | Perfect Golf Event | 2886 | 2 | 1.33 | 18.0504 | 46.827
__export__.project_task_3794_43da08b9 | Refund invoice | Sprint 2122 | 2021-05-24 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 95.9068
__export__.project_task_3793_473def71 | Update the Order | Sprint 2122 | 2021-05-24 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 58.0504
__export__.project_task_3792_d973fd23 | Change in Price in Quotation due to Insurance | Sprint 2122 | 2021-05-24 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 102.3262
__export__.project_task_3791_ad0ce362 | Gather more information from the customer related to Insurance | Sprint 2122 | 2021-05-24 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 3.33 | 100 |  |  | 1 | Complete | Perfect Golf Event | 2886 | 3 | -0.33 | 18.0504 | 98.0504
__export__.project_task_3790_03334149 | Follow up | Sprint 2122 | 2021-05-24 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 55.974
__export__.project_task_3789_cbdc9a5b | Capture Changes from Customer | Sprint 2122 | 2021-05-24 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 4.58 | 100 |  |  | 1 | Complete | Perfect Golf Event | 2886 | 3.5 | -1.08 | 18.0504 | 98.0504
__export__.project_task_3788_ab10c053 | Email to Customer with Tracking ID | Sprint 2122 | 2021-05-24 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 42.0504
__export__.project_task_3787_877b7e90 | Shipping notification to Perfect Golf with Tracking ID | Sprint 2122 | 2021-05-24 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 7.67 | 100 |  |  |  | Complete | Perfect Golf Event | 2886 | 4 | -3.67 | 18.0504 | 54.8004
__export__.project_task_3786_0459310a | Print/Production process | Sprint 2122 | 2021-05-24 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 2.17 | 86.8 |  |  | 1 | Complete | Perfect Golf Event | 2886 | 2.5 | 0.33 | 18.0504 | 55.0493
__export__.project_task_3784_46ca831b | Send approval to the vendor via Email (Purchase Order) | Sprint 2122 | 2021-05-24 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 3.5 | 100 |  |  | 2 | Complete | Perfect Golf Event | 2886 | 3.3333 | -0.16667 | 18.0504 | 98.0504
__export__.project_task_3783_ef6c7ba1 | Follow up and Approval from Customer | Sprint 2122 | 2021-05-24 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 2 | 66.67 |  |  | 1 | Complete | Perfect Golf Event | 2886 | 3 | 1 | 18.0504 | 98.0504
__export__.project_task_3781_4d48746f | Receive Proofs from vendor in Purchase Order | Sprint 2122 | 2021-05-24 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 95.9731
__export__.project_task_3779_2237bd6e | Word document created for signage for vendor | Sprint 2123 | 2021-05-31 | Other | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 74.0504
__export__.project_task_3778_375f720f | Customer response and follow up | Sprint 2122 | 2021-05-24 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 58.0504
__export__.project_task_3777_81df5e2f | Logos, Text for Signage and Shipping Address | Sprint 2122 | 2021-05-24 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 58.0504
__export__.project_task_3776_f177ea90 | Receiving the Cheque from Customer | Sprint 2122 | 2021-05-24 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 58.0504
__export__.project_task_3775_ec967ef1 | Waiting for Cheque from Customer | Sprint 2122 | 2021-05-24 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 58.0504
__export__.project_task_3774_66c3ae61 | Creating Customer Record | Sprint 2122 | 2021-05-24 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 90.0504
__export__.project_task_3773_ee797b84 | Pay now link from website | Sprint 2122 | 2021-05-24 | Other | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 96.462
__export__.project_task_3772_8b0cdba7 | Payment Method | Sprint 2122 | 2021-05-24 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 74.0504
__export__.project_task_3771_9106122d | Email Quotation to Customer | Sprint 2122 | 2021-05-24 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 58.0504
__export__.project_task_3770_d1165c6b | New Invoice for addition in SO | Sprint 2122 | 2021-05-24 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 96.6895
__export__.project_task_3769_5a963ea1 | Quotation Creation | Sprint 2122 | 2021-05-24 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 58.0504
__export__.project_task_3704_4c8c8bf1 | Remove default text about money back guarantee | Sprint 2122 | 2021-05-24 | Configuration | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Danish Hassan | 0.33 | 33 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 2901 | 1 | 0.67 | 0 | 6.8378
__export__.project_task_3703_33530d44 | TC-288,292,293,294,296,297,298 | Sprint 2123 | 2021-05-31 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 10.58 | 100 |  |  |  | Complete | Silverdale Technology LLC | 2901 | 10 | -0.58 | 0 | 48
__export__.project_task_3699_bd39661f | Add Close Order button to POs | Sprint 2121 | 2021-05-17 | Development | Wild Leaf: Help (P22) | Muhammad Afzaal | Aleem khan | 4.58 | 100 |  |  | 1 | Complete | Wild Leaf Beverage | 2905 | 2.5 | -2.08 | 0 | 56
__export__.project_task_3698_9e5f79a0 | Attach Sales Order to Deposit Invoices/Invoices | Sprint 2121 | 2021-05-17 | Development | Wild Leaf: Help (P22) | Muhammad Afzaal | Fahad Hassan | 5.17 | 57.44 |  |  | 4 | Cancelled | Wild Leaf Beverage | 2906 | 9 | 3.83 | 0 | 16
__export__.project_task_3689_85a11c8a | Show check numbers in bank reconciliation | Sprint 2121 | 2021-05-17 | Development | Wild Leaf: Help (P22) | Muhammad Afzaal | Raheel Aslam | 12.67 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 3005 | 7 | -5.67 | 0 | 96
__export__.project_task_3686_cfbb6f8d | Change the PDF and Customer Portal to show manually entered expected date | Sprint 2121 | 2021-05-17 | Development | Wild Leaf: Help (P22) | Muhammad Afzaal | Aleem khan | 4.5 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 3005 | 2.5 | -2 | 0 | 88
__export__.project_task_3684_0ea17104 | R&D Demand in Odoo |  |  | Development | Wild Leaf: Help (P22) | Muhammad Afzaal | Fahad Hassan | 0.17 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 3034 | 0 | -0.17 | 0 | 80
__export__.project_task_3680_43fade1e | Bank Reconciliation Report Format | Sprint 2123 | 2021-05-31 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Raheel Aslam | 20.5 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 3051 | 16.3333 | -4.1667 | 133.5475 | 128
__export__.project_task_3679_e8e5fd86 | Create Mailing Lists in Odoo |  |  | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 0.42 | 84 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3068 | 0.5 | 0.08 | 0 | 6.6608
__export__.project_task_3675_1f1e8909 | New Sales Order Line Item field for Outstanding Invoice Qty |  |  | Development | Wild Leaf: Consignment and Sales Improvements (P112) | Muhammad Afzaal | Muhammad Bilal | 4 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 3075 | 4 | 0 | 0 | 72
__export__.project_task_3674_1f7a6f89 | New Sales Order Line Item field for Outstanding Manufacturing Qty | Sprint 2121 | 2021-05-17 | Development | Wild Leaf: Consignment and Sales Improvements (P112) | Muhammad Afzaal | Muhammad Bilal | 1.83 | 61 |  |  | 2 | Complete | Wild Leaf Beverage | 3075 | 3 | 1.17 | 0 | 72
__export__.project_task_3673_9733dc5d | New Sales Order Line Item field for Manufacturing Done Qty |  |  | Development | Wild Leaf: Consignment and Sales Improvements (P112) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 3075 | 0 | 0 | 0 | 0
__export__.project_task_3670_5561a487 | TC-301-302-303-304-305 | Sprint 2123 | 2021-05-31 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 3.25 | 100 |  |  |  | Complete | Silverdale Technology LLC | 3139 | 3 | -0.25 | 0 | 16
__export__.project_task_3669_e844aec5 | TC-300 (Time Sheet) | Sprint 2123 | 2021-05-31 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 2 | 100 |  |  |  | Complete | Silverdale Technology LLC | 3141 | 2 | 0 | 0 | 8
__export__.project_task_3668_29b8b0ae | Git branch training |  |  | Other | Silverdale: Devops (P84) | Muzher Siddique | Muzher Siddique | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3144 | 2 | 2 | 682.3909 | 690.3909
__export__.project_task_3666_12ae6660 | Prevent create and edit on invoice, sales, customer payments, customers and vendor bills | Sprint 2120 | 2021-05-10 | Development | Wild Leaf: Help (P22) | Muhammad Afzaal | Raheel Aslam | 8 | 100 |  |  | 1 | Complete | Wild Leaf Beverage | 3146 | 5 | -3 | 0 | 40
__export__.project_task_3665_c2c66c12 | Client Success Dashboards |  |  | Configuration | Silverdale: Help (P12) | Muhammad Zubair |  | 2 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3147 | 0 | -2 | 0 | 16
__export__.project_task_3662_b8ffbe03 | Show product is out of stock | Sprint 2120 | 2021-05-10 | Development | Mid-America: Help (P37) | Naseeb Razaq | Danish Hassan | 6.08 | 93.54 |  |  | 2 | Complete | Mid-America Gardens, LLC | 3151 | 6.5 | 0.42 | 0 | 74.3718
__export__.project_task_3659_ad73162a | Message response default | Sprint 2121 | 2021-05-17 | Development | Wild Leaf: Help (P22) | Muhammad Afzaal | Raheel Aslam | 18.67 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 3172 | 10 | -8.67 | 0 | 112
__export__.project_task_3658_f6175ba5 | Customer / Vendor / Asset Number | Sprint 2120 | 2021-05-10 | Development | Wild Leaf: Help (P22) | Muhammad Afzaal | Danish Hassan | 8.67 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 3172 | 6.5 | -2.17 | 0 | 56
__export__.project_task_3649_f28878be | Demo first email to the Client and get feedback | Sprint 2127 | 2021-06-28 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 0.5 | 100 |  | SPLN |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.5 | 0 | 0.00052273 | 305.1419
__export__.project_task_3648_83034028 | Create the first test Odoo Email in the style of Constant Contact | Sprint 2120 | 2021-05-10 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 3 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.5 | -2.5 | 0.00024495 | 161.9839
__export__.project_task_3644_22af8f1f | Create a training video of how to create a new email contact | Sprint 2120 | 2021-05-10 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 1 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.5 | -0.5 | 0.00024495 | 152.3058
__export__.project_task_3636_a7512bd3 | Export data from Constant Contact | Sprint 2120 | 2021-05-10 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 0.17 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.16667 | -0.0033333 | 0 | 17.9839
__export__.project_task_3595_629076b4 | Verify client supplied credentials | Sprint 2120 | 2021-05-10 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 0.08 | 48 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.16667 | 0.086667 | 0.1649 | 18.1488
__export__.project_task_3594_d5d265fc | TC-306 (Create Building and Unit) | Sprint 2123 | 2021-05-31 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 2.5 | 100 |  |  |  | Complete | Silverdale Technology LLC | 3186 | 2.5 | 0 | 0 | 8
__export__.project_task_3591_f03cb11c | Odoo.sh Warning Reasons |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Muzher Siddique | 1.5 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3192 | 0 | -1.5 | 0 | 0
__export__.project_task_3590_ce77eaf3 | Pricelist Code Problem | Sprint 2121 | 2021-05-17 | Bug Fix | MMH Tools For Healing: Help (P107) | Naseeb Razaq | Muhammad Bilal | 4.33 | 43.3 |  |  | 4 | Complete | Mountain Meadow Herbs | 3193 | 10 | 5.67 | 0 | 192
__export__.project_task_3588_f21d8a89 | meeting |  |  | Internal Time Tracking | PWX: Survey (P70) | Muhammad Afzaal |  | 0.5 | 0 |  |  |  | Complete | EquityTeam | 3195 | 0 | -0.5 | 0 | 0
__export__.project_task_3587_94672c7d | TC-295 | Sprint 2123 | 2021-05-31 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 1.58 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3209 | 0 | -1.58 | 0 | 8
__export__.project_task_3586_be1d6a47 | TC-291 | Sprint 2123 | 2021-05-31 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 1.08 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3211 | 0 | -1.08 | 0 | 8
__export__.project_task_3585_7b1a3b62 | Move menus to Donation | Sprint 2120 | 2021-05-10 | Development | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Danish Hassan | 1.83 | 100 |  |  | 1 | Complete | Port Gamble Sâ€™Klallam Foundation | 3213 | 1.75 | -0.08 | 0 | 104
__export__.project_task_3584_4c2fcd16 | TC-290 |  |  | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 0.67 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3213 | 0 | -0.67 | 0 | 8
__export__.project_task_3583_15b073c3 | Rename the Customer field on sending document wizard |  |  | Development | Heronswood: Volunteer On-boarding (P79) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Port Gamble Sâ€™Klallam Foundation | 3216 | 0 | 0 | 0 | 0
__export__.project_task_3582_078f61ab | Change sequence for Donations Receiving, | Sprint 2120 | 2021-05-10 | Development | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Raheel Aslam | 7 | 100 |  |  | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 3217 | 7 | 0 | 0 | 136
__export__.project_task_3581_47a8e6de | Validation Pop-Up Verification for Inventory Adjustment | Sprint 2120 | 2021-05-10 | Development | Wild Leaf: Help (P22) | Muhammad Afzaal | Raheel Aslam | 7.5 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 3220 | 5.5 | -2 | 0 | 40
__export__.project_task_3579_01cf2b99 | Newest Membership Date on Donors form | Sprint 2120 | 2021-05-10 | Development | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Danish Hassan | 1.52 | 100 |  |  | 1 | Complete | Port Gamble Sâ€™Klallam Foundation | 3228 | 1.5 | -0.02 | 0.011197 | 71.0848
__export__.project_task_3576_fd0d9371 | Volunteer Signup contact | Sprint 2120 | 2021-05-10 | Development | Heronswood: Volunteer On-boarding (P79) | Naseeb Razaq | Danish Hassan | 4.33 | 100 |  |  | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 3238 | 3.5 | -0.83 | 0 | 72
__export__.project_task_3573_bdb09f54 | Bill Resequence |  |  | Configuration | Wild Leaf: Help (P22) | Muhammad Afzaal | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 3240 | 0 | 0 | 0 | 24
__export__.project_task_3571_44b172c6 | Modify ELS email template | Sprint 2119 | 2021-05-03 | Configuration | Silverdale: Help (P12) | Muhammad Afzaal | Danish Hassan | 2.42 | 96.8 |  |  | 1 | Complete | Silverdale Technology LLC | 3242 | 2.5 | 0.08 | 0 | 72
__export__.project_task_3567_bb4649bc | TC-289 | Sprint 2123 | 2021-05-31 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 2.33 | 100 |  |  |  | Complete | Silverdale Technology LLC | 3309 | 1.6667 | -0.66333 | 0 | 24
__export__.project_task_3566_2c62fb01 | Odoo Automation Bulk Module Install | Sprint 2123 | 2021-05-31 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 1.42 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3310 | 0 | -1.42 | 0 | 13.255
__export__.project_task_3565_0fc56cbd | meeting |  |  | Internal Time Tracking | PWX: Survey (P70) | Muhammad Afzaal | Levi Barnes | 2.5 | 0 |  |  |  | Complete | EquityTeam | 3312 | 0 | -2.5 | 0 | 0
__export__.project_task_3564_bcb8164c | On Aged payables and Aged Receivebles report, add Bill reference |  |  | Development | Wild Leaf: Help (P22) | Muhammad Afzaal | Aleem khan | 3.08 | 100 |  |  |  | Complete | Wild Leaf Beverage | 3312 | 3 | -0.08 | 0 | 56
__export__.project_task_3562_1ac0fecd | Improvement: applicant: Personality tab | Sprint 2119 | 2021-05-03 | Bug Fix | PWX: Survey (P70) | Muhammad Afzaal | Fahad Hassan | 0.5 | 0 |  |  |  | Cancelled | EquityTeam | 3314 | 0 | -0.5 | 0 | 0
__export__.project_task_3561_63a2e0e8 | Show Disclaimer on Process checkout page | Sprint 2119 | 2021-05-03 | Development | Mid-America: Help (P37) | Naseeb Razaq | Raheel Aslam | 4.92 | 70.29 |  |  | 2 | Complete | Mid-America Gardens, LLC | 3315 | 7 | 2.08 | 0 | 80
__export__.project_task_3560_b569ad0d | portal user not able to see lots on web. |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 3.17 | 0 |  |  |  | Complete | Cellpoint Corporation | 3316 | 0 | -3.17 | 0 | 0
__export__.project_task_3556_87f08864 | personality labels |  |  | Studio | PWX: Survey (P70) | Muhammad Afzaal | Levi Barnes | 0.25 | 100 |  |  |  | Complete | EquityTeam | 3318 | 0.25 | 0 | 0 | 58.0893
__export__.project_task_3554_654cb2f4 | Redirect Donation page into Odoo website | Sprint 2128 | 2021-07-05 | Development | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Danish Hassan | 1.75 | 50 |  | SPLN | 1 | Cancelled | Port Gamble Sâ€™Klallam Foundation | 3334 | 3.5 | 1.75 | 0 | 479.1664
__export__.project_task_3553_877e0926 | Product/Package/Lot/Quantity Barcode Label V2.0 | Sprint 2119 | 2021-05-03 | Development | Wild Leaf: Labeling (P60) | Jeff Gross | Muhammad Bilal | 10.23 | 100 |  | MA Review | 2 | Complete | Wild Leaf Beverage | 3336 | 4 | -6.23 | 0 | 88
__export__.project_task_3552_0cea6e1f | Create default Tasks template improvement 1 | Sprint 2119 | 2021-05-03 | Development | Silverdale: Devops (P84) | Levi Barnes | Muhammad Bilal | 2.5 | 75 |  |  | 1 | Complete | Silverdale Technology LLC | 3337 | 3.3333 | 0.83333 | 0 | 48
__export__.project_task_3551_0b788e4c | Audit of the best Practices and Features used by the client |  |  | Other | MMH: Odoo Audit (P100) | Jeff Gross | Bilal Ahmad Khan | 5.5 | 0 |  |  |  | Complete | Mountain Meadow Herbs | 3339 | 0 | -5.5 | 0 | 48
__export__.project_task_3550_5cb3507d | Multiple Packing on bar-code Module | Sprint 2119 | 2021-05-03 | Development | Wild Leaf: Help (P22) | Jeff Gross | Aleem khan | 8.63 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 3340 | 7 | -1.63 | 0 | 56
__export__.project_task_3549_b7793c82 | Create an Ecommerce website for AT&T |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Danish Hassan | 7.42 | 100 |  |  |  | Complete | Cellpoint Corporation | 3356 | 7 | -0.42 | 0 | 40
__export__.project_task_3548_82c8582e | Create some designs for CPBids app and web using the ecoATM color scheme |  |  | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Shehroz Faiq | 8.5 | 94.44 |  |  |  | Complete | Cellpoint Corporation | 3356 | 9 | 0.5 | 0 | 96
__export__.project_task_3545_52364823 | On activity date change by changing activity type |  |  | Configuration | Zuma: Help (P97) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3358 | 0 | 0 | 436.9908 | 5.5844
__export__.project_task_3540_07345669 | Automate script tc-286 |  |  | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 4.58 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3380 | 0 | -4.58 | 0 | 24
__export__.project_task_3539_6d310131 | Ticket Types and Stages Discussion |  |  | Improvements | Silverdale: Help (P12) | Nick Foy |  | 0.33 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3381 | 0 | -0.33 | 0 | 40
__export__.project_task_3538_b38ca7b7 | Remove user entry for CPBids Username - use email address instead |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Danish Hassan | 5.25 | 100 |  |  |  | Complete | Cellpoint Corporation | 3383 | 4.5 | -0.75 | 0 | 96
__export__.project_task_3537_e7b2c68c | Make CPBids Username unique |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Danish Hassan | 5.83 | 97.17 |  |  |  | Complete | Cellpoint Corporation | 3383 | 6 | 0.17 | 0 | 96
__export__.project_task_3535_4a83f0c5 | All Golf Courses create as Companies |  |  | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Jeff Gross | Danish Hassan | 3.75 | 75 |  |  | 1 | Complete | Perfect Golf Event | 3385 | 5 | 1.25 | 0 | 231.2478
__export__.project_task_3534_7f34dfab | Integrate Zoho for getting contacts into Odoo |  |  | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Jeff Gross | Muzher Siddique | 0 | 0 |  |  |  | Cancelled | Perfect Golf Event | 3385 | 0 | 0 | 0 | 56
__export__.project_task_3533_f043d63b | tuesday meeting |  |  | Internal Time Tracking | PWX: Help Desk (P65) | Levi Barnes |  | 1 | 100 |  |  |  | Complete | EquityTeam | 3386 | 1 | 0 | 0 | 0
__export__.project_task_3532_2f9e0661 | Mid America Gardens Web Site Automation | Sprint 2122 | 2021-05-24 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 2.92 | 73 |  |  |  | Complete | Silverdale Technology LLC | 3401 | 4 | 1.08 | 0 | 8
__export__.project_task_3531_86b1c1c4 | change qa fail process |  |  | Configuration | Silverdale: Help (P12) | Nick Foy | Levi Barnes | 0.33 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3404 | 0 | -0.33 | 0 | 0
__export__.project_task_3529_baf11c8a | Stages sequence for delivery |  |  | Improvements | Silverdale: Help (P12) | Nick Foy | Muzher Siddique | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3405 | 0 | 0 | 0 | 72
__export__.project_task_3528_af273862 | Dish / Sprint Tasks |  |  | Other | Cellpoint: CPBids Billable (P66) | Nick Foy |  | 6 | 0 |  |  |  | Complete | Cellpoint Corporation | 3406 | 0 | -6 | 0 | 0
__export__.project_task_3504_e58da886 | Default gender field should be blank | Sprint 2119 | 2021-05-03 | Development | Heronswood: Network for Good transition to Odoo (P78) | Jeff Gross | Danish Hassan | 1.25 | 83.33 |  |  | 1 | Complete | Port Gamble Sâ€™Klallam Foundation | 3410 | 1.5 | 0.25 | 0 | 56
__export__.project_task_3502_46c6c599 | Multiple Packing |  |  | Development | Wild Leaf: Help (P22) | Jeff Gross | Aleem khan | 10.72 | 100 |  |  |  | Complete | Wild Leaf Beverage | 3411 | 5 | -5.72 | 0 | 72
__export__.project_task_3500_80a02e89 | On Aged payables and Aged Receivebles report, add partner reference |  |  | Development | Wild Leaf: Help (P22) | Jeff Gross | Aleem khan | 3.33 | 100 |  |  |  | Complete | Wild Leaf Beverage | 3412 | 2.5 | -0.83 | 0 | 72
__export__.project_task_3499_a1970812 | Daily Client Success Team Meeting |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Jeff Gross | Muhammad Saqlain Alam | 1.68 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 3475 | 0 | -1.68 | 0 | 15.7108
__export__.project_task_3488_8deabc52 | All inventory to be labeled (Need to ask about this) |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3483 | 1 | 1 | 454.2561 | 453.6617
__export__.project_task_3485_69bbc9a1 | Physical inventory needs to taken | Sprint 2127 | 2021-06-28 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  | SPLN |  | Complete | Zuma Sales LLC | 3483 | 0 | 0 | 460.9908 | 364
__export__.project_task_3479_61df20a3 | Verify trial balances | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 | Follow Up | 2017-09-01 |  | Backlog | Zuma Sales LLC | 3483 | 1 | 1 | 460.8529 | 0
Asfand
__export__.project_task_3471_5d3dc762 | Set up credit limit functionality and reconcile against Quickbooks | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  | SPLN |  | Cancelled | Zuma Sales LLC | 3483 | 1 | 1 | 461.0788 | 673.2566
__export__.project_task_3448_4e66910f | Shut down the previous system at an appropriate time | Sprint 2136 | 2021-08-30 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  | SPLN |  | Cancelled | Zuma Sales LLC | 3484 | 0 | 0 | 462.1048 | 646.1048
__export__.project_task_3418_66c8a50f | Create default Tasks template |  |  | Development | Silverdale: Devops (P84) | Levi Barnes | Muhammad Bilal | 6.75 | 67.5 |  |  |  | Complete | Silverdale Technology LLC | 3500 | 10 | 3.25 | 0 | 88
__export__.project_task_3417_aae52b7e | Default Stages for Discover, Design and Deliver |  |  | Configuration | Silverdale: Help (P12) | Muhammad Afzaal | Muzher Siddique | 0.17 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3500 | 0 | -0.17 | 16 | 72
__export__.project_task_3415_570f30d9 | Q2 People performance Meeting |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Muzher Siddique | 3.13 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3501 | 0 | -3.13 | 0 | 0
__export__.project_task_3412_aebb58d8 | Be able to apply a deposit amount to specific invoices |  |  | Development | Wild Leaf: Help (P22) | Jeff Gross |  | 0.33 | 0 |  |  |  | Complete | Wild Leaf Beverage | 3505 | 0 | -0.33 | 0 | 64
__export__.project_task_3411_2d078f84 | Collecting trips cant create | Sprint 2118 | 2021-04-26 | Studio | Heronswood: Help (P54) | Jeff Gross | Danish Hassan | 2.75 | 100 |  |  | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 3505 | 2.5 | -0.25 | 0 | 55.5189
__export__.project_task_3409_02add9ce | Test the functional of Icon alignment and font size should be uniform | Sprint 2118 | 2021-04-26 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 4.75 | 100 |  |  | 2 | Complete | Cellpoint Corporation | 3506 | 3 | -1.75 | 0 | 88
__export__.project_task_3405_6a0bf3a6 | Office 365 Calendar to integrate with odoo | Sprint 2119 | 2021-05-03 | Development | Silverdale: Devops (P84) | Levi Barnes | Raheel Aslam | 2.67 | 44.5 |  |  | 1 | Complete | Silverdale Technology LLC | 3506 | 6 | 3.33 | 0 | 72
__export__.project_task_3399_cc7e6862 | Help out & Planning |  |  | Other | Silverdale Time Tracking (P56) | Muhammad Afzaal | Wajahat Ali | 41.83 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3526 | 0 | -41.83 | 0 | 112
__export__.project_task_3398_fc64f49c | Q2 Priorities Setting Meeting |  |  | Internal Time Tracking | Silverdale: Help (P12) | Muhammad Afzaal | Muzher Siddique | 1.5 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3527 | 0 | -1.5 | 0 | 0
__export__.project_task_3397_1726965e | Tribe Meeting |  |  | Internal Time Tracking | Silverdale: Help (P12) | Muhammad Afzaal | Muzher Siddique | 1 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3527 | 0 | -1 | 0 | 8
__export__.project_task_3395_c0b577cf | webshop product validation | Sprint 2118 | 2021-04-26 | Development | MMH: Help (P83) | Jeff Gross | Aleem khan | 7.92 | 100 |  |  | 2 | Complete | Mountain Meadow Herbs | 3529 | 2 | -5.92 | 0 | 72
__export__.project_task_3394_e30020a1 | Tasks Review - Backlog - Peer Review & ELS |  |  | Other | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 16.08 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3530 | 0 | -16.08 | 0 | 0
__export__.project_task_3393_490073fd | Silverdale Apps Tribe |  |  | Other | Silverdale: Devops (P84) | Muzher Siddique | Muzher Siddique | 0 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 3530 | 0 | 0 | 0 | 8
__export__.project_task_3386_77733918 | Split Manufacturing Order Date Warning Error | Sprint 2118 | 2021-04-26 | Development | Wild Leaf: Labeling (P60) | Jeff Gross | Aleem khan | 5.08 | 100 |  | PR-Failed | 2 | Complete | Wild Leaf Beverage | 3531 | 1.5 | -3.58 | 0 | 80
__export__.project_task_3383_9285622d | PayPal Fee calculation Feature in Odoo |  |  | Development | Heronswood: Help (P54) | Jeff Gross | Muhammad Bilal | 3 | 0 |  |  |  | Cancelled | Port Gamble Sâ€™Klallam Foundation | 3532 | 0 | -3 | 0 | 46.1356
__export__.project_task_3381_5f35d794 | Code revert or role back process flow |  |  | Configuration | Silverdale: Help (P12) | Levi Barnes | Sanaullah Khan | 1.08 | 72 |  | Leadership |  | Complete | Silverdale Technology LLC | 3548 | 1.5 | 0.42 | 8 | 112
__export__.project_task_3380_5f0a9977 | Sprint Review Meeting |  |  | Configuration | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 7.63 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3549 | 0 | -7.63 | 0 | 8
__export__.project_task_3376_99b72cb6 | Confirmation Email for donors | Sprint 2122 | 2021-05-24 | Development | Heronswood: Network for Good transition to Odoo (P78) | Jeff Gross | Danish Hassan | 5.25 | 100 |  |  | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 3551 | 5.25 | 0 | 0 | 232
__export__.project_task_3374_ff5c0049 | Print Label Button for MOs | Sprint 2118 | 2021-04-26 | Development | Wild Leaf: Help (P22) | Jeff Gross | Aleem khan | 3.02 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 3556 | 2 | -1.02 | 0 | 71.5189
__export__.project_task_3371_092b5143 | Deployment 20/04/2021: PWX | Sprint 2118 | 2021-04-26 | Configuration | PWX: Help (P23) | Levi Barnes | Sanaullah Khan | 4.55 | 0 |  |  |  | Complete | EquityTeam | 3575 | 0 | -4.55 | 0 | 8
__export__.project_task_3370_0f4c4aa7 | Function ELS-Complete Auto | Sprint 2118 | 2021-04-26 | Development | Silverdale: Devops (P84) | Levi Barnes | Danish Hassan | 7.83 | 100 |  |  | 2 | Complete | Silverdale Technology LLC | 3576 | 3.5 | -4.33 | 0 | 96
__export__.project_task_3369_b6962794 | In the transfers of Inventory, Source Document should be clickable |  |  | Development | Wild Leaf: Help (P22) | Jeff Gross | Aleem khan | 3.37 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 3577 | 2 | -1.37 | 0 | 79.5189
__export__.project_task_3367_f179d836 | FW: Customer and Vendor Numbers | Sprint 2120 | 2021-05-10 | Development | Wild Leaf: Help (P22) | Jeff Gross | Aleem khan | 1.5 | 90 |  |  | 2 | Complete | Wild Leaf Beverage | 3579 | 1.6667 | 0.16667 | 0 | 104
__export__.project_task_3366_0c93a300 | For Customers allow Consignment Purchase Orders to flow to Receipts | Sprint 2118 | 2021-04-26 | Development | Wild Leaf: Help (P22) | Jeff Gross | Danish Hassan | 12.52 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 3579 | 3 | -9.52 | 0 | 79.5189
__export__.project_task_3365_95a2e268 | Fw: PRODUCTION SFTP Access | Sprint 2118 | 2021-04-26 | Configuration | Cellpoint: ecoATM API (P50) | Nick Foy |  | 0.25 | 0 |  |  |  | Complete | Cellpoint Corporation | 3602 | 0 | -0.25 | 0 | 48
__export__.project_task_3364_01277dea | Email Button Auto Ticket | Sprint 2118 | 2021-04-26 | Development | Continuant: Customer Portal AR (P32) | Jeff Gross | Muhammad Bilal | 4.17 | 100 |  |  | 2 | Complete | Continuant | 3646 | 2.3333 | -1.8367 | 0 | 87.5189
__export__.project_task_3362_b1ad5459 | Create Odoo.sh Instance for Perfect Golf |  |  | Configuration | Perfect Golf: Help (P99) | Jeff Gross | Muzher Siddique | 0.58 | 58 |  |  |  | Complete | Perfect Golf Event | 3647 | 1 | 0.42 | 0 | 16
__export__.project_task_3361_bc6079d5 | Making LocalHost Setup according to github | Sprint 2117 | 2021-04-19 | Development | Silverdale Time Tracking (P56) | Muhammad Afzaal | Raheel Aslam | 3 | 100 |  |  | 1 | Complete | Silverdale Technology LLC | 3648 | 3 | 0 | 0 | 0
__export__.project_task_3360_f8877401 | Automation Script for Pallet Build Specs Testing |  |  | Development | Wild Leaf: Accounting (P64) | Levi Barnes | Muhammad Saqlain Alam | 8.8 | 0 |  |  | 4 | Complete | Wild Leaf Beverage | 3649 | 0 | -8.8 | 0 | 22.5019
__export__.project_task_3359_2e07d854 | Third party APIs triggered on test instance |  |  | Bug Fix | MMH Dr. Clark: Help (P106) | Jeff Gross |  | 3 | 100 |  |  |  | Complete | Mountain Meadow Herbs | 3653 | 3 | 0 | 0 | 88.9802
__export__.project_task_3356_75ad5ad6 | TC-287 Odoo Automation : Instant Contact Creation | Sprint 2123 | 2021-05-31 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 1.42 | 0 |  | Project |  | Complete | Silverdale Technology LLC | 3676 | 0 | -1.42 | 0 | 88
__export__.project_task_3355_5f1879c3 | Automation Script for Wildleaf's Sale Order | Sprint 2117 | 2021-04-19 | Development | Wild Leaf: Accounting (P64) | Levi Barnes |  | 7.33 | 0 |  |  | 4 | Complete | Wild Leaf Beverage | 3693 | 0 | -7.33 | 0 | 16
__export__.project_task_3347_8369d621 | Deployment 14/04/2021: Continuant | Sprint 2117 | 2021-04-19 | Configuration | Continuant: AV Warehouse (P34) | Jeff Gross | Wajahat Ali | 0.5 | 0 |  |  |  | Complete | Continuant | 3720 | 0 | -0.5 | 0 | 0
__export__.project_task_3346_7116074b | applicant email template (Change Req) | Sprint 2117 | 2021-04-19 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 2.33 | 100 |  |  | 2 | Complete | EquityTeam | 3721 | 1 | -1.33 | 0 | 72
__export__.project_task_3345_5c58fee4 | Change Bar color |  |  | Development | PWX: Help (P23) | Levi Barnes | Aleem khan | 8.17 | 100 |  |  | 3 | Complete | EquityTeam | 3721 | 3 | -5.17 | 0 | 48
__export__.project_task_3340_4b259147 | WildLeaf: Ability to toggle on and off zero dollar account balances in configuration - settings (this one may be the only one that takes time) | Sprint 2117 | 2021-04-19 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Muhammad Bilal | 11.33 | 100 |  |  | 4 | Complete | Wild Leaf Beverage | 3724 | 8 | -3.33 | 0 | 72
__export__.project_task_3338_96ecd441 | Import Donors Profile from Network for Goods Tool into Odoo |  |  | Configuration | Heronswood: Network for Good transition to Odoo (P78) | Jeff Gross |  | 2.42 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3727 | 0 | -2.42 | 0 | 123.2608
__export__.project_task_3336_2c7a2636 | Reporting | Sprint 2117 | 2021-04-19 | Development | Heronswood: Network for Good transition to Odoo (P78) | Jeff Gross | Danish Hassan | 4.33 | 100 |  |  | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 3747 | 3.5 | -0.83 | 0 | 119.5192
__export__.project_task_3332_5ac39faf | Deployment 12-04-2021:Wildleaf | Sprint 2117 | 2021-04-19 | Configuration | Wild Leaf: Accounting (P64) | Jeff Gross | Wajahat Ali | 3.67 | 0 |  |  |  | Complete | Wild Leaf Beverage | 3753 | 0 | -3.67 | 0.048474 | 12.1268
__export__.project_task_3331_78a74bdd | Continuant: If part number is blank, use the model number as the product name | Sprint 2117 | 2021-04-19 | Development | Continuant: AV Warehouse (P34) | Jeff Gross | Danish Hassan | 2 | 100 |  |  | 1 | Complete | Continuant | 3754 | 2 | 0 | 0 | 124.3575
__export__.project_task_3330_ec1fd528 | Donations Receiving Via Website into Odoo | Sprint 2118 | 2021-04-26 | Development | Heronswood: Network for Good transition to Odoo (P78) | Jeff Gross | Danish Hassan | 9 | 100 |  |  | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 3754 | 3.5 | -5.5 | 0 | 141.1324
__export__.project_task_3328_d3d43d3f | Deployment 09/04/2021: CPbid | Sprint 2116 | 2021-04-12 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 6.83 | 0 |  |  |  | Complete | Cellpoint Corporation | 3824 | 0 | -6.83 | 0.027924 | 19.4329
__export__.project_task_3325_6a545f1c | Deployement 08-04-2021:Willeaf | Sprint 2116 | 2021-04-12 | Configuration | Wild Leaf: Accounting (P64) | Jeff Gross | Wajahat Ali | 1.08 | 0 |  |  |  | Complete | Wild Leaf Beverage | 3847 | 0 | -1.08 | 2.2313e-05 | 2.6422
__export__.project_task_3322_996cf551 | Deployement 08-04-2021:PWX | Sprint 2116 | 2021-04-12 | Configuration | PWX: Help (P23) | Levi Barnes | Wajahat Ali | 3.83 | 0 |  |  |  | Complete | EquityTeam | 3850 | 0 | -3.83 | 0.010442 | 2.2207
__export__.project_task_3321_3d671518 | Deployement 07-04-2021:Continuant | Sprint 2116 | 2021-04-12 | Configuration | Continuant: AV Warehouse (P34) | Jeff Gross | Wajahat Ali | 1.33 | 0 |  |  |  | Complete | Continuant | 3866 | 0 | -1.33 | 0 | 0
__export__.project_task_3318_0366d9e9 | Manufacturing and pallet build notes should update from sales to mfg order | Sprint 2116 | 2021-04-12 | Development | Wild Leaf: Help (P22) | Jeff Gross | Danish Hassan | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 3867 | 0 | 0 | 0 | 5.3461
__export__.project_task_3317_2f52ee21 | Add Analytical account to Bank statement reconciliation page | Sprint 2116 | 2021-04-12 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Danish Hassan | 3.5 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 3868 | 2 | -1.5 | 0 | 12
__export__.project_task_3312_e8c1e769 | Change product invoicing Policy | Sprint 2116 | 2021-04-12 | Development | Wild Leaf: Help (P22) | Jeff Gross | Fahad Hassan | 0.25 | 0 |  |  | 1 | Cancelled | Wild Leaf Beverage | 3872 | 0 | -0.25 | 0 | 7.5817
__export__.project_task_3292_53c9977d | Deployment Friday: PWX | Sprint 2115 | 2021-04-05 | Configuration | PWX: Help (P23) | Levi Barnes | Wajahat Ali | 2 | 0 |  |  |  | Complete | EquityTeam | 3993 | 0 | -2 | 0 | 3.6419
__export__.project_task_3290_522bb854 | Deployement Thursday: Continuant | Sprint 2115 | 2021-04-05 | Configuration | Continuant: AV Warehouse (P34) | Jeff Gross | Wajahat Ali | 1.5 | 0 |  |  |  | Complete | Continuant | 4010 | 0 | -1.5 | 0 | 88
__export__.project_task_3276_0dd99273 | Below email field a new field "invoice delivery email" is needed |  |  | Development | Wild Leaf: Help (P22) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 4036 | 0 | 0 | 0 | 4.3884
__export__.project_task_3275_ea3754db | Show total count, total amount and delivery number on RFQ, Delivery order and Invoicing Slip: |  |  | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 0 | 0 |  |  |  | Cancelled | Mid-America Gardens, LLC | 4038 | 0 | 0 | 0 | 2.0747
__export__.project_task_3269_b770a631 | Deployment Tuesday: Wildleaf | Sprint 2115 | 2021-04-05 | Configuration | Wild Leaf: Accounting (P64) | Jeff Gross | Wajahat Ali | 2.33 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4062 | 0 | -2.33 | 0.0089524 | 2.1795
__export__.project_task_3260_66a305f8 | Deployment Monday: Mid-America | Sprint 2115 | 2021-04-05 | Configuration | Mid-America: Help (P37) | Levi Barnes | Wajahat Ali | 1.42 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4086 | 0 | -1.42 | 0.0077622 | 13.618
__export__.project_task_3257_aa20c065 | Deployement Monday: Wildleaf | Sprint 2115 | 2021-04-05 | Configuration | Wild Leaf: Accounting (P64) | Jeff Gross | Wajahat Ali | 4.83 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4089 | 0 | -4.83 | 0.5525 | 12
__export__.project_task_3253_db55b6e1 | Deployment Firday: Continuant | Sprint 2114 | 2021-03-29 | Configuration | Continuant: AV Warehouse (P34) | Jeff Gross | Wajahat Ali | 5.17 | 0 |  |  |  | Complete | Continuant | 4096 | 0 | -5.17 | 0 | 19.6164
__export__.project_task_3252_c35ab5b6 | deployment friday: continuant |  |  | Configuration | Continuant: AV Warehouse (P34) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Continuant | 4153 | 0 | 0 | 120 | 120
__export__.project_task_3250_55938b2b | Setup Internal Daily Meeting for WL |  |  | Other | Silverdale: Help (P12) | Nick Foy |  | 0 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 4156 | 0 | 0 | 0 | 0
__export__.project_task_3249_b007b8f8 | Deployment Friday: Mid-America | Sprint 2114 | 2021-03-29 | Configuration | Mid-America: Help (P37) | Levi Barnes | Wajahat Ali | 1.83 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4156 | 0 | -1.83 | 0.065907 | 40.2551
__export__.project_task_3243_1469bc3d | Fw: SSH key for QA access - second site |  |  |  | Cellpoint: ecoATM API (P50) | Nick Foy |  | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 4179 | 0 | 0 | 0 | 64
__export__.project_task_3240_6c8f71fd | PD-QA : PWX |  |  | Other | PWX: Help (P23) | Levi Barnes | Muhammad Saqlain Alam | 1.42 | 0 |  |  |  | Complete | EquityTeam | 4181 | 0 | -1.42 | 0 | 49.2089
__export__.project_task_3236_35b60b7b | CPBIDS SO Automation |  |  | Development | Silverdale: Devops (P84) | Levi Barnes |  | 6.92 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4182 | 0 | -6.92 | 129.9186 | 209.9186
__export__.project_task_3235_64819281 | PD-QA : Mid-America Gardens |  |  | Other | Mid-America: Help (P37) | Levi Barnes | Wishal Nasir | 3.75 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4182 | 0 | -3.75 | 0.029395 | 92.6291
__export__.project_task_3233_0ec5f0fe | Daily Meeting: All help desk tickets (BA + Dev+ QA+FE) |  |  | Other | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 4185 | 0 | 0 | 128.4862 | 128.4887
__export__.project_task_3230_2b9f429a | Out of Stock item should not be able to add in Customer Cart | Sprint 2114 | 2021-03-29 | Development | Mid-America: Help (P37) | Levi Barnes |  | 0 | 0 |  |  |  | Cancelled | Mid-America Gardens, LLC | 4186 | 0 | 0 | 0 | 13.038
__export__.project_task_3214_1831a09c | Mini-Order message shouldn't show on website for Gifts and Catalogs | Sprint 2114 | 2021-03-29 | Development | Mid-America: Help (P37) | Naseeb Razaq | Raheel Aslam | 3.5 | 87.5 |  |  | 2 | Complete | Mid-America Gardens, LLC | 4227 | 4 | 0.5 | 4.2781 | 64
__export__.project_task_3213_c14ce48b | deployment 23/03/2021: Mid America | Sprint 2114 | 2021-03-29 | Configuration | Mid-America: Help (P37) | Levi Barnes | Wajahat Ali | 4.17 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4231 | 0 | -4.17 | 0.0072327 | 26.6411
__export__.project_task_3206_bed4bc8e | On SO in notes tab | Sprint 2114 | 2021-03-29 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 1.42 | 47.33 |  |  | 1 | Complete | Mid-America Gardens, LLC | 4233 | 3 | 1.58 | 0 | 68
__export__.project_task_3196_098e37aa | Mid America Code refactor | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Muhammad Bilal | 13 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4300 | 0 | -13 | 0 | 0
__export__.project_task_3194_9dffff9e | Deployment 18/03/2021: mid-America |  |  | Configuration | Mid-America: Help (P37) | Levi Barnes | Wajahat Ali | 2.17 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4325 | 0 | -2.17 | 0.01614 | 40.6434
__export__.project_task_3192_3948bcb7 | Odoo instance timing out |  |  | Development | MMH: Help (P83) | Jeff Gross | Muzher Siddique | 0 | 0 |  |  |  | Complete | Mountain Meadow Herbs | 4328 | 0 | 0 | 0.015557 | 62.8947
__export__.project_task_3191_42acfca4 | Move Categories around | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 1.3 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 4328 | 0.83333 | -0.46667 | 0 | 49.2855
__export__.project_task_3189_831ed23e | Continuant: Customer Portal, change user views | Sprint 2114 | 2021-03-29 | Development | Continuant: Customer Portal AR (P32) | Jeff Gross | Muhammad Bilal | 2.87 | 0 |  |  | 2 | Complete | Continuant | 4330 | 0 | -2.87 | 0 | 84.9273
__export__.project_task_3187_034cbbb2 | Deployment 17/03/2021: CPBID | Sprint 2113 | 2021-03-22 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 5.42 | 0 |  |  |  | Complete | Cellpoint Corporation | 4344 | 0 | -5.42 | 0 | 8
__export__.project_task_3185_deb63761 | Client Test Scripts |  |  | Configuration | Silverdale: Help (P12) | Nick Foy | Muzher Siddique | 3.33 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4346 | 0 | -3.33 | 0 | 0
__export__.project_task_3184_9a41767f | Enlarge the size of image of product | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 3.92 | 98 |  |  | 2 | Complete | Mid-America Gardens, LLC | 4347 | 4 | 0.08 | 0 | 88
__export__.project_task_3183_134489dc | Invoices needs to be with and without pricing | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Danish Hassan | 6.83 | 100 |  |  | 2 | Complete | Mid-America Gardens, LLC | 4347 | 4 | -2.83 | 0 | 88
__export__.project_task_3181_87fe918d | Remove the transparency from the pictures | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 2.17 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 4347 | 2 | -0.17 | 0 | 53.3719
__export__.project_task_3179_ed43e5ef | PWX merge code of modules | Sprint 2113 | 2021-03-22 | Development | PWX: Survey (P70) | Levi Barnes | Raheel Aslam | 1.33 | 100 |  |  |  | Complete | EquityTeam | 4349 | 1 | -0.33 | 1.5552e-05 | 53.7283
__export__.project_task_3178_5ec791a4 | Downloading and uploading data base | Sprint 2113 | 2021-03-22 | Development | MMH: Help (P83) | Jeff Gross | Muzher Siddique | 4.4 | 0 |  |  | 2 | Complete | Mountain Meadow Herbs | 4350 | 0 | -4.4 | 0 | 117.5349
__export__.project_task_3176_c30362ee | Email and Phone no. should be visible on all slips | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Danish Hassan | 8.75 | 100 |  |  | 1 | Complete | Mid-America Gardens, LLC | 4355 | 5 | -3.75 | 0 | 93.4632
__export__.project_task_3175_22157e15 | Alphabetical order must be followed on all slip | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Danish Hassan | 5.17 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 4355 | 5 | -0.17 | 0 | 59.0841
__export__.project_task_3051_be94efd26 | Initiate incident/technical issue management procedures |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0.00061774 | 206.1934
__export__.project_task_3038_d47ddecb | Deployment 17/03/2021: Mid-america | Sprint 2113 | 2021-03-22 | Configuration | Mid-America: Help (P37) | Levi Barnes | Wajahat Ali | 2.5 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4372 | 0 | -2.5 | 0 | 56
__export__.project_task_3032_1f6ba087 | Categories on the left side in Product Page |  |  | Development | Mid-America: Help (P37) | Levi Barnes | Muhammad Bilal | 0.83 | 55.33 |  |  |  | Complete | Mid-America Gardens, LLC | 4379 | 1.5 | 0.67 | 0 | 66.8597
__export__.project_task_3031_e81b28ee | Delivery report modifications | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Danish Hassan | 4.83 | 100 |  |  | 1 | Complete | Mid-America Gardens, LLC | 4379 | 4 | -0.83 | 0 | 101.4704
__export__.project_task_3027_24af710d | Deployment 2111: Mid america | Sprint 2113 | 2021-03-22 | Configuration | Mid-America: Help (P37) | Levi Barnes | Wajahat Ali | 2.17 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4398 | 0 | -2.17 | 0 | 5.8285
__export__.project_task_3019_2e9ec6ed | Deployment 2111: Wildleaf | Sprint 2113 | 2021-03-22 | Configuration | Wild Leaf: Help (P22) | Jeff Gross | Wajahat Ali | 1.83 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4402 | 0 | -1.83 | 0.021621 | 69.1305
__export__.project_task_3017_ca89797f | '+(plus) sign of the menu is not available on mobile |  |  | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 0.5 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4403 | 0 | -0.5 | 0 | 9.277
__export__.project_task_3009_db5227da | Testing of Android and IOS builds | Sprint 2113 | 2021-03-22 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 8.25 | 0 |  |  |  | Complete | Cellpoint Corporation | 4418 | 0 | -8.25 | 0 | 40
__export__.project_task_3008_f020f7ac | Change password/username for continuant demo environment | Sprint 2118 | 2021-04-26 | Configuration | Continuant: Help (SOR-17614) | Fahad Hussain Malik |  | 0.5 | 100 |  |  |  | Complete | Continuant | 4418 | 0.33333 | -0.16667 | 1003.7841 | 209.2333
__export__.project_task_3006_8100a88c | Demo: Inventory Module Demo |  |  | Demo to the client | Wild Leaf: Help (P22) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 4422 | 0 | 0 | 0 | 10.267
__export__.project_task_2992_55115579 | SO confirmation email template | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Danish Hassan | 1 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4491 | 0 | -1 | 0 | 85.4447
__export__.project_task_2991_157dda30 | deliver slip with pricing | Sprint 2113 | 2021-03-22 | Development | Mid-America: Help (P37) | Levi Barnes | Danish Hassan | 4 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 4491 | 3.5 | -0.5 | 0 | 85.4533
__export__.project_task_2940_636b6c68 | Hide product count from customer | Sprint 2112 | 2021-03-15 | Development | Mid-America: Help (P37) | Levi Barnes | Muhammad Bilal | 1.33 | 66.5 |  |  |  | Cancelled | Mid-America Gardens, LLC | 4546 | 2 | 0.67 | 0 | 4.414
__export__.project_task_2935_70c1ea70 | Address Clarification |  |  | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 2 | 0 |  |  |  | Cancelled | Mid-America Gardens, LLC | 4563 | 0 | -2 | 0 | 8
__export__.project_task_2932_afe42e6b | themes | Sprint 2115 | 2021-04-05 | Configuration | PWX: Help (P23) | Levi Barnes | Danish Hassan | 1.5 | 60 |  |  |  | Cancelled | EquityTeam | 4565 | 2.5 | 1 | 0 | 144.9867
__export__.project_task_2931_98a2412d | Deployment 2110: PWX | Sprint 2112 | 2021-03-15 | Configuration | PWX: app cleanup (P67) | Levi Barnes | Wajahat Ali | 2.67 | 0 |  |  |  | Complete | EquityTeam | 4565 | 0 | -2.67 | 0.0090929 | 0.98798
__export__.project_task_2929_32a934c7 | Deployement 2110: Dialed Supply: Hydrofarm API | Sprint 2112 | 2021-03-15 | Configuration | Dialed Supply: Help (P21) | Levi Barnes | Wajahat Ali | 2.17 | 0 |  |  |  | Complete | Dialed Supply | 4568 | 0 | -2.17 | 0 | 6.628
__export__.project_task_2927_612a0468 | Deployment 2110: Wildleaf | Sprint 2112 | 2021-03-15 | Configuration | Wild Leaf: Helcim Integration (P38) | Jeff Gross | Wajahat Ali | 2 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4568 | 0 | -2 | 0.01054 | 38.8408
__export__.project_task_2924_33a71585 | Post Deployment QA | Sprint 2112 | 2021-03-15 | Configuration | Silverdale: Help (P12) | Nick Foy | Wishal Nasir | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4568 | 0 | 0 | 0.034176 | 75.2314
__export__.project_task_2912_2815ffde | Create an as-is system map |  |  |  | DESIGN (P77) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1049.8096
__export__.project_task_2872_b921d64d | Deployement:silverdale | Sprint 2112 | 2021-03-15 | Development | Silverdale: Help (P12) | Nick Foy | Wajahat Ali | 5.58 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4593 | 0 | -5.58 | 0.009118 | 8.1758
__export__.project_task_2863_3465ff02 | create record security for project tasks |  |  | Development | PWX: Help (P23) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | EquityTeam | 4661 | 0 | 0 | 2.8505e-05 | 85.3417
__export__.project_task_2862_f1ef12f3 | WildLeaf: ELearning Setup | Sprint 2112 | 2021-03-15 | Configuration | Wild Leaf: Help (P22) | Jeff Gross | Bilal Ahmad Khan | 15 | 100 |  |  |  | Complete | Wild Leaf Beverage | 4662 | 15 | 0 | 0 | 161.736
__export__.project_task_2860_af5f6eeb | Set up Dashboard Ninja for Client |  |  | Development | Wild Leaf: Help (P22) | Jeff Gross | Muzher Siddique | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 4662 | 0 | 0 | 0 | 1.6466
__export__.project_task_2859_b4678ff9 | deployment Cbid Support | Sprint 2110 | 2021-03-01 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 4.17 | 0 |  |  |  | Complete | Cellpoint Corporation | 4664 | 0 | -4.17 | 0.010244 | 7.5472
__export__.project_task_2858_ceaadd23 | Deployment ecoatm | Sprint 2110 | 2021-03-01 | Configuration | Cellpoint: ecoATM API (P50) | Nick Foy | Wajahat Ali | 2.17 | 0 |  |  |  | Complete | Cellpoint Corporation | 4664 | 0 | -2.17 | 0.0075302 | 7.6748
__export__.project_task_2844_d44433f0 | New Buyer Signup - Part 2 New Buyer Signup:steps and lucidchart for automated steps | Sprint 2110 | 2021-03-01 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 3 | 0 |  |  |  | Complete | Cellpoint Corporation | 4687 | 0 | -3 | 9.1446e-05 | 7.6568
__export__.project_task_2842_ed2542cd | Max Bid display / Bids increment issues |  |  | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Muzher Siddique | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 4691 | 0 | 0 | 0 | 1.3904
__export__.project_task_2831_7e981b10 | add logos and replace gucci name |  |  | Development | Moln: 3 New Portal Websites (P62) | Levi Barnes |  | 0.33 | 0 |  |  |  | Complete | Moln Solutions, LLC | 4708 | 0 | -0.33 | 0 | 48
__export__.project_task_2828_362a903a | temp email template setup |  |  | Configuration | Moln: 3 New Portal Websites (P62) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Moln Solutions, LLC | 4732 | 0 | 0 | 0 | 31.9022
__export__.project_task_2825_b0319ce8 | Deployment 2109: Moln Portal | Sprint 2110 | 2021-03-01 | Configuration | Moln: 3 New Portal Websites (P62) | Levi Barnes | Wajahat Ali | 1.42 | 0 |  |  |  | Complete | Moln Solutions, LLC | 4734 | 0 | -1.42 | 0 | 1.9118
__export__.project_task_2824_3bf8ca55 | Deployment 2109: PWX:HR | Sprint 2110 | 2021-03-01 | Configuration | PWX: HR (P61) | Levi Barnes | Wajahat Ali | 1.5 | 0 |  |  |  | Complete | EquityTeam | 4735 | 0 | -1.5 | 0.011157 | 2.5084
__export__.project_task_2822_6d4ea786 | Deployment 2109: Heronwood Events | Sprint 2110 | 2021-03-01 | Configuration | Heronswood: Events (P3) | Nick Foy | Wajahat Ali | 1.33 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 4736 | 0 | -1.33 | 0 | 2.4095
__export__.project_task_2821_b211ee25 | Deployment 2109: Wildleaf Accounting | Sprint 2110 | 2021-03-01 | Configuration | Wild Leaf: Accounting (P64) | Nick Foy | Wajahat Ali | 5.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4737 | 0 | -5.5 | 0 | 8
__export__.project_task_2812_74a5fbfc | Test task from Nick |  |  |  | Wild Leaf: Accounting (P64) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 4831 | 0 | 0 | 42.9476 | 42.9476
__export__.project_task_2811_8ea30fe0 | Test Task |  |  |  | Wild Leaf: Accounting (P64) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 4831 | 0 | 0 | 42.9606 | 42.9606
__export__.project_task_2806_3b56b585 | Purchase | Sprint 2110 | 2021-03-01 | Internal Training | Silverdale: Help (P12) | Fahad Hussain Malik | Bilal Ahmad Khan | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4855 | 0 | 0 | 0.023242 | 253.3007
__export__.project_task_2805_eb5e158e | Purchase | Sprint 2110 | 2021-03-01 | Configuration | Silverdale: Help (P12) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 4855 | 0 | 0 | 0.0099869 | 26.1886
__export__.project_task_2804_2cea8772 | Sales | Sprint 2110 | 2021-02-22 | Configuration | Silverdale: Help (P12) | Fahad Hussain Malik | Bilal Ahmad Khan | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4857 | 0 | 0 | 0 | 17.6819
__export__.project_task_2798_710e255f | Deployement 2108: PWX HR | Sprint 2110 | 2021-02-22 | Configuration | PWX: HR (P61) | Levi Barnes | Wajahat Ali | 2.25 | 0 |  |  |  | Complete | EquityTeam | 4905 | 0 | -2.25 | 0 | 4
__export__.project_task_2797_0eafc558 | Deployment 2108: PWX Strategic | Sprint 2110 | 2021-02-22 | Configuration | PWX: Strategic Planning (P43) | Levi Barnes | Wajahat Ali | 2.67 | 0 |  |  |  | Complete | EquityTeam | 4905 | 0 | -2.67 | 0 | 1.7147
__export__.project_task_2796_5d076b07 | Deployment 2108: WildLeaf | Sprint 2110 | 2021-02-22 | Configuration | Wild Leaf: Accounting (P64) | Nick Foy | Wajahat Ali | 3.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4906 | 0 | -3.5 | 0 | 1.7997
__export__.project_task_2794_c46b31ad | Module Terms & Conditions bugs |  |  | Other | Continuant: Quotation Management / Automation (P31) | Jeff Gross | Muzher Siddique | 0.17 | 0 |  |  |  | Cancelled | Continuant | 4920 | 0 | -0.17 | 72 | 72
__export__.project_task_2791_9fb1479e | Module auto_close_order Bugs |  |  | Other | Continuant: Quotation Management / Automation (P31) | Jeff Gross |  | 6.5 | 0 |  |  |  | Cancelled | Continuant | 4921 | 0 | -6.5 | 72 | 72
__export__.project_task_2788_0a248fa8 | Deployment: CPBids Support | Sprint 2109 | 2021-02-15 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 5 | 0 |  |  |  | Complete | Cellpoint Corporation | 4998 | 0 | -5 | 0 | 2.3206
__export__.project_task_2782_fbf3fcf9 | Labeling (non-real-time):ZPL code R&D | Sprint 2109 | 2021-02-15 | Other | Wild Leaf: Labeling (P60) | Nick Foy | Muhammad Bilal | 2.83 | 99.88 |  |  |  | Complete | Wild Leaf Beverage | 5019 | 2.8333 | 0.0033333 | 0 | 8
__export__.project_task_2777_f29c42e1 | waffle bug |  |  | Bug Fix | Silverdale: Help (P12) | Nick Foy | Fahad Hassan | 1 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5045 | 0 | -1 | 0 | 95.29
__export__.project_task_2770_c1a4a4cf | Heronswood: Events deployment 2107 | Sprint 2109 | 2021-02-15 | Other | Heronswood: Events (P3) | Nick Foy | Muzher Siddique | 1.25 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 5068 | 0.66667 | -0.58333 | 0 | 64
__export__.project_task_2769_689ce506 | Property Worx HR Deployment 2107 | Sprint 2109 | 2021-02-15 | Other | PWX: HR (P61) | Levi Barnes | Muzher Siddique | 1.92 | 100 |  |  |  | Complete | EquityTeam | 5068 | 1.5 | -0.42 | 0 | 4
__export__.project_task_2767_b7c1c4ba | Wildleaf support deployment 2107 | Sprint 2109 | 2021-02-15 | Other | Wild Leaf: Help (P22) | Nick Foy | Muzher Siddique | 1.33 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5072 | 1 | -0.33 | 0.10583 | 7.8878
__export__.project_task_2764_a56dd926 | Payment process surcharge - 3% Fee for Credit Card Transactions |  |  | Development | Wild Leaf: Accounting (P64) | Jeff Gross |  | 0.42 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5089 | 0 | -23.05 | 112 | 237.4889
__export__.project_task_2763_98f6724e | 207:Watchlist - Mybids Web: Module updation Issue,Status, Link | Sprint 2110 | 2021-03-01 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Muhammad Bilal | 13.67 | 100 |  |  |  | Complete | Cellpoint Corporation | 5092 | 9 | -4.67 | 0 | 160
__export__.project_task_2749_906179b9 | Purchase Units of Measure |  |  | Configuration | Wild Leaf: Help (P22) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5137 | 0 | 0 | 120 | 237.4039
__export__.project_task_2724_4b418226 | WON Auctions: Not Showing in Web and Mobile App (BugFix) |  |  | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 6 | 100 |  |  |  | Complete | Cellpoint Corporation | 5184 | 5 | -1 | 0 | 124.4042
__export__.project_task_2719_dd6bdbcc | Buyer Performance Discrepancy |  |  | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 6.67 | 0 |  |  |  | Complete | Cellpoint Corporation | 5192 | 0 | -6.67 | 0 | 7.3897
__export__.project_task_2717_d8fa7d68 | Set-Up Stripe as a Payment Acquirer |  |  | Bug Fix | Heronswood: Events (P3) | Nick Foy |  | 0 | 0 |  |  |  | Cancelled | Port Gamble Sâ€™Klallam Foundation | 5231 | 0 | 0 | 0 | 0
__export__.project_task_2714_61574332 | Deployment: 2105 | Sprint 2108 | 2021-02-08 | Configuration | Dialed Supply: Help (P21) | Levi Barnes | Wajahat Ali | 0.67 | 0 |  |  |  | Complete | Dialed Supply | 5240 | 0 | -0.67 | 0 | 3.6875
__export__.project_task_2713_810fa709 | Upgradation of RAM |  |  | Other | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5242 | 0 | 0 | 0.12647 | 385.6812
__export__.project_task_2704_76e57749 | Receive chart of accounts from Ryan (for WildPack Beverage Inc.) |  |  | Configuration | Wild Leaf: Accounting (P64) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5324 | 0 | 0 | 160 | 205.2806
__export__.project_task_2703_8b85c155 | Please change the name of the second company to WildPack Beverage Inc. (Parent) |  |  | Configuration | Wild Leaf: Accounting (P64) | Nick Foy |  | 0.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5324 | 0 | -0.25 | 0 | 48
__export__.project_task_2701_9ecdf68b | Inventory Training |  |  | Other | Wild Leaf: Help (P22) | Nick Foy |  | 1.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5329 | 0 | -1.5 | 0 | 0
__export__.project_task_2692_620a1d39 | Create a Schedule Activity type of "Create Deposit Invoice" same day, specific person |  |  |  | Wild Leaf: Help (P22) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5334 | 0 | 0 | 162.0891 | 162.0891
__export__.project_task_2691_77bf9340 | Sales Quotation restrict the Create Invoice to a User Group |  |  |  | Wild Leaf: Help (P22) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5334 | 0 | 0 | 162.0937 | 162.0937
__export__.project_task_2673_d590cfe4 | Switch to Stripe |  |  | Configuration | Heronswood: Help (P54) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 5352 | 0 | 0 | 0 | 167.4783
__export__.project_task_2645_e6dbf6df | Deployment 2104: PWX General |  |  | Configuration | PWX: Help (P23) | Levi Barnes | Wajahat Ali | 3.5 | 0 |  |  |  | Complete | EquityTeam | 5409 | 0 | -3.5 | 0 | 2.1113
__export__.project_task_2639_b826a214 | Error Message when Adding CCD Feed(1004) |  |  | Bug Fix | PWX: Help (P23) | Levi Barnes |  | 0.5 | 0 |  |  |  | Complete | EquityTeam | 5427 | 0 | -0.5 | 0 | 64
__export__.project_task_2631_3c7227c7 | Process for Unreliable Procurement |  |  | Configuration | Wild Leaf: Help (P22) | Nick Foy | Nick Foy | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 5493 | 0 | 0 | 8 | 80
__export__.project_task_2630_62970a4f | Unit of Measure Configuration |  |  | Configuration | Wild Leaf: Help (P22) | Nick Foy | Nick Foy | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 5493 | 0 | 0 | 8 | 80
__export__.project_task_2629_03e675ef | Training Modules |  |  | Configuration | Wild Leaf: Help (P22) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5496 | 0 | 0 | 200 | 472
__export__.project_task_2627_2b524b7a | Training Grant | Sprint 2109 | 2021-02-15 | Configuration | Wild Leaf: Help (P22) | Nick Foy | Nick Foy | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5496 | 0 | 0 | 8 | 125.5919
__export__.project_task_2624_83bfe3de | Helpdesk Timesheets |  |  | Development | Silverdale: Help (P12) | Nick Foy | Faizan Zia Malik | 4 | 0 |  | Timesheets |  | Cancelled | Silverdale Technology LLC | 5499 | 0 | -4 | 0 | 8
__export__.project_task_2446_24521bba | WIP Manufacturing Process Requirements |  |  | Configuration | Wild Leaf: Help (P22) | Jeff Gross | Nick Foy | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5568 | 0 | 0 | 224 | 528
__export__.project_task_2418_45e0e811 | Continuant Database Local Restoration |  |  | Configuration | Silverdale: Help (P12) | Muhammad Afzaal |  | 13.83 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5594 | 0 | -13.83 | 0 | 24
__export__.project_task_2405_45991da9 | changing the one2many to many2many in more good possible way. |  |  | Development | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 3 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5666 | 3 | 0 | 0 | 0
__export__.project_task_2404_c759bc7f | debugging and analyse code |  |  | Bug Fix | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 3 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5670 | 3 | 0 | 2.5878e-05 | 2.2292
__export__.project_task_2403_8ec97109 | restoring latest database in local system |  |  | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 0.5 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5673 | 0.5 | 0 | 0 | 0
__export__.project_task_2385_546e2c0d | Inventory Count: Streamline Quantity Entry Requirements | Sprint 2118 | 2021-04-26 | Configuration | Wild Leaf: Help (P22) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 5734 | 0 | 0 | 264 | 528
__export__.project_task_2352_b132c602 | Odoo to SFTP Server |  |  | Development | Silverdale: Help (P12) | Nick Foy | Danish Hassan | 4 | 100 |  |  |  | Complete | Silverdale Technology LLC | 5766 | 4 | 0 | 0 | 9.7607
__export__.project_task_2342_827ca059 | PO Order Tracking Requirements |  |  | Configuration | Wild Leaf: Vendor Portal - Phase 1 (P49) | Jeff Gross | Naseeb Razaq | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 5813 | 0 | 0 | 280 | 280
__export__.project_task_2327_c704c3fb | deployment sprint 2101 tasks on production | Sprint 2103 | 2021-01-11 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 3.5 | 0 |  |  |  | Complete | Cellpoint Corporation | 5856 | 0 | -3.5 | 0 | 4
__export__.project_task_2325_7abb8571 | UI Review | Sprint 2103 | 2021-01-11 | Configuration | Continuant: AV Warehouse (P34) | Kaesi Lee |  | 2 | 0 |  |  |  | Complete | Continuant | 5858 | 0 | -2 | 0 | 8
__export__.project_task_2306_8d3568b1 | Silverdale Tech Task Error | Sprint 2103 | 2021-01-11 | Bug Fix | Silverdale: Help (P12) | Nick Foy | Muzher Siddique | 0.42 | 84 |  |  |  | Complete | Silverdale Technology LLC | 5881 | 0.5 | 0.08 | 0 | 0
__export__.project_task_2301_fd18f88f | Generate requirements and create project tasks and schedule |  |  | Configuration | Wild Leaf: IL2000 Integration (P40) | Nick Foy | Nick Foy | 1.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5887 | 0 | -1.5 | 106.6396 | 296.5824
__export__.project_task_2300_0c01c327 | Create new tasks for the remainder of the project | Sprint 2103 | 2021-01-11 | Configuration | PWX: Field Service to Invoicing (P47) | Levi Barnes | Levi Barnes | 0.5 | 0 |  |  |  | Complete | EquityTeam | 5887 | 0 | -0.5 | 0 | 19.1179
__export__.project_task_2297_b1c51c05 | restoring database, with latest code in local host |  |  | Development | PWX: Field Service to Invoicing (P47) | Levi Barnes | Raheel Aslam | 1 | 100 |  |  |  | Complete | EquityTeam | 5888 | 1 | 0 | 0 | 0.039522
__export__.project_task_2270_8b51019b | Fahad Functional Intern Plan: | Sprint 2105 | 2021-01-25 | Configuration | Silverdale: Help (P12) | Faisal Huda Khan | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5910 | 0 | 0 | 0.0032382 | 119.0577
__export__.project_task_2260_b2271032 | Deployment Wildleaf 2101 | Sprint 2103 | 2021-01-11 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Muzher Siddique | 0.62 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5913 | 0.61667 | -0.0033333 | 0 | 1.0251
__export__.project_task_2227_ef17bdce | FW: questions regarding web site |  |  |  | Albers Vista (P20) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Albers Marcovina Vista Gardens | 5958 | 0 | 0 | 0 | 20.3972
__export__.project_task_2226_eb8e7278 | Photos on website |  |  | Configuration | Albers Vista (P20) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Albers Marcovina Vista Gardens | 5958 | 0 | 0 | 0 | 20.3994
__export__.project_task_2162_85a564d8 | Fw: Data Exchange for future proofing business w ecoATM |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Nick Foy | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 6044 | 0 | 0 | 0 | 101.0569
__export__.project_task_2160_e606e2ad | Capture Additional Pricing Data |  |  | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Faizan Zia Malik | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 6048 | 0 | 0 | 0 | 200
__export__.project_task_2095_fa6e85a8 | Employee Evaluation Enhancement | Sprint 2102 | 2021-01-04 |  | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 5.58 | 99.94 |  |  |  | Cancelled | Silverdale Technology LLC | 6169 | 5.5833 | 0.0033333 | 0 | 160
__export__.project_task_2075_2186687b | Make components visible on work order steps |  |  |  | Wild Leaf: Help (P22) | Kaesi Lee |  | 0.5 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 6212 | 0 | -0.5 | 0 | 176
__export__.project_task_2068_d0ee34a6 | Set-Up PLM Module |  |  |  | Wild Leaf: Help (P22) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6219 | 0 | 0 | 0 | 79.8456
__export__.project_task_2041_398b5df2 | Create a module named Employee Evaluation |  |  | Development | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 6272 | 0 | -6.08 | 0 | 259.7883
__export__.project_task_2039_b6fcbeae | appraisals core evaluation: Feedback from client |  |  |  | PWX: Help (P23) | Levi Barnes | Levi Barnes | 0.33 | 33 |  |  |  | Cancelled | EquityTeam | 6381 | 1 | 0.67 | 0 | 216
__export__.project_task_2035_ea2f170c | FW: web site |  |  | Configuration | Albers Vista (P20) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Albers Marcovina Vista Gardens | 6387 | 0 | 0 | 0 | 96
__export__.project_task_2024_d9d78511 | Dialed Supply Deployment 2051 | Sprint 2051 | 2020-12-14 | Configuration | Dialed Supply: Help (P21) | Levi Barnes | Muzher Siddique | 1 | 100 |  |  |  | Complete | Dialed Supply | 6416 | 1 | 0 | 0 | 3.7516
__export__.project_task_2023_7e4c4569 | Deployment Heronswood | Sprint 2051 | 2020-12-14 | Configuration | Heronswood: Events (P3) | Nick Foy | Muzher Siddique | 0.7 | 70 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 6416 | 1 | 0.3 | 0 | 0.32583
__export__.project_task_2005_caab3ab5 | Add new field in project Task | Sprint 2052 | 2020-12-21 | Development | Silverdale: Help (P12) | Muhammad Afzaal | Danish Hassan | 1.33 | 88.67 |  |  |  | Complete | Silverdale Technology LLC | 6441 | 1.5 | 0.17 | 0 | 96.8247
__export__.project_task_1999_444bdcd7 | Staging Environment setup |  |  | Configuration | KMI: Help (P41) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | KMI Zeolite | 6506 | 0 | 0 | 0 | 100.7225
__export__.project_task_1991_f34a17f7 | Product Variant Method for Purchasing |  |  |  | Wild Leaf: Help (P22) | Kaesi Lee |  | 1 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 6508 | 0 | -1 | 0 | 240
__export__.project_task_1990_46b2c334 | Changing Ownership of Inventory using Consignment |  |  | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6508 | 0 | 0 | 0 | 143.9092
__export__.project_task_1989_aad3614e | Configure Product Versioning |  |  | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6508 | 0 | 0 | 0 | 143.9347
__export__.project_task_1988_7def2a08 | Configure Asset Management |  |  | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6508 | 0 | 0 | 0 | 143.9117
__export__.project_task_1987_521ea794 | Expiration Dates Configuration |  |  | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 1.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6508 | 0 | -1.5 | 0 | 143.9144
__export__.project_task_1897_1574d68f | FW: Log-in Issues |  |  | Bug Fix | Wild Leaf: Help (P22) | Kaesi Lee |  | 0.33 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6575 | 0 | -0.33 | 0 | 22.3944
__export__.project_task_1891_2725e1e4 | FW: You have been assigned to Time Dr. |  |  | Configuration | PWX: Time Doctor (P44) | Levi Barnes |  | 0 | 0 |  |  |  | Cancelled | EquityTeam | 6582 | 0 | 0 | 0.12671 | 1088.3237
__export__.project_task_1887_e9529f41 | WildLeaf General Deployment 2050 | Sprint 2050 | 2020-12-07 | Configuration | Wild Leaf: Help (P22) | Muzher Siddique | Muzher Siddique | 1.17 | 100 |  |  |  | Complete | Wild Leaf Beverage | 6583 | 1 | -0.17 | 0 | 1.0392
__export__.project_task_1873_cd358e6f | Error Encountered In Manufacturing |  |  | Bug Fix | Wild Leaf: Help (P22) | Kaesi Lee |  | 1 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6600 | 0 | -1 | 0 | 0
__export__.project_task_1866_648cd053 | Email Set-Up | Sprint 2053 | 2020-12-28 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 1 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6605 | 0 | -4.25 | 0.47822 | 172.4782
__export__.project_task_1862_ac55be7d | Send Chatter message to Customer |  |  | Development | Silverdale: Help (P12) | Muzher Siddique |  | 0.33 | 8.25 |  |  |  | Cancelled | Silverdale Technology LLC | 6678 | 4 | 3.67 | 0 | 282.2805
__export__.project_task_1861_b82d4f73 | Sales Team Training Dec 11 | Sprint 2050 | 2020-12-07 | Configuration | Wild Leaf: Help (P22) | Nick Foy | Nick Foy | 4.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6693 | 0 | -4.5 | 0 | 15.5408
__export__.project_task_1846_8febab74 | Auto Refresh issue in iOS | Sprint 2049 | 2020-11-30 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 1 | 0 |  |  |  | Complete | Cellpoint Corporation | 6736 | 0 | -1 | 0 | 2.6117
__export__.project_task_1844_f1b187d5 | add view to meeting in calendar kanban |  |  |  | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 3.25 | 27.08 |  | SPriority |  | Cancelled | EquityTeam | 6739 | 12 | 8.75 | 0 | 304
__export__.project_task_1838_7b7acd09 | Help Desk: Help Desk Task to Project Task |  |  | Development | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 0.17 | 3.4 |  |  |  | Cancelled | Silverdale Technology LLC | 6746 | 5 | 4.83 | 394.2642 | 406.4992
__export__.project_task_1837_a3259167 | Help Desk: HelpDesk task to Project Task |  |  | Development | Silverdale: Help (P12) | Muzher Siddique | Kaleem Khan | 0 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 6746 | 0 | 0 | 0 | 384
__export__.project_task_1830_9fbefe42 | Support: Log In Issue |  |  | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 0.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6750 | 0 | -0.25 | 0 | 1.5085
__export__.project_task_1817_7d55649f | Create a post event message to include Vimeo details | Sprint 2050 | 2020-12-07 | Configuration | Heronswood: Events (P3) | Nick Foy | Fahad Hassan | 4 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 6766 | 2.5 | -1.5 | 0 | 94.5861
__export__.project_task_1816_b51cfb5e | On Event add fields for post-event Vimeo link and password | Sprint 2050 | 2020-12-07 | Studio | Heronswood: Events (P3) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 6766 | 0 | 0 | 0 | 94.5861
__export__.project_task_1815_99fb8ec9 | On Event Registration emails add Zoom details | Sprint 2050 | 2020-12-07 | Configuration | Heronswood: Events (P3) | Nick Foy | Fahad Hassan | 4.42 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 6766 | 3 | -1.42 | 0 | 94.5861
__export__.project_task_1809_4aef9111 | Set-Up Online Payments | Sprint 2050 | 2020-12-07 | Configuration | Heronswood: Events (P3) | Nick Foy | Nick Foy | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 6768 | 0 | 0 | 0 | 94.5861
__export__.project_task_1808_dd8be37a | Set-Up Events | Sprint 2050 | 2020-12-07 | Configuration | Heronswood: Events (P3) | Nick Foy | Nick Foy | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 6768 | 0 | 0 | 0 | 94.5861
__export__.project_task_1705_fc6884ed | Price List User Groups to prevent Users changing terms and Price Lists in Quotations/Sales Orders | Sprint 2050 | 2020-12-07 | Development | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 12.5 | 100 |  |  |  | Complete | Wild Leaf Beverage | 6894 | 12 | -0.5 | 0 | 120.8862
__export__.project_task_1699_5a908b08 | Import Products to CPBids | Sprint 2050 | 2020-12-07 | Configuration | Cellpoint CPBids: Help (P7) | Nick Foy | Raheel Aslam | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 6907 | 0 | 0 | 0 | 56
__export__.project_task_1672_156bd2ad | Fwd: Worksheet ECO LG auction Non YYY |  |  | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 0.67 | 0 |  |  |  | Complete | Cellpoint Corporation | 6984 | 0 | -0.67 | 0 | 15.3919
__export__.project_task_1671_0179e93c | Fwd: Wroksheet_Grade_YYY.xlsx -ECO LG Trial |  |  | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 0.67 | 0 |  |  |  | Complete | Cellpoint Corporation | 6984 | 0 | -0.67 | 0 | 15.3967
__export__.project_task_1619_9f80e33e | New Seller Onboarding: EcoATM |  |  | Configuration | CPBids: ecoATM Onboarding (P35) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 7223 | 0 | 0 | 0 | 656
__export__.project_task_1614_5e0871a8 | CpBids monitoring,Testing,helpdesk |  |  | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 102.08 | 0 |  |  |  | Complete | Cellpoint Corporation | 7234 | 0 | -102.08 | 0.01228 | 412.5139
__export__.project_task_1608_f9284048 | Chatter expand/minimize |  |  | Development | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 4.08 | 100 |  |  |  | Complete | EquityTeam | 7284 | 3 | -11.12 | 0 | 91.8274
__export__.project_task_1594_7f4b2425 | Sprint 2046: Thrusday |  |  |  | Silverdale: Help (P12) | Muzher Siddique |  | 0.75 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 7372 | 0 | -0.75 | 0 | 448.047
__export__.project_task_1557_fe97f9f3 | Blocked Tasks On Dashboard | Sprint 2045 | 2020-11-02 | Configuration | Silverdale: Help (P12) | Muhammad Afzaal | Muzher Siddique | 35 | 0 |  |  |  | Complete | Silverdale Technology LLC | 7536 | 0 | -35 | 15.1656 | 0
__export__.project_task_1555_b3515aeb | URGENT: gucci not able to place orders | Sprint 2046 | 2020-11-09 | Bug Fix | Moln: Help (P16) | Kaesi Lee | Muzher Siddique | 0.75 | 0 |  | Need Assistance |  | Complete | Moln Solutions, LLC | 7538 | 0 | -0.75 | 0 | 95.2103
__export__.project_task_1554_a518986e | cpbids workflow | Sprint 2044 | 2020-10-26 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Raheel Aslam | 7 | 0 |  |  |  | Complete | Cellpoint Corporation | 7538 | 0 | -7 | 5.2433 | 48
__export__.project_task_1553_228fa776 | gucci user invitations - not being logged, why? | Sprint 2045 | 2020-11-02 | Configuration | Moln: Help (P16) | Kaesi Lee | Fahad Hassan | 11 | 0 |  | Email Configuration |  | Complete | Moln Solutions, LLC | 7539 | 0 | -11 | 0 | 56
__export__.project_task_1540_c98afbda | Project Module: Search for Assign to Developer | Sprint 2045 | 2020-11-02 | Development | Silverdale: Help (P12) | Kaesi Lee | Muzher Siddique | 1 | 50 |  |  |  | Complete | Silverdale Technology LLC | 7568 | 2 | 1 | 0 | 19.6828
__export__.project_task_1538_1eb92f52 | Thursday |  |  | Configuration | Silverdale: Help (P12) | Muzher Siddique |  | 138.4 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 7568 | 0 | -138.4 | 0 | 504.8604
__export__.project_task_1533_a6cc2a28 | Code Access | Sprint 2045 | 2020-11-02 | Configuration | PWX: Help (P23) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | EquityTeam | 7570 | 0 | 0 | 0 | 4.9895
__export__.project_task_1532_2dbab1b2 | Horizontal Scrollbar in Mobile Devices on Website Homepage | Sprint 2045 | 2020-11-02 | Bug Fix | Silverdale: Help (P12) | Faizan Zia Malik | Muzher Siddique | 2 | 0 |  | iOS |  | Complete | Silverdale Technology LLC | 7584 | 0 | -2 | 0 | 8
Website
__export__.project_task_1527_6c0d411f | Reviews: Integration with Facebook Reviews. | Sprint 2047 | 2020-11-16 | Configuration | PWX: Reviews Module (P53) | Levi Barnes | Danish Hassan | 17.92 | 0 |  |  |  | Complete | EquityTeam | 7587 | 0 | -17.92 | 0 | 176
__export__.project_task_1524_1e0a542b | Silverdale Tech Documents Error | Sprint 2045 | 2020-11-02 | Bug Fix | Silverdale: Help (P12) | Nick Foy | Danish Hassan | 1.5 | 0 |  |  |  | Complete | Silverdale Technology LLC | 7610 | 0 | -1.5 | 0 | 40
__export__.project_task_1498_a090dcab | Upgrade to v14:create vm |  |  | Configuration | Silverdale: Help (P12) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 7846 | 0 | 0 | 0 | 0
__export__.project_task_1490_dc4f6c96 | redirection issue - weshield orders redirecting to drprotect | Sprint 2043 | 2020-10-19 | Bug Fix | Moln: Help (P16) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Moln Solutions, LLC | 7890 | 0 | 0 | 7.2719 | 8
__export__.project_task_1485_b49636a9 | Belmont Request: Standardize Auction Lot Views | Sprint 2044 | 2020-10-26 | Studio | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 0.5 | 0 |  |  |  | Complete | Cellpoint Corporation | 7895 | 0 | -0.5 | 0 | 46.8111
__export__.project_task_1482_455a8f1b | Show US flag on PDF catalog | Sprint 2044 | 2020-10-26 | Development | Moln: Help (P16) | Kaesi Lee | Gadha Continuant | 9 | 100 |  |  |  | Complete | Moln Solutions, LLC | 7900 | 8 | -1 | 0.15598 | 65.2296
__export__.project_task_1440_a8d5be78 | Accounting GL Import and Set-Up | Sprint 2041 | 2020-10-05 | Configuration | Wild Leaf: Help (P22) | Nick Foy |  | 2 | 100 |  |  |  | Complete | Wild Leaf Beverage | 8014 | 2 | 0 | 0 | 0
__export__.project_task_1428_8e1ef8ad | Migrate Employee Data from v13 to v14 | Sprint 2041 | 2020-10-05 | Configuration | PWX: Help (P23) | Levi Barnes |  | 4 | 100 |  |  |  | Complete | EquityTeam | 8038 | 4 | 0 | 104 | 8
__export__.project_task_1381_de88b384 | remove this text-block on detail pages | Sprint 33 | 2020-09-28 | Configuration | Moln: Help (P16) | Nick Foy |  | 0.5 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8253 | 0 | -0.5 | 5.7161 | 8
__export__.project_task_1366_7bb082b1 | Send best practice for location barcodes | Sprint 2041 | 2020-10-05 | Configuration | Wild Leaf: Help (P22) | Nick Foy |  | 0.25 | 100 |  |  |  | Complete | Wild Leaf Beverage | 8348 | 0.25 | 0 | 0 | 40
__export__.project_task_1364_10e43862 | Missing Bids: QGZXX | Sprint 2041 | 2020-10-05 | Bug Fix | Cellpoint CPBids: Help (P7) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8351 | 0 | 0 | 0 | 5.2431
__export__.project_task_1363_9e370d1a | Odoo v14 Upgrade | Sprint 33 | 2020-09-28 | Configuration | Wild Leaf: Help (P22) | Nick Foy |  | 8 | 100 |  |  |  | Complete | Wild Leaf Beverage | 8352 | 6 | -2 | 0 | 80
__export__.project_task_1352_af93e89c | FW: Your Odoo account at Cellpoint Corporation | Sprint 33 | 2020-09-28 | Configuration | Cellpoint CPBids: Help (P7) |  |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8383 | 0 | 0 | 0 | 2.6611
__export__.project_task_1351_601d9c15 | Drift Javascript snippet | Sprint 32 | 2020-09-21 | Configuration | Moln: Help (P16) | Kaesi Lee |  | 0.5 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8396 | 0 | -0.5 | 14.8128 | 24
__export__.project_task_1346_63d1ea0f | my bids is not working, cascade bids, auction, manifest and notificationsÂ | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8398 | 0 | 0 | 0 | 20
__export__.project_task_1339_f75a5b2c | Change hidden notification text as well | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8398 | 0 | 0 | 0 | 16
__export__.project_task_1336_a6671ff8 | Sort CPBids Notification table Ascending order | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8398 | 0 | 0 | 0 | 6.0247
__export__.project_task_1316_a8b04cf5 | says "Â© 2020 weshield.us. All Rights Reserved." in the footer. | Sprint 32 | 2020-09-21 | Bug Fix | Moln: Help (P16) |  |  | 0 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8428 | 0 | 0 | 0 | 0
__export__.project_task_1305_6397e2a5 | is our odoo.sh hosted from Europe? | Sprint 32 | 2020-09-21 | Configuration | Moln: Help (P16) |  |  | 0.25 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8451 | 0 | -0.25 | 0 | 8
__export__.project_task_1290_f3070264 | forefront should only display 3 products | Sprint 33 | 2020-09-28 | Bug Fix | Moln: Help (P16) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8500 | 0 | 0 | 8 | 8
__export__.project_task_1287_ceae5243 | aoa.drprotect.com blog | Sprint 32 | 2020-09-21 | Configuration | Moln: Help (P16) | Nick Foy |  | 0.5 | 0 |  | Blogs |  | Complete | Moln Solutions, LLC | 8525 | 0 | -0.5 | 0.94708 | 0.94708
__export__.project_task_1260_5eea0ca8 | order processing error with auhorize.net | Sprint 32 | 2020-09-21 | Configuration | Moln: Help (P16) | Nick Foy |  | 0.25 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8662 | 0 | -0.25 | 8 | 8
__export__.project_task_1198_ae3efcbb | Test Connection to Hydrofarm API | Sprint 31 | 2020-09-14 | Development | Dialed Supply: Help (P21) | Anusha |  | 0 | 0 |  |  |  | Complete | Dialed Supply | 8855 | 0 | -2.25 | 0 | 0
__export__.project_task_1176_887c4dbe | drProtect design and copy updates | Sprint 30 | 2020-09-07 | Configuration | Moln: Help (P16) | Kaesi Lee |  | 4 | 100 |  |  |  | Complete | Moln Solutions, LLC | 9042 | 4 | 0 | 8 | 0
__export__.project_task_1174_7e9f5685 | Auction Lot Display Issue | Sprint 29 | 2020-08-31 | Bug Fix | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9053 | 0 | 0 | 0 | 0
__export__.project_task_1107_be36abd4 | Master Data Import | Sprint 27 | 2020-08-17 |  | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 9460 | 0 | 0 | 0 | 1164.2885
__export__.project_task_1061_c8a229b2 | Seller Permissions Group: Rename Sellers Buyers to "My Buyers" | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_1049_ae9ee596 | Seller Permissions Group: Remove Chatter Window | Sprint 27 | 2020-08-17 | Development | CPBids Migration AWS->odoo (P5) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 25.6286 | 0
__export__.project_task_567_75c0361e | API:Shoot mail to Admin to approve the account | Sprint 23 | 2020-07-20 |  | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  | API-Odoo |  | Cancelled | Cellpoint Corporation | 10147 | 0 | 0 | 0 | 1332
__export__.project_task_288_aa83d89b | Remove Incorrect Bid - NILXQ | Sprint 23 | 2020-07-20 | Development | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  | Need Assistance |  | Complete | Cellpoint Corporation | 10251 | 0 | 0 | 56 | 0
__export__.project_task_237_5c93ebbc | Sprint 21 - Test Scripts | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Need Assistance |  | Complete | Cellpoint Corporation | 10478 | 0 | 0 | 0 | 0
__export__.project_task_4794_e9c2785e | Confirm project with Dwayne |  |  | Client Meetings | DGS: Odoo website help (P209) | Erin Olson |  | 0 | 0 | Please add next activity | 2015-09-01 |  | New | DG Solutions Inc. | 288 | 0 | 0 | 8.9039e-06 | 0
__export__.project_task_4575_04ba560c | Master Data is imported for all modules | Sprint 2136 | 2021-08-30 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 1 | 33.33 |  | SPLN |  | Complete | Zuma Sales LLC | 799 | 3 | 2 | 0 | 173.4228
__export__.project_task_4476_d89c0e97 | Mechanism to define Mechanisms |  |  | Documentation | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair | Muhammad Zubair | 0 | 0 | Please add next activity |  |  | Backlog | Silverdale Technology LLC | 894 | 0 | 0 | 0.0096196 | 0
__export__.project_task_4146_2e6b8682 | Creating Sales Order on Terex | Sprint 2129 | 2021-07-12 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 10.5 | 100 |  | SPLN | 3 | Complete | Zuma Sales LLC | 1830 | 8 | -2.5 | 94.9407 | 105.9329
__export__.project_task_4115_41c00add | Home Page Migration | Sprint 2127 | 2021-06-28 | Development | DGS: Odoo Website Migration (P126) | Fahad Hussain Malik | Danish Hassan | 3 | 42.86 |  | SPLN | 2 | Complete | DG Solutions Inc. | 1973 | 7 | 4 | 0.71609 | 88.7161
__export__.project_task_4078_abd51659 | Import Orders in bulk or choose specific order to import based on date range |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 | Plan it for sprint |  |  | Planning | Mountain Meadow Herbs | 2048 | 2 | 2 | 0 | 0
__export__.project_task_4044_2abcbad5 | Quality setup | Sprint 2126 | 2021-06-21 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2142 | 0 | 0 | 166.4774 | 49.4697
__export__.project_task_4011_2e57ef2d | Map existing general ledger accounts to Odoo accounts |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 2188 | 0 | 0 | 180.9908 | 173.6792
__export__.project_task_3863_4adf7ba7 | Sellers & Buyers page | Sprint 2138 | 2021-09-13 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Sajjad Hussain | 0.33 | 11 | Please add next activity |  |  | Backlog | Cellpoint Corporation | 2570 | 3 | 2.67 | 468.0381 | 0
__export__.project_task_3688_b4c0252d | Install Third Party Pivot Table App | Sprint 2121 | 2021-05-17 | Configuration | Wild Leaf: Financial statement pivot views and filters (P116) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 3005 | 0.016667 | 0.016667 | 0 | 32
__export__.project_task_3661_23070403 | TC-299 | Sprint 2123 | 2021-05-31 | Development | Silverdale: Devops (P84) | Levi Barnes | Wishal Nasir | 3.5 | 100 |  |  |  | Complete | Silverdale Technology LLC | 3164 | 3.5 | 0 | 0 | 24
__export__.project_task_3487_9a448dba | All Products have Barcodes (Need to ask about this) | Sprint 2129 | 2021-07-12 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 1 | 100 |  | SPLN |  | Complete | Zuma Sales LLC | 3483 | 1 | 0 | 364 | 442.5236
__export__.project_task_3486_0b50f2d4 | Physical inventory adjustments validated for all locations | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.8197 | 637.5425
__export__.project_task_3456_182810cd | Verify the completion of the production environment | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0.5 | 16.67 | Follow Up | 2017-09-01 |  | Backlog | Zuma Sales LLC | 3484 | 3 | 2.5 | 461.9784 | 0
Fahad
Asfand
__export__.project_task_3354_4d45ba68 | generate critical function list |  |  | Other | PWX: Help (P23) | Levi Barnes | Levi Barnes | 0 | 0 |  |  |  | Complete | EquityTeam | 3693 | 0 | 0 | 0 | 22.4942
__export__.project_task_3050_be94efd25 | Initiate using the live Odoo site |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0.00033996 | 206.1934
__export__.project_task_2923_a0e6813a | Select Shipping Quote from IL2000:R&D | Sprint 2119 | 2021-05-03 | Development | Wild Leaf: IL2000 Integration (P40) | Jeff Gross | Fahad Hassan | 8.08 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4569 | 6 | -2.08 | 0 | 292
__export__.project_task_2914_2cea75f9 | Plan the MOS workshop |  |  |  | DESIGN (P77) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1049.8079
__export__.project_task_2802_87f57727 | invoice report modification | Sprint 2110 | 2021-03-01 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 6.83 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 4866 | 6.5 | -0.33 | 0 | 143.0989
__export__.project_task_2730_fb94797b | Employee: Private | Sprint 2110 | 2021-02-22 | Development | PWX: HR (P61) | Levi Barnes | Danish Hassan | 6.28 | 96.62 |  |  |  | Complete | EquityTeam | 5182 | 6.5 | 0.22 | 0 | 175.4231
__export__.project_task_2375_33197703 | Time Description | Sprint 2109 | 2021-02-15 | Development | Silverdale: Help (P12) | Muhammad Afzaal | Muzher Siddique | 0.33 | 11 |  | WK |  | Complete | Silverdale Technology LLC | 5743 | 3 | 2.67 | 0.052056 | 187.1396
__export__.project_task_2264_62f17d30 | Employee Appraisal & Evaluation. |  |  | Development | Silverdale: Help (P12) | Faisal Huda Khan |  | 0.25 | 5 |  |  |  | Cancelled | Silverdale Technology LLC | 5912 | 5 | 4.75 | 0 | 348
__export__.project_task_2098_6896be0d | Close helpdesk ticket after 10 days in pending resolution | Sprint 2108 | 2021-02-08 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 4.17 | 100 |  |  |  | Complete | Cellpoint Corporation | 6104 | 4 | -0.17 | 0.060964 | 338.3318
__export__.project_task_2045_5018405f | Convert custom modules to V14 | Sprint 2105 | 2021-01-25 | Development | Silverdale: v14 Upgrade (P46) | Muhammad Afzaal | Raheel Aslam | 7.83 | 78.3 |  | Difficulty 3 |  | Complete | Silverdale Technology LLC | 6267 | 10 | 2.17 | 392 | 200
__export__.project_task_1879_fc591634 | Create a migration plan and proposal | Sprint 2052 | 2020-12-21 | Configuration | KMI: Help (P41) | Levi Barnes |  | 3 | 0 |  | SPriority |  | Complete | KMI Zeolite | 6597 | 0 | -3 | 0 | 48
__export__.project_task_1860_d833e4c6 | modify ci survey options to chose from | Sprint 2050 | 2020-12-07 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 5.2 | 100 |  |  |  | Complete | EquityTeam | 6694 | 4.75 | -6.42 | 0 | 96
__export__.project_task_1587_87b5f9a1 | Kaesi: Odoo Expert Certification |  |  | Configuration | Silverdale: Help (P12) | Nick Foy |  | 0 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 7415 | 0 | 0 | 472 | 629.5122
__export__.project_task_1584_7553f7b6 | User Roles and Access Rights | Sprint 2046 | 2020-11-09 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 3 | 0 |  | Users |  | Complete | Wild Leaf Beverage | 7416 | 0 | -3 | 0 | 71.2128
__export__.project_task_1539_cd5cf855 | Friday |  |  | Configuration | Silverdale: Help (P12) | Muzher Siddique |  | 80.45 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 7568 | 0 | -80.45 | 0 | 504.8623
__export__.project_task_1379_fb5d109d | Duplicate New Buyer Registration Tickets | Sprint 2045 | 2020-11-02 | Bug Fix | Cellpoint CPBids: Help (P7) | Kaesi Lee | Roshan Mecoth | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8258 | 0 | 0 | 0 | 160
__export__.project_task_1356_4dad4390 | Contacts / Properties | Sprint 2048 | 2020-11-23 | Configuration | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 25 | 100 |  |  |  | Complete | EquityTeam | 8373 | 25 | 0 | 184 | 376
__export__.project_task_1258_a5771127 | Migrate Dialed Supply to Odoo.sh | Sprint 2047 | 2020-11-16 | Configuration | Dialed Supply: Help (P21) | Levi Barnes | Levi Barnes | 0.33 | 100 |  | Odoo.sh Migration |  | Complete | Dialed Supply | 8667 | 2 | -1 | 271.3428 | 432
__export__.project_task_1250_09c6156c | order confirmation - showing correct brand | Sprint 2042 | 2020-10-12 | Development | Moln: Help (P16) | Kaesi Lee | Gadha Continuant | 10 | 25 |  | eCommerce |  | Complete | Moln Solutions, LLC | 8686 | 40 | 30 | 136 | 176.1233
Sales
Invoicing
__export__.project_task_1226_838d0636 | Authorize.net not charging correct amount? | Sprint 31 | 2020-09-14 | Bug Fix | Moln: Help (P16) | Nick Foy |  | 0.25 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8753 | 0 | -0.25 | 5.7783 | 0
__export__.project_task_1101_61e1bd19 | Highest Bidder Name not populated | Sprint 27 | 2020-08-17 | Bug Fix | CPBids Migration AWS->odoo (P5) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9506 | 0 | 0 | 36 | 0
__export__.project_task_1056_34dd8bee | When you click save, Original End Date Time should be populated by End DateTIme and then Original End Date Time should be Read-Only | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_930_d652e83e | 583: iOS Release | Sprint 24 | 2020-07-27 | Development | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9924 | 2 | 2 | 0 | 0
__export__.project_task_261_ad308b31 | Add Select all for Sellers | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10310 | 0 | 0 | 20.2222 | 0
__export__.project_task_207_e3219600 | Watchlist - Mybids Web |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 1 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 10783 | 0 | -24.25 | 0 | 1425.0541
__export__.project_task_4833_d5c645a8 | Account Questions/Training | Sprint 2137 | 2021-09-06 | Client Meetings | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 1 | 100 |  | 2021-10-09 |  | Complete | Zuma Sales LLC | 170 | 1 | 0 | 0 | 18.3194
Meeting w/Bonnie
Asfand
__export__.project_task_4832_b2a76fed | AP / AR Training | Sprint 2137 | 2021-09-06 | Client Meetings | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 1.25 | 100 |  | 2021-10-09 |  | ELS | Zuma Sales LLC | 170 | 1 | -0.25 | 0 | 0
Meeting w/Bonnie
Asfand
__export__.project_task_4790_34f4addb | P&L Reports Totals for Groups - Part 3 |  |  | Development | Wild Leaf: P&L Reports Totals for groups (P193) | Abdul Hameed | Aleem khan | 0 | 0 | Update your actual hours on this task |  |  | New | Wild Leaf Beverage | 289 | 18 | 18 | 0 | 0
__export__.project_task_4518_c50d985e | COE Mechanism |  |  | Improvements | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 849 | 0 | 0 | 0 | 0
__export__.project_task_4145_f5d47f63 | API Authentication of connection | Sprint 2129 | 2021-07-12 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 3.83 | 95.75 |  | SPLN | 3 | Complete | Zuma Sales LLC | 1830 | 4 | 0.17 | 94.9578 | 105.95
__export__.project_task_4077_713ff480 | Import Operations Testing |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 | Plan it for the sprint |  |  | Planning | Mountain Meadow Herbs | 2048 | 2 | 2 | 0 | 0
__export__.project_task_3990_fdb5046b | Purchasing setup | Sprint 2125 | 2021-06-14 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2216 | 0 | 0 | 192.6891 | 51.6813
__export__.project_task_3864_29b1f105 | Contact Us Page | Sprint 2138 | 2021-09-13 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Wajahat Ali | 0.33 | 11 | Please add next activity |  |  | Backlog | Cellpoint Corporation | 2570 | 3 | 2.67 | 468.0153 | 0
__export__.project_task_3824_725bc5a0 | Don't allow to ready stage until every product is available in MO | Sprint 2123 | 2021-05-31 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Muhammad Bilal | 10.75 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 2745 | 4.5 | -6.25 | 89.5475 | 60
__export__.project_task_3657_93ffa349 | Setup and test email sending server in Odoo | Sprint 2124 | 2021-06-07 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq | Muhammad Bilal | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.25 | 0.25 | 0 | 159.1743
__export__.project_task_3637_77947f9a | Map the source fields to Odoo fields | Sprint 2120 | 2021-05-10 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 0.25 | 50 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.5 | 0.25 | 0 | 17.9839
__export__.project_task_3593_9592023b | Testing builds for android and ios needed. | Sprint 2120 | 2021-05-10 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 3189 | 0 | 0 | 0 | 24
__export__.project_task_3527_7b40c604 | Technical Training | Sprint 2137 | 2021-09-06 | Internal Time Tracking | Silverdale Technical Training (P115) | Faisal Huda Khan | Sanaullah Khan | 8.42 | 94.43 |  | SPLN |  | ELS | Silverdale Technology LLC | 3406 | 8.9167 | 0.49667 | 2.4414 | 0
__export__.project_task_3349_93d9e003 | Midamerica: Odoo Sale Order Automation | Sprint 2118 | 2021-04-26 | Development | Mid-America: Help (P37) | Levi Barnes | Wishal Nasir | 3.75 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 3717 | 0 | -3.75 | 0 | 32
__export__.project_task_3334_c3028b95 | Create pipline |  |  | Development | PWX: HR (P61) | Levi Barnes |  | 1 | 12.5 |  |  |  | Cancelled | EquityTeam | 3749 | 8 | 7 | 0 | 48.4112
__export__.project_task_3284_e7c82861 | On Put in Pack then pop-up with Pack number with OK button to close | Sprint 2115 | 2021-04-05 | Development | Wild Leaf: Help (P22) | Jeff Gross | Aleem khan | 9.58 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 4019 | 3 | -6.58 | 0 | 93.5238
__export__.project_task_3049_be94efd24 | Verification of data import |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0.00033996 | 206.1934
__export__.project_task_2921_77ba2b92 | Upload Journal Entries using CSV template | Sprint 2112 | 2021-03-15 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Wajahat Ali | 0.25 | 30 |  |  |  | Complete | Wild Leaf Beverage | 4570 | 0.83333 | 0.58333 | 0 | 76.4179
__export__.project_task_2918_f719a3c9 | Create an accountability matrix |  |  |  | DESIGN (P77) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1049.8037
__export__.project_task_2838_d0db5ba2 | Select Shipping Quote from IL2000 | Sprint 2119 | 2021-05-03 | Development | Wild Leaf: IL2000 Integration (P40) | Jeff Gross | Raheel Aslam | 15.17 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 4700 | 14 | -1.17 | 16 | 456
__export__.project_task_2793_ec5e11a1 | Helcim: 2 Decimal Places in Amount | Sprint 2110 | 2021-03-01 | Development | Wild Leaf: Helcim Integration (P38) | Jeff Gross | Wajahat Ali | 3.5 | 100 |  |  |  | Complete | Wild Leaf Beverage | 4921 | 3.5 | 0 | 72 | 159.1017
__export__.project_task_2790_45e85f8b | General 2108 |  |  | Internal Time Tracking | PWX: Help (P23) | Levi Barnes | Levi Barnes | 3 | 0 |  |  |  | Complete | EquityTeam | 4996 | 0 | -3 | 0 | 164
__export__.project_task_2759_0a78532a | Accountability: Description | Sprint 2109 | 2021-02-15 | Development | PWX: Strategic Planning (P43) | Levi Barnes | Raheel Aslam | 1.58 | 79 |  |  |  | Complete | EquityTeam | 5094 | 2 | 0.42 | 0 | 96.7454
__export__.project_task_2042_7396fa42 | Create a module named Employee Evaluation: | Sprint 2053 | 2020-12-28 | Development | Silverdale: Help (P12) | Muhammad Afzaal | Kaleem Khan | 4.75 | 95 |  |  |  | Complete | Silverdale Technology LLC | 6272 | 5 | 0.25 | 18.2242 | 96
__export__.project_task_1998_0ba282e4 | Routes |  |  | Configuration | KMI: Help (P41) | Levi Barnes |  | 0.75 | 0 |  |  |  | Complete | KMI Zeolite | 6506 | 0 | -0.75 | 0 | 100.7389
__export__.project_task_1845_1218fe0f | change calendar description to html widget | Sprint 2050 | 2020-12-07 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 1.55 | 100 |  |  |  | Complete | EquityTeam | 6739 | 1 | -0.55 | 0 | 86.5861
__export__.project_task_1832_c1b268f3 | Plan CpBids Transition: 2050 | Sprint 2050 | 2020-12-07 | Configuration | Cellpoint CPBids: Help (P7) | Muzher Siddique | Wajahat Ali | 11.17 | 100 |  |  |  | Complete | Cellpoint Corporation | 6749 | 11 | -0.17 | 0 | 23.7688
__export__.project_task_1637_29557bd6 | Saturday |  |  | Configuration | Silverdale: Help (P12) | Muzher Siddique |  | 1.08 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 7113 | 0 | -1.08 | 0 | 400.9136
__export__.project_task_1632_f6fca8dc | website error: product page not loading |  |  | Configuration | Moln: Help (P16) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Moln Solutions, LLC | 7192 | 0 | 0 | 14.9853 | 103.9033
__export__.project_task_1413_17db1938 | Icons on the detail page are different sizes | Sprint 2044 | 2020-10-26 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 2 | 0 |  |  |  | Complete | Cellpoint Corporation | 8092 | 0 | -2 | 0 | 38.6946
__export__.project_task_1389_80e5e2ad | Gucci: Sales Orders delayed in Odoo | Sprint 2043 | 2020-10-19 | Development | Moln: Help (P16) | Nick Foy | Gadha Continuant | 1 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8229 | 0 | -1 | 0 | 70.7189
__export__.project_task_1387_5a569321 | Daily QA for Moln Websites | Sprint 2045 | 2020-11-02 | Configuration | Moln: Help (P16) | Kaesi Lee | Faizan Zia Malik | 23.5 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8232 | 0 | -23.5 | 0 | 168
__export__.project_task_1048_03f66197 | Seller Permissions Group: Hide the "Sales" tab | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_931_19d67425 | 583: Chinese Store Release | Sprint 24 | 2020-07-27 | Development | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9924 | 2 | 2 | 0 | 0
__export__.project_task_262_75c346cb | When Select All Option on | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10308 | 0 | 0 | 18.8907 | 0
__export__.project_task_164_10ac1d47 | 1.3 Lot Pricing - Shipping Terms(1hour) | Sprint 27 | 2020-08-17 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 0
__export__.project_task_4715_b290409a | Activity - Rollout - Internal |  |  | Internal Training | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Plan |  |  | New | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 0
__export__.project_task_4642_89da190c | Deploy to Deployment + Production | Sprint 2135 | 2021-08-23 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 8.17 | 90.78 |  | SPLN |  | Complete | Zuma Sales LLC | 557 | 9 | 0.83 | 0 | 30.5824
__export__.project_task_4508_1be878f8 | Deployment to Production | Sprint 2133 | 2021-08-09 | Deployment | CraftAG: Set-up Dashboard Ninja (P172) | Fahad Hussain Malik | Fahad Hassan | 5 | 83.33 |  |  |  | Complete | CraftAG | 870 | 6 | 1 | 0 | 33.5338
__export__.project_task_4483_82844061 | Project Kick-off Mechanism |  |  |  | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 892 | 0 | 0 | 0 | 0
__export__.project_task_4351_5d7ddb18 | Investigate if the 520 issue is caused by Cloudflare or Odoo.sh | Sprint 2139 | 2021-09-20 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Kaleem Khan | 31.33 | 95.91 | Generate an estimate |  | 3 | Backlog | Cellpoint Corporation | 1372 | 32.6667 | 1.3367 | 181.944 | 0
__export__.project_task_4295_859daa49 | Deploy to Deployment + Production (Zuma - 2129) | Sprint 2129 | 2021-07-12 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hassan | 5.17 | 100 |  |  |  | Complete | Zuma Sales LLC | 1567 | 5 | -0.17 | 0.043765 | 10.619
__export__.project_task_4144_32a46b70 | R&D Terex Products | Sprint 2128 | 2021-07-05 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 3.17 | 63.4 |  |  | 3 | Complete | Zuma Sales LLC | 1830 | 5 | 1.83 | 94.9823 | 37.7623
__export__.project_task_4106_ac5c963e | Customs Document | Sprint 2128 | 2021-07-05 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Raheel Aslam | 0.17 | 100 |  |  |  | Cancelled | Zuma Sales LLC | 1974 | 0.16667 | -0.0033333 | 126.9238 | 60.4971
__export__.project_task_4076_2e72cd41 | Create Credit Note and Send Refund |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 | Plan it for the sprint |  |  | Planning | Mountain Meadow Herbs | 2048 | 3 | 3 | 0 | 0
__export__.project_task_3946_6b19e3d3 | Create SFTP Connection | Sprint 2126 | 2021-06-21 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 2.67 | 66.75 |  | reuse | 1 | Complete | Zuma Sales LLC | 2312 | 4 | 1.33 | 208.5482 | 99.5835
SADL
__export__.project_task_3807_cb668c91 | TL Activities | Sprint 2123 | 2021-05-31 | Other | Silverdale Time Tracking (P56) | Muhammad Afzaal | Wajahat Ali | 85.42 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 2878 | 0 | -85.42 | 0 | 224
__export__.project_task_3681_6542ebdb | Remove the work of sign up online for volunteer | Sprint 2121 | 2021-05-17 | Development | Heronswood: Volunteer On-boarding (P79) | Naseeb Razaq | Danish Hassan | 0.75 | 75 |  |  | 2 | Complete | Port Gamble Sâ€™Klallam Foundation | 3051 | 1 | 0.25 | 0 | 24
__export__.project_task_3652_7df8bbdf | Share Odoo email marketing training course from Silverdale Odoo | Sprint 2120 | 2021-05-10 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.16667 | 0.16667 | 0.00052273 | 160.2861
__export__.project_task_3483_285f30a9 | All customer deliveries up to date | Sprint 2129 | 2021-07-12 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3483 | 1 | 1 | 460.9908 | 456
__export__.project_task_3481_813f0aec | All pending receipts processed |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.9908 | 453.7736
__export__.project_task_3344_bf812be5 | Language issue on website | Sprint 2122 | 2021-05-24 | Development | MMH Dr. Clark: Help (P106) | Jeff Gross | Aleem khan | 20.5 | 100 |  |  | 3 | Complete | Mountain Meadow Herbs | 3721 | 4 | -16.5 | 0 | 312
__export__.project_task_3180_6c904a61 | dig list print report/label in excel | Sprint 2114 | 2021-03-29 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 15 | 100 |  |  | 3 | Complete | Mid-America Gardens, LLC | 4348 | 14 | -1 | 0 | 168
__export__.project_task_3048_be94efd23 | Shut down the previous system at an appropriate time |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 4355 | 0 | 0 | 0.00033996 | 301.7467
__export__.project_task_2917_82969058 | Set-up and plan DILO sessions with key team members |  |  |  | DESIGN (P77) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1049.8049
__export__.project_task_2879_1cde5bc2 | post job service |  |  | Development | PWX: Field Service to Invoicing (P47) | Naseeb Razaq |  | 2.5 | 0 | To bring it in weekly meeting |  |  | Planning | EquityTeam | 4589 | 0 | -2.5 | 1039.9407 | 0
__export__.project_task_2861_0c457bce | Receive Shipping Details and BoL from IL2000 | Sprint 2119 | 2021-05-03 | Development | Wild Leaf: IL2000 Integration (P40) | Jeff Gross | Fahad Hassan | 8.72 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 4662 | 6 | -2.72 | 2.1576 | 442.1576
__export__.project_task_2758_c85ad33a | Accountability: Main | Sprint 2109 | 2021-02-15 | Development | PWX: Strategic Planning (P43) | Levi Barnes | Raheel Aslam | 1.83 | 45.75 |  |  |  | Complete | EquityTeam | 5094 | 4 | 2.17 | 0 | 96.754
__export__.project_task_2754_a7474322 | CPBids Web: Transparent PNG Images for MarketPlace Logos | Sprint 2112 | 2021-03-15 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 0.83 | 99.6 |  |  |  | Complete | Cellpoint Corporation | 5101 | 0.83333 | 0.0033333 | 0.00026413 | 206.6858
__export__.project_task_2599_38469148 | Change static Template to Dynamic:Automate Belmont Emails |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Muhammad Bilal | 13.28 | 100 |  |  |  | Cancelled | Cellpoint Corporation | 5552 | 9 | -4.28 | 5.0347e-05 | 163.9917
__export__.project_task_2296_379b44c6 | Schedule B for T and C in Sign Module Requirements |  |  | Configuration | Wild Leaf: Help (P22) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 5888 | 0 | 0 | 299.7985 | 971.7985
__export__.project_task_2278_497d91c3 | Project - Part 2 | Sprint 2113 | 2021-03-22 | Internal Training | Silverdale: Help (P12) | Faisal Huda Khan | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5910 | 0 | 0 | 0.03754 | 388.5739
__export__.project_task_2254_0d1d37b4 | FW: Upload issues | Sprint 2103 | 2021-01-11 | Configuration | KMI: Help (P41) | Levi Barnes | Levi Barnes | 0.17 | 0 |  |  |  | Complete | KMI Zeolite | 5926 | 0 | -0.17 | 0 | 112
__export__.project_task_2107_a4ad4b78 | Events: Add a "Want to register for another event?" option | Sprint 2108 | 2021-02-08 | Development | Heronswood: Events (P3) | Jeff Gross | Raheel Aslam | 10.67 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 6101 | 4 | -6.67 | 352.9052 | 368.9052
__export__.project_task_1905_48d88062 | lot-"LIBHX"-extension-issue | Sprint 2051 | 2020-12-14 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 6.58 | 0 |  | P1 |  | Complete | Cellpoint Corporation | 6554 | 0 | -15.91 | 0 | 68
__export__.project_task_1867_0bb0ea25 | Billing - Direct cost billing | Sprint 2053 | 2020-12-28 | Development | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 3.2 | 100 |  | Potential Silverdale App |  | Complete | Wild Leaf Beverage | 6605 | 3.5 | -9.86 | 0.46105 | 172.461
__export__.project_task_1812_c849f637 | Set-Up SMTP2GO for Heronswood | Sprint 2050 | 2020-12-07 | Configuration | Heronswood: Events (P3) | Nick Foy |  | 0.17 | 51 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 6768 | 0.33333 | 0.16333 | 0 | 94.5861
__export__.project_task_1711_345569e5 | Use Silverdale Colors in Portal | Sprint 2110 | 2021-03-01 | Development | Silverdale: Help (P12) | Nick Foy | Raheel Aslam | 9.5 | 100 |  |  |  | Complete | Silverdale Technology LLC | 6893 | 9 | -0.5 | 0 | 624.3269
__export__.project_task_1654_da1f6fad | Android All Auction pagination issue : Getting same results again if more than 10 products created | Sprint 2048 | 2020-11-23 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 1.5 | 0 |  | 3.0.5 |  | Complete | Cellpoint Corporation | 7066 | 0 | -1.5 | 0.35442 | 68.8808
__export__.project_task_1640_3145a4e1 | Propertyworx Deployment 2047 | Sprint 2047 | 2020-11-16 | Configuration | PWX: Help (P23) | Muzher Siddique |  | 0.42 | 0 |  |  |  | Complete | EquityTeam | 7108 | 0 | -0.42 | 0 | 64
__export__.project_task_1534_9bedee09 | Daily Activities |  |  | Configuration | Silverdale: Help (P12) | Muzher Siddique |  | 0 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 7568 | 0 | -607.23 | 0 | 504.8999
__export__.project_task_1424_aca52e1d | require phone-number on web orders | Sprint 2042 | 2020-10-12 | Development | Moln: Help (P16) | Kaesi Lee | Gadha Continuant | 3 | 37.5 |  |  |  | Complete | Moln Solutions, LLC | 8061 | 8 | 5 | 8 | 32.2947
__export__.project_task_1030_3628ad30 | Hide My watch bidders | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_583_f12b5826 | Unable to Navigate to Marketplace Selection from All Auctions | Sprint 24 | 2020-07-27 | Bug Fix | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10081 | 2 | 2 | 46.4153 | 0
__export__.project_task_218_826326eb | Use Github to Push Code to Production | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10735 | 0 | 0 | 125.3588 | 0
__export__.project_task_4503_605cbe5c | Export Inventories to SFTP |  |  | Development | Zuma: Odoo Implementation Phase 2 (P204) | Asfand Yaar | Aleem khan | 0 | 0 | Please add next activity |  |  | New | Zuma Sales LLC | 871 | 0 | 0 | 113.3442 | 0
__export__.project_task_4485_8c7b4170 | Solution Design Mechanism |  |  |  | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 892 | 0 | 0 | 0 | 0
__export__.project_task_4470_dae629e9 | Meetings Asfand | Sprint 2133 | 2021-08-09 | Client Meetings | Silverdale Time Tracking (P56) | Muhammad Afzaal | Asfand Yaar | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 899 | 7 | 7 | 0 | 66.9303
__export__.project_task_4116_fa699872 | Solutions Menu/submenus Migration | Sprint 2127 | 2021-06-28 | Development | DGS: Odoo Website Migration (P126) | Fahad Hussain Malik | Danish Hassan | 0.67 | 16.75 |  | SPLN | 1 | Complete | DG Solutions Inc. | 1973 | 4 | 3.33 | 0.70842 | 88.7084
__export__.project_task_4110_f5c16eb8 | Link Delivery orders with Sale order | Sprint 2127 | 2021-06-28 | Development | Wild Leaf: Help (P22) | Muhammad Zubair | Raheel Aslam | 3.42 | 42.75 |  | SPLN | 3 | Complete | Wild Leaf Beverage | 1973 | 8 | 4.58 | 0.00014735 | 56.1196
__export__.project_task_4108_378a86dc | One other Invoice format need to be created | Sprint 2129 | 2021-07-12 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Raheel Aslam | 17.17 | 85.85 |  | SPLN | 3 | Complete | Zuma Sales LLC | 1974 | 20 | 2.83 | 46.3533 | 137.7908
__export__.project_task_4075_0f110e20 | Cancel Order Testing |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 | Plan for sprint |  |  | Planning | Mountain Meadow Herbs | 2048 | 0.5 | 0.5 | 0 | 0
__export__.project_task_3930_a20305b3 | Upgrade Custom modules | Sprint 2126 | 2021-06-21 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 2.42 | 0 |  | Odoo Migration |  | Complete | Zuma Sales LLC | 2333 | 0 | -2.42 | 214.0831 | 62.767
__export__.project_task_3785_a55c2e8c | Added to Sign vendor queue | Sprint 2123 | 2021-05-31 | Development | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq | Danish Hassan | 2.75 | 100 |  |  | 1 | Complete | Perfect Golf Event | 2886 | 2.5 | -0.25 | 18.0504 | 137.3051
__export__.project_task_3678_bdc81beb | Add any unsubscribed contacts in Constant Contact to Odoo Blacklist | Sprint 2121 | 2021-05-17 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 0.17 | 68 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3069 | 0.25 | 0.08 | 0 | 6.7014
__export__.project_task_3482_bd7f9a90 | All outstanding receipts with correct Scheduled Dates |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.9908 | 453.7789
__export__.project_task_3480_66c68aed | Verify daily reconciliation process |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.9908 | 453.6975
__export__.project_task_3478_bfba9c97 | Upload trial balances | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 | Follow Up | 2017-09-01 |  | Backlog | Zuma Sales LLC | 3483 | 2 | 2 | 460.8568 | 0
Asfand
__export__.project_task_3231_8f865ed3 | Daily Meetings Mid America |  |  | Internal Time Tracking | Mid-America: Help (P37) | Levi Barnes |  | 1.42 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4186 | 0 | -1.42 | 0.026436 | 375.6162
__export__.project_task_3047_be94efd22 | Performance acceptance testing |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0.00033996 | 206.1934
__export__.project_task_2948_0ed279ef | R & D How do web based buyers get notifications? | Sprint 2136 | 2021-08-30 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Muhammad Bilal | 33.17 | 100 |  | SPLN | 3 | Complete | Cellpoint Corporation | 4531 | 30.1667 | -3.0033 | 904.0122 | 971.2411
__export__.project_task_2916_5b92a5d0 | Conduct a DILO exercise |  |  |  | DESIGN (P77) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 3.895e-06 | 1049.8058
__export__.project_task_2839_d5898d21 | Add Shipping Details to Customer Delivery Order | Sprint 2119 | 2021-05-03 | Development | Wild Leaf: IL2000 Integration (P40) | Jeff Gross | Fahad Hassan | 7.25 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4700 | 6 | -1.25 | 16 | 456
__export__.project_task_2775_007debac | Approved for Insurance | Sprint 2110 | 2021-03-01 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Danish Hassan | 3.42 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5059 | 3 | -0.42 | 104 | 191.1067
__export__.project_task_2766_5773e4c8 | cpbids bug fix support and cpbids test scripts and Android and IOS builds testing |  |  | Internal Time Tracking | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 9.5 | 100 |  |  |  | Complete | Cellpoint Corporation | 5076 | 8 | -1.5 | 0.0088878 | 150.7122
__export__.project_task_2745_8931b5f9 | price and total count | Sprint 2110 | 2021-02-22 | Development | Mid-America: Help (P37) | Levi Barnes | Muhammad Bilal | 9.92 | 99.2 |  |  |  | Complete | Mid-America Gardens, LLC | 5167 | 10 | 0.08 | 5.1638e-05 | 139.0395
__export__.project_task_2720_8f59a82b | Conflicts with CPBids Database | Sprint 2108 | 2021-02-08 | Other | Cellpoint: ecoATM API (P50) | Nick Foy | Muzher Siddique | 2.25 | 90 |  |  |  | Complete | Cellpoint Corporation | 5188 | 2.5 | 0.25 | 0 | 0
__export__.project_task_2415_ea2c8c5a | Planning : The Integration of Helcim Payment Gateway with Odoo | Sprint 2105 | 2021-01-25 | Development | Wild Leaf: Helcim Integration (P38) | Kaesi Lee | Wajahat Ali | 4 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5602 | 3.5 | -0.5 | 2.1929e-05 | 24.9109
__export__.project_task_2370_026f495d | Implement Helpdesk for tracking accounting requests/issues and resolution time | Sprint 2136 | 2021-08-30 | Configuration | Wild Leaf: Implement Helpdesk (P184) | Naseeb Razaq | Naseeb Razaq | 0 | 0 |  | SPLN |  | Complete | Wild Leaf Beverage | 5758 | 0 | 0 | 1118.3996 | 1310.901
__export__.project_task_2279_654d8a51 | MRP | Sprint 2118 | 2021-04-26 | Internal Training | Silverdale: Help (P12) | Faisal Huda Khan | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5910 | 0 | 0 | 0.023912 | 593.9942
__export__.project_task_2277_7004e403 | Project - Part 1 | Sprint 2113 | 2021-03-22 | Internal Training | Silverdale: Help (P12) | Faisal Huda Khan | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5910 | 0 | 0 | 0.046534 | 388.9215
__export__.project_task_2002_30e18fba | price lists |  |  | Configuration | KMI: Help (P41) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | KMI Zeolite | 6506 | 0 | 0 | 0 | 100.7431
__export__.project_task_1984_dfd1749b | Sales Specification Delivery Method for Manufacturing Orders |  |  | Configuration | Wild Leaf: Help (P22) | Jeff Gross |  | 0 | 100 |  |  |  | Cancelled | Wild Leaf Beverage | 6508 | 0.25 | -6.33 | 440 | 440
__export__.project_task_1833_a81e642a | Plan CPBids Transition 2051 | Sprint 2051 | 2020-12-14 | Configuration | Cellpoint CPBids: Help (P7) | Muzher Siddique | Wajahat Ali | 6.92 | 0 |  |  |  | Complete | Cellpoint Corporation | 6748 | 0 | -6.92 | 0 | 60.2934
__export__.project_task_1719_9b3e3fdf | Set-Up PWX Projects: Convert module V13 to V14 | Sprint 2050 | 2020-12-07 | Development | PWX: Help (P23) | Levi Barnes | Fahad Hassan | 4.08 | 100 |  |  |  | Complete | EquityTeam | 6874 | 4 | -0.08 | 0 | 115.6929
__export__.project_task_1564_0045e1bb | Portal User Creation: Incorrect Company Assigned | Sprint 2046 | 2020-11-09 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 7510 | 4 | 4 | 0 | 48
__export__.project_task_1350_ab9c60b0 | generate PDF catalogue of published commerce products | Sprint 2043 | 2020-10-19 | Development | Moln: Help (P16) | Kaesi Lee | Gadha Continuant | 20 | 100 |  |  |  | Complete | Moln Solutions, LLC | 8396 | 8 | -12 | 72 | 160.6736
__export__.project_task_1150_ae46cd9b | Website Specific Pricing | Sprint 29 | 2020-08-31 | Development | Moln: Help (P16) | Kaesi Lee |  | 1.5 | 37.5 |  |  |  | Complete | Moln Solutions, LLC | 9238 | 4 | 2.5 | 24 | 0
__export__.project_task_1031_cf515680 | Hide Number of Views | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_600_1c416053 | CPBids Outage | Sprint 25 | 2020-08-03 | Bug Fix | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10069 | 0 | 0 | 0 | 0
__export__.project_task_250_5d46872e | Number sequence for Product | Sprint 22 | 2020-07-12 | Development | Silverdale: Help: Contains Data (P11) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 10398 | 2 | 2 | 1.4602 | 0
__export__.project_task_184_2d3168c7 | Make Username/Buyer Unique | Sprint 27 | 2020-08-17 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10809 | 0 | 0 | 0 | 0
__export__.project_task_4708_db2b66e1 | Set up Tools - Trends and Actions Recommendation |  |  | Development | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Decide task type |  |  | New | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 0
__export__.project_task_4486_78c6453f | Project Audit Mechanism |  |  |  | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 892 | 0 | 0 | 0 | 0
__export__.project_task_4469_e08f648c | Asfand Helpdesk Buffer | Sprint 2133 | 2021-08-09 | Configuration | Silverdale Time Tracking (P56) | Muhammad Afzaal | Asfand Yaar | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 899 | 8 | 8 | 0 | 66.9328
__export__.project_task_4341_30ebd18c | Helpdesk Buffer | Sprint 2131 | 2021-07-26 | Configuration | Zuma: Help (P97) | Fahad Hussain Malik | Fahad Hussain Malik | 8 | 100 |  |  |  | Complete | Zuma Sales LLC | 1470 | 8 | 0 | 0 | 68.5652
__export__.project_task_4109_07880a8a | Bank Reconciliation Report fields Changes | Sprint 2127 | 2021-06-28 | Development | Wild Leaf: Help (P22) | Muhammad Zubair | Danish Hassan | 3.75 | 46.88 |  | SPLN | 1 | Complete | Wild Leaf Beverage | 1973 | 8 | 4.25 | 0 | 56.1533
__export__.project_task_4074_bae875d9 | Update Order Status of completed orders |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 | Plan for the sprint |  |  | Planning | Mountain Meadow Herbs | 2048 | 0.5 | 0.5 | 0 | 0
__export__.project_task_3928_031453a1 | Get the latest DB backup and custom code from existing server | Sprint 2123 | 2021-05-31 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  | Odoo.sh Migration |  | Complete | Zuma Sales LLC | 2333 | 0 | 0 | 214.2175 | 13.7128
__export__.project_task_3780_4303ed12 | Details to Graphics Designer at the Sign Vendor | Sprint 2123 | 2021-05-31 | Configuration | Perfect Golf: Odoo Implementation Phase 1 (P110) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Perfect Golf Event | 2886 | 0 | 0 | 18.0504 | 95.9851
__export__.project_task_3676_55d7f6d3 | Membership Menu/Page on Website | Sprint 2121 | 2021-05-17 | Configuration | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Danish Hassan | 0.75 | 50 |  |  | 1 | Complete | Port Gamble Sâ€™Klallam Foundation | 3072 | 1.5 | 0.75 | 0 | 32
__export__.project_task_3464_5b13f323 | Declare the new Odoo system live | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 | Declare Live | 2020-09-01 |  | Backlog | Zuma Sales LLC | 3483 | 2 | 2 | 461.1599 | 0
Fahad
Asfand
__export__.project_task_3433_601cb6c8 | Complete General Settings | Sprint 2128 | 2021-07-05 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 3 | 100 |  | SPLN |  | Complete | Zuma Sales LLC | 3484 | 3 | 0 | 461.2662 | 408.2754
__export__.project_task_3320_49cf389d | R&D cpbid modules not upgrading, remove front end changes | Sprint 2137 | 2021-09-06 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Kaleem Khan | 39.92 | 99.8 | If the work is remaining why its not moved to next sprint? | SPLN | 2 | Deployment | Cellpoint Corporation | 3866 | 40 | 0.08 | 748.0103 | 0
PR
__export__.project_task_3046_be94efd21 | Set up by client success team w/users and e-learning module |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0.00033996 | 206.1934
__export__.project_task_2915_72b4f680 | Run the MOS workshop |  |  |  | DESIGN (P77) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1049.8068
__export__.project_task_2706_70e13097 | Set consolidation module (not urgent) |  |  | Configuration | Wild Leaf: Help (P22) | Muhammad Zubair |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 5324 | 0 | 0 | 686.6139 | 832
__export__.project_task_2671_2ee77532 | Fw: Employee, Recruitment, Application record views updated |  |  | Internal Time Tracking | PWX: HR (P61) | Levi Barnes | Levi Barnes | 5.5 | 0 |  |  |  | Complete | EquityTeam | 5353 | 0 | -5.5 | 0 | 136
__export__.project_task_2406_c6286aac | Remove Hardcoded Continuant Credentials |  |  | Bug Fix | Continuant: Quotation Management / Automation (P31) | Jeff Gross | Muzher Siddique | 1 | 0 |  | Security |  | Complete | Continuant | 5666 | 0 | -1 | 240 | 240
__export__.project_task_2383_aee8a91c | computed filter | Sprint 2119 | 2021-05-03 | Development | Silverdale: Help (P12) | Nick Foy | Raheel Aslam | 4.92 | 100 |  |  | 4 | Cancelled | Silverdale Technology LLC | 5738 | 3.4167 | -1.5033 | 0 | 552
__export__.project_task_2124_7aa9043f | FW: Driving barcodes to our applicators |  |  | Configuration | Wild Leaf: Help (P22) | Jeff Gross |  | 0 | 0 |  | 2018-01-01 |  | Complete | Wild Leaf Beverage | 6074 | 0 | 0 | 344 | 648
__export__.project_task_2027_2065842c | Studio Training |  |  | Studio | Wild Leaf: Help (P22) | Jeff Gross | Nick Foy | 0.25 | 100 |  |  |  | Cancelled | Wild Leaf Beverage | 6408 | 0.25 | 0 | 424 | 424
__export__.project_task_1997_527f7609 | Warehouses |  |  | Configuration | KMI: Help (P41) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | KMI Zeolite | 6506 | 0 | 0 | 0 | 56
__export__.project_task_1834_16beb75d | CPBids Transition 2052 | Sprint 2052 | 2020-12-21 | Configuration | Cellpoint CPBids: Help (P7) | Muzher Siddique | Wajahat Ali | 6.5 | 0 |  |  |  | Complete | Cellpoint Corporation | 6748 | 0 | -6.5 | 0 | 94.3596
__export__.project_task_1687_7b8852d6 | chatter default minimized | Sprint 2050 | 2020-12-07 | Development | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 1.5 | 100 |  |  |  | Complete | EquityTeam | 6916 | 2 | -3.67 | 0 | 126.7313
__export__.project_task_1599_ab21c844 | Change comments field to HTML | Sprint 2048 | 2020-11-23 | Configuration | PWX: Help (P23) | Levi Barnes |  | 0.33 | 0 |  |  |  | Complete | EquityTeam | 7350 | 0 | -0.33 | 0 | 129.505
__export__.project_task_1523_a7303ad2 | Appraisals / Company Settings Part 2 | Sprint 2047 | 2020-11-16 | Development | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 9.92 | 99.2 |  |  |  | Complete | EquityTeam | 7678 | 10 | 0.08 | 16 | 175.4111
__export__.project_task_1398_0890bb3e | Set-Up Tasks | Sprint 2042 | 2020-10-12 | Configuration | Wild Leaf: Help (P22) | Nick Foy |  | 0.5 | 25 |  |  |  | Complete | Wild Leaf Beverage | 8187 | 2 | 1.5 | 0 | 86.0731
__export__.project_task_1046_23758457 | Update Manifest Button is not working | Sprint 27 | 2020-08-17 | Development | CPBids Migration AWS->odoo (P5) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 25.6833 | 0
__export__.project_task_1032_d0477a01 | Hide Current Bid | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_831_dfcaa8ce | Update terms and conditions iOS-Implementation | Sprint 2046 | 2020-11-09 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 5 | 100 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | -4 | 435.2516 | 675.2516
iOS
3.0.2
__export__.project_task_587_2eac532b | New Update Available Alert Error | Sprint 25 | 2020-08-03 | Bug Fix | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10080 | 0 | 0 | 80 | 0
__export__.project_task_265_f38c281f | Auction Link Field in Pricing Grid | Sprint 22 | 2020-07-12 | Development | Silverdale: Help: Contains Data (P11) | Deepak Krishnan |  | 0 | 0 |  | Need Assistance |  | Complete | Silverdale Technology LLC | 10297 | 0.33333 | 0.33333 | 8 | 0
__export__.project_task_193_2df82dcd | Email Server Setup - CPBids.com | Sprint 27 | 2020-08-17 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10806 | 0 | 0 | 0 | 0
__export__.project_task_167_487dc95a | Test Scripts | Sprint 27 | 2020-08-17 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 0
__export__.project_task_4707_63939ed4 | Set up Tools - Critical Functions Automation |  |  | Development | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | New | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 0
__export__.project_task_4488_f2240820 | Tickets Response Mechanism |  |  |  | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 892 | 0 | 0 | 0 | 0
__export__.project_task_4468_9fcfeec9 | Trainings | Sprint 2133 | 2021-08-09 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 899 | 20 | 20 | 0.013369 | 41.7784
__export__.project_task_4340_8f5ade60 | Task Creation, Project Closure, PM Review | Sprint 2131 | 2021-07-26 | Configuration | Zuma: Help (P97) | Fahad Hussain Malik | Fahad Hussain Malik | 10 | 100 |  |  |  | Complete | Zuma Sales LLC | 1470 | 10 | 0 | 0 | 68.6355
__export__.project_task_4299_4761d407 | Auction import format | Sprint 2135 | 2021-08-23 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Kaleem Khan | 5.17 | 100 |  | SPLN | 1 | Complete | Cellpoint Corporation | 1545 | 5 | -0.17 | 224.0075 | 261.4244
__export__.project_task_4130_3e48da93 | Odoo website Migration (QA) | Sprint 2127 | 2021-06-28 | Development | DGS: Odoo Website Migration (P126) | Fahad Hussain Malik | Danish Hassan | 1.83 | 11.44 |  | SADL | 2 | Complete | DG Solutions Inc. | 1883 | 16 | 14.17 | 1.4642 | 78.1964
__export__.project_task_4117_e8ff7d5f | Industries Pages Migration | Sprint 2127 | 2021-06-28 | Development | DGS: Odoo Website Migration (P126) | Fahad Hussain Malik | Danish Hassan | 6.5 | 40.62 |  | SPLN | 2 | Complete | DG Solutions Inc. | 1973 | 16 | 9.5 | 0.69665 | 88.6966
__export__.project_task_4094_a6464946 | Validate Delivery Order, Delivery Report and the Diglist | Sprint 2128 | 2021-07-05 | Development | Mid-America: Help (P37) | Naseeb Razaq | Raheel Aslam | 9.5 | 59.38 |  | SPLN | 2 | Complete | Mid-America Gardens, LLC | 2017 | 16 | 6.5 | 0 | 136
__export__.project_task_4073_8ba3e4b9 | Publish or Unpublish Products to WooCommerce Store from Odoo |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 | Plan for the sprint |  |  | Planning | Mountain Meadow Herbs | 2048 | 0.5 | 0.5 | 0 | 0
__export__.project_task_3687_0772d0ef | Create a sequential number field for product barcode field | Sprint 2123 | 2021-05-31 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Raheel Aslam | 7.67 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 3005 | 6 | -1.67 | 133.5475 | 133.3064
__export__.project_task_3671_d0e0d267 | Product prices inadvertently changing when in edit mode | Sprint 2121 | 2021-05-17 | Development | Wild Leaf: Help (P22) | Muhammad Afzaal | Danish Hassan | 5.53 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 3133 | 4.5 | -1.03 | 0 | 40
__export__.project_task_3431_a18563a2 | Set up the users in the new system (Anyone who isn't already in Odoo) |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.2774 | 440.2868
__export__.project_task_3363_bd03bdbb | Analyse the code quality in custom modules | Sprint 2133 | 2021-08-09 | Improvements | MMH: Odoo Audit (P100) | Naseeb Razaq | Muhammad Bilal | 15.58 | 97.38 |  | SPLN | 4 | Complete | Mountain Meadow Herbs | 3647 | 16 | 0.42 | 497.7326 | 679.1609
__export__.project_task_3223_a5594e68 | Fix the Manifest Pop-up and use modal form with scroll bars | Sprint 2118 | 2021-04-26 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 6.92 | 100 |  |  | 2 | Complete | Cellpoint Corporation | 4206 | 4 | -2.92 | 0 | 258.0839
__export__.project_task_3045_be94efd20 | Define contingency strategy, staff and procedures |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0.00033996 | 206.1934
__export__.project_task_2913_5f7a5ff3 | Create a gap-fit analysis repository |  |  |  | DESIGN (P77) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1049.8089
__export__.project_task_2874_fa1b9353 | Apple Push Notification service (APNs) provider API | Sprint 2113 | 2021-03-22 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 5.17 | 0 |  |  |  | Complete | Cellpoint Corporation | 4590 | 0 | -5.17 | 0.00012027 | 111.3735
__export__.project_task_2668_c4ccb598 | Fw: How do we route credit card transactions to 3 separate projects | Sprint 2108 | 2021-02-08 | Configuration | PWX: Help (P23) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | EquityTeam | 5353 | 0 | 0 | 0 | 7.9106
__export__.project_task_2390_4dc33ce1 | Android and IOS builds for cpbids | Sprint 2105 | 2021-01-25 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 4.33 | 0 |  |  |  | Complete | Cellpoint Corporation | 5719 | 0 | -4.33 | 0.0020179 | 51.2159
__export__.project_task_2257_b8b00dae | employee bug |  |  | Bug Fix | Silverdale: Help (P12) | Nick Foy | Wajahat Ali | 2.33 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5924 | 0 | -2.33 | 0 | 312
__export__.project_task_1982_877d94ba | Add Total Weight to SO Form | Sprint 2052 | 2020-12-21 | Development | KMI: Help (P41) | Levi Barnes | Muzher Siddique | 0.92 | 30.67 |  |  |  | Complete | KMI Zeolite | 6518 | 3 | 2.08 | 0 | 108.7525
__export__.project_task_1730_868fc3c5 | odoo.sh setup | Sprint 2049 | 2020-11-30 | Configuration | Heronswood: Events (P3) | Muhammad Afzaal | Wajahat Ali | 0.83 | 83 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 6870 | 1 | 0.17 | 0 | 25.3667
__export__.project_task_1718_c5b2ff0c | R2 Buyer Group for Super Selections | Sprint 2053 | 2020-12-28 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 7.83 | 100 |  |  |  | Complete | Cellpoint Corporation | 6886 | 6 | -1.83 | 0 | 236
__export__.project_task_1704_6b37b726 | Set-Up Manufacturing for Pallet Break Down Process |  |  | Configuration | Wild Leaf: Help (P22) | Jeff Gross | Nick Foy | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6894 | 0 | 0 | 538.309 | 810.309
__export__.project_task_1622_a0fbc6b2 | New Seller Onboarding: EcoATM: Technical Set-Up | Sprint 2048 | 2020-11-23 | Configuration | CPBids: ecoATM Onboarding (P35) | Nick Foy | Raheel Aslam | 2.83 | 99.88 |  |  |  | Complete | Cellpoint Corporation | 7223 | 2.8333 | 0.0033333 | 0 | 104
__export__.project_task_1593_5c0e9ae3 | Intake form | Sprint 2047 | 2020-11-16 | Development | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 10.08 | 100 |  |  |  | Complete | EquityTeam | 7388 | 7 | -3.08 | 0 | 111.4144
__export__.project_task_1438_6541dcd0 | update email |  |  | Studio | Moln: Help (P16) |  |  | 0.25 | 0 |  |  |  | Complete | Moln Solutions, LLC | 8019 | 0 | -0.25 | 0 | 39.1072
__export__.project_task_1429_f73f251b | Remove Pagination from Web Bidding | Sprint 2046 | 2020-11-09 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Shajahan | 4 | 100 |  |  |  | Complete | Cellpoint Corporation | 8024 | 3 | -1 | 0 | 212
__export__.project_task_1103_4ed6ca72 | Number of Bidders not populated | Sprint 27 | 2020-08-17 | Bug Fix | CPBids Migration AWS->odoo (P5) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9506 | 0 | 0 | 36 | 0
__export__.project_task_1034_e65d18e8 | Re-label "Finished" with "Completed" | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_947_790f03a7 | Upgrade AWS - 3+ Tier | Sprint 25 | 2020-08-03 | Configuration | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9748 | 0 | 0 | 0.022703 | 0
__export__.project_task_233_642e3753 | Corrections in Marketplace | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10478 | 0 | 0 | 27.6631 | 0
__export__.project_task_157_2da8cc80 | 1.6.1 Select Tag(1 hour) | Sprint 27 | 2020-08-17 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 0
__export__.project_task_4706_3827a1a3 | Set up Tools - Ticket Types TAT Automation - Notifications - Internal and External |  |  | Development | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | New | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 0
__export__.project_task_4510_db5ccb1d | Hiring Mechanism |  |  | Improvements | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 869 | 0 | 0 | 0 | 0
__export__.project_task_4467_9e5cc1c0 | PM Review, Internal Discussions | Sprint 2133 | 2021-08-09 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 3 | 60 |  |  |  | Complete | Zuma Sales LLC | 900 | 5 | 2 | 0 | 42.3867
__export__.project_task_4338_b416ddbf | Zuma daily standup + Requirement Gathering +Trainings | Sprint 2131 | 2021-07-26 | Configuration | Zuma: Help (P97) | Fahad Hussain Malik | Fahad Hussain Malik | 16 | 88.89 |  |  |  | Complete | Zuma Sales LLC | 1470 | 18 | 2 | 0 | 69.1374
__export__.project_task_4305_85895473 | Watchlist added on mobile should also be added on web | Sprint 2134 | 2021-08-16 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Kaleem Khan | 11.67 | 100 |  | SPLN | 2 | Complete | Cellpoint Corporation | 1536 | 8 | -3.67 | 219.3092 | 256.7267
__export__.project_task_4119_85b94faf | Terex Purchase Orders |  |  | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 1969 | 0 | 0 | 125.0081 | 36.1114
__export__.project_task_4072_d420b1a0 | Update Product Price, Stock levels & Images (From Odoo to Woocommerce) |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 | Plan for the sprint |  |  | Planning | Mountain Meadow Herbs | 2048 | 2 | 2 | 0 | 0
__export__.project_task_3677_9e2cd703 | Add DN with the SO as SO0001-DN0001 | Sprint 2120 | 2021-05-10 | Development | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Raheel Aslam | 3.58 | 100 |  |  | 3 | Complete | Port Gamble Sâ€™Klallam Foundation | 3072 | 2 | -1.58 | 0 | 40
__export__.project_task_3667_3a1211a8 | Install Plugin from Dr. Clark IT partner | Sprint 2121 | 2021-05-17 | Other | MMH Dr. Clark: Help (P106) | Naseeb Razaq | Muhammad Bilal | 1.08 | 32.4 |  |  | 2 | Complete | Mountain Meadow Herbs | 3144 | 3.3333 | 2.2533 | 0 | 123.0697
__export__.project_task_3477_3ddad032 | Post and Reconcile all outstanding journal entries |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.9908 | 520.0192
__export__.project_task_3427_fb9c0c12 | Install the correct modules for zuma |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.3045 | 412.3139
__export__.project_task_3044_be94efd19 | Ensure reporting formats are correctly setup |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0.00033996 | 206.1934
__export__.project_task_2910_aa985949 | Create a list of processes |  |  |  | DESIGN (P77) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1049.812
__export__.project_task_2346_0706be8c | Internal: Project UX Review |  |  | Configuration | Dialed Supply: Help (P21) | Levi Barnes |  | 0.42 | 0 |  |  |  | Complete | Dialed Supply | 5809 | 0 | -18.16 | 0 | 254.0214
__export__.project_task_2323_2983cf8c | Update Requirements and Scope |  |  | Configuration | Wild Leaf: Vendor Portal - Phase 1 (P49) | Jeff Gross | Naseeb Razaq | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 5860 | 0 | 0 | 288 | 288
__export__.project_task_2311_676b2ce7 | Add Production Location (Warehouse) to the Invoice | Sprint 2108 | 2021-02-08 | Development | Wild Leaf: Help (P22) | Nick Foy | Danish Hassan | 8.75 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5877 | 3 | -5.75 | 104 | 278.4142
__export__.project_task_2266_7bc00da1 | Fahad Functional Intern Plan |  |  | Internal Training | Silverdale: Help (P12) | Nick Foy | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5910 | 0 | 0 | 6.7695 | 594.1473
__export__.project_task_2218_9afb16e3 | Change Company of Work Times to OpCo (There should be unique Work Times for each warehouse location) | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy |  | 0.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5998 | 0 | -0.25 | 0 | 90.9636
__export__.project_task_2020_3e032d2d | Import this CSV as Tasks into "3.0.Ops.Tasks" | Sprint 2053 | 2020-12-28 | Configuration | PWX: Help (P23) | Levi Barnes | Danish Hassan | 4.83 | 96.6 |  |  |  | Complete | EquityTeam | 6434 | 5 | 0.17 | 0 | 132
__export__.project_task_1995_4d3e1604 | Customer, Vendor, Product Data |  |  | Configuration | KMI: Help (P41) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | KMI Zeolite | 6506 | 0 | 0 | 0 | 100.7731
__export__.project_task_1740_fec14eed | QA of production builds. | Sprint 2049 | 2020-11-30 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 6854 | 0 | 0 | 0 | 7.1758
__export__.project_task_1729_df61e484 | Github Setup | Sprint 2049 | 2020-11-30 | Configuration | Heronswood: Events (P3) | Muhammad Afzaal | Wajahat Ali | 2.42 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 6870 | 1 | -1.42 | 0 | 25.3827
__export__.project_task_1667_a01a6e2b | In Android Price showing in decimal on Watchlist screen | Sprint 2048 | 2020-11-23 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 1.83 | 0 |  | 3.0.5 |  | Complete | Cellpoint Corporation | 7047 | 0 | -1.83 | 0 | 64
__export__.project_task_1125_9c20d22d | Back End Changes - 1 | Sprint 28 | 2020-08-24 | Development | CPBids Migration AWS->odoo (P5) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9423 | 0 | 0 | 24 | 0
__export__.project_task_1102_d2963bdf | Highest Bid not populated | Sprint 27 | 2020-08-17 | Bug Fix | CPBids Migration AWS->odoo (P5) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9506 | 0 | 0 | 36 | 0
__export__.project_task_1029_0d692f0f | Add End Date TIme | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_899_ed51299a | Update terms and conditions Android-Implementation | Sprint 2046 | 2020-11-09 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 5 | 100 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | -4 | 443.2418 | 675.2418
Android
__export__.project_task_285_869ff6e5 | Remove Export options - Seller | Sprint 23 | 2020-07-20 | Development | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10253 | 1 | 1 | 31.9574 | 0
__export__.project_task_239_f9f0d884 | Filters selection consistent | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10477 | 0 | 0 | 40 | 0
__export__.project_task_183_b6a53639 | Duplicate Notifications on iOS | Sprint 27 | 2020-08-17 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10809 | 0 | 0 | 0 | 0
__export__.project_task_4827_256d1f65 | Set up sales quote template for parts | Sprint 2137 | 2021-09-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  | 2021-10-09 |  | Complete | Zuma Sales LLC | 171 | 1 | 1 | 0 | 18.6796
Meeting w/Bonnie
Asfand
__export__.project_task_4704_20bb5aa0 | Set up Tools - Automated Ticket Responses |  |  | Development | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | New | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 0
__export__.project_task_4557_9c0e291f | Import open AR and AP (be sure to include a reference allowing you to find the document when you need to apply payment and do not add a product to the Invoice or Bill line) using the suspense account as the counterpart so the summary balance is cleared when all Invoices and Bills are imported. | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.5 | 33.33 | Follow Up | 2017-09-01 |  | Backlog | Zuma Sales LLC | 799 | 1.5 | 1 | 0 | 0
Asfand
__export__.project_task_4511_b8fcdf17 | Training Mechanism |  |  | Improvements | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 869 | 0 | 0 | 0 | 0
__export__.project_task_4466_81bf1c82 | eBay, Amazon and Shopify Integration | Sprint 2133 | 2021-08-09 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 6 | 42.86 |  |  |  | Complete | Zuma Sales LLC | 900 | 14 | 8 | 0 | 42.4338
__export__.project_task_4335_48dffc2d | Hide checkout and cart functions for buyers | Sprint 2135 | 2021-08-23 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Kaleem Khan | 5.92 | 84.57 |  | SPLN | 2 | Complete | Cellpoint Corporation | 1471 | 7 | 1.08 | 200.0056 | 245.4211
__export__.project_task_4313_902a35e9 | Install eLearning third party module | Sprint 2129 | 2021-07-12 | Deployment | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Wajahat Ali | 2 | 0 |  | SPLN |  | Complete | Zuma Sales LLC | 1489 | 0 | -2 | 0 | 52.0192
__export__.project_task_4098_a64de4fa | Shift Tracker discussion |  |  | Other | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 1992 | 0 | 0 | 0 | 78.5717
__export__.project_task_4071_4b30b2ca | Create, export & update Product Categories, Tags & Coupons (From Odoo to Woocommerce) |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 | Plan for the sprint |  |  | Planning | Mountain Meadow Herbs | 2048 | 2 | 2 | 0 | 0
__export__.project_task_3663_9ef922ce | Add mark-up to accepted quote | Sprint 2121 | 2021-05-17 | Development | Wild Leaf: June Close Out Plan (P121) | Muhammad Zubair | Fahad Hassan | 19.97 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 3150 | 8 | -11.97 | 151.3593 | 81.8118
__export__.project_task_3476_fceff3ac | Upload all open purchase orders (and scrub before entry) |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.9908 | 520.0192
__export__.project_task_3201_9ec13343 | Understanding of Working Flow of Existing Shipping Method in Odoo | Sprint 2116 | 2021-04-12 | Development | Wild Leaf: IL2000 Integration (P40) | Jeff Gross | Fahad Hassan | 8.5 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4256 | 8 | -0.5 | 0 | 155.7852
__export__.project_task_3043_be94efd18 | Ensure mail servers are properly setup |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0.00033996 | 206.1934
__export__.project_task_3040_5b99aadc | Demo: Check Run |  |  | Demo to the client | Wild Leaf: Accounting (P64) | Jeff Gross | Bilal Ahmad Khan | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4367 | 0 | 0 | 0 | 208
__export__.project_task_3039_30ec0340 | QA deployment - critcal | Sprint 2117 | 2021-04-19 | Other | Silverdale: Devops (P84) | Levi Barnes | Levi Barnes | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4367 | 0 | 0 | 0 | 184
__export__.project_task_2896_8550ee4f | Send Deliverables to Client |  |  |  | DISCOVERY (P76) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1050.1229
__export__.project_task_2731_67a6c8ad | Employee: Other | Sprint 2109 | 2021-02-15 | Development | PWX: HR (P61) | Levi Barnes | Danish Hassan | 2.5 | 100 |  |  |  | Complete | EquityTeam | 5182 | 2.5 | 0 | 0 | 110.4894
__export__.project_task_2646_d02863ec | Deployment 2104: CPBids | Sprint 2105 | 2021-01-25 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 1 | 100 |  |  |  | Complete | Cellpoint Corporation | 5408 | 1 | 0 | 0 | 0.0086111
__export__.project_task_2211_0c0ce252 | Move Open Purchase orders | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy |  | 2 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5998 | 0 | -2 | 0 | 90.965
__export__.project_task_2171_9fbbfce9 | Export all error | Sprint 2103 | 2021-01-11 | Bug Fix | KMI: Help (P41) | Levi Barnes | Muzher Siddique | 0.83 | 99.6 |  | Difficulty 3 |  | Complete | KMI Zeolite | 6024 | 0.83333 | 0.0033333 | 0 | 120
__export__.project_task_2166_775cc56d | Display Components on Work Orders | Sprint 2108 | 2021-02-08 | Development | Wild Leaf: Help (P22) | Nick Foy | Raheel Aslam | 1.08 | 36 |  |  |  | Complete | Wild Leaf Beverage | 6029 | 3 | 1.92 | 136.357 | 229.6781
__export__.project_task_1892_df56cda0 | Deployment of cpbid's tasks On production | Sprint 2051 | 2020-12-14 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 0.5 | 50 |  |  |  | Complete | Cellpoint Corporation | 6581 | 1 | 0.5 | 0.016068 | 1.3363
__export__.project_task_1486_2ed360ee | Display Error: Auction Lot HCUKB | Sprint 2047 | 2020-11-16 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 6 | 100 |  |  |  | Complete | Cellpoint Corporation | 7895 | 4 | -2 | 0 | 174.1836
__export__.project_task_1267_8bd9d571 | Automate Belmont Emails | Sprint 2053 | 2020-12-28 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 11.17 | 100 |  |  |  | Complete | Cellpoint Corporation | 8591 | 9 | -26.95 | 88 | 644
__export__.project_task_1104_1f818159 | Add menu for "Bids" | Sprint 27 | 2020-08-17 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9506 | 0 | 0 | 0 | 0
__export__.project_task_1055_f684b139 | Investigate Extend Upto Field and Function | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_1047_9a99ea30 | Lot Pictures: Remove "Shop" Header | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_574_5ed444d4 | Release Noted - 2.109 | Sprint 23 | 2020-07-20 | Development | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10147 | 0 | 0 | 10.3294 | 0
__export__.project_task_287_ff471d8d | Broad Cast Message -Issue | Sprint 22 | 2020-07-12 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10252 | 0 | 0 | 16.1153 | 0
__export__.project_task_217_2746b701 | Buyer Registration | Sprint 27 | 2020-08-17 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Sprint 20 |  | Complete | Cellpoint Corporation | 10747 | 0 | 0 | 0 | 0
__export__.project_task_146_95fdf235 | 5, BroadCast Notification(4 hours) | Sprint 2046 | 2020-11-09 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 4 | 80 |  |  |  | Complete | Cellpoint Corporation | 11570 | 5 | 1 | 0 | 1056
__export__.project_task_145_bf45a230 | 2. All Buyers | Sprint 28 | 2020-08-24 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 0
__export__.project_task_4831_c1e68d43 | Bank Reconciliation Training | Sprint 2137 | 2021-09-06 | Client Meetings | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 1 | 100 |  | 2021-10-09 |  | Complete | Zuma Sales LLC | 170 | 1 | 0 | 3.2144e-05 | 18.2661
Meeting w/Bonnie
Asfand
__export__.project_task_4703_bfadd9da | Set up Tools - Audit Dashboard and KPIs |  |  | Configuration | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | New | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 0
__export__.project_task_4484_1dd6e38a | Project Handling Mechanism |  |  |  | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 892 | 0 | 0 | 0 | 0
__export__.project_task_4465_d8c3d821 | Helpdesk Buffer | Sprint 2133 | 2021-08-09 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 900 | 8 | 8 | 0 | 66.9356
__export__.project_task_4312_d1cbc80d | Set-up SMTP2GO for their outbound email server | Sprint 2131 | 2021-07-26 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 1 | 100 |  | SPLN |  | Complete | Zuma Sales LLC | 1496 | 1 | 0 | 0.0097321 | 82.3225
__export__.project_task_4070_f143302c | Export & Update Products |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 | plan for the sprint |  |  | Planning | Mountain Meadow Herbs | 2048 | 2 | 2 | 0 | 0
__export__.project_task_4045_a163a379 | Shopify Connection | Sprint 2132 | 2021-08-02 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 13.75 | 100 |  | SPLN |  | Complete | Zuma Sales LLC | 2137 | 10 | -3.75 | 165.0078 | 312.0192
__export__.project_task_3672_771b00e9 | Add a â€œPackaging Dateâ€ when the manufacturing order is marked as Done | Sprint 2121 | 2021-05-17 | Development | Wild Leaf: Consignment and Sales Improvements (P112) | Muhammad Afzaal | Muhammad Bilal | 10.5 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 3075 | 3 | -7.5 | 0 | 72
__export__.project_task_3569_334e9c64 | Cutover time tracking |  |  | Internal Time Tracking | Wild Leaf: Accounting (P64) | Muhammad Afzaal |  | 11 | 0 |  |  |  | Complete | Wild Leaf Beverage | 3261 | 0 | -11 | 0 | 205.6092
__export__.project_task_3475_4c87062e | Upload all open sales orders (and scrub before entry) |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.9908 | 520.0192
__export__.project_task_3423_dbe55867 | Any merger of accounts required? Specifically for customers and vendors |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.3323 | 454.054
__export__.project_task_3277_90efa0a7 | TDD e-learning |  |  | Configuration | Silverdale: Devops (P84) | Muzher Siddique |  | 0 | 0 | Please add next activity |  |  | Backlog | Silverdale Technology LLC | 4035 | 8 | 8 | 860.9121 | 0
__export__.project_task_3042_be94efd17 | Ensure proper setup of companies, accounting part, languages, banks and currencies etc |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0.00033996 | 206.1934
__export__.project_task_3030_6ef85327 | General Time | Sprint 2118 | 2021-04-26 | Other | Mid-America: Help (P37) | Levi Barnes |  | 8.33 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4394 | 0 | -8.33 | 0 | 216
__export__.project_task_2894_4d751951 | Hold Kick-Off Session |  |  |  | DISCOVERY (P76) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1050.1277
__export__.project_task_2817_47132dc7 | Create csv file for "Returned" | Sprint 2135 | 2021-08-23 | Development | Cellpoint: ecoATM API (P50) | Farman Ahmad Cheema | Fahad Hassan | 4.58 | 100 |  | SPLN | 2 | ELS | Cellpoint Corporation | 4758 | 4.5 | -0.08 | 968 | 0
__export__.project_task_2420_12518cee | Analytic Accounts Setup and Configuration | Sprint 2105 | 2021-01-25 | Configuration | Wild Leaf: Help (P22) | Nick Foy | Nick Foy | 0.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5591 | 0 | -0.5 | 40 | 214.1022
__export__.project_task_2274_585a0c77 | Accounting - Part 2 |  |  | Internal Training | Silverdale: Help (P12) | Faisal Huda Khan | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5910 | 0 | 0 | 0.077595 | 594.0423
__export__.project_task_2066_a23f1bba | Update the Product/Vendor list for all Sleeves to vendor Quality Tape and Label | Sprint 2103 | 2021-01-11 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Kaesi Lee | 1 | 100 |  | 2013-01-01 |  | Complete | Wild Leaf Beverage | 6220 | 0.5 | -0.5 | 0 | 80
__export__.project_task_2054_779aa820 | Add field is_freight_vendor in Contact form | Sprint 2053 | 2020-12-28 | Development | KMI: Help (P41) | Levi Barnes | Muzher Siddique | 0.25 | 25 |  |  |  | Complete | KMI Zeolite | 6248 | 1 | 0.75 | 0 | 87.4863
__export__.project_task_1641_f07d7621 | URGENT: gucci not able to place orders | Sprint 2048 | 2020-11-23 | Bug Fix | Moln: Help (P16) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Moln Solutions, LLC | 7106 | 0 | 0 | 0 | 80
__export__.project_task_1610_c91ad9db | 10X bid restriction for web | Sprint 2047 | 2020-11-16 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 6 | 0 |  | P1 |  | Complete | Cellpoint Corporation | 7258 | 0 | -6 | 0 | 84.6691
__export__.project_task_1028_17608e83 | Add Start Time | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_565_1426a46e | API:Scan Qr Code | Sprint 2046 | 2020-11-09 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 5 | 5 | 69.8778 | 728
3.0.3
__export__.project_task_263_902533a3 | Select All Buyers | Sprint 22 | 2020-07-12 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10308 | 0 | 0 | 35.0027 | 0
__export__.project_task_219_ed59a8a0 | Test Scripts - Sprint 20 | Sprint 27 | 2020-08-17 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Sprint 20 |  | Complete | Cellpoint Corporation | 10735 | 0 | 0 | 0 | 0
__export__.project_task_4825_a83f28f4 | Set up test bank account for Bonnie | Sprint 2138 | 2021-09-13 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 | Get credentials from Bonnie | 2015-09-01 |  | Backlog | Zuma Sales LLC | 171 | 1 | 1 | 0 | 0
This task missed the deadline!
Your task missed the deadline!
Meeting w/Bonnie
__export__.project_task_4702_1ee05c18 | Set up Tools - Team Dashboard and Alerts |  |  | Configuration | Silverdale Cares 24/7 (P188) | Muhammad Zubair |  | 0 | 0 | Please add next activity | Dashboard |  | New | Silverdale Technology LLC | 391 | 0 | 0 | 0 | 0
__export__.project_task_4482_c19b09fb | Audit Projects Mechanism |  |  | Improvements | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 892 | 0 | 0 | 0 | 0
__export__.project_task_4464_04fec817 | Fahad Meetings | Sprint 2133 | 2021-08-09 | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 900 | 11 | 11 | 0 | 52.5542
__export__.project_task_4308_feea578d | Zuma Sales Meeting |  |  | Internal Time Tracking | Zuma: Help (P97) | Fahad Hussain Malik |  | 13.58 | 0 |  |  |  | Complete | Zuma Sales LLC | 1512 | 0 | -13.58 | 0 | 235.2011
__export__.project_task_4069_79c5669d | Connect Sales order |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 | Plan for the sprint |  |  | Planning | Mountain Meadow Herbs | 2048 | 2 | 2 | 0 | 0
__export__.project_task_4008_b9aa1d82 | WhatsApp Connector | Sprint 2128 | 2021-07-05 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hassan | 2.5 | 83.33 |  | SPLN | 1 | Complete | Zuma Sales LLC | 2189 | 3 | 0.5 | 182.1187 | 161.1553
__export__.project_task_3919_dc284331 | Advance Filter Search | Sprint 2128 | 2021-07-05 | Development | Wild Leaf: Help (P22) | Muhammad Afzaal |  | 3.5 | 100 |  | SPLN | 1 | Complete | Wild Leaf Beverage | 2354 | 2 | -1.5 | 0 | 200
__export__.project_task_3891_fe927b5c | MM Herbs: Re-ordering rules only triggering for finished goods | Sprint 2125 | 2021-06-14 | Configuration | MMH: Help (P83) | Naseeb Razaq |  | 5.25 | 100 |  |  |  | Complete | Mountain Meadow Herbs | 2478 | 5 | -0.25 | 0 | 69.5851
__export__.project_task_3574_9619cfec | In the Calendar of MOs, Only scheduled end date should be reflected | Sprint 2121 | 2021-05-17 | Development | Wild Leaf: Help (P22) | Muhammad Afzaal | Fahad Hassan | 14.17 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 3240 | 10 | -4.17 | 0 | 112
__export__.project_task_3568_23ff5049 | Daily Tasks and Tickets Meeting |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Muzher Siddique | 4.83 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3309 | 0 | -4.83 | 0 | 72
__export__.project_task_3474_8b557a60 | Reconcile loans and set amortization |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.9908 | 520.0192
__export__.project_task_3261_3659a4eb | Planned Hours Logged |  |  | Development | Silverdale: Help (P12) | Muhammad Afzaal | Danish Hassan | 7.17 | 100 |  |  |  | Complete | Silverdale Technology LLC | 4085 | 6.5 | -0.67 | 168.8082 | 216.8082
__export__.project_task_3041_be94efd16 | Ensure automated actions are running fine |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0.00033996 | 206.1934
__export__.project_task_2891_f3e809d5 | Prepare Kick-off deliverable doc |  |  |  | DISCOVERY (P76) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1050.1452
__export__.project_task_2869_1a05ddc9 | Changes to Traveller SHIPPING_CHARGE field | Sprint 2135 | 2021-08-23 | Development | Cellpoint: ecoATM API (P50) | Farman Ahmad Cheema | Fahad Hassan | 9.58 | 100 |  | SPLN | 2 | ELS | Cellpoint Corporation | 4655 | 9.5 | -0.08 | 931.0579 | 0
__export__.project_task_2656_8b152057 | Ground Truthing Report |  |  | Bug Fix | Heronswood: Help (P54) | Jeff Gross | Raheel Aslam | 4.67 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 5379 | 0 | -4.67 | 176 | 176
__export__.project_task_2321_78992520 | Calendar event invite error: links still getting internal errors |  |  | Bug Fix | KMI: Help (P41) | Levi Barnes | Muzher Siddique | 0 | 0 |  |  |  | Complete | KMI Zeolite | 5861 | 0 | 0 | 0 | 96.2278
__export__.project_task_2309_13a33b4a | Billing - Direct cost billing: Don't Populate Customer Data | Sprint 2108 | 2021-02-08 | Development | Wild Leaf: Help (P22) | Nick Foy | Danish Hassan | 3.33 | 100 |  |  |  | Complete | Wild Leaf Beverage | 5877 | 2.5 | -0.83 | 104 | 278.3881
__export__.project_task_1656_b254944c | My bids API showing losing and winning on time out auctions | Sprint 2048 | 2020-11-23 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0.83 | 0 |  | 3.0.5 |  | Complete | Cellpoint Corporation | 7066 | 0 | -0.83 | 0.19471 | 68.7564
__export__.project_task_1422_affc3e75 | Integration with Rippling Payroll Systems |  |  | Development | Wild Leaf: Rippling Payroll Integration (P39) | Mir Muhammad Muzammil |  | 1 | 0 |  |  |  | Complete | Wild Leaf Beverage | 8064 | 0 | -6 | 1648.0192 | 311.2125
__export__.project_task_1037_3447d0b9 | Seller Permissions Group: Remove Activities | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_220_61176847 | Remote Access Apps | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Sprint 21 |  | Complete | Cellpoint Corporation | 10732 | 0 | 0 | 0 | 0
__export__.project_task_214_e4951a96 | Select Tag | Sprint 27 | 2020-08-17 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Sprint 20 |  | Complete | Cellpoint Corporation | 10763 | 0 | 0 | 0 | 0
__export__.project_task_211_c193183b | Auto refresh update in odoo app |  |  | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10782 | 0 | 0 | 97.4032 | 1345.3099
__export__.project_task_156_d1c55d24 | 1.6 Lot Details(8 hours) | Sprint 27 | 2020-08-17 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 0
__export__.project_task_4538_5a6df238 | Bug Tracking |  |  | Internal Time Tracking | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 824 | 0 | 0 | 0.00013545 | 0
__export__.project_task_4304_818659e0 | Edit Accounting training video |  |  | Other | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0.67 | 100 |  |  |  | Complete | Zuma Sales LLC | 1537 | 0.66667 | -0.0033333 | 0 | 2.5797
__export__.project_task_4068_d087bea8 | Connect inventory Odoo/Woocommerce |  |  | Configuration | MMH: WooCommerce Integration (P134) | Naseeb Razaq |  | 0 | 0 | Plan for the sprint |  |  | Planning | Mountain Meadow Herbs | 2048 | 4 | 4 | 0 | 0
__export__.project_task_3988_a1852603 | Inventory setup | Sprint 2125 | 2021-06-14 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2216 | 0 | 0 | 192.7095 | 51.7017
__export__.project_task_3473_f77020f5 | Reconcile Cash |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.9908 | 520.0192
__export__.project_task_3040_be94efd15 | Ensure db has been allocated sufficiently |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0.00033996 | 206.1934
__export__.project_task_2888_6b84634a | Send Kick-Off Agenda |  |  |  | DISCOVERY (P76) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1050.1596
__export__.project_task_2866_b37a21c8 | Change the logic for TRANSACTION_CHARGE fields | Sprint 2113 | 2021-03-22 | Development | Cellpoint: ecoATM API (P50) | Nick Foy | Muhammad Bilal | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 4655 | 1.1667 | 1.1667 | 0 | 48
__export__.project_task_2667_8169c5ee | Fw: Odoo studio screwed up | Sprint 2107 | 2021-02-01 | Studio | PWX: Help (P23) | Levi Barnes | Levi Barnes | 0.08 | 0 |  |  |  | Complete | EquityTeam | 5353 | 0 | -0.08 | 0 | 150.3133
__export__.project_task_2607_a10648d9 | General 2104 | Sprint 2105 | 2021-01-25 | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 2 | 0 |  |  |  | Complete | EquityTeam | 5548 | 0 | -2 | 0 | 39.4411
__export__.project_task_2355_5005128b | Belmont CP Analytics Daily Publish task (Timesheet) |  |  | Internal Time Tracking | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Faizan Zia Malik | 292.83 | 100 |  |  |  | Complete | Cellpoint Corporation | 5764 | 54.9167 | -237.9133 | 1206.4407 | 1234.302
__export__.project_task_1971_8a394687 | Set Customer Sales Person | Sprint 2052 | 2020-12-21 | Configuration | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 2 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 2 | 0 | 14.4119 | 108.7322
__export__.project_task_1783_994aeb24 | Default 00 Seconds on Start and End Selections | Sprint 2108 | 2021-02-08 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Danish Hassan | 1.92 | 96 |  |  |  | Complete | Cellpoint Corporation | 6836 | 2 | 0.08 | 0 | 502.41
__export__.project_task_1623_4f474095 | New Seller Onboarding: EcoATM: Testing | Sprint 2048 | 2020-11-23 | Configuration | CPBids: ecoATM Onboarding (P35) | Nick Foy | Faisal Huda Khan | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 7223 | 4 | 4 | 0 | 104
__export__.project_task_1542_5193448b | FW: Accountant Intro |  |  | Configuration | Dialed Supply: Help (P21) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Dialed Supply | 7560 | 0 | 0 | 0 | 104
__export__.project_task_1025_2301b732 | Hide Number of Views | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_249_228485d5 | Calculated Fields for Master Data | Sprint 22 | 2020-07-12 | Development | Silverdale: Help: Contains Data (P11) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 10399 | 2 | 2 | 1.8094 | 0
__export__.project_task_195_0b1ede11 | Manifest fields update |  |  | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10783 | 0 | 0 | 98.5971 | 1346.5007
__export__.project_task_176_fff637ed | Unable to complete new Buyer registration | Sprint 27 | 2020-08-17 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10871 | 0 | 0 | 0 | 0
__export__.project_task_4835_98d50383 | Post go-live support (Allocated Support Hours) | Sprint 2139 | 2021-09-20 | Other | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 | Start Support | 2027-09-01 |  | Backlog | Zuma Sales LLC | 170 | 33 | 33 | 0 | 0
__export__.project_task_4472_f523ebec | Deployment Mechanism |  |  | Improvements | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair | Muzher Siddique | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 897 | 0 | 0 | 0 | 0
__export__.project_task_4303_c896df26 | Create a dropdown for Order Type on purchase order form |  |  | Development | Zuma: Odoo Implementation Phase 2 (P204) | Asfand Yaar | Danish Hassan | 14.17 | 100 |  |  | 2 | Cancelled | Zuma Sales LLC | 1537 | 14.1667 | -0.0033333 | 275.5927 | 344.4594
__export__.project_task_4180_a635c33c | Android App (Implementation) - ecoATM logo on all pages | Sprint 2134 | 2021-08-16 | Development | Cellpoint: Change Color Theme for CPBids (P123) | Farman Ahmad Cheema | Apps Maven | 1.17 | 3.9 |  | SPLN |  | Cancelled | Cellpoint Corporation | 1827 | 30 | 28.83 | 285.1016 | 293.1016
__export__.project_task_4059_1e1a0af1 | Fwd: Odoo CRM Clean-up |  |  |  | Wild Leaf: Help (P22) | Muhammad Zubair |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 2065 | 0 | 0 | 0 | 96
__export__.project_task_3987_8a3ae07e | E-Learning setup | Sprint 2125 | 2021-06-14 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2216 | 0 | 0 | 192.7 | 59.7094
__export__.project_task_3888_29fe2299 | Correction of Transaction dates of uploaded data | Sprint 2124 | 2021-06-07 | Configuration | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq | Danish Hassan | 6.5 | 100 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 2478 | 5 | -1.5 | 0 | 74.29
__export__.project_task_3866_9a0cf6b7 | General Feedback (Rate our App) |  |  | Other | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 0.33 | 8.25 |  |  |  | Cancelled | Cellpoint Corporation | 2570 | 4 | 3.67 | 0 | 454.81
__export__.project_task_3484_e8c2aa3c | All internal transfers up to date | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.8279 | 637.5534
__export__.project_task_3353_65d71bf4 | Update Test Scripts | Sprint 2117 | 2021-04-19 | Studio | Silverdale: Help (P12) | Naseeb Razaq |  | 0.33 | 66 |  |  |  | Complete | Silverdale Technology LLC | 3697 | 0.5 | 0.17 | 0 | 8
__export__.project_task_3039_be94efd14 | Ensure backups are running correctly |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 6.2184e-05 | 206.1934
__export__.project_task_2886_0072924e | Prepare Kick-Off Presentation |  |  |  | DISCOVERY (P76) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4581 | 0 | 0 | 0 | 1050.1663
__export__.project_task_2683_6b1833ce | JP: Comp | Sprint 2108 | 2021-02-08 | Development | PWX: HR (P61) | Levi Barnes | Raheel Aslam | 1.75 | 87.5 |  |  |  | Complete | EquityTeam | 5342 | 2 | 0.25 | 0 | 150.4081
__export__.project_task_2258_240a091a | General 2102 |  |  | Configuration | KMI: Help (P41) | Levi Barnes | Levi Barnes | 2 | 0 |  |  |  | Complete | KMI Zeolite | 5924 | 0 | -2 | 0 | 40
__export__.project_task_1921_37898ebc | P37: Parent task for Customer Set-Up |  |  | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6524 | 0 | -12.67 | 14.4119 | 215.4147
__export__.project_task_1651_e9c97855 | Buy now price contains decimal value in Android | Sprint 2048 | 2020-11-23 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 1.83 | 0 |  | 3.0.5 |  | Complete | Cellpoint Corporation | 7066 | 0 | -1.83 | 0.4443 | 68.9654
__export__.project_task_1638_49adbdb1 | Create Project Stage Defaults | Sprint 2051 | 2020-12-14 | Development | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 11.22 | 100 |  |  |  | Complete | Silverdale Technology LLC | 7109 | 8.6667 | -2.5533 | 0 | 205.1335
__export__.project_task_1571_c5b5e588 | CellPoint and CPBids Training Materials | Sprint 2047 | 2020-11-16 | Configuration | Cellpoint CPBids: Help (P7) | Kaesi Lee | Muhammad Afzaal | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 7445 | 0 | 0 | 0 | 120.1294
__export__.project_task_1568_ad9b9b86 | Search View: Add a new field in project Task | Sprint 2046 | 2020-11-09 | Configuration | Silverdale: Help (P12) | Muzher Siddique | Fahad Hassan | 0.83 | 0 |  |  |  | Complete | Silverdale Technology LLC | 7450 | 0 | -0.83 | 0 | 12.5074
__export__.project_task_1537_abe0f744 | Wednesday |  |  |  | Silverdale: Help (P12) | Muzher Siddique |  | 7 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 7568 | 0 | -7 | 0 | 504.8818
__export__.project_task_1355_dd3281a7 | Reviews |  |  | Development | PWX: Reviews Module (P53) | Naseeb Razaq | Danish Hassan | 14.25 | 99.99 | Bring this up with Mark and Estimate the Fixed Price Effort |  |  | Planning | EquityTeam | 8373 | 69.5167 | 0.0066667 | 1928 | 0
__export__.project_task_1051_1836dc9c | Seller Permissions Group: Remove Live/Demo Selection | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_241_298d9173 | Reserve Displayed as Highest Bid | Sprint 21 | 2020-07-06 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Sprint 21 |  | Complete | Cellpoint Corporation | 10446 | 0 | 0 | 26.2074 | 0
__export__.project_task_179_52b2aa2b | Unable to Change Seller | Sprint 27 | 2020-08-17 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10809 | 0 | 0 | 0 | 0
__export__.project_task_4479_b1cff6a9 | Project Closing Mechanism - Announcement and Rewards |  |  | Improvements | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 893 | 0 | 0 | 0.00019368 | 0
__export__.project_task_4297_996f58d8 | Manufacturer List Price, Conventional Tier Cost, Economy Tier Cost, MPN, NET/NON-NET on Product Form | Sprint 2129 | 2021-07-12 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 5.78 | 100 |  | SPLN | 1 | Complete | Zuma Sales LLC | 1560 | 4 | -1.78 | 0 | 128.0192
__export__.project_task_4178_a3afbe65 | Android App (Design) - Logos on all their respective pages of marketplace | Sprint 2136 | 2021-08-30 | Development | Cellpoint: ecoATM logo on all pages (including Mobile App Details page) (P144) | Farman Ahmad Cheema | Apps Maven | 0.25 | 3.12 |  |  |  | Complete | Cellpoint Corporation | 1827 | 8 | 7.75 | 285.1756 | 313.4712
__export__.project_task_4057_c7913f78 | Show Event while making attendance |  |  |  | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Port Gamble Sâ€™Klallam Foundation | 2066 | 0 | 0 | 0 | 102.8264
__export__.project_task_3957_e4aa901e | Auto scheduler action for creating products from terex into odoo | Sprint 2128 | 2021-07-05 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 2.75 | 45.83 |  | reuse | 2 | Complete | Zuma Sales LLC | 2310 | 6 | 3.25 | 206.6917 | 185.7011
SPLN
__export__.project_task_3865_69f24c34 | Status Page |  |  | Improvements | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 2570 | 1 | 1 | 0 | 454.8181
__export__.project_task_3414_9f0c5938 | Breaks/Dinner |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Muzher Siddique | 1019.75 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3501 | 0 | -1019.75 | 0 | 642.8217
__export__.project_task_3350_eddfc729 | Creating multiple packs from a transfer | Sprint 2119 | 2021-05-03 | Development | Wild Leaf: Help (P22) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 3701 | 0 | 0 | 0 | 72.5468
__export__.project_task_3038_be94efd13 | Back up the production system |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 6.2184e-05 | 206.1934
__export__.project_task_2727_158b0b8a | Employee: Work Info/HR settings | Sprint 2109 | 2021-02-15 | Development | PWX: HR (P61) | Levi Barnes | Danish Hassan | 1.83 | 91.5 |  |  |  | Complete | EquityTeam | 5182 | 2 | 0.17 | 0 | 110.4919
__export__.project_task_2684_8a585cb2 | JP: Referrals/Other | Sprint 2108 | 2021-02-08 | Development | PWX: HR (P61) | Levi Barnes | Raheel Aslam | 3.17 | 100 |  |  |  | Complete | EquityTeam | 5342 | 3 | -0.17 | 0 | 150.4089
__export__.project_task_2443_23ef1cc9 | Dialed: Deployment | Sprint 2105 | 2021-01-25 | Configuration | Dialed Supply: Help (P21) | Levi Barnes | Wajahat Ali | 1.25 | 100 |  |  |  | Complete | Dialed Supply | 5570 | 1 | -0.25 | 0 | 4
__export__.project_task_2150_ebf9740f | 2106:Test Scripts/QA: Test Scripts Table (for Customer) | Sprint 2104 | 2021-01-18 | Development | Silverdale: Help (P12) | Muhammad Afzaal | Kaleem Khan | 4.83 | 100 |  |  |  | Complete | Silverdale Technology LLC | 6056 | 4 | -0.83 | 3.0395 | 139.9217
__export__.project_task_2112_f5893e48 | support |  |  | Configuration | KMI: Help (P41) | Levi Barnes |  | 4 | 0 |  |  |  | Complete | KMI Zeolite | 6089 | 0 | -4 | 0 | 0
__export__.project_task_1975_8da21a94 | Associate Alternative Products |  |  | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 0 | 0 | 14.4119 | 148.9211
__export__.project_task_1798_8135741a | turn website into catalog | Sprint 2049 | 2020-11-30 | Development | Moln: Help (P16) | Levi Barnes |  | 1.25 | 0 |  |  |  | Complete | Moln Solutions, LLC | 6811 | 0 | -1.25 | 0 | 15.8881
__export__.project_task_1745_b54317e0 | onchange related contact change follower | Sprint 2051 | 2020-12-14 | Development | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 7 | 100 |  |  |  | Complete | EquityTeam | 6843 | 7 | 0 | 0 | 132
__export__.project_task_1624_c8bfb74e | New Seller Onboarding: EcoATM: Trials and Training | Sprint 2048 | 2020-11-23 | Configuration | CPBids: ecoATM Onboarding (P35) | Nick Foy | Kaleem Khan | 1.5 | 75 |  |  |  | Complete | Cellpoint Corporation | 7223 | 2 | 0.5 | 0 | 40
__export__.project_task_1567_892246a7 | Search View: Search by Delivery Partner | Sprint 2046 | 2020-11-09 | Configuration | Silverdale: Help (P12) | Muzher Siddique | Fahad Hassan | 0.17 | 0 |  |  |  | Complete | Silverdale Technology LLC | 7450 | 0 | -0.17 | 0 | 1.1731
__export__.project_task_1560_8d3c3e2a | Integration with IL2000: Research IL2000 API | Sprint 2047 | 2020-11-16 | Development | Wild Leaf: IL2000 Integration (P40) | Kaesi Lee | Danish Hassan | 10 | 100 |  |  |  | Complete | Wild Leaf Beverage | 7532 | 10 | 0 | 0 | 175.2019
__export__.project_task_1526_e28ae97c | Reviews: Integration with Google Reviews. |  |  | Development | PWX: Reviews Module (P53) | Naseeb Razaq | Danish Hassan | 10.67 | 88.92 | To bring it in weekly meeting |  |  | Backlog | EquityTeam | 7587 | 12 | 1.33 | 1750.2792 | 0
__export__.project_task_1053_c75a19ba | Provide Buy Now Option: If selected, require Buy Now price field. | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_1027_9e009071 | Add Field to view: Auction ID | Sprint 28 | 2020-08-24 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_151_7a4f059d | 3.2 Edit Seller(1 hour) | Sprint 27 | 2020-08-17 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 0
__export__.project_task_4481_8256a050 | Project Go Live Mechanism |  |  | Improvements | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 892 | 0 | 0 | 0 | 0
__export__.project_task_4296_98e900e3 | Settings for Free Shipping on Product form |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Farman Ahmad Cheema | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 1560 | 3 | 3 | 0 | 96.0192
__export__.project_task_3911_459a8b8d | Developer support or rework for ecoATM Tasks | Sprint 2135 | 2021-08-23 | Development | Cellpoint: ecoATM API (P50) | Farman Ahmad Cheema | Wajahat Ali | 4.33 | 54.12 |  | SPLN |  | Complete | Cellpoint Corporation | 2381 | 8 | 3.67 | 423.2279 | 535.2279
__export__.project_task_3877_3ada1a9e | Set up email servers | Sprint 2123 | 2021-05-31 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Muhammad Bilal | 0.33 | 8.25 |  | Odoo Migration |  | Complete | Zuma Sales LLC | 2496 | 4 | 3.67 | 253.0078 | 52.8983
__export__.project_task_3848_69197fda | Invite Multiple Attendees to join Multiple Courses | Sprint 2125 | 2021-06-14 | Development | MMH: Help (P83) | Naseeb Razaq | Muhammad Bilal | 12.83 | 100 |  |  | 2 | Complete | Mountain Meadow Herbs | 2644 | 7 | -5.83 | 0.033166 | 176.0382
__export__.project_task_3470_2efb7f62 | Confirm asset depreciation models are correctly flowing |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.9908 | 520.0192
__export__.project_task_3404_a5fc9d2a | Silverdale Odoo14 upgrade |  |  | Other | Silverdale: v14 Upgrade (P46) | Muhammad Afzaal | Muzher Siddique | 39.95 | 99.88 |  |  |  | Complete | Silverdale Technology LLC | 3506 | 40 | 0.05 | 0 | 584.0192
__export__.project_task_3339_d0dedf80 | onchange hours spent automated action | Sprint 2119 | 2021-05-03 | Development | Silverdale: Help (P12) | Muhammad Afzaal | Danish Hassan | 7.83 | 100 |  |  | 2 | Complete | Silverdale Technology LLC | 3724 | 7 | -0.83 | 87.4306 | 232
__export__.project_task_3037_be94efd12 | Verify the online operation of the applications |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 6.2184e-05 | 206.1934
__export__.project_task_2347_b77e12da | RFQ review shcheduled activity | Sprint 2105 | 2021-01-25 | Development | PWX: Field Service to Invoicing (P47) | Levi Barnes | Raheel Aslam | 3.17 | 79.25 |  |  |  | Complete | EquityTeam | 5773 | 4 | 0.83 | 0 | 262.1017
__export__.project_task_2000_dc3bc776 | Email setup |  |  | Configuration | KMI: Help (P41) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | KMI Zeolite | 6506 | 0 | -2.5 | 0 | 96
__export__.project_task_1928_8a9c4ba0 | P37: Parent task for User Set-Up | Sprint 2052 | 2020-12-21 | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6524 | 0 | 0 | 14.4119 | 200
__export__.project_task_1818_7c6829a8 | Ground Truthing Report | Sprint 2051 | 2020-12-14 | Development | Heronswood: Events (P3) | Nick Foy | Muzher Siddique | 3.25 | 73.58 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 6765 | 4.4167 | 1.1667 | 0 | 124
__export__.project_task_1565_747c3cf3 | 1477:2 Minutes Extension | Sprint 2046 | 2020-11-09 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Shajahan | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 7454 | 6 | 6 | 0 | 15.9411
__export__.project_task_1559_60275a11 | Integration with Rippling Payroll Systems: Research Rippling Payroll API | Sprint 2049 | 2020-11-30 | Development | Wild Leaf: Rippling Payroll Integration (P39) | Mir Muhammad Muzammil | Raheel Aslam | 5 | 83.33 |  |  |  | Complete | Wild Leaf Beverage | 7532 | 6 | 1 | 1520.0192 | 175.2103
__export__.project_task_1529_c1f36258 | Integration with Zillow |  |  | Development | PWX: Reviews Module (P53) | Naseeb Razaq | Danish Hassan | 10.67 | 88.92 | To bring it in weekly meeting |  |  | Backlog | EquityTeam | 7587 | 12 | 1.33 | 1750.1324 | 0
__export__.project_task_1033_671fba36 | Re-label "Closed" with "Expired" | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_175_8b585054 | Unable to view Sources menu item | Sprint 27 | 2020-08-17 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11283 | 0 | 0 | 0 | 0
__export__.project_task_4480_0f385605 | Identifying P1s and Treatment |  |  | Improvements | Silverdale Internal Processes and Mechanisms (P182) | Muhammad Zubair |  | 0 | 0 | Please add next activity |  |  | Planning | Silverdale Technology LLC | 892 | 0 | 0 | 0 | 0
__export__.project_task_4290_ebb760ee | Meeting for Shopfiy with Vendors | Sprint 2129 | 2021-07-12 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 1 | 100 |  |  |  | Complete | Zuma Sales LLC | 1640 | 1 | 0 | 0 | 32.5722
__export__.project_task_3859_345889b7 | Individual Auction Detail View | Sprint 2135 | 2021-08-23 | Development | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Kaleem Khan | 12.25 | 94.23 |  | SPLN | 2 | Complete | Cellpoint Corporation | 2575 | 13 | 0.75 | 472 | 541.4194
__export__.project_task_3490_935f29c8 | All Sales Orders have Deposit Invoices | Sprint 2127 | 2021-06-28 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0.33 | 0 |  | SPLN |  | Complete | Zuma Sales LLC | 3483 | 0 | -0.33 | 460.9906 | 364
__export__.project_task_3469_f218cc29 | Confirm assets are uploaded, reconciled against Quickbooks and asset listing |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.9908 | 520.0192
__export__.project_task_3463_bf38351a | Confirm that all components of the new Odoo system are operational | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  | SPLN |  | Complete | Zuma Sales LLC | 3484 | 0.5 | 0.5 | 461.9352 | 674.1194
__export__.project_task_3373_d49c2a4a | Development Manager DILO |  |  | Internal Time Tracking | Silverdale: Help (P12) | Muhammad Afzaal | Muzher Siddique | 71.17 | 0 |  |  |  | Complete | Silverdale Technology LLC | 3573 | 0 | -71.17 | 0 | 666.8311
__export__.project_task_3309_f6fa068a | Resize Package Barcode | Sprint 2119 | 2021-05-03 | Development | Wild Leaf: Help (P22) | Umer Farooq |  | 0 | 0 |  |  | 2 | Complete | Wild Leaf Beverage | 3874 | 0 | 0 | 0.0038967 | 124.8058
__export__.project_task_3262_5417b65d | PWX: Vendors bills default analytic account and group | Sprint 2117 | 2021-04-19 | Development | PWX: Help (P23) | Levi Barnes | Aleem khan | 11.92 | 100 |  |  | 2 | Complete | EquityTeam | 4068 | 4 | -7.92 | 1.4298 | 158.7206
__export__.project_task_3035_be94efd10 | Load Vendor, Customer data |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 6.2184e-05 | 206.1934
__export__.project_task_3014_225cfc02 | CI/CD cost evaluations |  |  | Other | Silverdale: Devops (P84) | Muzher Siddique | Muzher Siddique | 0 | 0 | Please add next activity |  |  | Backlog | Silverdale Technology LLC | 4414 | 1 | 1 | 953.1433 | 0
__export__.project_task_2664_3c0f756d | Alert messaging for translation:Needs to be added in the system. | Sprint 2108 | 2021-02-08 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 3.67 | 100 |  |  |  | Complete | Cellpoint Corporation | 5358 | 3 | -0.67 | 0 | 151.9153
__export__.project_task_2269_fe198c0a | Purchase | Sprint 2104 | 2021-01-18 | Configuration | Silverdale: Help (P12) | Faisal Huda Khan | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5910 | 0 | 0 | 0.13771 | 69.2047
__export__.project_task_1920_e17b3b4d | P37: Parent task for Product Set-Up |  |  | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6524 | 0 | -5.6 | 14.4119 | 192
__export__.project_task_1850_70399183 | routing issue | Sprint 2051 | 2020-12-14 | Configuration | KMI: Help (P41) | Levi Barnes |  | 11 | 0 |  |  |  | Complete | KMI Zeolite | 6724 | 0 | -11 | 0 | 40
__export__.project_task_1841_a0da4b31 | add company archive abillity | Sprint 2051 | 2020-12-14 | Development | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 1.47 | 100 |  |  |  | Complete | EquityTeam | 6740 | 1 | -2.05 | 0 | 116
__export__.project_task_1627_dc299195 | Notification Centre: Android | Sprint 2047 | 2020-11-16 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0.33 | 0 |  | P1 |  | Complete | Cellpoint Corporation | 7208 | 0 | -0.33 | 0 | 67.1944
__export__.project_task_1625_3de66a17 | New Seller Onboarding: EcoATM: Go-Live | Sprint 2049 | 2020-11-30 | Configuration | CPBids: ecoATM Onboarding (P35) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 7223 | 0 | 0 | 0 | 52.1089
__export__.project_task_1595_e7e0c92f | issues with placing orders on AAO website | Sprint 2048 | 2020-11-23 | Bug Fix | Moln: Help (P16) | Levi Barnes | Muzher Siddique | 45 | 0 |  | P1 |  | Complete | Moln Solutions, LLC | 7371 | 0 | -45 | 22.6344 | 136
__export__.project_task_1531_de0e7c4a | Project Module: New Field: Odoo Version # | Sprint 2046 | 2020-11-09 | Development | Silverdale: Help (P12) | Kaesi Lee | Muzher Siddique | 2 | 50 |  |  |  | Complete | Silverdale Technology LLC | 7586 | 4 | 2 | 0 | 40
__export__.project_task_1160_3829eea5 | Forget Password | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9201 | 0 | 0 | 0 | 164.0042
__export__.project_task_1023_7a893f67 | Add End Date Time | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_4289_9c390b2e | Setup Accounting General Settings | Sprint 2131 | 2021-07-26 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 4 | 40 |  | SPLN |  | Complete | Zuma Sales LLC | 1640 | 10 | 6 | 0 | 168.1803
__export__.project_task_4181_3d56fb2e | iOS App (Implementation) - ecoATM logo on all pages | Sprint 2134 | 2021-08-16 | Development | Cellpoint: Change Color Theme for CPBids (P123) | Farman Ahmad Cheema | Apps Maven | 2.5 | 8.33 |  |  |  | Cancelled | Cellpoint Corporation | 1827 | 30 | 27.5 | 285.0703 | 293.0703
__export__.project_task_4053_5c08174a | Shift Setting while making attendance |  |  |  | Heronswood: Volunteer Shift Tracker (P81) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Port Gamble Sâ€™Klallam Foundation | 2067 | 0 | 0 | 0 | 102.85
__export__.project_task_4017_b9cb4f3a | Sponsor Review Meeting | Sprint 2126 | 2021-06-21 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  | 2 | Complete | Zuma Sales LLC | 2167 | 16 | 16 | 176.2012 | 51.2396
__export__.project_task_3468_e514175d | Reconcile open A/R |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.9908 | 520.0192
__export__.project_task_3462_26527705 | Initiate support | Sprint 2133 | 2021-08-09 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 460.9911 | 611.8519
__export__.project_task_3237_20dee0cb | PD-QA : Heronswood | Sprint 2118 | 2021-04-26 | Other | Heronswood: Help (P54) | Jeff Gross | Wishal Nasir | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 4182 | 0 | 0 | 0 | 153.7134
__export__.project_task_3034_be94efd9 | Complete General Settings |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 6.2184e-05 | 206.1934
__export__.project_task_2725_47345572 | Employee: Main | Sprint 2109 | 2021-02-15 | Development | PWX: HR (P61) | Levi Barnes | Danish Hassan | 4.42 | 100 |  |  |  | Complete | EquityTeam | 5182 | 4 | -0.42 | 0 | 110.4956
__export__.project_task_2679_6db35e20 | JP: Main | Sprint 2108 | 2021-02-08 | Development | PWX: HR (P61) | Levi Barnes | Raheel Aslam | 3.08 | 100 |  |  |  | Complete | EquityTeam | 5342 | 3 | -0.08 | 0 | 150.4036
__export__.project_task_2441_b4783b56 | Cpbid: Deployment sprint 2103 | Sprint 2105 | 2021-01-25 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 2.5 | 83.33 |  |  |  | Complete | Cellpoint Corporation | 5575 | 3 | 0.5 | 0.00012132 | 2.9404
__export__.project_task_2148_05ab1109 | 2106:Test Scripts/QA: Master Table | Sprint 2104 | 2021-01-18 | Development | Silverdale: Help (P12) | Muhammad Afzaal | Kaleem Khan | 3.1 | 100 |  |  |  | Complete | Silverdale Technology LLC | 6056 | 3 | -0.1 | 9.7764 | 140
__export__.project_task_1994_7a77edda | freight vendor email: SO button | Sprint 2053 | 2020-12-28 | Development | KMI: Help (P41) | Levi Barnes | Muzher Siddique | 3.67 | 91.75 |  |  |  | Complete | KMI Zeolite | 6506 | 4 | 0.33 | 0 | 140
__export__.project_task_1972_5f4f107e | Set Customer Payment Terms | Sprint 2053 | 2020-12-28 | Configuration | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 0.25 | 50 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 0.5 | 0.25 | 14.4119 | 148
__export__.project_task_1854_182fc0d6 | Log of stages of task. | Sprint 2051 | 2020-12-14 | Development | Silverdale: Help (P12) | Muzher Siddique | Danish Hassan | 4.3 | 100 |  |  |  | Complete | Silverdale Technology LLC | 6707 | 4 | -0.3 | 0 | 105.8687
__export__.project_task_1653_9d8fe432 | My bids keeps on loading or hand while going to the end in iOS | Sprint 2048 | 2020-11-23 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 2.83 | 0 |  | 3.0.5 |  | Complete | Cellpoint Corporation | 7066 | 0 | -2.83 | 0.39228 | 68.9009
__export__.project_task_1650_7602e6f9 | Manifest Revise | Sprint 2049 | 2020-11-30 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 4 | 100 |  |  |  | Complete | Cellpoint Corporation | 7070 | 2 | -2 | 0 | 79.8878
__export__.project_task_1585_04595248 | BoMs: Import BoMs Data | Sprint 2047 | 2020-11-16 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 8.17 | 0 |  |  |  | Complete | Wild Leaf Beverage | 7416 | 0 | -8.17 | 0 | 110.9267
__export__.project_task_1511_5f7bf5d1 | Continuant Testing Feedback 10/30 | Sprint 2046 | 2020-11-09 | Bug Fix | Continuant: eCommerce (P9) | Kaesi Lee | Muzher Siddique | 19.37 | 0 |  |  |  | Complete | Continuant | 7681 | 0 | -19.37 | 0 | 104
__export__.project_task_1073_ac509486 | Stress Testing | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Muhammad Afzaal |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9534 | 0 | 0 | 0 | 241.6353
__export__.project_task_1045_07a480d5 | Change Main "Lot Category" Field to single selection | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_4638_5dda4ed0 | Deployment: cellpoint(p165) | Sprint 2136 | 2021-08-30 | Other | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 16.83 | 99.98 |  | SPLN |  | Complete | Cellpoint Corporation | 564 | 16.8333 | 0.0033333 | 0 | 56
__export__.project_task_3986_5a79141f | Installation and configuration of helpdesk |  |  | Configuration | Zuma: CRM (P130) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 2217 | 0 | 0 | 193.0935 | 68.1023
__export__.project_task_3932_91b88505 | Cut-0ver for AWS usage | Sprint 2123 | 2021-05-31 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 4 | 0 |  | Odoo.sh Migration |  | Complete | Zuma Sales LLC | 2333 | 0 | -4 | 214.0039 | 37.0134
__export__.project_task_3467_86a21551 | Reconcile open A/P |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.9911 | 520.0192
__export__.project_task_3458_3e901be4 | Distribute the initial production schedule | Sprint 2133 | 2021-08-09 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 460.9911 | 611.8694
__export__.project_task_3239_573ec3d5 | PD-QA : Wildleaf |  |  | Other | Wild Leaf: Help (P22) | Jeff Gross | Muhammad Saqlain Alam | 2.67 | 89 |  |  |  | Cancelled | Wild Leaf Beverage | 4182 | 3 | 0.33 | 0 | 560.4417
__export__.project_task_3033_be94efd8 | Set up and verify User groups and access rights |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 6.2184e-05 | 206.1934
__export__.project_task_3034_ab8a9165 | Tracing ticket from task, like we have option on ticket for tracing task |  |  | Development | Silverdale: Help (P12) | Muhammad Afzaal | Aleem khan | 4.08 | 81.6 |  |  |  | Complete | Silverdale Technology LLC | 4376 | 5 | 0.92 | 2.3147 | 276
__export__.project_task_3002_b3906d1e | Modification of existing module "hr.skill" | Sprint 2116 | 2021-04-12 | Development | PWX: HR (P61) | Levi Barnes | Danish Hassan | 19.83 | 100 |  |  | 2 | Complete | EquityTeam | 4428 | 17 | -2.83 | 0 | 198.8598
__export__.project_task_2835_0e439529 | survey roadmap |  |  | Internal Time Tracking | PWX: Survey (P70) | Levi Barnes |  | 2 | 100 |  |  |  | Complete | EquityTeam | 4701 | 1 | -1 | 0 | 64
__export__.project_task_2682_f3ff4974 | JP: Goals/KPI's | Sprint 2108 | 2021-02-08 | Development | PWX: HR (P61) | Levi Barnes | Raheel Aslam | 1.67 | 83.5 |  |  |  | Complete | EquityTeam | 5342 | 2 | 0.33 | 0 | 150.4075
__export__.project_task_2344_99db1645 | Internal: Project UX Review | Sprint 2104 | 2021-01-18 | Configuration | Continuant: Customer Portal AR (P32) | Kaesi Lee |  | 0.33 | 0 |  |  |  | Complete | Continuant | 5809 | 0 | -0.33 | 0 | 40
__export__.project_task_2299_98491f41 | Change the Task Type field to be a list in Configuration | Sprint 2105 | 2021-01-25 | Development | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 6.67 | 100 |  | WK |  | Complete | Silverdale Technology LLC | 5887 | 5 | -1.67 | 0 | 281.0914
__export__.project_task_1993_d75321e9 | freight vendor email: template | Sprint 2053 | 2020-12-28 | Development | KMI: Help (P41) | Levi Barnes | Muzher Siddique | 2.75 | 100 |  |  |  | Complete | KMI Zeolite | 6506 | 2.75 | 0 | 0 | 140
__export__.project_task_1953_fce5d74f | Import Product Categories | Sprint 2052 | 2020-12-21 | Configuration | Mid-America: Help (P37) | Levi Barnes | Nick Foy | 0.17 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 0 | -0.17 | 14.4119 | 108.7458
__export__.project_task_1865_55d25bfd | add company archive abillity:Validation Check | Sprint 2051 | 2020-12-14 | Development | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 1.58 | 79 |  |  |  | Complete | EquityTeam | 6607 | 2 | 0.42 | 0 | 86.5364
__export__.project_task_1647_181aeb33 | Show Stage and assign to developer on kanban view | Sprint 2048 | 2020-11-23 | Studio | Silverdale: Help (P12) | Muzher Siddique | Kaleem Khan | 2 | 100 |  |  |  | Complete | Silverdale Technology LLC | 7082 | 2 | 0 | 0 | 3.1153
__export__.project_task_1617_6f9ef194 | Notification time in-correct: iOS | Sprint 2047 | 2020-11-16 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0.5 | 0 |  | P1 |  | Complete | Cellpoint Corporation | 7232 | 0 | -0.5 | 0 | 74.8181
__export__.project_task_1227_1e5bfe0c | FedEx US: Package Type Invalid | Sprint 2046 | 2020-11-09 | Bug Fix | Continuant: eCommerce (P9) | Kaesi Lee | Muzher Siddique | 8 | 0 |  |  |  | Complete | Continuant | 8743 | 0 | -8 | 129.2709 | 346.8084
__export__.project_task_1172_0eb68dfe | Seller Portal: Hide Action Menu | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9076 | 0 | 0 | 56 | 136
__export__.project_task_1050_3755f5a3 | Remove "Auction For" from automatically populating before the auction Name | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_147_4dd26b3b | 1.6.4 Select Location(1 hour) | Sprint 28 | 2020-08-24 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 0
__export__.project_task_4621_7ba36012 | Change Label: Validate Serial to Check Serials | Sprint 2135 | 2021-08-23 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Danish Hassan | 0.08 | 2.67 |  | SPLN |  | Complete | Cellpoint Corporation | 720 | 3 | 2.92 | 0 | 79.8639
__export__.project_task_4282_f4d30dbe | Zuma daily standup + Requirement Gathering +Trainings | Sprint 2129 | 2021-07-12 | Configuration | Zuma: Help (P97) | Fahad Hussain Malik | Fahad Hussain Malik | 13 | 100 |  |  |  | Complete | Zuma Sales LLC | 1656 | 13 | 0 | 0 | 48
__export__.project_task_3985_b4e270e1 | Visibility of internal notes added on lead form from contact form |  |  | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2219 | 0 | 0 | 194.372 | 253.3831
__export__.project_task_3923_321899d4 | Latest Backup of DB to upload | Sprint 2123 | 2021-05-31 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 4 | 0 |  | Odoo Migration |  | Complete | Zuma Sales LLC | 2334 | 0 | -4 | 214.4945 | 14.212
__export__.project_task_3857_e4080b47 | Marketplace Logo and Marketplace Profile |  |  | Improvements | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 0.33 | 7.33 |  |  |  | Complete | Cellpoint Corporation | 2576 | 4.5 | 4.17 | 0 | 458.8475
__export__.project_task_3466_94569fd3 | Reconcile all paid Vendor Bills |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.9911 | 520.0192
__export__.project_task_3032_be94efd7 | Set up the users in the new system |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 6.2184e-05 | 206.1934
__export__.project_task_2680_241cd98c | JP: job description | Sprint 2108 | 2021-02-08 | Development | PWX: HR (P61) | Levi Barnes | Raheel Aslam | 3 | 100 |  |  |  | Complete | EquityTeam | 5342 | 2.5 | -0.5 | 0 | 150.405
__export__.project_task_2444_a41349dd | Accounting Training Session | Sprint 2107 | 2021-02-01 | Configuration | Wild Leaf: Help (P22) | Nick Foy | Nick Foy | 4 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5569 | 0 | -4 | 32 | 61.925
__export__.project_task_2379_25c28773 | universal demo | Sprint 2105 | 2021-01-25 | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 1 | 0 |  |  |  | Complete | EquityTeam | 5741 | 0 | -1 | 0 | 88.1887
__export__.project_task_2343_f6c53229 | Internal: Project UX Review | Sprint 2104 | 2021-01-18 | Configuration | Continuant: Customer Invoice Delivery Preferences (P33) | Kaesi Lee |  | 0.17 | 0 |  |  |  | Complete | Continuant | 5809 | 0 | -0.17 | 0 | 40
__export__.project_task_2276_e6e15235 | Timesheets | Sprint 2110 | 2021-03-01 | Internal Training | Silverdale: Help (P12) | Faisal Huda Khan | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5910 | 0 | 0 | 0.056674 | 328.4539
__export__.project_task_2077_372701f5 | Change sequence starting value | Sprint 2102 | 2021-01-04 | Configuration | KMI: Help (P41) | Levi Barnes |  | 1.25 | 62.5 |  |  |  | Complete | KMI Zeolite | 6203 | 2 | 0.75 | 2.5482e-05 | 144.3342
__export__.project_task_1922_0b5c0c31 | P37: Parent task for Vendor Set-Up |  |  | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6524 | 0 | 0 | 14.4119 | 192
__export__.project_task_1902_bfa6f3c3 | Delete "Core Focus" and make fields HTML: | Sprint 2051 | 2020-12-14 | Development | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 1.25 | 100 |  |  |  | Complete | EquityTeam | 6557 | 1 | -0.25 | 3.1579e-05 | 68.4684
__export__.project_task_1668_90d9ea28 | Web Biding Video | Sprint 2048 | 2020-11-23 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Gadha Continuant | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 7045 | 20 | 20 | 0 | 22.6239
__export__.project_task_1509_bd607bcc | Work Centers | Sprint 2047 | 2020-11-16 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 9.25 | 100 |  |  |  | Complete | Wild Leaf Beverage | 7684 | 5 | -4.25 | 0 | 166.9275
__export__.project_task_1086_28711d73 | Buy Now Price Set | Sprint 26 | 2020-08-10 | Configuration | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9528 | 0 | 0 | 0 | 0
__export__.project_task_845_48f7135b | Filter Screen fuctionality iOS-Implementation | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 2 | 2 | 0.00018745 | 347.2516
iOS
__export__.project_task_4262_e86d277b | Remove extra info tab from Opportunity and replace it in Quick Add | Sprint 2129 | 2021-07-12 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 3.92 | 98 |  | SPLN | 1 | Complete | Zuma Sales LLC | 1657 | 4 | 0.08 | 0 | 64
__export__.project_task_3984_b7c2e5de | Addition of product details on lead form for marketing purpose |  |  | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2219 | 0 | 0 | 194.3965 | 253.4076
__export__.project_task_3497_0354c212 | Lucid Charts |  |  | Other | Silverdale: Command Center (P113) | Levi Barnes | Levi Barnes | 2 | 25 |  |  |  | Cancelled | Silverdale Technology LLC | 3476 | 8 | 6 | 0 | 336
__export__.project_task_3465_787a50f5 | Reconcile all paid Invoices |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3483 | 0 | 0 | 460.9911 | 520.0192
__export__.project_task_3443_f768f2a3 | Ensure reporting formats are correctly setup | Sprint 2136 | 2021-08-30 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.33 | 33 |  |  |  | Complete | Zuma Sales LLC | 3484 | 1 | 0.67 | 462.1405 | 718.4402
__export__.project_task_3410_01a02387 | Vendor Integration: Genie Industries | Sprint 2124 | 2021-06-07 | Other | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 1 | 0 |  |  |  | Complete | Zuma Sales LLC | 3505 | 0 | -1 | 469.0078 | 272
__export__.project_task_3031_be94efd6 | Secure access to the production environment |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 6.2184e-05 | 206.1934
__export__.project_task_2939_2b7333c0 | Create an estimate for Joan | Sprint 2118 | 2021-04-26 | Other | Heronswood: Volunteer Shift Tracker (P81) | Jeff Gross | Nick Foy | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 4549 | 0 | 0 | 0 | 359.4274
__export__.project_task_2681_213b67d4 | JP: Skills & Exp | Sprint 2108 | 2021-02-08 | Development | PWX: HR (P61) | Levi Barnes | Raheel Aslam | 2 | 80 |  |  |  | Complete | EquityTeam | 5342 | 2.5 | 0.5 | 0 | 150.4061
__export__.project_task_2676_44157897 | Perfect Golf Events: Process walkthrough in Odoo | Sprint 2107 | 2021-02-01 | Internal Time Tracking | Silverdale: Biz Dev (P63) | Nick Foy | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5351 | 0 | 0 | 0 | 133.8636
__export__.project_task_2423_cc37df57 | Lead Times | Sprint 2105 | 2021-01-25 | Configuration | Wild Leaf: Help (P22) | Nick Foy | Nick Foy | 1.75 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5591 | 0 | -1.75 | 40 | 214.0972
__export__.project_task_2354_7c2051ab | Training. | Sprint 2104 | 2021-01-18 | Configuration | Silverdale: Help (P12) | Nick Foy | Faisal Huda Khan | 17.92 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5765 | 0 | -17.92 | 1.7421e-05 | 41.1639
__export__.project_task_2326_f91b8a05 | Daily Belmont data migration to Azure. |  |  | Internal Time Tracking | Cellpoint CPBids: Help (P7) | Farman Ahmad Cheema | Faizan Zia Malik | 172.17 | 0 |  |  |  | Complete | Cellpoint Corporation | 5856 | 0 | -172.17 | 1219.9005 | 1247.7666
__export__.project_task_2047_cd55269b | Upgrade Studio changes |  |  | Development | Silverdale: v14 Upgrade (P46) | Muhammad Afzaal | Danish Hassan | 6 | 100 |  | Difficulty 3 |  | Cancelled | Silverdale Technology LLC | 6267 | 6 | 0 | 392 | 664
__export__.project_task_1976_1358aaf4 | Associate Accessory Products |  |  | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 0 | 0 | 14.4117 | 192
__export__.project_task_1629_b38666b4 | Install Direct Print Module | Sprint 2048 | 2020-11-23 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Muzher Siddique | 0.42 | 84 |  |  |  | Complete | Wild Leaf Beverage | 7200 | 0.5 | 0.08 | 0 | 44
__export__.project_task_1609_587408c2 | Listview & Watchlist API | Sprint 2047 | 2020-11-16 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0 | 0 |  | P1 |  | Complete | Cellpoint Corporation | 7275 | 0 | 0 | 0 | 87.38
__export__.project_task_1074_e9d8e25b | Stability Testing | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Muhammad Afzaal |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9534 | 0 | 0 | 0 | 241.6228
__export__.project_task_1036_627b7084 | New Item: Create New Auction | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_4260_1e5a0cc5 | Create user group for leads | Sprint 2129 | 2021-07-12 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0.5 | 50 |  |  |  | Complete | Zuma Sales LLC | 1657 | 1 | 0.5 | 0 | 46.1053
__export__.project_task_4179_a9c08a35 | iOS App (Design) - Logos on all pages of respective Marketplaces | Sprint 2136 | 2021-08-30 | Development | Cellpoint: ecoATM logo on all pages (including Mobile App Details page) (P144) | Farman Ahmad Cheema | Apps Maven | 0.25 | 3.12 |  |  |  | Complete | Cellpoint Corporation | 1827 | 8 | 7.75 | 285.1397 | 313.4378
__export__.project_task_4147_cf06ab73 | Update PO on updating of SO of Terex | Sprint 2129 | 2021-07-12 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 6.17 | 100 |  | SPLN | 3 | Complete | Zuma Sales LLC | 1830 | 6 | -0.17 | 94.9218 | 108.7238
__export__.project_task_3983_ded31a89 | Configuration of lost reasons |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2219 | 0 | 0 | 194.4163 | 253.4274
__export__.project_task_3829_cfdbd06f | Dr. Clark: Pricing being shown as "now only -- instead of" prices in eu and switzerland |  |  | Development | MMH Dr. Clark: Help (P106) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Mountain Meadow Herbs | 2741 | 0 | 0 | 0 | 513.5069
__export__.project_task_3030_be94efd5 | Install the database on the database servers |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 6.2184e-05 | 206.1934
__export__.project_task_2826_ce8900e8 | portal User imports |  |  | Development | Moln: 3 New Portal Websites (P62) | Levi Barnes |  | 0 | 0 |  |  |  | Cancelled | Moln Solutions, LLC | 4732 | 0 | 0 | 0 | 487.1129
__export__.project_task_2800_88e56e1f | Demo - MaxFireSec | Sprint 2110 | 2021-02-22 | Other | Silverdale: Biz Dev (P63) | Nick Foy | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4872 | 0 | 0 | 0 | 98.4408
__export__.project_task_2369_7210dc4c | Default Contact payment terms to 50/50 terms | Sprint 2104 | 2021-01-18 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Nick Foy | 0.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5760 | 0 | -0.5 | 0 | 72
__export__.project_task_2271_c71c51f3 | CRM | Sprint 2107 | 2021-02-01 | Configuration | Silverdale: Help (P12) | Faisal Huda Khan | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5910 | 0 | 0 | 0.11344 | 184.8921
__export__.project_task_2046_99350502 | Research/Develop Script for Up gradation |  |  | Development | Silverdale: v14 Upgrade (P46) | Muhammad Afzaal | Wajahat Ali | 3.5 | 58.33 |  | Difficulty 4 |  | Complete | Silverdale Technology LLC | 6267 | 6 | 2.5 | 392 | 664
__export__.project_task_1962_ff52eaaf | Publish products to website | Sprint 2053 | 2020-12-28 | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 0 | 0 | 14.4119 | 148
__export__.project_task_1713_a1c42d67 | Customer portal view - restrict hours for clients |  |  | Development | Silverdale: Help (P12) | Muzher Siddique |  | 0 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 6890 | 0 | 0 | 0 | 415.9339
__export__.project_task_1694_8528a452 | goal progress bar | Sprint 2049 | 2020-11-30 | Development | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 1.5 | 75 |  |  |  | Complete | EquityTeam | 6915 | 2 | 0.5 | 0 | 39.8864
__export__.project_task_1655_dbd03579 | QA for app stability and improvement | Sprint 2048 | 2020-11-23 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 5 | 0 |  |  |  | Complete | Cellpoint Corporation | 7066 | 0 | -5 | 0.33277 | 16.8653
__export__.project_task_1521_7ab8b9f4 | Manual Purchasing Process | Sprint 2112 | 2021-03-15 | Development | Continuant: Quotation Management / Automation (P31) | Jeff Gross | Kaleem Khan | 4.75 | 59.38 |  |  |  | Cancelled | Continuant | 7679 | 8 | 3.25 | 720 | 760
__export__.project_task_1479_1daa371f | Power BI: Belmont Reporting Changes | Sprint 2047 | 2020-11-16 | Configuration | Cellpoint CPBids: Help (P7) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 7924 | 0 | 0 | 0 | 230.9283
__export__.project_task_1220_b22ce57d | Bid History | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8772 | 0 | 0 | 0 | 70.8773
__export__.project_task_1062_8888800a | Seller Permissions Group: Make all buyer fields read only | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_230_492bedf3 | Change layout of marketplace in apps | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Sprint 21 |  | Complete | Cellpoint Corporation | 10478 | 0 | 0 | 40 | 0
__export__.project_task_163_b881d6d0 | 2.1 Buyers List(2 hours) |  |  | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 1536
__export__.project_task_4362_ef5c1ce7 | NMS Bounce Form View (Export Utility) | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 10.75 | 100 |  | SPLN | 3 | Complete | Cellpoint Corporation | 1229 | 10 | -0.75 | 0 | 200.0701
__export__.project_task_4257_6885f552 | Add new Tab for Quick Add Contact in Leads | Sprint 2129 | 2021-07-12 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 3.58 | 89.5 |  | SPLN | 1 | Complete | Zuma Sales LLC | 1657 | 4 | 0.42 | 0 | 64
__export__.project_task_4089_2dd97e77 | Amazon Connection | Sprint 2128 | 2021-07-05 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Raheel Aslam | 2 | 100 |  | SPLN | 1 | Complete | Zuma Sales LLC | 2023 | 2 | 0 | 143.4279 | 122.4679
__export__.project_task_3982_0fb9e00f | Training on how to track lost leads |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2219 | 0 | 0 | 194.4353 | 253.4464
__export__.project_task_3803_8368a27e | Post deployment Process with Levi and Sana Ullah |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal | Muzher Siddique | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 2884 | 0 | 0 | 0 | 518.0857
__export__.project_task_3029_be94efd4 | Configure printer drivers |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 6.2184e-05 | 206.1934
__export__.project_task_2834_9cb1f73e | plan the rest of the FS to Inv |  |  | Internal Time Tracking | PWX: Field Service to Invoicing (P47) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | EquityTeam | 4704 | 3 | 3 | 0 | 248
__export__.project_task_2666_fbf4ff9f | cpbids test scripts and Android and IOS builds testing | Sprint 2107 | 2021-02-01 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 6.17 | 100 |  |  |  | Complete | Cellpoint Corporation | 5354 | 4 | -2.17 | 0 | 2.9592
__export__.project_task_2322_658b0a69 | add contact properties to help desk ticket | Sprint 2105 | 2021-01-25 | Development | PWX: Field Service to Invoicing (P47) | Levi Barnes | Danish Hassan | 4.75 | 100 |  |  |  | Complete | EquityTeam | 5860 | 3.5 | -1.25 | 0 | 270.0969
__export__.project_task_1961_4214b3f3 | Assign ecommerce categories | Sprint 2052 | 2020-12-21 | Configuration | Mid-America: Help (P37) | Levi Barnes | Nick Foy | 0.17 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 0 | -0.17 | 14.4119 | 108.7561
__export__.project_task_1742_f28dd84b | Android application submit to store | Sprint 2049 | 2020-11-30 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 6850 | 0 | 0 | 0.013393 | 1.7881
__export__.project_task_1683_78f9daf7 | Development: PropertyWorx | Sprint 2048 | 2020-11-23 | Configuration | PWX: Help (P23) | Muzher Siddique |  | 0.25 | 50 |  |  |  | Complete | EquityTeam | 6921 | 0.5 | 0.25 | 0 | 0.063945
__export__.project_task_1026_64b27f61 | Seller Permissions Group: Change label from "Marketplace Working Auctions" to "Seller Running Auctions" | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_912_c8f4f4e2 | update data through notifications (8 types of notification) Android-Implementation | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 8 | 8 | 0.00016651 | 347.2418
Android
__export__.project_task_240_bca337a4 | Auction limitation | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Sprint 21 |  | Complete | Cellpoint Corporation | 10470 | 0 | 0 | 0 | 0
__export__.project_task_162_00c66dbe | 2.1.1 Reset Password(4 hours) |  |  | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 1536
__export__.project_task_4238_4478d583 | Quick Add Button Removal | Sprint 2129 | 2021-07-12 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 3.17 | 100 |  | SPLN | 2 | Complete | Zuma Sales LLC | 1662 | 3 | -0.17 | 3.1476e-05 | 65.5367
__export__.project_task_3981_1b4386f0 | Make fields mandatory based on stages on pipeline form |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2219 | 0 | 0 | 194.4474 | 253.4585
__export__.project_task_3925_a1399f92 | DNS setup | Sprint 2123 | 2021-05-31 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  | Odoo Migration |  | Complete | Zuma Sales LLC | 2334 | 0 | 0 | 214.4523 | 14.2342
__export__.project_task_3572_19fd0187 | Wordpress Connector |  |  | Development | Zuma: Help (P97) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3241 | 0 | 0 | 411.48 | 589.6491
__export__.project_task_3028_be94efd3 | Create user accounts |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 6.2184e-05 | 206.1934
__export__.project_task_2386_dd162357 | retail product setup | Sprint 2104 | 2021-01-18 | Configuration | KMI: Help (P41) | Levi Barnes | Levi Barnes | 1.17 | 0 |  |  |  | Complete | KMI Zeolite | 5734 | 0 | -1.17 | 0 | 64
__export__.project_task_2292_d5579335 | Deerfield Portal Access | Sprint 2105 | 2021-01-25 | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 0 | 0 |  |  |  | Complete | EquityTeam | 5890 | 0 | 0 | 0 | 75.1049
__export__.project_task_2057_4855c868 | Set defaults on inventory valuation methods on product categories | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Nick Foy | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6236 | 0 | 0 | 0 | 154.9519
__export__.project_task_2029_7a0effcb | salesorder add products smart button | Sprint 2053 | 2020-12-28 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 6.5 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 6403 | 6.3333 | -0.16667 | 0 | 124
__export__.project_task_1675_1902d96f | Add CI info to applicant | Sprint 2049 | 2020-11-30 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 2.92 | 97.33 |  |  |  | Complete | EquityTeam | 6941 | 3 | 0.08 | 0 | 48.6355
__export__.project_task_1631_b36919d7 | Coaching | Sprint 2047 | 2020-11-16 | Configuration | CPBids: ecoATM Onboarding (P35) | Nick Foy |  | 1 | 0 |  |  |  | Complete | Cellpoint Corporation | 7198 | 0 | -1 | 0 | 0
__export__.project_task_1416_ec97fe03 | Integration with IL2000 |  |  | Configuration | Wild Leaf: IL2000 Integration (P40) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 8088 | 0 | -10 | 0 | 319.2064
__export__.project_task_1063_d3781cb5 | Seller Permissions Group: Hide Seller Profile from Menu | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_844_14b43460 | update data through notifications (8 types of notification) iOS-Implementation | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 8 | 8 | 0.00018745 | 347.2516
iOS
__export__.project_task_260_3f60b1e9 | Delete Auction HQZAJ | Sprint 22 | 2020-07-12 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10366 | 0 | 0 | 12.6325 | 0
__export__.project_task_161_fbb8e6ff | 2.1.2 Edit(3 hours) |  |  | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Cancelled | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 1536
__export__.project_task_4631_b0c7e30c | Custom fields on Product Template should be inherited on Product Product | Sprint 2135 | 2021-08-23 | Bug Fix | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 2.33 | 77.67 |  | SPLN |  | Complete | Cellpoint Corporation | 702 | 3 | 0.67 | 0 | 77.2595
__export__.project_task_4237_70dbd4ce | Search by Name, Email, Company name and phone/cell no | Sprint 2129 | 2021-07-12 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 4.42 | 88.4 |  | SPLN | 1 | Complete | Zuma Sales LLC | 1662 | 5 | 0.58 | 4.4122e-05 | 65.7073
__export__.project_task_3980_f624d115 | Training on how to create tags for pipelines |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2219 | 0 | 0 | 194.4788 | 253.4899
__export__.project_task_3924_6c1acc08 | Update client after uploading latest DB and to ask them to start work on | Sprint 2124 | 2021-06-07 | Other | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  | Odoo Migration |  | Complete | Zuma Sales LLC | 2334 | 0 | 0 | 214.4752 | 57.4674
__export__.project_task_3461_ce338e1a | Initiate open issues and create tickets where necessary | Sprint 2133 | 2021-08-09 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 460.9911 | 520.0192
__export__.project_task_3027_be94efd3 | Install the operation system and networking software |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0 | 206.3324
__export__.project_task_3001_df8efb50 | Personality scatter chart | Sprint 2128 | 2021-07-05 | Development | PWX: Survey (P70) | Levi Barnes | Raheel Aslam | 12.5 | 96.15 |  | Tech Review | 4 | Cancelled | EquityTeam | 4428 | 13 | 0.5 | 0 | 621.6376
__export__.project_task_2670_7275f501 | Fw: Issues with personal info from employee profiles showing up as part of employee id? |  |  | Bug Fix | PWX: Help (P23) | Levi Barnes | Fahad Hassan | 0.5 | 0 |  |  |  | Complete | EquityTeam | 5353 | 0 | -0.5 | 0 | 222.4933
__export__.project_task_2616_c1ea7f73 | FW: emails from Odoo sent to clients | Sprint 2117 | 2021-04-19 | Configuration | PWX: Help (P23) | Levi Barnes |  | 1.42 | 0 |  |  |  | Complete | EquityTeam | 5524 | 0 | -1.42 | 0 | 520.1469
__export__.project_task_2080_52403d95 | Billing - Direct cost billing: Show a link between the Vendor Bill and the Customer Invoice | Sprint 2102 | 2021-01-04 | Development | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 3.58 | 71.6 |  |  |  | Complete | Wild Leaf Beverage | 6194 | 5 | 1.42 | 0 | 138.9517
__export__.project_task_2019_aab160a2 | Export all applications with all fields from v13 to v14 | Sprint 2104 | 2021-01-18 | Configuration | PWX: Help (P23) | Levi Barnes | Danish Hassan | 5.25 | 87.5 |  |  |  | Complete | EquityTeam | 6434 | 6 | 0.75 | 0 | 232
__export__.project_task_1977_0acc7d96 | P37: Parent task for Product Picture Set-Up |  |  | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 0 | -5.84 | 14.4117 | 192
__export__.project_task_1741_e89b9bfb | iOS application submit to store | Sprint 2049 | 2020-11-30 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 6850 | 0 | 0 | 0.03774 | 1.7964
__export__.project_task_1723_e8b52da9 | R2 Yes/No and R2 Expiry Date Fields on backend | Sprint 2053 | 2020-12-28 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 5.17 | 100 |  |  |  | Complete | Cellpoint Corporation | 6874 | 4 | -1.17 | 0 | 193.1605
__export__.project_task_1042_8853cb39 | Clicking Save populates the Create Auction page "lot" field with the Lot that was just saved | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_159_d801b709 | Webkul Task - odoo Backend | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 728
__export__.project_task_142_51737554 | 1. Add Product | Sprint 28 | 2020-08-24 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 0
__export__.project_task_4629_3659164f | UEDF ASN should not update IMEI UEDF Status and UEDF File | Sprint 2135 | 2021-08-23 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 4.83 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 704 | 3 | -1.83 | 0 | 77.4211
Priority
__export__.project_task_4229_2cdae64b | Ninja Dashboard | Sprint 2129 | 2021-07-12 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 2.17 | 43.4 |  | SPLN |  | Complete | Zuma Sales LLC | 1683 | 5 | 2.83 | 0 | 80.0192
__export__.project_task_3979_86d55abd | Restrict Contacts Duplication |  |  | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2219 | 0 | 0 | 194.5335 | 253.5446
__export__.project_task_3961_bf0ff94d | VAT on direct invoice creation issue | Sprint 2128 | 2021-07-05 | Development | MMH Dr. Clark: Help (P106) | Naseeb Razaq | Muhammad Bilal | 23.33 | 100 |  | SPLN | 4 | Complete | Mountain Meadow Herbs | 2239 | 23 | -0.33 | 0 | 218.75
__export__.project_task_3489_637fc4af | All Sales Orders in the correct state (Quotation versus Sales Order) | Sprint 2127 | 2021-06-28 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0.5 | 0 |  | SPLN |  | Complete | Zuma Sales LLC | 3483 | 0 | -0.5 | 460.9906 | 364
__export__.project_task_3460_72b6b75b | Initiate using the live Odoo site | Sprint 2133 | 2021-08-09 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3484 | 0 | 0 | 460.9911 | 520.0192
__export__.project_task_3026_be94efd2 | Back-up existing odoo.sh install |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4355 | 0 | 0 | 0 | 206.3324
__export__.project_task_2655_b92700e2 | General 2105 | Sprint 2107 | 2021-02-01 | Internal Time Tracking | PWX: Help (P23) | Levi Barnes | Levi Barnes | 2 | 0 |  |  |  | Complete | EquityTeam | 5381 | 0 | -2 | 0 | 23.6544
__export__.project_task_2439_dfd8a75d | PropertyWorx: Deployment sprint 2103 | Sprint 2105 | 2021-01-25 | Configuration | PWX: Help (P23) | Levi Barnes | Wajahat Ali | 2 | 0 |  |  |  | Complete | EquityTeam | 5578 | 0 | -2 | 0 | 8.4218
__export__.project_task_2378_a2b6ada2 | contact webkul for demo | Sprint 2104 | 2021-01-18 | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 0 | 0 |  |  |  | Complete | EquityTeam | 5741 | 0 | 0 | 0 | 32.8506
__export__.project_task_291_39c92576 | SLA one to many on helpdesks |  |  | Development | PWX: Help (P23) | Levi Barnes |  | 0.83 | 0 |  |  |  | Cancelled | EquityTeam | 5931 | 0 | -0.83 | 0 | 1200.0192
__export__.project_task_2085_2d01e41e | FW: You have been assigned to issue with emails from workflows not sending in RECRUITING (#49) | Sprint 2102 | 2021-01-04 | Bug Fix | PWX: Help (P23) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | EquityTeam | 6190 | 0 | 0 | 0 | 138.9511
__export__.project_task_1954_bacb7b82 | Assign Products to Categories | Sprint 2052 | 2020-12-21 | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0.17 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 0 | -0.17 | 14.4119 | 108.7706
__export__.project_task_1724_842753bf | R2 Yes/No and R2 Expiry Date Fields:online form | Sprint 2053 | 2020-12-28 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 8 | 100 |  |  |  | Complete | Cellpoint Corporation | 6874 | 7 | -1 | 0 | 193.1396
__export__.project_task_1618_b0ccc303 | Import Locations | Sprint 2047 | 2020-11-16 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 0.67 | 0 |  |  |  | Complete | Wild Leaf Beverage | 7223 | 0 | -0.67 | 0 | 0
__export__.project_task_1548_3beb33b2 | Client Electronic Invoice Delivery Preferences |  |  | Development | Continuant: Customer Invoice Delivery Preferences (P33) | Jeff Gross |  | 27.08 | 100 |  |  |  | Complete | Continuant | 7559 | 40.0833 | -26.4967 | 696 | 736
__export__.project_task_1434_baaeee71 | Barcoding Inventory | Sprint 2049 | 2020-11-30 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 0.75 | 0 |  |  |  | Complete | Wild Leaf Beverage | 8019 | 0 | -0.75 | 0 | 295.8856
__export__.project_task_1057_98e14ffd | Seller Permissions Group: Invite Buyers>Invite Selected Buyers>Add Search Button here for buyers to select | Sprint 32 | 2020-09-21 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 52 | 256
__export__.project_task_1021_61bbffc4 | change label "Marketplace" to "Auctions" | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_231_8f433f39 | Remove Approval Request Email | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Sprint 21 |  | Complete | Cellpoint Corporation | 10478 | 0 | 0 | 27.5064 | 0
__export__.project_task_4619_40363408 | Vendor ASN Import Issues | Sprint 2135 | 2021-08-23 | Bug Fix | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 8.33 | 83.3 |  | SPLN |  | Complete | Cellpoint Corporation | 720 | 10 | 1.67 | 0 | 79.9416
Priority
__export__.project_task_4227_d87386a7 | NewLiftParts.com Automatic Lead creation | Sprint 2135 | 2021-08-23 | Development | Zuma: Help (P97) | Fahad Hussain Malik |  | 0 | 0 |  | SPLN |  | Cancelled | Zuma Sales LLC | 1683 | 0 | 0 | 0 | 276.8652
__export__.project_task_4152_da5249ba | Customs Document: Attachment show to invoice | Sprint 2129 | 2021-07-12 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Raheel Aslam | 19 | 100 |  | SPLN | 4 | Complete | Zuma Sales LLC | 1830 | 18 | -1 | 94.5951 | 105.5873
__export__.project_task_3978_4ac48676 | Web forms integration with lead/Pipeline form |  |  | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 2219 | 0 | 0 | 194.5438 | 253.5549
__export__.project_task_3459_38340737 | Obtain approval for beginning production | Sprint 2133 | 2021-08-09 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 460.9911 | 520.0192
__export__.project_task_3036_9b6ce3b0 | Setup PrintNode Application for WildLeaf Las Vegas |  |  | Development | Wild Leaf: Las Vegas Go-Live (P57) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4374 | 0 | 0 | 0 | 209.5816
__export__.project_task_2938_85f6736f | Create estimate for setting up Odoo v14 for client |  |  | Other | MMH: Transition to Odoo v15 (P82) | Naseeb Razaq |  | 1.17 | 0 |  |  |  | Cancelled | Mountain Meadow Herbs | 4550 | 0 | -1.17 | 720 | 987.1869
__export__.project_task_2690_81d2ebe8 | Client Electronic Invoice Delivery Preferences:Part2 | Sprint 2108 | 2021-02-08 | Development | Continuant: Customer Invoice Delivery Preferences (P33) | Nick Foy | Fahad Hassan | 10.25 | 100 |  |  |  | Complete | Continuant | 5337 | 6 | -4.25 | 0 | 146.4156
__export__.project_task_2392_4a591df9 | General 2103 |  |  | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 1 | 0 |  |  |  | Complete | EquityTeam | 5716 | 0 | -1 | 0.0057359 | 22.741
__export__.project_task_2374_4070d161 | Deployment 2101 Property Worx | Sprint 2104 | 2021-01-18 | Configuration | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 0.58 | 58 |  | Difficulty 1 |  | Complete | EquityTeam | 5745 | 1 | 0.42 | 0 | 20.3464
__export__.project_task_2265_0f87bc69 | Employee Training & Skill Improvement plan. |  |  | Internal Training | Silverdale: Help (P12) | Faisal Huda Khan |  | 0 | 0 | is this done? |  |  | Planning | Silverdale Technology LLC | 5912 | 0 | 0 | 0 | 0
__export__.project_task_2215_c5a3947a | Move CRM Opportunities to new OpCo | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy |  | 0.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5998 | 0 | -0.25 | 0 | 90.9508
__export__.project_task_1960_27e4a98d | Create ecommerce categories | Sprint 2052 | 2020-12-21 | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0.17 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 0 | -0.17 | 14.4119 | 108.7756
__export__.project_task_1676_508277f0 | Default for Buyer Name | Sprint 2049 | 2020-11-30 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 4 | 80 |  |  |  | Complete | Cellpoint Corporation | 6938 | 5 | 1 | 0 | 7.9875
__export__.project_task_1589_9c9314cd | Daily Auctions Data and Other Data Import (For Timesheets) |  |  | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Faizan Zia Malik | 701.33 | 100 |  |  |  | Complete | Cellpoint Corporation | 7399 | 648.8333 | -52.4967 | 968 | 1578.8611
__export__.project_task_1569_97166379 | Deployment & Rollback Process | Sprint 2047 | 2020-11-16 | Configuration | Silverdale: Help (P12) | Levi Barnes | Muzher Siddique | 0.5 | 0 |  |  |  | Complete | Silverdale Technology LLC | 7449 | 0 | -0.5 | 0.03122 | 74.1668
__export__.project_task_1064_0c36c8b5 | Seller Permissions Group: Make Seller Profile Fields Read Only | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_914_42b7999e | All auctions to detail page and detail page to all auction screen data updation Android-Implementation | Sprint 31 | 2020-09-14 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 2 | 2 | 0.00016651 | 322.1118
Android
__export__.project_task_216_996dd98d | All Manifest Download | Sprint 21 | 2020-07-06 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Sprint 21 |  | Complete | Cellpoint Corporation | 10763 | 0 | 0 | 89.3944 | 0
__export__.project_task_4530_163015c5 | Print Labels and Scan labels corrections | Sprint 2134 | 2021-08-16 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Muhammad Bilal | 10.67 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 841 | 6 | -4.67 | 0 | 100.9228
__export__.project_task_4226_14a3e95c | Setup - Odoo Live Chat | Sprint 2129 | 2021-07-12 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 2 | 100 |  |  |  | Complete | Zuma Sales LLC | 1683 | 2 | 0 | 0 | 53.8272
__export__.project_task_4118_18514c2a | Header/Footer Migration | Sprint 2127 | 2021-06-28 | Development | DGS: Odoo Website Migration (P126) | Fahad Hussain Malik | Danish Hassan | 1 | 25 |  | SPLN | 2 | Complete | DG Solutions Inc. | 1973 | 4 | 3 | 0.68853 | 88.6885
__export__.project_task_3977_5493e7cd | WhatsApp Odoo Integration |  |  | Development | Zuma: CRM (P130) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 2219 | 0 | 0 | 194.5396 | 101.5485
__export__.project_task_3927_e794e290 | Push the custom code | Sprint 2124 | 2021-06-07 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  | Odoo.sh Migration |  | Complete | Zuma Sales LLC | 2333 | 0 | 0 | 214.2444 | 57.2366
__export__.project_task_3266_411b0a30 | WIldLeaf: Deposit invoices default to 50% down payment | Sprint 2115 | 2021-04-05 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Osama Khalid | 4.42 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4064 | 4 | -0.42 | 2.1719e-05 | 107.9611
__export__.project_task_3025_86a2815c | Setup configurations management plan |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4401 | 0 | 0 | 0 | 220
__export__.project_task_2755_b341d7ec | Create "Brand Strategy" app | Sprint 2109 | 2021-02-15 | Development | PWX: Strategic Planning (P43) | Levi Barnes | Raheel Aslam | 1.33 | 53.2 |  |  |  | Complete | EquityTeam | 5094 | 2.5 | 1.17 | 0 | 96.7861
__export__.project_task_2644_c3b86fae | Deployment 2104: WildLeaf | Sprint 2107 | 2021-02-01 | Configuration | Wild Leaf: Help (P22) | Wajahat Ali | Wajahat Ali | 1 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5410 | 0 | -1 | 1.2184 | 1.3432
__export__.project_task_2364_a8a40496 | Internal: Project UX Review: remove select column when creating products | Sprint 2105 | 2021-01-25 | Development | Dialed Supply: Help (P21) | Levi Barnes | Raheel Aslam | 0.67 | 100 |  |  |  | Complete | Dialed Supply | 5762 | 0.33333 | -0.33667 | 0 | 254.0281
__export__.project_task_2340_726680f6 | AV Project Room Export Button | Sprint 2105 | 2021-01-25 | Development | Continuant: AV Warehouse (P34) | Nick Foy | Kaleem Khan | 4.08 | 100 |  | MA Review |  | Complete | Continuant | 5830 | 2.5 | -1.58 | 88 | 262.1067
__export__.project_task_2228_fedb278a | Move Projects to OpCo and create a new field for Production Location | Sprint 2102 | 2021-01-04 | Studio | Wild Leaf: Single OpCo (P48) | Nick Foy | Nick Foy | 0.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5954 | 0 | -0.25 | 0 | 90.9503
__export__.project_task_2094_0f299f40 | General Time 2053 | Sprint 2053 | 2020-12-28 | Configuration | PWX: Help (P23) | Levi Barnes |  | 1 | 0 |  |  |  | Complete | EquityTeam | 6190 | 0 | -1 | 0 | 16
__export__.project_task_1925_1649b201 | P37: Parent task for Inventory Set-Up |  |  | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6524 | 0 | 0 | 14.4119 | 192
__export__.project_task_1725_00f597b8 | Create an AV Project Pick List :Updated Req | Sprint 2049 | 2020-11-30 | Development | Continuant: AV Warehouse (P34) | Kaesi Lee | Danish Hassan | 5.33 | 100 |  |  |  | Complete | Continuant | 6871 | 4.5 | -0.83 | 0 | 26.955
__export__.project_task_1712_7d8ed5e0 | Heronswood collectors databases |  |  | Development | Heronswood: Collectors Database Phase 1 (P142) | Naseeb Razaq |  | 0 | 0 |  |  |  | Cancelled | Port Gamble Sâ€™Klallam Foundation | 6893 | 0 | 0 | 1272.6223 | 1272.6223
__export__.project_task_1516_a9a2c6f6 | Create Azure Server | Sprint 2047 | 2020-11-16 | Configuration | Continuant: Power BI Integration (P30) | Levi Barnes | Muzher Siddique | 0 | 0 |  |  |  | Complete | Continuant | 7680 | 3 | 3 | 0 | 135.1164
__export__.project_task_1370_b6834764 | Test Latest Continuant Database | Sprint 2042 | 2020-10-12 | Development | Continuant: eCommerce (P9) | Kaesi Lee | Anusha | 16 | 0 |  |  |  | Complete | Continuant | 8287 | 0 | -16 | 50.7042 | 120.6698
__export__.project_task_1359_b8f18266 | Odoo 14 | Sprint 2041 | 2020-10-05 | Configuration | PWX: Help (P23) | Levi Barnes |  | 3 | 100 |  |  |  | Complete | EquityTeam | 8373 | 2 | -1 | 184 | 48
__export__.project_task_1221_774d7b9e | Push Notification | Sprint 31 | 2020-09-14 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8772 | 0 | 0 | 0.0080585 | 45.5758
__export__.project_task_1178_4d484a17 | Price Uplift: Use Product Markup Margin Field | Sprint 30 | 2020-09-07 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9029 | 0 | 0 | 0 | 0
__export__.project_task_949_c3500935 | Add Bid for FIGJD | Sprint 26 | 2020-08-10 | Configuration | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9742 | 0 | 0 | 0 | 0
__export__.project_task_232_e792e71e | Show Active Sellers Only | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Sprint 21 |  | Complete | Cellpoint Corporation | 10478 | 0 | 0 | 27.6575 | 0
__export__.project_task_155_28bb35ce | 1.2 Lot Timezone(4 hour) | Sprint 27 | 2020-08-17 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 0
__export__.project_task_4489_dc6e20b1 | Set-up of the Vendor Description and SKU for each product to avoid sending Customer data to Vendors | Sprint 2135 | 2021-08-23 | Configuration | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Farman Ahmad Cheema | 0 | 0 |  | SPLN |  | Complete | Cellpoint Corporation | 892 | 0 | 0 | 3.6541e-05 | 139.0598
__export__.project_task_4380_1b7dcd09 | Superseded Product Field On Product Form | Sprint 2132 | 2021-08-02 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 5.17 | 100 |  |  | 2 | Complete | Zuma Sales LLC | 1160 | 4.5 | -0.67 | 0 | 68
__export__.project_task_4218_22dd6008 | Deploy to Production (Zuma - 2127) | Sprint 2128 | 2021-07-05 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hassan | 2.83 | 70.75 |  |  |  | Complete | Zuma Sales LLC | 1714 | 4 | 1.17 | 1.1767e-05 | 3.425
__export__.project_task_3976_46704b26 | Training on how to sent quotations |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 2219 | 0 | 0 | 194.5653 | 253.5764
__export__.project_task_3457_42e58051 | Confirm Zuma's senior management commitment via the client success team | Sprint 2123 | 2021-05-31 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.0081 | 284
__export__.project_task_3024_0523098e | Confirmation from client on existing data cleaning |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 4401 | 0 | 0 | 0 | 315.5558
__export__.project_task_2728_b01a8545 | Employee: Scorecard |  |  | Development | PWX: HR (P61) | Levi Barnes |  | 0 | 0 |  |  |  | Cancelled | EquityTeam | 5182 | 0 | 0 | 0 | 790.7244
__export__.project_task_2394_7d5e394f | Testing Odoo: Unit Testing | Sprint 2113 | 2021-03-22 | Configuration | Silverdale: Help (P12) | Levi Barnes | Levi Barnes | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 5715 | 9 | 9 | 0 | 416
__export__.project_task_2308_9460bc7d | Make Analytic Account Mandatory on Invoice Lines | Sprint 2105 | 2021-01-25 | Studio | Wild Leaf: Help (P22) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5877 | 0 | 0 | 104 | 278.0947
__export__.project_task_2013_94c4d98f | Review 3rd Party Apps: universal appointments |  |  | Development | PWX: Help (P23) | Levi Barnes |  | 1.33 | 100 |  |  |  | Complete | EquityTeam | 6437 | 0.5 | -0.83 | 0 | 56.9301
__export__.project_task_1956_f80864b9 | Set all products to Invoice on Ordered Quantities | Sprint 2052 | 2020-12-21 | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0.17 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 0 | -0.17 | 14.4119 | 108.7775
__export__.project_task_1899_5b89e313 | Add LucidChart tab to Project Details | Sprint 2102 | 2021-01-04 | Development | Silverdale: Help (P12) | Nick Foy | Muzher Siddique | 9.45 | 100 |  | Website |  | Complete | Silverdale Technology LLC | 6560 | 6.1667 | -3.2833 | 5.8278e-05 | 230.6334
Project
__export__.project_task_1721_1cc98b52 | Create a new Module for "AV Tracker" Updated Req | Sprint 2049 | 2020-11-30 | Development | Continuant: AV Warehouse (P34) | Kaesi Lee | Danish Hassan | 4.75 | 100 |  |  |  | Complete | Continuant | 6874 | 4 | -0.75 | 0 | 28.464
__export__.project_task_1648_de3d4992 | gucci user creation/invite | Sprint 2048 | 2020-11-23 | Configuration | Moln: Help (P16) | Levi Barnes |  | 1.83 | 73.2 |  |  |  | Complete | Moln Solutions, LLC | 7078 | 2.5 | 0.67 | 0 | 8
__export__.project_task_1605_6d3ec51d | Auto-Create AV Items from Delivery Order Receipt | Sprint 2053 | 2020-12-28 | Development | Continuant: AV Warehouse (P34) | Kaesi Lee | Danish Hassan | 22.42 | 100 |  |  |  | Complete | Continuant | 7342 | 12 | -10.42 | 8 | 128
__export__.project_task_1582_8f7076b9 | Customer Payment Option Configuration | Sprint 2051 | 2020-12-14 | Development | Continuant: Quotation Management / Automation (P31) | Kaesi Lee | Muzher Siddique | 8.75 | 100 |  |  |  | Complete | Continuant | 7417 | 10 | -53.72 | 0 | 448
__export__.project_task_1478_6e95de2a | CPBids: Delegate Tier One Support to Pakistan Team | Sprint 2047 | 2020-11-16 | Configuration | Silverdale: Help (P12) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 7925 | 0 | 0 | 0 | 170.565
__export__.project_task_1186_020e2800 | Purchase Order: Markup Margin Configuration | Sprint 30 | 2020-09-07 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 8932 | 0 | 0 | 0 | 0
__export__.project_task_1157_52fda384 | Remove Lot Category | Sprint 28 | 2020-08-24 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9202 | 0 | 0 | 0 | 0
__export__.project_task_973_dbe2de7f | Delete Auction XCWHN | Sprint 26 | 2020-08-10 | Configuration | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9600 | 0 | 0 | 0 | 0
__export__.project_task_342_dde57c93 | Carrier: set-up tracking links in Odoo to carrier sites | Sprint 32 | 2020-09-21 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 353.7145 | 425.7145
__export__.project_task_236_457e7a92 | Old Records - Title and Manifest | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Sprint 21 |  | Complete | Cellpoint Corporation | 10478 | 0 | 0 | 40 | 0
__export__.project_task_4452_f5f1f77c | UEDF ASN File | Sprint 2134 | 2021-08-16 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 7.67 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 968 | 7 | -0.67 | 0 | 129.0608
__export__.project_task_4211_a196bdf7 | Deploy to Deployment (Zuma - PDQA - 2127) | Sprint 2128 | 2021-07-05 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hassan | 3.42 | 85.5 |  |  |  | Complete | Zuma Sales LLC | 1735 | 4 | 0.58 | 0.015213 | 8.9872
__export__.project_task_4090_9eeafe23 | Rework to do |  |  | Configuration | Heronswood: Network for Good transition to Odoo (P78) | Naseeb Razaq |  | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 2021 | 0 | 0 | 0.016915 | 56.2975
__export__.project_task_3975_018b53d0 | Reporting- Metrics |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 2219 | 0 | 0 | 194.5753 | 253.5864
__export__.project_task_3931_4475bc20 | Configurations after version upgrade | Sprint 2129 | 2021-07-12 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 10.5 | 100 |  | Odoo Migration |  | Complete | Zuma Sales LLC | 2333 | 9 | -1.5 | 214.0168 | 225.0593
SPLN
__export__.project_task_3653_dce4b31a | Follow-up with the client after they create first email | Sprint 2127 | 2021-06-28 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 0 | 0 |  | SPLN |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.5 | 0.5 | 0.00052273 | 305.1216
__export__.project_task_3023_be94efd2 | Acquiring Customers and Vendors master data |  |  | Configuration | Wild Leaf: Cutover April 1 (P69) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4401 | 0 | 0 | 0 | 220
__export__.project_task_2756_43592bdb | Goals: Main | Sprint 2109 | 2021-02-15 | Development | PWX: Strategic Planning (P43) | Levi Barnes | Raheel Aslam | 2.67 | 66.75 |  |  |  | Complete | EquityTeam | 5094 | 4 | 1.33 | 0 | 96.7808
__export__.project_task_2642_d089171c | Dialed Supply Deployment 2104 | Sprint 2107 | 2021-02-01 | Other | Dialed Supply: Help (P21) | Levi Barnes | Muzher Siddique | 1.5 | 100 |  |  |  | Complete | Dialed Supply | 5411 | 1.5 | 0 | 4.3086e-06 | 1.4056
__export__.project_task_2365_0a2a620b | Internal: Project UX Review: change import products button to create products | Sprint 2105 | 2021-01-25 | Development | Dialed Supply: Help (P21) | Levi Barnes | Raheel Aslam | 0.42 | 100 |  |  |  | Complete | Dialed Supply | 5762 | 0.33333 | -0.086667 | 0 | 254.0306
__export__.project_task_2207_d1c7c941 | Move the inventory | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy |  | 1.75 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5998 | 0 | -1.75 | 0 | 90.9458
__export__.project_task_1929_46bd08c5 | P37: Parent task for Settings Set-Up | Sprint 2052 | 2020-12-21 | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6524 | 0 | 0 | 14.4119 | 108.7797
__export__.project_task_1636_6b2b7689 | Add different validation checks. | Sprint 2047 | 2020-11-16 | Development | Continuant: AV Warehouse (P34) | Kaesi Lee | Danish Hassan | 3.67 | 100 |  |  |  | Complete | Continuant | 7114 | 3 | -0.67 | 0 | 43.5408
__export__.project_task_1634_8d032c1f | Research Chatter expand/minimize Option | Sprint 2048 | 2020-11-23 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 3.25 | 81.25 |  |  |  | Complete | EquityTeam | 7180 | 4 | 0.75 | 0 | 21.1357
__export__.project_task_1633_8aba35c6 | Set-Up PWX Projects | Sprint 2050 | 2020-12-07 | Configuration | PWX: Help (P23) | Levi Barnes |  | 1.5 | 100 |  |  |  | Complete | EquityTeam | 7181 | 5.25 | -0.33 | 0 | 182.9873
__export__.project_task_1620_1f1fdf1e | New Seller Onboarding: EcoATM: Pre-Sales | Sprint 2047 | 2020-11-16 | Configuration | CPBids: ecoATM Onboarding (P35) | Nick Foy |  | 5 | 0 |  |  |  | Complete | Cellpoint Corporation | 7223 | 0 | -5 | 0 | 22.9992
__export__.project_task_1519_1c23dc02 | Data Migration from Odoo to Azure: Data Transfer Wizard | Sprint 2046 | 2020-11-09 | Development | Continuant: Power BI Integration (P30) | Levi Barnes | Fahad Hassan | 22 | 100 |  |  |  | Complete | Continuant | 7680 | 7 | -15 | 0 | 128
__export__.project_task_1115_4a02cffc | Tech Data: Generate Shipping Quoatation | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9456 | 0 | 0 | 0 | 0
__export__.project_task_917_abd93d54 | API:Download csv :Postman | Sprint 27 | 2020-08-17 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9927 | 0.5 | 0.5 | 0 | 0
Postman
__export__.project_task_229_6003e250 | Create Table for Sprint | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Deepak Krishnan |  | 0 | 0 |  | Sprint 21 |  | Complete | Cellpoint Corporation | 10589 | 0 | 0 | 37.2593 | 0
__export__.project_task_4620_9e08de74 | Vendor ASN Import and Validate Serial Button only on Receipt | Sprint 2135 | 2021-08-23 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Danish Hassan | 3.2 | 91.43 |  | SPLN |  | Complete | Cellpoint Corporation | 720 | 3.5 | 0.3 | 0 | 79.8983
__export__.project_task_3963_a23bdbf6 | Video and Picture Editing |  |  | Internal Time Tracking | Silverdale: Help (P12) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 2238 | 0 | 0 | 0 | 378.6463
__export__.project_task_3926_72156315 | Project create on sh. | Sprint 2123 | 2021-05-31 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  | Odoo.sh Migration |  | Complete | Zuma Sales LLC | 2333 | 0 | 0 | 214.264 | 13.7634
__export__.project_task_3651_1a884412 | Demo second email to the client and get feedback | Sprint 2127 | 2021-06-28 | Configuration | Heronswood: Replace Constant Contact with Odoo (P80) | Naseeb Razaq |  | 0 | 0 |  | SPLN |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3174 | 0.33333 | 0.33333 | 0.00052273 | 305.1308
__export__.project_task_3455_0219c872 | Verify that users are trained | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3484 | 0 | 0 | 461.9835 | 661.9835
__export__.project_task_3435_9fade3f8 | Add pricelists | Sprint 2131 | 2021-07-26 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  | SPLN |  | Complete | Zuma Sales LLC | 3484 | 4 | 4 | 454.3646 | 523.7921
__export__.project_task_3314_be6d5a8b | Product/Package/Lot/Quantity Barcode Label | Sprint 2116 | 2021-04-12 | Development | Wild Leaf: Help (P22) | Jeff Gross | Muhammad Bilal | 4.58 | 100 |  |  | 3 | Complete | Wild Leaf Beverage | 3870 | 3.5 | -1.08 | 0 | 57.6141
__export__.project_task_2986_1e3b8b0c | FW: Christmas Light Pros Work Flow |  |  |  | Silverdale: Biz Dev (P63) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 4510 | 0 | 0 | 0 | 320
__export__.project_task_2650_b152936a | Test the access keys provided by ecoATM | Sprint 2107 | 2021-02-01 | Development | Cellpoint: ecoATM API (P50) | Nick Foy | Muzher Siddique | 3 | 100 |  |  |  | Complete | Cellpoint Corporation | 5406 | 2.5 | -0.5 | 0 | 15.0132
__export__.project_task_2393_d3f1bf80 | Additional av.tracker item fields | Sprint 2105 | 2021-01-25 | Development | Continuant: AV Warehouse (P34) | Nick Foy | Kaleem Khan | 2.42 | 100 |  |  |  | Complete | Continuant | 5716 | 1.5 | -0.92 | 64 | 238.1042
__export__.project_task_2348_9ff11ed0 | create task per SO line item | Sprint 2105 | 2021-01-25 | Development | PWX: Field Service to Invoicing (P47) | Levi Barnes | Raheel Aslam | 8.33 | 100 |  |  |  | Complete | EquityTeam | 5773 | 4.1667 | -4.1633 | 0 | 262.0897
__export__.project_task_252_ac940356 | Import Silverdale eLearning for Odoo | Sprint 2110 | 2021-03-01 | Configuration | PWX: Help (P23) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | EquityTeam | 5931 | 0 | 0 | 0 | 357.0294
__export__.project_task_1955_17da736f | Add Internal References | Sprint 2052 | 2020-12-21 | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 0 | 0 | 14.4119 | 59.9825
__export__.project_task_1734_703de6e1 | Add a flag for Test and Demo Auctions | Sprint 2102 | 2021-01-04 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 4.33 | 86.6 |  |  |  | Complete | Cellpoint Corporation | 6867 | 5 | 0.67 | 0 | 298.9447
__export__.project_task_1673_3f9c8153 | Fwd: Help! Fouled Up Import | Sprint 2049 | 2020-11-30 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 0.75 | 100 |  |  |  | Complete | Wild Leaf Beverage | 6957 | 0.5 | -0.25 | 3.93 | 8
__export__.project_task_1517_069c868c | Data Migration from Odoo to Azure: Connector Configuration | Sprint 2046 | 2020-11-09 | Development | Continuant: Power BI Integration (P30) | Levi Barnes | Fahad Hassan | 4.17 | 100 |  | Need Assistance |  | Complete | Continuant | 7680 | 2 | -2.17 | 0 | 128
__export__.project_task_974_2cdb6932 | Replace Access Keys | Sprint 26 | 2020-08-10 | Configuration | Cellpoint CPBids: Help (P7) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9586 | 0 | 0 | 0.033363 | 0
__export__.project_task_846_f7b4a411 | All auctions to detail page and detail page to all auction screen data updation iOS-Implementation | Sprint 31 | 2020-09-14 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 2 | 2 | 0.00018745 | 322.1244
iOS
__export__.project_task_346_c71b42d0 | Production Release #3 | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 0.00032117 | 0
__export__.project_task_258_8941c47c | Buyers-> Rexi | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Sprint 21 |  | Complete | Cellpoint Corporation | 10375 | 0 | 0 | 0.27403 | 0
__export__.project_task_153_88bfb282 | 1.6.5 Live - Demo(4 hours) | Sprint 27 | 2020-08-17 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 0
__export__.project_task_4411_331f018f | Print Labels Data and Field Mapping | Sprint 2135 | 2021-08-23 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Muhammad Bilal | 18.32 | 96.42 |  | SPLN |  | Complete | Cellpoint Corporation | 1087 | 19 | 0.68 | 0 | 165.4214
__export__.project_task_4150_0dbfc57a | UPS Integration | Sprint 2129 | 2021-07-12 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 4 | 100 |  | SPLN |  | Complete | Zuma Sales LLC | 1830 | 2 | -2 | 94.6661 | 76.2117
__export__.project_task_3839_04d02a97 | Post Deployment List on Tickets/Tasks |  |  | Development | Silverdale: Help (P12) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 2669 | 0 | 0 | 0.00014151 | 474.1393
__export__.project_task_3454_ccc839f9 | Confirm the production cutover |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 460.9911 | 440
__export__.project_task_3441_888b2e43 | Ensure proper setup of companies, accounting part, languages, banks and currencies etc | Sprint 2131 | 2021-07-26 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 2 | 100 |  | SPLN |  | Complete | Zuma Sales LLC | 3484 | 2 | 0 | 453.86 | 523.4358
__export__.project_task_3303_b2947dcb | Deployement 06-04-2021:Mid-America | Sprint 2116 | 2021-04-12 | Configuration | Mid-America: Help (P37) | Levi Barnes | Wajahat Ali | 2.25 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 3892 | 0 | -2.25 | 0.011735 | 64.0948
__export__.project_task_2943_8bbe4475 | Workcenters |  |  | Configuration | Wild Leaf: Wildpack Printing (P68) | Umer Farooq |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4543 | 0 | 0 | 0.0076829 | 251.1082
__export__.project_task_2361_b04a3c1c | Internal: Project UX Review: Rename button to Fetch All Products | Sprint 2105 | 2021-01-25 | Development | Dialed Supply: Help (P21) | Levi Barnes | Raheel Aslam | 0.42 | 100 |  |  |  | Complete | Dialed Supply | 5762 | 0.33333 | -0.086667 | 0 | 254.0328
__export__.project_task_2305_fd8607cb | Category filter does not work on biding page |  |  | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 4.17 | 100 |  |  |  | Complete | Cellpoint Corporation | 5885 | 1 | -3.17 | 0.077567 | 296.7465
__export__.project_task_2213_0af2f048 | Change all Users default Company to OpCo | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy |  | 0.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5998 | 0 | -0.25 | 0 | 90.9475
__export__.project_task_2129_9bc6ee1a | FW: You have been assigned to Edits to Recruitment Module (#45): source disappears | Sprint 2102 | 2021-01-04 | Bug Fix | PWX: Help (P23) | Levi Barnes | Danish Hassan | 2.5 | 0 |  |  |  | Complete | EquityTeam | 6072 | 0 | -2.5 | 0 | 114.9656
__export__.project_task_1968_c29bd972 | Import Customer Basic Details | Sprint 2052 | 2020-12-21 | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0.17 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 0 | -0.17 | 14.4119 | 108.8128
__export__.project_task_1543_f7db4ddb | Customer Invoice Portal |  |  | Development | Continuant: Customer Portal AR (P32) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 7559 | 0 | -27.96 | 0 | 271.3058
__export__.project_task_1514_92791e4d | Data Migration from Odoo to Azure: Export Preview | Sprint 2047 | 2020-11-16 | Development | Continuant: Power BI Integration (P30) | Levi Barnes | Fahad Hassan | 14.87 | 100 |  | Need Assistance |  | Complete | Continuant | 7680 | 3 | -11.87 | 0 | 192
__export__.project_task_1044_a7ca8b85 | Move Main "Lot Category" field to the information Tab. | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_957_ed7cc677 | Match Product Template to GFK Fields | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 9695 | 0 | 0 | 56 | 0
__export__.project_task_819_6f916a68 | Lot view iOS-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
iOS
__export__.project_task_235_bafeb925 | New Buyer Registration odoo | Sprint 21 | 2020-07-06 | Development | Cellpoint CPBids: Help (P7) | Deepak Krishnan |  | 0 | 0 |  | Sprint 21 |  | Complete | Cellpoint Corporation | 10478 | 0 | 0 | 30.9114 | 0
__export__.project_task_154_279c7fe6 | 1.4 Lot Manifest(2 hours) | Sprint 27 | 2020-08-17 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 0
__export__.project_task_4632_f33cd55d | ASN 1 - Data not correct | Sprint 2135 | 2021-08-23 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 9.17 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 702 | 5 | -4.17 | 0 | 76.9982
__export__.project_task_3577_3719bdc6 | Changing automation scripts to run on QA Server |  |  | Development | Wild Leaf: Help (P22) | Levi Barnes |  | 5.67 | 0 |  |  | 4 | Cancelled | Wild Leaf Beverage | 3236 | 0 | -5.67 | 0 | 344
__export__.project_task_3546_1b8b53d5 | Filters are working properly on Pipeline, ie: Phone number is not able to filter out | Sprint 2133 | 2021-08-09 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0.17 | 0 |  |  |  | Complete | Zuma Sales LLC | 3358 | 0 | -0.17 | 436.9906 | 587.8022
__export__.project_task_3453_999b10f8 | Conduct production readiness verification |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3484 | 0 | 0 | 460.9911 | 453.7989
__export__.project_task_3248_6462ec77 | WildLeaf: Separate Sequence for Deposit Invoice | Sprint 2115 | 2021-04-05 | Development | Wild Leaf: Help (P22) | Jeff Gross | Danish Hassan | 11.4 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4159 | 2 | -9.4 | 1.0484e-05 | 123.2017
__export__.project_task_2942_820d1787 | Vendor List and payment terms |  |  | Configuration | Wild Leaf: Wildpack Printing (P68) | Umer Farooq |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 4543 | 0 | 0 | 0.0096922 | 251.1727
__export__.project_task_2696_5c65f7ac | validate doc |  |  | Configuration | PWX: Help Desk (P65) | Levi Barnes |  | 0 | 0 |  |  |  | Cancelled | EquityTeam | 5333 | 0 | 0 | 215.3727 | 915.7205
__export__.project_task_2337_a90540e8 | Update reserve and populate serial numbers | Sprint 2105 | 2021-01-25 | Development | Continuant: AV Warehouse (P34) | Nick Foy | Kaleem Khan | 2.5 | 83.33 |  |  |  | Complete | Continuant | 5837 | 3 | 0.5 | 88.9718 | 263.0746
__export__.project_task_2120_de9e7ea1 | Add LucidChart tab to Task Details | Sprint 2102 | 2021-01-04 | Development | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 0.67 | 100 |  | Website |  | Complete | Silverdale Technology LLC | 6080 | 1 | -0.09 | 0 | 118.4843
Project
__export__.project_task_2011_f4988e18 | Review 3rd Party Apps: recurring task checklist |  |  | Development | PWX: Help (P23) | Levi Barnes |  | 0.67 | 100 |  |  |  | Complete | EquityTeam | 6437 | 0.5 | -0.17 | 0 | 56.9353
__export__.project_task_1688_55ecd8e3 | Set-up Odoo SH | Sprint 2049 | 2020-11-30 | Configuration | Mid-America: Help (P37) | Muhammad Afzaal | Muzher Siddique | 0.2 | 20 |  |  |  | Complete | Mid-America Gardens, LLC | 6916 | 1 | 0.8 | 0 | 39.8906
__export__.project_task_1283_42d8e565 | Database Restore Issue | Sprint 32 | 2020-09-21 | Bug Fix | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 8548 | 0 | 0 | 0 | 94.0748
__export__.project_task_1085_052e3577 | eCommerce Select Customer: Filter Results | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9532 | 0 | 0 | 0 | 0
__export__.project_task_1024_542f98e4 | Hide Number of My watch Bidders | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_828_ef9d130a | Category list iOS-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_4630_2c1f0ade | Different SKU in one Pallet not allowed | Sprint 2134 | 2021-08-16 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 1.42 | 47.33 |  | SPLN |  | Complete | Cellpoint Corporation | 702 | 3 | 1.58 | 0 | 69.4128
Priority
__export__.project_task_4149_912670b6 | Ecommerce setup | Sprint 2128 | 2021-07-05 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 1 | 100 |  | SPLN |  | Complete | Zuma Sales LLC | 1830 | 1 | 0 | 94.7194 | 57.7116
__export__.project_task_3494_6d2137b3 | Zuma Tasks and Tickets |  |  | Internal Time Tracking | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 94.25 | 94.25 |  |  |  | Complete | Zuma Sales LLC | 3477 | 100 | 5.75 | 456 | 715.5683
__export__.project_task_3452_8620525b | Review the production readiness verification checklist |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3484 | 0 | 0 | 460.9911 | 453.7961
__export__.project_task_2928_724fdbc3 | Deployment 2110: Mid-America Gardens: Odoo Launch | Sprint 2112 | 2021-03-15 | Configuration | Mid-America: Help (P37) | Levi Barnes | Wajahat Ali | 1.5 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4568 | 0 | -1.5 | 2.3406e-06 | 3.9039
__export__.project_task_2689_b8204bc3 | Client Electronic Invoice Delivery Preferences:Part1 | Sprint 2109 | 2021-02-15 | Development | Continuant: Customer Invoice Delivery Preferences (P33) | Nick Foy | Muzher Siddique | 19.92 | 100 |  |  |  | Complete | Continuant | 5337 | 14 | -5.92 | 0 | 146.4706
__export__.project_task_2358_405dcd0e | Internal: Project UX Review: Generalize configuration menu | Sprint 2105 | 2021-01-25 | Development | Dialed Supply: Help (P21) | Levi Barnes | Raheel Aslam | 1.25 | 100 |  |  |  | Complete | Dialed Supply | 5762 | 0.91667 | -0.33333 | 0 | 254.035
__export__.project_task_2214_c1ee911f | Move CRM Sales Teams to new OpCo | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy |  | 0.17 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5998 | 0 | -0.17 | 0 | 90.9481
__export__.project_task_1573_142c7338 | Invoices Ready for AR Team | Sprint 2109 | 2021-02-15 | Development | Continuant: Customer Invoice Delivery Preferences (P33) | Kaesi Lee | Raheel Aslam | 16.05 | 100 |  |  |  | Complete | Continuant | 7442 | 5 | -11.05 | 0 | 592
__export__.project_task_933_be8743bb | Account Manager Show and Tell | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 9912 | 0 | 0 | 0 | 0
__export__.project_task_824_b51ecc95 | Download csv iOS-Implementation | Sprint 30 | 2020-09-07 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_149_921a91a5 | 3.1 Create Seller(3 hours) | Sprint 27 | 2020-08-17 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 0
__export__.project_task_4393_8ad76ecf | Scan Master Carton Labels | Sprint 2134 | 2021-08-16 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 12.17 | 86.93 |  | SPLN |  | Complete | Cellpoint Corporation | 1154 | 14 | 1.83 | 0 | 173.2863
__export__.project_task_3966_baa46b9f | Product master importsâ€‹ | Sprint 2132 | 2021-08-02 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 20.08 | 100 |  |  |  | Complete | Zuma Sales LLC | 2238 | 20 | -0.08 | 191.777 | 345.5378
__export__.project_task_3451_6fe45752 | Verify pre-conversion data cleanup has been completed | Sprint 2124 | 2021-06-07 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.0624 | 264.0544
__export__.project_task_3379_cee6acb9 | Task Assignation & Tracking |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 3 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 3551 | 0 | -3 | 0.0052696 | 660.2733
__export__.project_task_2851_f4f47ea7 | Add a last activity filter for employees | Sprint 2116 | 2021-04-12 | Development | Wild Leaf: Help (P22) | Jeff Gross | Danish Hassan | 0 | 0 |  |  | 1 | Complete | Wild Leaf Beverage | 4683 | 0 | 0 | 8 | 248
__export__.project_task_2823_5a070e95 | Deployment 2109: Mid-America Garden | Sprint 2110 | 2021-03-01 | Configuration | Mid-America: Help (P37) | Levi Barnes | Wajahat Ali | 2.5 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4735 | 0 | -2.5 | 0.019264 | 1.2457
__export__.project_task_2202_37681346 | Change Lucky Clover Baltimore to Lucky Clover Packaging (OpCo) | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy |  | 0.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5998 | 0 | -0.25 | 0 | 90.9453
__export__.project_task_2135_240439f7 | FW: You have been assigned to Edits to Recruitment Module (#45): Appointment link | Sprint 2105 | 2021-01-25 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 3.37 | 100 |  |  |  | Complete | EquityTeam | 6072 | 2 | -1.37 | 0 | 326.085
__export__.project_task_2064_bf63e9c6 | Set-Up Asset Management and Depreciation |  |  | Configuration | Wild Leaf: Help (P22) | Jeff Gross | Nick Foy | 1.5 | 0 |  | 2013-01-01 |  | Complete | Wild Leaf Beverage | 6220 | 0 | -1.5 | 376 | 463.2222
__export__.project_task_2015_15103472 | Review 3rd Party Apps: helpdesk |  |  | Development | PWX: Help (P23) | Levi Barnes |  | 0.5 | 100 |  |  |  | Complete | EquityTeam | 6437 | 0.5 | 0 | 0 | 56.9263
__export__.project_task_1612_a7d3e137 | Pull Estimated tax on quotation from Avalara |  |  | Development | Continuant: Quotation Management / Automation (P31) | Kaesi Lee | Danish Hassan | 7.25 | 45.31 |  |  |  | Complete | Continuant | 7245 | 16 | 8.75 | 0 | 119.1433
__export__.project_task_1583_27ead9f2 | Once order is fully paid and received - auto close order | Sprint 2048 | 2020-11-23 | Development | Continuant: Quotation Management / Automation (P31) | Kaesi Lee | Raheel Aslam | 8.08 | 100 |  |  |  | Complete | Continuant | 7417 | 7.0833 | -0.99667 | 0 | 152
__export__.project_task_1236_d60f2e25 | Add increment field to the auction dashboard | Sprint 31 | 2020-09-14 | Studio | Cellpoint: Odoo Back-End (P8) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8717 | 0 | 0 | 0 | 23.5186
__export__.project_task_1127_63f0b0cf | Sales Order: Add Field for Distributor | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9415 | 0 | 0 | 0 | 0
__export__.project_task_4617_92ebfcb2 | POS Label Print Validations | Sprint 2134 | 2021-08-16 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Muhammad Bilal | 4 | 0 |  | SPLN |  | Complete | Cellpoint Corporation | 720 | 0 | -4 | 0 | 72.6027
Priority
__export__.project_task_3950_29f79a3a | Terex products import into odoo | Sprint 2128 | 2021-07-05 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 16 | 100 |  | SPLN | 2 | Complete | Zuma Sales LLC | 2312 | 16 | 0 | 208.4661 | 187.512
__export__.project_task_3450_b7fd325c | Ensure external access to system available | Sprint 2124 | 2021-06-07 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.0848 | 304.0768
__export__.project_task_3377_aa582bd8 | Helpdesk overview & Status Update |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 16.25 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 3551 | 0 | -16.25 | 0.0088098 | 660.7208
__export__.project_task_3238_653b0ce7 | Registration for past events should be disable |  |  | Development | Heronswood: Help (P54) | Jeff Gross | Danish Hassan | 5.58 | 93 |  |  | 1 | Complete | Port Gamble Sâ€™Klallam Foundation | 4182 | 6 | 0.42 | 0 | 129.5179
__export__.project_task_2799_fdc3663f | Deployment 2108: Mid America Gardens: Odoo Launch | Sprint 2110 | 2021-02-22 | Configuration | Mid-America: Help (P37) | Levi Barnes | Wajahat Ali | 1.5 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 4904 | 0 | -1.5 | 0 | 4
__export__.project_task_2398_c0de312b | Click through T&C's on customer portal | Sprint 2108 | 2021-02-08 | Development | Continuant: Quotation Management / Automation (P31) | Nick Foy | Muhammad Bilal | 22.28 | 100 |  |  |  | Complete | Continuant | 5686 | 11 | -11.28 | 56 | 230.4131
__export__.project_task_2368_c3635efb | Internal: Project UX Review: add api product category to ecommerce and product category | Sprint 2105 | 2021-01-25 | Development | Dialed Supply: Help (P21) | Levi Barnes | Raheel Aslam | 2.08 | 100 |  |  |  | Complete | Dialed Supply | 5761 | 1 | -1.08 | 0 | 254.0358
__export__.project_task_2212_1107ec02 | Ensure all Users have access to OpCo | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy |  | 0.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5998 | 0 | -0.25 | 0 | 90.9372
__export__.project_task_2014_7a72862f | Review 3rd Party Apps: helpdesk to task |  |  | Development | PWX: Help (P23) | Levi Barnes |  | 0.5 | 100 |  |  |  | Complete | EquityTeam | 6437 | 0.5 | 0 | 0 | 56.928
__export__.project_task_1579_0f75bc70 | Once User sends quote from record change status to quote sent | Sprint 2049 | 2020-11-30 | Development | Continuant: Quotation Management / Automation (P31) | Kaesi Lee | Muzher Siddique | 1 | 33.33 |  |  |  | Complete | Continuant | 7417 | 3 | 2 | 0 | 159.8939
__export__.project_task_1156_f60584dc | CPBids Email Server | Sprint 28 | 2020-08-24 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9202 | 0 | 0 | 0 | 0
__export__.project_task_1111_baa6e3a4 | Ingram Micro: Obtain Pricing and Availability | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9457 | 0 | 0 | 0 | 0
__export__.project_task_148_26aedbbc | 1.6.3 Select Category(1 hour) | Sprint 27 | 2020-08-17 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 11570 | 0 | 0 | 0 | 0
__export__.project_task_4531_a9feeb2a | UEDF Activation xml and UEDF ASN xml file corrections | Sprint 2134 | 2021-08-16 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 4.5 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 841 | 3 | -1.5 | 0 | 97.232
__export__.project_task_4478_e0356911 | Deploy to Deployment + Production(2132) | Sprint 2131 | 2021-07-26 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hassan | 0 | 0 |  |  | 2 | Complete | Zuma Sales LLC | 893 | 4 | 4 | 0 | 5.2878
__export__.project_task_3449_82ad65e1 | Ensure all network communications are in place | Sprint 2123 | 2021-05-31 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.0909 | 284.0998
__export__.project_task_2771_d3a68476 | Mid America Gardens deployment 2107 | Sprint 2109 | 2021-02-15 | Other | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 0.92 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 5068 | 0.66667 | -0.25333 | 0 | 8
__export__.project_task_2203_fddf5015 | Create Contact (delivery addresses) for each location | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy |  | 0.17 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5998 | 0 | -0.17 | 0 | 90.9358
__export__.project_task_2063_d7f535ef | Set-up Product Landed Costs | Sprint 2105 | 2021-01-25 | Configuration | Wild Leaf: Help (P22) | Nick Foy | Nick Foy | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6220 | 0 | 0 | 184 | 358.0694
__export__.project_task_1663_c1d4d598 | Chatter expand/minimize:Messages | Sprint 2049 | 2020-11-30 | Development | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 3.87 | 77.4 |  |  |  | Complete | EquityTeam | 7061 | 5 | 1.13 | 0 | 73.0436
__export__.project_task_1604_933efa31 | Create a new Module for "AV Tracker" | Sprint 2047 | 2020-11-16 | Development | Continuant: AV Warehouse (P34) | Kaesi Lee | Danish Hassan | 8.92 | 100 |  |  |  | Complete | Continuant | 7342 | 3 | -14.34 | 8 | 107.4386
__export__.project_task_1513_c7bd4721 | Data Migration from Odoo to Azure: Field Configuration | Sprint 2047 | 2020-11-16 | Development | Continuant: Power BI Integration (P30) | Levi Barnes | Fahad Hassan | 24.75 | 100 |  |  |  | Complete | Continuant | 7680 | 1 | -23.75 | 0 | 192
__export__.project_task_1155_31f7372d | Duplicate bids | Sprint 30 | 2020-09-07 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9202 | 0 | 0 | 0.0065181 | 0
__export__.project_task_1124_fe7ce8fe | Integrate GfK Etilize Catalog: Import Manufacturer Number | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9456 | 0 | 0 | 0 | 0
__export__.project_task_4616_e2643d56 | Scan POS Label Validations in Package | Sprint 2134 | 2021-08-16 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 2.42 | 96.8 |  | SPLN |  | Complete | Cellpoint Corporation | 720 | 2.5 | 0.08 | 0 | 72.6078
Priority
__export__.project_task_4336_ffea40e8 | Deploy to Deployment+Production(Zuma+2129) | Sprint 2131 | 2021-07-26 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hassan | 5.17 | 100 |  |  | 2 | Complete | Zuma Sales LLC | 1471 | 4 | -1.17 | 1.8586 | 48.9453
__export__.project_task_2856_6c4aa17a | job position view modifications | Sprint 2114 | 2021-03-29 | Development | PWX: HR (P61) | Levi Barnes | Danish Hassan | 7.75 | 96.88 |  |  | 2 | Complete | EquityTeam | 4678 | 8 | 0.25 | 0 | 248
__export__.project_task_2665_d1c0c4b6 | General 2105 |  |  | Internal Time Tracking | Mid-America: Help (P37) | Levi Barnes | Levi Barnes | 2.75 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 5356 | 0 | -2.75 | 0 | 15.0344
__export__.project_task_2654_f2aa7e2e | Satellite Warehouse Location |  |  | Configuration | Wild Leaf: Help (P22) | Jeff Gross |  | 0.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5401 | 0 | -0.5 | 184 | 271.2267
__export__.project_task_2359_bb3a741f | Internal: Project UX Review: vendor mapping -> api mapping under main api submenu | Sprint 2105 | 2021-01-25 | Development | Dialed Supply: Help (P21) | Levi Barnes | Raheel Aslam | 0.17 | 8.5 |  |  |  | Complete | Dialed Supply | 5762 | 2 | 1.83 | 0 | 254.0589
__export__.project_task_2205_8b983391 | Create new warehouses | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy |  | 0.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5998 | 0 | -0.5 | 0 | 90.9344
__export__.project_task_2089_7445e023 | FW: You have been assigned to Helpdesk workflows and SLA's |  |  | Configuration | PWX: Help (P23) | Levi Barnes |  | 0 | 0 |  |  |  | Cancelled | EquityTeam | 6190 | 0 | 0 | 0 | 1256.0192
__export__.project_task_1596_86f3854c | Create project requirements - Phase 1 | Sprint 2046 | 2020-11-09 | Configuration | Continuant: AV Warehouse (P34) | Nick Foy | Nick Foy | 1 | 100 |  |  |  | Complete | Continuant | 7367 | 1 | 0 | 0 | 24
__export__.project_task_1480_e539364d | Free Sign-Up | Sprint 2043 | 2020-10-19 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 0 | 0 |  | Website |  | Complete | Cellpoint Corporation | 7919 | 0 | 0 | 0 | 32
__export__.project_task_1210_df3e1e44 | Re-calculate Tax with Address Change | Sprint 31 | 2020-09-14 | Bug Fix | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 8786 | 0 | 0 | 0 | 55.5692
__export__.project_task_830_a7356adf | Bid history iOS-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 2 | 2 | 0.00018745 | 0
iOS
__export__.project_task_347_8213b43a | Production Release #4 | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 0.00032117 | 0
__export__.project_task_4674_0ca09ca6 | Create a video for Email Templates | Sprint 2136 | 2021-08-30 | Other | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Shehroz Faiq | 2 | 100 |  |  |  | Complete | Zuma Sales LLC | 512 | 1 | -1 | 0 | 50.3206
__export__.project_task_4397_22c55dae | Print Packing slip (Delivery Slip) report | Sprint 2134 | 2021-08-16 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 10.08 | 72 |  | SPLN |  | Complete | Cellpoint Corporation | 1154 | 14 | 3.92 | 0 | 173.1806
__export__.project_task_3447_621acc34 | Execute the acceptance test script |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3484 | 0 | 0 | 461.1034 | 520.1315
__export__.project_task_2328_92f9b0a3 | Call to Tenders | Sprint 2105 | 2021-01-25 | Development | PWX: Field Service to Invoicing (P47) | Levi Barnes | Raheel Aslam | 4.7 | 100 |  |  |  | Complete | EquityTeam | 5855 | 4.5 | -0.2 | 0 | 270.0689
__export__.project_task_2307_0cef0bde | Computed Fields not being Transfered |  |  | Bug Fix | Continuant: Power BI Integration (P30) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 5877 | 0 | 0 | 0 | 32
__export__.project_task_2262_af067b09 | Deployment Mid-America 2101 | Sprint 2103 | 2021-01-11 | Configuration | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 0.33 | 99 |  |  |  | Complete | Mid-America Gardens, LLC | 5913 | 0.33333 | 0.0033333 | 0 | 1.1433
__export__.project_task_2012_a55435f7 | Review 3rd Party Apps:portal dashboard |  |  | Development | PWX: Help (P23) | Levi Barnes |  | 0.5 | 100 |  |  |  | Complete | EquityTeam | 6437 | 0.5 | 0 | 0 | 56.9337
__export__.project_task_1577_110ef8c2 | Make Quotation/sales order email editable for Account Executives | Sprint 2049 | 2020-11-30 | Development | Continuant: Quotation Management / Automation (P31) | Kaesi Lee | Muzher Siddique | 2.17 | 100 |  |  |  | Complete | Continuant | 7417 | 1 | -1.17 | 0 | 159.8892
__export__.project_task_1340_24875972 | Check for buyers registered under other companies check Nick messages | Sprint 2041 | 2020-10-05 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8398 | 0 | 0 | 0 | 96
__export__.project_task_1282_a8256fe9 | change order confirmation message | Sprint 32 | 2020-09-21 | Configuration | Moln: Help (P16) | Gadha Continuant |  | 4 | 0 |  | eCommerce |  | Complete | Moln Solutions, LLC | 8573 | 0 | -4 | 0.068554 | 24.6083
__export__.project_task_1152_15c2a5e4 | Individual Log Ins for Each Seller Personnel | Sprint 2102 | 2021-01-04 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 17.25 | 100 |  |  |  | Complete | Cellpoint Corporation | 9221 | 25.0833 | -1.4967 | 168.6899 | 859.6238
__export__.project_task_969_5218686b | Checkout Process: Send Quotation Button | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9624 | 0 | 0 | 0 | 0
__export__.project_task_945_9e326cea | CPBids Company | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9786 | 3 | 3 | 0 | 0
__export__.project_task_4645_ee9cd343 | Purchase Order List View | Sprint 2135 | 2021-08-23 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 8.17 | 100 |  | SPLN |  | Complete | Zuma Sales LLC | 537 | 7.1667 | -1.0033 | 0 | 69.4192
__export__.project_task_4614_d6382300 | UEDF ASN Validations | Sprint 2134 | 2021-08-16 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 2.67 | 66.75 |  | SPLN |  | Complete | Cellpoint Corporation | 721 | 4 | 1.33 | 0.58476 | 73.3198
Priority
__export__.project_task_3446_ad0ef5cd | Validate the acceptance test environment |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.1093 | 520.1373
__export__.project_task_3198_60b427a8 | Addition of new field on Sales order form (Other Info Tab) | Sprint 2114 | 2021-03-29 | Development | Wild Leaf: Help (P22) | Jeff Gross | Danish Hassan | 1.25 | 100 |  |  | 1 | Complete | Wild Leaf Beverage | 4281 | 1 | -0.25 | 0 | 160
__export__.project_task_2282_a08a86dd | Employee multiple skills,levels selection | Sprint 2103 | 2021-01-11 | Development | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 2.42 | 100 |  |  |  | Complete | Silverdale Technology LLC | 5908 | 1.5 | -0.92 | 0 | 163.2736
__export__.project_task_2078_92f6c8cd | Assign the seller rights to the user | Sprint 2102 | 2021-01-04 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 9.33 | 99.96 |  |  |  | Complete | Cellpoint Corporation | 6194 | 9.3333 | 0.0033333 | 0 | 138.9353
__export__.project_task_1958_e20125e9 | Add Customer Lead Times | Sprint 2052 | 2020-12-21 | Configuration | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 1.5 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 1.5 | 0 | 14.4119 | 108.8272
__export__.project_task_1644_6efe35a3 | Deploy Continuant: Quotation Management 2047 | Sprint 2047 | 2020-11-16 | Development | Continuant: Quotation Management / Automation (P31) | Muzher Siddique |  | 0.58 | 58 |  |  |  | Complete | Continuant | 7085 | 1 | 0.42 | 0 | 57.2912
__export__.project_task_1508_e2640204 | CI Field on Employee | Sprint 2046 | 2020-11-09 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 12.42 | 100 |  |  |  | Complete | EquityTeam | 7684 | 4 | -8.42 | 55.4879 | 128.0887
__export__.project_task_1400_2e637bed | Create project proposal and quotation | Sprint 2044 | 2020-10-26 | Configuration | Continuant: eCommerce 1.2 (P25) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Continuant | 8183 | 1 | 1 | 0 | 110.4542
__export__.project_task_1259_dae8ddfd | Install Knowledge Management Module | Sprint 2041 | 2020-10-05 | Configuration | Silverdale: Help (P12) | Muhammad Afzaal |  | 0.25 | 0 |  |  |  | Complete | Silverdale Technology LLC | 8665 | 0 | -0.25 | 0 | 48
__export__.project_task_1110_24e11211 | Tech Data: Obtain Pricing and Availability | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9457 | 0 | 0 | 0 | 0
__export__.project_task_893_54ec4ff8 | Tag list Android-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
Android
__export__.project_task_15_7927ce8c | Add a calculated field for Binomial | Sprint 28 | 2020-08-24 | Studio | Heronswood: Events (P3) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 11595 | 0 | 0 | 0 | 0
__export__.project_task_4613_59398d9a | Usertype column in Settings>users | Sprint 2135 | 2021-08-23 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Aleem khan | 3.59 | 97.91 |  | SPLN |  | Complete | Zuma Sales LLC | 722 | 3.6667 | 0.076667 | 0 | 105.768
__export__.project_task_4395_93ab1284 | Download ASN file to send to Dish (Customer) | Sprint 2134 | 2021-08-16 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 16.33 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 1154 | 15 | -1.33 | 0 | 173.2243
__export__.project_task_3445_0a6a0ad8 | Back up the production environment for later availability |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.1136 | 520.1416
__export__.project_task_3341_a87cbcbc | Deployment 14/04/2021: Wildleaf | Sprint 2117 | 2021-04-19 | Configuration | Wild Leaf: Accounting (P64) | Jeff Gross | Wajahat Ali | 3.97 | 0 |  |  |  | Complete | Wild Leaf Beverage | 3723 | 0 | -3.97 | 0 | 72
__export__.project_task_2223_27bdbc54 | Move Product lot details from old to new opco | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy | Nick Foy | 0.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5980 | 0 | -0.5 | 0 | 90.9364
__export__.project_task_2144_eeca91f4 | Add Chatter to Job Position form | Sprint 2110 | 2021-02-22 | Development | Silverdale: Help (P12) | Nick Foy | Muhammad Bilal | 1.95 | 97.5 |  |  | 2 | Complete | Silverdale Technology LLC | 6067 | 2 | 0.05 | 0 | 469.3008
__export__.project_task_2010_82166cdc | Review 3rd Party Apps:user audit |  |  | Development | PWX: Help (P23) | Levi Barnes |  | 0.67 | 100 |  |  |  | Complete | EquityTeam | 6437 | 0.5 | -0.17 | 0 | 57.1302
__export__.project_task_1959_c9767b37 | Add Ecommerce description | Sprint 2052 | 2020-12-21 | Configuration | Mid-America: Help (P37) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 0 | 0 | 14.4119 | 59.9783
__export__.project_task_1698_54bf86cb | Remove the Location filter pop-up | Sprint 2049 | 2020-11-30 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 1 | 0 |  | 3.0.5 |  | Complete | Cellpoint Corporation | 6908 | 0 | -1 | 0 | 39.8944
__export__.project_task_1626_71fced15 | Scheduled Data Transfer | Sprint 2047 | 2020-11-16 | Development | Continuant: Power BI Integration (P30) | Kaesi Lee | Muzher Siddique | 1.58 | 52.67 |  |  |  | Complete | Continuant | 7222 | 3 | 1.42 | 0 | 29.4842
__export__.project_task_1189_b5f717b0 | Make /shop the home page | Sprint 30 | 2020-09-07 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 8905 | 0 | 0 | 0 | 0
__export__.project_task_1133_a692c29a | Check Availability: Highlight Previously Selected Vendor | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9270 | 0 | 0 | 0 | 0
__export__.project_task_202_fcb0e3ba | Complete Profile Settings Web | Sprint 22 | 2020-07-12 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10783 | 16 | 16 | 98.499 | 0
__export__.project_task_4612_40694ec3 | Tracking On Purchase Orders | Sprint 2135 | 2021-08-23 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Aleem khan | 10 | 71.43 |  | SPLN |  | Complete | Zuma Sales LLC | 723 | 14 | 4 | 0 | 105.7837
__export__.project_task_4358_80653f78 | Add Parent Package field (In Package) | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 6 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 1230 | 4 | -2 | 0 | 200.8518
__export__.project_task_3444_abe71f82 | Set up by client success team | Sprint 2123 | 2021-05-31 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.1353 | 284.1272
__export__.project_task_3267_37005969 | Discount items have separate section on sales order slip and invoice slip(with and without pricing) and delivery slip |  |  | Development | Mid-America: Help (P37) | Levi Barnes | Danish Hassan | 11.25 | 100 |  |  | 3 | Complete | Mid-America Gardens, LLC | 4064 | 7 | -4.25 | 0 | 107.9069
__export__.project_task_2712_5bf0f9c6 | General 2107 | Sprint 2108 | 2021-02-08 | Internal Time Tracking | Mid-America: Help (P37) | Levi Barnes | Levi Barnes | 4 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 5253 | 0 | -4 | 0 | 38.9814
__export__.project_task_2134_3bdfb5a7 | FW: You have been assigned to Edits to Recruitment Module (#45): move field | Sprint 2105 | 2021-01-25 | Development | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 2.12 | 100 |  |  |  | Complete | EquityTeam | 6072 | 2 | -0.12 | 0 | 326.0508
__export__.project_task_1684_57292ed4 | not able to change deadline field | Sprint 2049 | 2020-11-30 | Configuration | PWX: Help (P23) | Levi Barnes |  | 2 | 0 |  |  |  | Complete | EquityTeam | 6918 | 0 | -2 | 0 | 42.1939
__export__.project_task_1598_ed9fcd06 | Demo CP solution | Sprint 2046 | 2020-11-09 | Configuration | Continuant: AV Warehouse (P34) | Nick Foy |  | 1 | 100 |  |  |  | Complete | Continuant | 7367 | 1 | 0 | 0 | 8
__export__.project_task_1518_fb88abae | Data Migration from Odoo to Azure: Test Connection Feature | Sprint 2046 | 2020-11-09 | Development | Continuant: Power BI Integration (P30) | Levi Barnes | Fahad Hassan | 33.25 | 100 |  | Need Assistance |  | Complete | Continuant | 7680 | 2 | -31.25 | 0 | 128
__export__.project_task_1507_0c2f133b | Accepting Bids after Auction Times Out | Sprint 2045 | 2020-11-02 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 0 | 0 |  | 3.0.2 |  | Complete | Cellpoint Corporation | 7685 | 0 | 0 | 0 | 88.997
__export__.project_task_1179_11ba1997 | Lot Reference Bug | Sprint 28 | 2020-08-24 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9027 | 0 | 0 | 0 | 0
__export__.project_task_1132_3541c64e | Integrate GfK Etilize Catalog: Unit of Measurement Correction | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Gadha Continuant |  | 0 | 0 |  |  |  | Complete | Continuant | 9361 | 0 | 0 | 0 | 0
__export__.project_task_4611_4a64b041 | Add tags textfield and then column in Purchase ListView | Sprint 2135 | 2021-08-23 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Aleem khan | 3.5 | 100 |  | SPLN |  | Complete | Zuma Sales LLC | 723 | 3.5 | 0 | 0 | 105.8049
__export__.project_task_4360_975c786b | Import Phone check file to Odoo | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Kaleem Khan | 31 | 100 |  | SPLN | 2 | Complete | Cellpoint Corporation | 1230 | 29 | -2 | 0 | 200.6115
__export__.project_task_3324_2ea4e0dc | Deployement 08-04-2021:Mid-America | Sprint 2116 | 2021-04-12 | Configuration | Mid-America: Help (P37) | Levi Barnes | Wajahat Ali | 1 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 3847 | 0 | -1 | 0 | 50.9818
__export__.project_task_2440_4e69cce1 | Mid-America GOL: Deplayment sprint 2103 | Sprint 2105 | 2021-01-25 | Configuration | Mid-America: Help (P37) | Levi Barnes | Wajahat Ali | 2 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 5578 | 2 | 0 | 1.2324e-05 | 7.7967
__export__.project_task_2341_94c03ba5 | FW: Inventory Counts | Sprint 2105 | 2021-01-25 | Configuration | Wild Leaf: Help (P22) | Nick Foy | Nick Foy | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5813 | 0 | 0 | 88 | 262.0622
__export__.project_task_2204_afa2c8e1 | Edit current warehouse name with prefix x_ | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy |  | 0.08 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5998 | 0 | -0.08 | 0 | 90.9328
__export__.project_task_1500_6c8176f3 | Appraisals / Company Settings Part 1 | Sprint 2046 | 2020-11-09 | Development | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 14.58 | 100 |  |  |  | Complete | EquityTeam | 7759 | 13 | -1.58 | 42.8789 | 154.8789
__export__.project_task_1492_f01247bc | Add Lot Ref to Search Bar | Sprint 2044 | 2020-10-26 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 1 | 0 |  |  |  | Complete | Cellpoint Corporation | 7877 | 0 | -1 | 0.61818 | 39.2546
__export__.project_task_1211_f5a9f465 | Sales Order / Quotation: PDF Template Bug | Sprint 31 | 2020-09-14 | Bug Fix | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 8786 | 0 | 0 | 0 | 55.5681
__export__.project_task_1119_ac1b753b | Tech Data: Obtain Order Confirmation | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Gadha Continuant |  | 0 | 0 |  |  |  | Complete | Continuant | 9456 | 0 | 0 | 31.2272 | 0
__export__.project_task_943_d3f3a1f5 | Lots Dashboard | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9786 | 3 | 3 | 0 | 0
__export__.project_task_358_20630403 | Tax: Sign-off tax | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 49.7145 | 0
__export__.project_task_4610_a018fffb | Create Purchase Ninja Dashboard | Sprint 2136 | 2021-08-30 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.5 | 50 |  |  |  | Complete | Zuma Sales LLC | 723 | 1 | 0.5 | 0 | 93.0296
__export__.project_task_4356_2cebfe32 | ASN import utility on Transfer form | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Danish Hassan | 35.5 | 100 |  | SPLN | 2 | Complete | Cellpoint Corporation | 1230 | 35.5 | 0 | 0 | 201.0436
__export__.project_task_3442_deafb7dc | Ensure mail servers are properly setup | Sprint 2123 | 2021-05-31 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.154 | 284.1459
__export__.project_task_3315_83a5037d | FW: Move of Approved for Insurance Box / Pivot | Sprint 2116 | 2021-04-12 | Development | Wild Leaf: Accounting (P64) | Jeff Gross | Danish Hassan | 2.23 | 89.2 |  |  | 1 | Complete | Wild Leaf Beverage | 3869 | 2.5 | 0.27 | 0 | 56.5385
__export__.project_task_2715_631330b9 | Deployment: 2105 | Sprint 2108 | 2021-02-08 | Configuration | Mid-America: Help (P37) | Levi Barnes | Wajahat Ali | 1.17 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 5240 | 0 | -1.17 | 0 | 1.5197
__export__.project_task_2430_0cf575f9 | invoice_ready_custom unit testing | Sprint 2107 | 2021-02-01 | Development | Continuant: Unit Testing (P51) | Nick Foy | Raheel Aslam | 5.58 | 100 |  |  |  | Complete | Continuant | 5589 | 4 | -1.58 | 40 | 214.3333
__export__.project_task_2252_6e0dd23a | Send to Pick: Delivery Order Selection: Default to single WH/OUT delivery order | Sprint 2105 | 2021-01-25 | Development | Continuant: AV Warehouse (P34) | Nick Foy | Kaleem Khan | 15.92 | 100 |  | Difficulty 2 |  | Complete | Continuant | 5927 | 2.5 | -13.42 | 120 | 294.1006
NF Review
__export__.project_task_2217_effe642c | Change Bill of Materials Company to OpCo | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Single OpCo (P48) | Nick Foy |  | 0.25 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5998 | 0 | -0.25 | 0 | 90.9322
__export__.project_task_2133_76c9aa62 | FW: You have been assigned to Edits to Recruitment Module (#45): refuse auto move | Sprint 2105 | 2021-01-25 | Development | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 1.5 | 100 |  |  |  | Complete | EquityTeam | 6072 | 1 | -0.5 | 0 | 326.0503
__export__.project_task_2008_d01499b2 | Review 3rd Party Apps:kpi scorecard |  |  | Development | PWX: Help (P23) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | EquityTeam | 6437 | 0.5 | 0.5 | 0 | 57.1351
__export__.project_task_1310_4d345485 | Users on v3.0 are able to place bids | Sprint 33 | 2020-09-28 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8431 | 0 | 0 | 0.019378 | 57.2305
__export__.project_task_946_ea843ea8 | Test Connection to Synnex | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9767 | 0 | 0 | 0 | 0
__export__.project_task_936_34cda6f5 | API:Notification list api: Postman | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9894 | 1 | 1 | 0.00636 | 0
Postman
__export__.project_task_4628_5be32d55 | Package - Pallet (Parent Package) - Remove add a line from front end | Sprint 2135 | 2021-08-23 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 0.58 | 58 |  | SPLN |  | Complete | Cellpoint Corporation | 704 | 1 | 0.42 | 0 | 77.4214
__export__.project_task_4608_3b896a83 | Hide Create invoice button from sales team after creating a sales order | Sprint 2135 | 2021-08-23 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0.25 | 6.25 |  | SPLN |  | Complete | Zuma Sales LLC | 723 | 4 | 3.75 | 0 | 89.828
__export__.project_task_2372_45736808 | Enable advanced Routes for MTO process | Sprint 2105 | 2021-01-25 | Configuration | Wild Leaf: Help (P22) | Nick Foy | Nick Foy | 9 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5757 | 0 | -9 | 80 | 254.0617
__export__.project_task_2163_4352804e | Lucid Chart Demo | Sprint 2102 | 2021-01-04 | Configuration | Silverdale: Help (P12) | Nick Foy | Muhammad Afzaal | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 6034 | 0 | 0 | 0 | 9.6484
__export__.project_task_2028_c7628599 | salesorder gift button | Sprint 2053 | 2020-12-28 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 4.92 | 98.4 |  |  |  | Complete | Mid-America Gardens, LLC | 6403 | 5 | 0.08 | 0 | 124
__export__.project_task_1685_18f4b76f | activity view | Sprint 2050 | 2020-12-07 | Development | PWX: Help (P23) | Levi Barnes | Fahad Hassan | 2 | 0 |  |  |  | Complete | EquityTeam | 6917 | 0 | -6 | 0 | 88.0877
__export__.project_task_1677_ce8fec26 | Error Message during Data Migration | Sprint 2049 | 2020-11-30 | Development | Continuant: Power BI Integration (P30) | Kaesi Lee | Fahad Hassan | 23.08 | 88.77 |  |  |  | Complete | Continuant | 6936 | 26 | 2.92 | 0 | 47.8931
__export__.project_task_1222_9f73bd23 | Production Release #8 | Sprint 31 | 2020-09-14 | Configuration | Continuant: eCommerce (P9) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Continuant | 8767 | 0 | 0 | 0 | 50.36
__export__.project_task_1207_d5d3cb8c | Stripe Bug: ID | Sprint 31 | 2020-09-14 | Bug Fix | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 8791 | 0 | 0 | 0 | 0
__export__.project_task_970_a8dd1565 | Checkout Process: Address Page | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9624 | 0 | 0 | 0 | 0
__export__.project_task_892_3a5cc705 | Download csv Android-Implementation | Sprint 30 | 2020-09-07 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
Android
__export__.project_task_4627_bc3d39ee | Labels Fixes | Sprint 2134 | 2021-08-16 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Muhammad Bilal | 3.08 | 0 |  | SPLN |  | Complete | Cellpoint Corporation | 705 | 0 | -3.08 | 0 | 69.4244
__export__.project_task_4607_4a2a2fa7 | Dropship checkbox in product menu | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Danish Hassan | 1.58 | 45.14 |  |  |  | Complete | Zuma Sales LLC | 723 | 3.5 | 1.92 | 0 | 40.439
__export__.project_task_3440_77673cd4 | Ensure automated actions are running fine | Sprint 2123 | 2021-05-31 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.1646 | 284.5718
__export__.project_task_3306_342d2769 | Job Position: Interview Survey | Sprint 2116 | 2021-04-12 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 1.92 | 96 |  |  | 1 | Complete | EquityTeam | 3888 | 2 | 0.08 | 0 | 64
__export__.project_task_2136_d8561483 | FW: You have been assigned to Edits to Recruitment Module (#45): Recruiter Signature | Sprint 2105 | 2021-01-25 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 5.17 | 100 |  |  |  | Complete | EquityTeam | 6072 | 2 | -3.17 | 0 | 326.0492
__export__.project_task_2100_4ab7af62 | Security Audits:For all team in pakistan office | Sprint 2102 | 2021-01-04 | Configuration | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 1.33 | 0 |  |  |  | Complete | Silverdale Technology LLC | 6104 | 0 | -1.33 | 0 | 62.6035
__export__.project_task_2031_a5932fef | invoice template for line items with no prices | Sprint 2053 | 2020-12-28 | Development | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 2.17 | 72.33 |  |  |  | Complete | Mid-America Gardens, LLC | 6403 | 3 | 0.83 | 0 | 124
__export__.project_task_2007_5129259a | Review 3rd Party Apps: scheduled activity |  |  | Development | PWX: Help (P23) | Levi Barnes |  | 0.67 | 100 |  |  |  | Complete | EquityTeam | 6437 | 0.5 | -0.17 | 0 | 57.1905
__export__.project_task_1239_1b58e67c | Import of Product Master List | Sprint 32 | 2020-09-21 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 8713 | 0 | 0 | 0 | 104
__export__.project_task_1185_3fe676d8 | Distributor API: Order Confirmation | Sprint 30 | 2020-09-07 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 8932 | 0 | 0 | 0 | 0
__export__.project_task_1148_14c17300 | GFK Integration: Create GFK Manufacturer Name and Manufacturer ID table | Sprint 29 | 2020-08-31 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9239 | 0 | 0 | 0 | 0
__export__.project_task_823_bf4026fb | Select city iOS-Implementation | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_243_16d0c493 | Email for APP Maven | Sprint 28 | 2020-08-24 | Development | Silverdale: Help (P12) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 10445 | 0 | 0 | 0 | 0
__export__.project_task_4624_2de3e011 | UEDF Activation Validation Error Message | Sprint 2134 | 2021-08-16 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 1.5 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 719 | 1.5 | 0 | 0 | 71.146
__export__.project_task_4606_d7a65294 | All products need to be dropship | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 723 | 0.5 | 0.5 | 0 | 21.0186
__export__.project_task_3439_7c355316 | Ensure backups are running correctly | Sprint 2123 | 2021-05-31 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.1699 | 284.6832
__export__.project_task_3305_062317bf | applicant email template | Sprint 2116 | 2021-04-12 | Configuration | PWX: Help (P23) | Levi Barnes | Danish Hassan | 2.2 | 100 |  |  |  | Complete | EquityTeam | 3888 | 2 | -0.2 | 0 | 64
__export__.project_task_2400_6268f29d | Brand Customer Portal | Sprint 2108 | 2021-02-08 | Development | Continuant: Quotation Management / Automation (P31) | Nick Foy | Fahad Hassan | 3.78 | 100 |  |  |  | Complete | Continuant | 5686 | 2.3333 | -1.4467 | 56 | 230.3906
__export__.project_task_2102_68c96422 | Security Audits:For all server related credentials | Sprint 2102 | 2021-01-04 | Configuration | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 0.5 | 0 |  |  |  | Complete | Silverdale Technology LLC | 6104 | 0 | -0.5 | 0 | 55.6425
__export__.project_task_1843_a917a5c2 | create survey buttons for meeting | Sprint 2053 | 2020-12-28 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 16 | 100 |  |  |  | Complete | EquityTeam | 6740 | 16 | 0 | 0 | 204
__export__.project_task_1797_4ea75634 | New Field for Lost Opportunity | Sprint 2105 | 2021-01-25 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 4.25 | 100 |  |  |  | Complete | Cellpoint Corporation | 6836 | 3 | -1.25 | 0 | 502.0425
__export__.project_task_1689_8fd1e984 | Set-Up Odoo Instance | Sprint 2049 | 2020-11-30 | Configuration | Mid-America: Help (P37) | Muhammad Afzaal | Muzher Siddique | 0.67 | 44.67 |  |  |  | Complete | Mid-America Gardens, LLC | 6916 | 1.5 | 0.83 | 0 | 8
__export__.project_task_1209_34e7a0bd | Update Order Successfully Placed Page | Sprint 31 | 2020-09-14 | Bug Fix | Continuant: eCommerce (P9) | Gadha Continuant |  | 0 | 0 |  |  |  | Complete | Continuant | 8789 | 0 | 0 | 0 | 55.9475
__export__.project_task_1142_badb4364 | Loading Graphic for Get Availability | Sprint 30 | 2020-09-07 | Development | Continuant: eCommerce (P9) | Gadha Continuant |  | 0 | 0 |  |  |  | Complete | Continuant | 9241 | 0 | 0 | 0 | 0
__export__.project_task_837_7ae427b6 | Forcefully update iOS-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_169_c20ab084 | Error when creating a new User | Sprint 27 | 2020-08-17 | Bug Fix | Heronswood: Events (P3) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 11468 | 0 | 0 | 0 | 0
__export__.project_task_4622_eba52a19 | Phone Check Import Issue | Sprint 2135 | 2021-08-23 | Bug Fix | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 18.08 | 82.18 |  | SPLN |  | Complete | Cellpoint Corporation | 719 | 22 | 3.92 | 0 | 79.2784
Priority
__export__.project_task_4605_e1040bd1 | Training for quotation template | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0.5 | 100 |  |  |  | Complete | Zuma Sales LLC | 723 | 0.5 | 0 | 0 | 44.4623
__export__.project_task_3438_6e18e39e | Backup the production environment | Sprint 2123 | 2021-05-31 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.1779 | 284.7026
__export__.project_task_3304_a8aa7baa | Deployment 06/04/2021 | Sprint 2116 | 2021-04-12 | Configuration | Heronswood: Help (P54) | Jeff Gross | Wajahat Ali | 0.5 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 3891 | 0 | -0.5 | 0 | 64
__export__.project_task_2610_586b67f7 | General 2104 | Sprint 2105 | 2021-01-25 | Configuration | Mid-America: Help (P37) | Levi Barnes | Levi Barnes | 3 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 5541 | 0 | -3 | 0 | 23.1286
__export__.project_task_2425_36c8b697 | customer_payment_option unit testing | Sprint 2107 | 2021-02-01 | Development | Continuant: Unit Testing (P51) | Nick Foy | Danish Hassan | 4.92 | 100 |  |  |  | Complete | Continuant | 5590 | 4 | -0.92 | 40 | 214.3303
__export__.project_task_2367_5698c61b | Internal: Project UX Review: product categories | Sprint 2105 | 2021-01-25 | Development | Dialed Supply: Help (P21) | Levi Barnes | Raheel Aslam | 1.75 | 95.45 |  |  |  | Complete | Dialed Supply | 5762 | 1.8333 | 0.083333 | 0 | 254.0403
__export__.project_task_2101_a68a0b61 | Security Audits:For the USA team | Sprint 2102 | 2021-01-04 | Configuration | Silverdale: Help (P12) | Nick Foy | Kaleem Khan | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 6104 | 0 | 0 | 0 | 55.595
__export__.project_task_1784_6fc9c50f | Make Column Headers Sticky in Lot Views | Sprint 2050 | 2020-12-07 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Fahad Hassan | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 6836 | 0 | 0 | 0 | 102.5861
__export__.project_task_1646_4237863e | web editor error | Sprint 2050 | 2020-12-07 | Development | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 2.58 | 64.5 |  |  |  | Complete | EquityTeam | 7084 | 4 | 1.42 | 0 | 166.7977
__export__.project_task_1606_c54cb3e5 | Create an AV Project Pick List | Sprint 2047 | 2020-11-16 | Development | Continuant: AV Warehouse (P34) | Kaesi Lee | Danish Hassan | 12.08 | 100 |  |  |  | Complete | Continuant | 7341 | 8 | -4.08 | 8 | 108.8033
__export__.project_task_1139_e10d0769 | Billing And Shipping: Select Client Delivery Address | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Gadha Continuant |  | 0 | 0 |  |  |  | Complete | Continuant | 9246 | 0 | 0 | 0 | 0
__export__.project_task_822_484c359b | Select state iOS-Implementation | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_4604_1593ace4 | Customer reference show in top fields in SO | Sprint 2135 | 2021-08-23 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Aleem khan | 2.75 | 91.67 |  | SPLN |  | Complete | Zuma Sales LLC | 723 | 3 | 0.25 | 0 | 105.8988
__export__.project_task_4451_945ae340 | FW: rearrange job web page paragraphs | Sprint 2134 | 2021-08-16 | Development | PWX: Help (P23) | Farman Ahmad Cheema | Danish Hassan | 0 | 0 |  | SPLN |  | Complete | EquityTeam | 969 | 0 | 0 | 0 | 125.4244
__export__.project_task_3302_a144f87b | Stop to proceed negative quantity in POS | Sprint 2116 | 2021-04-12 | Development | MMH: Help (P83) | Jeff Gross | Muhammad Bilal | 8.08 | 100 |  |  | 4 | Complete | Mountain Meadow Herbs | 3895 | 7 | -1.08 | 7.8014e-06 | 66.692
__export__.project_task_2373_e7101177 | Deployment 2102 Mid America Gardens | Sprint 2104 | 2021-01-18 | Configuration | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 0.67 | 33.5 |  |  |  | Complete | Mid-America Gardens, LLC | 5746 | 2 | 1.33 | 0 | 6.8116
__export__.project_task_2362_5650870c | Internal: Project UX Review: Add corn job to update products | Sprint 2105 | 2021-01-25 | Development | Dialed Supply: Help (P21) | Levi Barnes | Danish Hassan | 4.17 | 100 |  |  |  | Complete | Dialed Supply | 5762 | 3 | -1.17 | 0 | 254.0386
__export__.project_task_1665_5d21dd95 | Quality | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Nick Foy | 0.5 | 50 |  |  |  | Complete | Wild Leaf Beverage | 7056 | 1 | 0.5 | 0 | 224
__export__.project_task_1611_ccdcd202 | Mybids: Not showing time remaining order | Sprint 2048 | 2020-11-23 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 2.5 | 0 |  |  |  | Complete | Cellpoint Corporation | 7253 | 0 | -2.5 | 0 | 112.8577
__export__.project_task_1601_3fc4712f | Google Calendar sync | Sprint 2049 | 2020-11-30 | Configuration | PWX: Help (P23) | Levi Barnes | Danish Hassan | 3.5 | 100 |  |  |  | Complete | EquityTeam | 7350 | 3 | -3.5 | 0 | 137.3903
__export__.project_task_1522_c9e2c6e5 | Import Parts List to Product Master |  |  | Development | Continuant: Quotation Management / Automation (P31) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 7678 | 0 | -35.25 | 0 | 215.9039
__export__.project_task_1212_a3a6f6d7 | Sales Order Form View: Button Linking PO | Sprint 31 | 2020-09-14 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 8786 | 0 | 0 | 0 | 55.5678
__export__.project_task_1162_57add2b8 | Product Form Page: Make Description for Vendors Read Only | Sprint 29 | 2020-08-31 | Development | Continuant: eCommerce (P9) | Gadha Continuant |  | 0 | 0 |  |  |  | Complete | Continuant | 9192 | 0 | 0 | 0 | 0
__export__.project_task_542_7c31f09f | API:Select City | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 10.7572 | 0
__export__.project_task_4603_ca201244 | Delivery address should be visible in footer of page | Sprint 2135 | 2021-08-23 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Aleem khan | 3.42 | 97.71 |  | SPLN |  | Complete | Zuma Sales LLC | 723 | 3.5 | 0.08 | 0 | 105.9118
__export__.project_task_4363_90b927d9 | Scan each item in Odoo Receiving and Phone Check Option | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Kaleem Khan | 10.67 | 100 |  | SPLN | 2 | Complete | Cellpoint Corporation | 1225 | 10.6667 | -0.0033333 | 0 | 196.5684
__export__.project_task_3300_c42c75f3 | Deployment Wildleaf (06-04-21) | Sprint 2116 | 2021-04-12 | Other | Wild Leaf: Labeling (P60) | Jeff Gross | Wajahat Ali | 7.35 | 0 |  |  |  | Complete | Wild Leaf Beverage | 3897 | 0 | -7.35 | 0 | 68.313
__export__.project_task_2433_503de673 | invoice_portal_details unit testing | Sprint 2107 | 2021-02-01 | Development | Continuant: Unit Testing (P51) | Nick Foy | Kaleem Khan | 4.08 | 100 |  |  |  | Complete | Continuant | 5589 | 3 | -1.08 | 40 | 214.3292
__export__.project_task_2363_e15e443d | Internal: Project UX Review: add related product id to api output | Sprint 2105 | 2021-01-25 | Development | Dialed Supply: Help (P21) | Levi Barnes | Raheel Aslam | 1.92 | 100 |  |  |  | Complete | Dialed Supply | 5762 | 1.5 | -0.42 | 0 | 254.0367
__export__.project_task_2320_18282377 | shipping receive by | Sprint 2107 | 2021-02-01 | Development | Mid-America: Help (P37) | Levi Barnes | Kaleem Khan | 9.92 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 5861 | 6.5 | -6.92 | 0 | 270.9027
__export__.project_task_2221_9b6aa25e | P1: cpbids.com/marketplace for Belmont not loading | Sprint 2102 | 2021-01-04 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Wajahat Ali | 9.33 | 0 |  | P1 |  | Complete | Cellpoint Corporation | 5996 | 0 | -9.33 | 0 | 40
__export__.project_task_1510_1717a1f2 | User Roles Module | Sprint 2045 | 2020-11-02 | Configuration | PWX: Help (P23) | Levi Barnes |  | 0.25 | 0 |  |  |  | Complete | EquityTeam | 7683 | 0 | -0.25 | 15.4203 | 48
__export__.project_task_1395_19044382 | Auto Update for iOS | Sprint 2042 | 2020-10-12 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8188 | 0 | 0 | 0 | 16
__export__.project_task_1163_36f544dc | Sales Quotation: Order Type and Quote Type | Sprint 29 | 2020-08-31 | Development | Continuant: eCommerce (P9) | Gadha Continuant |  | 0 | 0 |  |  |  | Complete | Continuant | 9190 | 0 | 0 | 0 | 0
__export__.project_task_1121_2e4eba3c | Synnex: Order Shipment and Tracking | Sprint 31 | 2020-09-14 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Continuant | 9456 | 0 | 0 | 176 | 208
__export__.project_task_1035_919ef66b | Match Column fields with Completed Auctions | Sprint 28 | 2020-08-24 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 88.8483 | 0
__export__.project_task_4602_e4e2bf3f | Expiration date default to 7 days | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 1.33 | 66.5 |  | SPLN |  | Complete | Zuma Sales LLC | 723 | 2 | 0.67 | 0 | 81.9254
__export__.project_task_4455_ad6c3b83 | Pallet Scanning on Delivery Order | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 5.92 | 84.57 |  | SPLN |  | Complete | Cellpoint Corporation | 968 | 7 | 1.08 | 0 | 125.4244
__export__.project_task_3289_99fabaeb | If the product is having zero price, then the substitute column automatically fills with a gift in the sales quotation. | Sprint 2115 | 2021-04-05 | Development | Mid-America: Help (P37) | Levi Barnes | Danish Hassan | 3.18 | 100 |  |  | 1 | Complete | Mid-America Gardens, LLC | 4015 | 2.5 | -0.68 | 2.0976e-05 | 90.5992
__export__.project_task_2360_703e6095 | Internal: Project UX Review:api security group | Sprint 2105 | 2021-01-25 | Development | Dialed Supply: Help (P21) | Levi Barnes | Danish Hassan | 2.92 | 100 |  |  |  | Complete | Dialed Supply | 5762 | 2.5 | -0.42 | 0 | 254.0364
__export__.project_task_2009_10381c79 | Review 3rd Party Apps:oi base |  |  | Development | PWX: Help (P23) | Levi Barnes |  | 0.67 | 100 |  |  |  | Complete | EquityTeam | 6437 | 0.5 | -0.17 | 0 | 57.1321
__export__.project_task_1690_77ee14d7 | Set-Up Github | Sprint 2049 | 2020-11-30 | Configuration | Mid-America: Help (P37) | Muhammad Afzaal | Muzher Siddique | 0.17 | 17 |  |  |  | Complete | Mid-America Gardens, LLC | 6916 | 1 | 0.83 | 0 | 8
__export__.project_task_1562_d8caec4c | Procurement | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 7 | 100 |  |  |  | Complete | Wild Leaf Beverage | 7514 | 7 | 0 | 0 | 328
__export__.project_task_1545_18eee67c | Customer Invoice Portal: Set Up Customer Access | Sprint 2048 | 2020-11-23 | Development | Continuant: Customer Portal AR (P32) | Kaesi Lee | Fahad Hassan | 13.92 | 100 |  |  |  | Complete | Continuant | 7559 | 10.9167 | -3.0033 | 0 | 184
__export__.project_task_1293_7a525aac | Only accept lower case email addresses | Sprint 2045 | 2020-11-02 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 0 | 0 |  | 3.0.2 |  | Complete | Cellpoint Corporation | 8477 | 0 | 0 | 64 | 288
__export__.project_task_1140_0cb11cb4 | GFK Integration: Use Correct Vendors for Catalog Data | Sprint 29 | 2020-08-31 | Development | Continuant: eCommerce (P9) | Gadha Continuant |  | 0 | 0 |  |  |  | Complete | Continuant | 9246 | 0 | 0 | 0 | 0
__export__.project_task_927_03c63d15 | API:Auction detail:Postman | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9926 | 1 | 1 | 0 | 0
Postman
__export__.project_task_350_c8db2160 | Production Release #7 | Sprint 30 | 2020-09-07 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 0.00032117 | 0
__export__.project_task_4600_9b5a819b | Default Immediate Payment in Sales | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Raheel Aslam | 0.42 | 100 |  |  |  | Complete | Zuma Sales LLC | 723 | 0.25 | -0.17 | 0.012978 | 28.5246
__export__.project_task_4449_98b08d73 | Remove Fields | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 2.5 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 969 | 2.5 | 0 | 0 | 93.4233
__export__.project_task_3434_f860a636 | Import Customer/Vendors data | Sprint 2126 | 2021-06-21 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.2565 | 336.2654
__export__.project_task_3280_fb765de4 | Under the pallet build menu, make all the fields non-mandatory. | Sprint 2115 | 2021-04-05 | Development | Wild Leaf: Help (P22) | Jeff Gross | Fahad Hassan | 1.25 | 100 |  |  | 1 | Complete | Wild Leaf Beverage | 4019 | 0.83333 | -0.41667 | 0 | 93.6945
__export__.project_task_2298_9c03e872 | Client walkthrough and feedback session | Sprint 2104 | 2021-01-18 | Configuration | Mid-America: Help (P37) | Levi Barnes | Levi Barnes | 3.25 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 5887 | 3.25 | 0 | 0 | 67.0708
__export__.project_task_2125_816e591c | Microsoft account | Sprint 2102 | 2021-01-04 | Configuration | Silverdale: Help (P12) | Muhammad Afzaal | Nick Foy | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 6074 | 0 | 0 | 0 | 21.195
__export__.project_task_1868_27481932 | Review 3rd Party Apps | Sprint 2052 | 2020-12-21 | Configuration | PWX: Help (P23) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | EquityTeam | 6604 | 0 | -5.51 | 0.26423 | 133.082
__export__.project_task_1213_66dec83b | Bug: Synnex: Obtaining Order Confirmation | Sprint 31 | 2020-09-14 | Bug Fix | Continuant: eCommerce (P9) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Continuant | 8786 | 0 | 0 | 16 | 0
__export__.project_task_1208_446299a6 | Tech Data: Order Shipment and Tracking | Sprint 32 | 2020-09-21 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Continuant | 8791 | 0 | 0 | 18.473 | 119.7636
__export__.project_task_1149_4ce870d6 | OEM field: a search field with drop down menu | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9239 | 0 | 0 | 0 | 0
__export__.project_task_1123_2e802f8a | Ingram Micro: Order Shipment and Tracking | Sprint 31 | 2020-09-14 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Continuant | 9456 | 0 | 0 | 176 | 216
__export__.project_task_885_77c9f680 | Place a bid Android-Implementation | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 2 | 2 | 0 | 0
Android
__export__.project_task_4588_897bb90d | Share the data format | Sprint 2136 | 2021-08-30 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 2.5 | 100 |  |  |  | Complete | Zuma Sales LLC | 799 | 1.5 | -1 | 0 | 105.3956
__export__.project_task_4394_6a2da223 | Add validation that device is ready to be shipped | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 4.67 | 58.38 |  | SPLN |  | Complete | Cellpoint Corporation | 1154 | 8 | 3.33 | 0 | 169.6167
Priority
__export__.project_task_3272_ebd58e74 | Purchases on Item not showing the details | Sprint 2115 | 2021-04-05 | Development | MMH: Help (P83) | Jeff Gross | Raheel Aslam | 2.5 | 71.43 |  |  | 1 | Complete | Mountain Meadow Herbs | 4060 | 3.5 | 1 | 0 | 104
__export__.project_task_2319_71c78bcb | SO line item substitute note(and checkbox) | Sprint 2105 | 2021-01-25 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 9.83 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 5861 | 8 | -1.83 | 0 | 270.7034
__export__.project_task_1700_84ce7af3 | Delete "Core Focus" and make fields HTML | Sprint 2050 | 2020-12-07 | Development | PWX: Help (P23) | Levi Barnes | Fahad Hassan | 4.42 | 100 |  |  |  | Complete | EquityTeam | 6901 | 3 | -2.67 | 0 | 126.5861
__export__.project_task_1574_e8109b01 | Make Price Editable for Account Executives | Sprint 2048 | 2020-11-23 | Development | Continuant: Quotation Management / Automation (P31) | Kaesi Lee | Raheel Aslam | 10.08 | 100 |  |  |  | Complete | Continuant | 7441 | 7 | -3.08 | 0 | 472
__export__.project_task_1141_5d582eb6 | Conditional Dropship Order | Sprint 30 | 2020-09-07 | Development | Continuant: eCommerce (P9) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Continuant | 9241 | 0 | 0 | 0 | 0
__export__.project_task_1137_4cb96f53 | Carrier Code for UPS and FedEx Ground | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 9247 | 0 | 0 | 0 | 0
__export__.project_task_224_6502ca5c | Server Disconnected | Sprint 21 | 2020-07-06 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10638 | 0 | 0 | 86.9805 | 0
__export__.project_task_206_a875557e | Sorting and Search Web | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10783 | 8 | 8 | 98.4621 | 0
__export__.project_task_4587_186abc73 | All business processes in place |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 3.5 | 100 |  | SPLN |  | Complete | Zuma Sales LLC | 799 | 3 | -0.5 | 0 | 40
__export__.project_task_4454_b185c82c | User Validation Error on Vendor ASN Import, Phone Check Import, UEDF Response | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Kaleem Khan | 14.92 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 968 | 8 | -6.92 | 0 | 93.4233
__export__.project_task_3271_7b419dfa | Editing field not allowing | Sprint 2115 | 2021-04-05 | Development | MMH: Help (P83) | Jeff Gross | Raheel Aslam | 2.5 | 100 |  |  | 1 | Complete | Mountain Meadow Herbs | 4060 | 2 | -0.5 | 0 | 104
__export__.project_task_2330_dacbde80 | wishlist install | Sprint 2104 | 2021-01-18 | Configuration | Mid-America: Help (P37) | Levi Barnes | Levi Barnes | 0.25 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 5853 | 0 | -0.25 | 0 | 88
__export__.project_task_1827_422512d1 | Continuant Quotation Response Deployment 2049 | Sprint 2049 | 2020-11-30 | Configuration | Continuant: Quotation Management / Automation (P31) | Muzher Siddique |  | 0.67 | 67 |  |  |  | Complete | Continuant | 6751 | 1 | 0.33 | 0 | 1.3913
__export__.project_task_1693_7c9b8ae3 | appraisals core evaluation | Sprint 2051 | 2020-12-14 | Development | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 12.67 | 100 |  |  |  | Complete | EquityTeam | 6915 | 12 | -1 | 0 | 156
__export__.project_task_1206_f85e2e44 | Back End Fixes | Sprint 30 | 2020-09-07 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8793 | 0 | 0 | 0 | 52
__export__.project_task_1169_d8a77030 | Check Distributors for Shipping Notification Policy | Sprint 29 | 2020-08-31 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 9102 | 0 | 0 | 0 | 0
__export__.project_task_1041_a4d30a7f | Clicking Save re-directs them to the Create Auction Page | Sprint 26 | 2020-08-10 | Development | CPBids Migration AWS->odoo (P5) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 0 | 0
__export__.project_task_338_bf65f665 | Carrier: Receive tracking numbers from dropshippers | Sprint 31 | 2020-09-14 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 353.7145 | 393.7145
__export__.project_task_173_01b2d35a | Prevent Duplicate Entries | Sprint 27 | 2020-08-17 | Studio | Heronswood: Events (P3) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 11286 | 0 | 0 | 0 | 0
__export__.project_task_4585_6d35d360 | Critical Test Cases have been completely run on production database (Copy of Production on Staging) (copy) |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 799 | 3 | 3 | 0 | 6.7487
__export__.project_task_4447_eff91d06 | UEDF Validations Required | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 3.17 | 90.57 |  | SPLN |  | Complete | Cellpoint Corporation | 970 | 3.5 | 0.33 | 0 | 93.4233
__export__.project_task_3265_a3babc83 | Gift Price should not be picked in Sales Order line in case of changing quantity on line | Sprint 2115 | 2021-04-05 | Development | Mid-America: Help (P37) | Levi Barnes | Muhammad Bilal | 1.92 | 64 |  |  | 2 | Complete | Mid-America Gardens, LLC | 4066 | 3 | 1.08 | 0.00012918 | 108.9801
__export__.project_task_2659_8736d1ce | payment credentials | Sprint 2107 | 2021-02-01 | Configuration | Mid-America: Help (P37) | Levi Barnes | Levi Barnes | 0.25 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 5370 | 0 | -0.25 | 0 | 62.9853
__export__.project_task_1787_acee0dfc | Move Bid Limit field | Sprint 2050 | 2020-12-07 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Fahad Hassan | 0.17 | 17 |  |  |  | Complete | Cellpoint Corporation | 6836 | 1 | 0.83 | 0 | 102.5861
__export__.project_task_1512_7ee6c995 | Data Migration from Odoo to Azure |  |  | Development | Continuant: Power BI Integration (P30) | Levi Barnes | Muzher Siddique | 8.83 | 0 |  |  |  | Complete | Continuant | 7681 | 0 | -107.87 | 0 | 215.9042
__export__.project_task_1322_939618fc | Display Name on Contact | Sprint 2045 | 2020-11-02 | Development | PWX: Help (P23) | Levi Barnes | Danish Hassan | 11.83 | 100 |  | Contacts |  | Complete | EquityTeam | 8421 | 8 | -3.83 | 200 | 272
__export__.project_task_1135_3a0ff575 | Sales Delivery Order Automation | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9264 | 0 | 0 | 0 | 0
__export__.project_task_1075_5d310607 | Deploy as a Module | Sprint 29 | 2020-08-31 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9534 | 0 | 0 | 0 | 0
__export__.project_task_928_032f4b95 | API:Make an offer:Postman | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9926 | 1 | 1 | 0 | 0
Postman
__export__.project_task_841_de9ae46d | Get batch API iOS-Implementation | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_588_8e418716 | API:Login:APPMAVEN | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10070 | 5 | 5 | 0 | 0
Postman
__export__.project_task_544_9f0f369f | API:Tag list | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 10.7981 | 0
__export__.project_task_534_a1f0c54e | API:Forgot Password | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 10.7256 | 0
__export__.project_task_4584_d16b100e | Critical Test Cases have been completely run on production database (Copy of Production on Staging) |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hassan | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 799 | 3 | 3 | 0 | 6.7613
__export__.project_task_4450_ac09f329 | UEDF File Status on Stock Production Lot | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 6.75 | 90 |  | SPLN |  | Complete | Cellpoint Corporation | 969 | 7.5 | 0.75 | 0 | 93.4233
__export__.project_task_3432_82fc5c34 | Set up and verify User groups and access rights |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.2711 | 398.3233
__export__.project_task_3430_76bb8762 | Secure access to the production environment |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.2842 | 520.3123
__export__.project_task_3264_3dfae8de | Stock Availability Message | Sprint 2115 | 2021-04-05 | Development | Mid-America: Help (P37) | Levi Barnes | Aleem khan | 3.17 | 100 |  |  | 2 | Complete | Mid-America Gardens, LLC | 4067 | 2.5 | -0.67 | 0 | 109.726
__export__.project_task_2316_7a4f4c74 | image facebook | Sprint 2105 | 2021-01-25 | Development | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 2.5 | 41.67 |  |  |  | Complete | Mid-America Gardens, LLC | 5861 | 6 | 3.5 | 0 | 270.7308
__export__.project_task_1826_627d884c | Deployment AV Warehouse 2049 | Sprint 2049 | 2020-11-30 | Configuration | Continuant: AV Warehouse (P34) | Muzher Siddique |  | 1.58 | 100 |  |  |  | Complete | Continuant | 6751 | 1 | -0.58 | 0 | 0.0013433
__export__.project_task_1657_70257fcf | Test both applications for API response time | Sprint 2048 | 2020-11-23 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 2 | 0 |  |  |  | Complete | Cellpoint Corporation | 7066 | 0 | -2 | 0.13606 | 68.7033
__export__.project_task_1607_e76ad7ca | Process AV Items at Receipt | Sprint 2048 | 2020-11-23 | Development | Continuant: AV Warehouse (P34) | Kaesi Lee | Danish Hassan | 3.42 | 100 |  |  |  | Complete | Continuant | 7341 | 2.6667 | -0.75333 | 8 | 128
__export__.project_task_1138_5d3b5bb6 | Check Availability: Display all three vendors | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Gadha Continuant |  | 0 | 0 |  |  |  | Complete | Continuant | 9247 | 0 | 0 | 0 | 0
__export__.project_task_1059_1f03e0ac | Seller Permissions Group: Bug with "invite selected buyers" Selecting individual buyers then unselecting the invite selected buyers removes the buyer list from view. | Sprint 28 | 2020-08-24 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 88.3803 | 0
__export__.project_task_894_71094e60 | Seller list Android-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
Android
__export__.project_task_592_262178fa | API:Version updation:APPMAVEN | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10070 | 2 | 2 | 0 | 0
Postman
__export__.project_task_541_30e0f1b9 | API:Select state | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 10.7361 | 0
__export__.project_task_205_14855eb2 | Using Multiple devices | Sprint 22 | 2020-07-12 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10783 | 8 | 8 | 98.4689 | 0
__export__.project_task_4583_0d921f09 | Client Domain pointing to Odoo.sh address has been configured | Sprint 2136 | 2021-08-30 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Raheel Aslam | 0 | 0 |  | SPLN |  | Complete | Zuma Sales LLC | 799 | 0 | 0 | 0 | 133.4208
__export__.project_task_4446_da2e2ddf | Menus for Custom Models | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 4 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 970 | 4 | 0 | 0 | 93.4233
__export__.project_task_3429_60948b5e | Install the system management tools |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.295 | 520.3228
__export__.project_task_3263_c3afe3a2 | Two decimal to set on minimum order msg, on website. | Sprint 2115 | 2021-04-05 | Development | Mid-America: Help (P37) | Levi Barnes | Muhammad Bilal | 1.33 | 88.67 |  |  | 1 | Complete | Mid-America Gardens, LLC | 4067 | 1.5 | 0.17 | 0 | 109.8368
__export__.project_task_2740_3de63114 | shop/address modifications | Sprint 2109 | 2021-02-15 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 4.25 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 5168 | 3.8333 | -0.41667 | 0 | 106.4642
__export__.project_task_1572_36125ea4 | Invoice Portal Access Data from Excel | Sprint 2046 | 2020-11-09 | Development | Continuant: Customer Invoice Delivery Preferences (P33) | Kaesi Lee | Muzher Siddique | 4.83 | 80.5 |  |  |  | Complete | Continuant | 7442 | 6 | 1.17 | 0 | 79.2092
__export__.project_task_1431_00ee4072 | CPBids Mobile App: App Crashing | Sprint 2045 | 2020-11-02 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8020 | 0 | 0 | 0 | 40.1103
__export__.project_task_1190_b0981695 | Distributor Status: Set default to N/A | Sprint 30 | 2020-09-07 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 8881 | 0 | 0 | 0 | 0
__export__.project_task_1147_052bcb12 | Deploy Shipping Uplift | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9239 | 0 | 0 | 0 | 0
__export__.project_task_890_b424faca | Select state Android-Implementation | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
Android
__export__.project_task_887_f257d0a3 | Lot view Android-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
Android
__export__.project_task_817_1d3e4dbe | Place a bid iOS-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 2 | 2 | 0 | 0
iOS
__export__.project_task_598_56c75f02 | API:Tag list :APPMAVEN | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10070 | 3 | 3 | 0 | 0
Postman
__export__.project_task_596_97203851 | API:Forcefully Update:APPMAVEN | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10070 | 3 | 3 | 0 | 0
Postman
__export__.project_task_560_5132d979 | API:Notification list api | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 6 | 6 | 10.6608 | 0
__export__.project_task_4582_8587a9ea | Email Configuration has been tested | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.5 | 100 |  |  |  | Complete | Zuma Sales LLC | 799 | 0.5 | 0 | 0 | 40
__export__.project_task_4448_fe3fb5e8 | Product Form(product.product) should be same as Product Template | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Kaleem Khan | 2.5 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 969 | 2 | -0.5 | 0 | 93.4233
__export__.project_task_3428_479ffdd3 | Configure the standard applications database objects | Sprint 2126 | 2021-06-21 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.3003 | 336.3089
__export__.project_task_3246_2e702c2b | Need to add a selection field on SO for Gift & Substitute items | Sprint 2114 | 2021-03-29 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 2.58 | 100 |  |  | 1 | Complete | Mid-America Gardens, LLC | 4162 | 2 | -0.58 | 0 | 124.8827
__export__.project_task_2883_638e2dbd | Appraisal & Evaluations Planning Tribe |  |  | Other | Silverdale Time Tracking (P56) | Faisal Huda Khan | Wajahat Ali | 0 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 4588 | 0 | 0 | 8 | 228.3981
__export__.project_task_2652_4f3a8a1d | shipping receive by: Backup Restoration | Sprint 2107 | 2021-02-01 | Development | Mid-America: Help (P37) | Levi Barnes | Kaleem Khan | 3.5 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 5403 | 3.5 | 0 | 0 | 3.5311
__export__.project_task_2294_d5cf8aee | Deerfield: Add email addresses to Blacklist | Sprint 2103 | 2021-01-11 | Configuration | PWX: Help (P23) | Levi Barnes | Nick Foy | 0.08 | 0 |  |  |  | Complete | EquityTeam | 5888 | 0 | -0.08 | 0 | 99.9307
__export__.project_task_2115_a6958ede | Deployed tasks Meeting | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee | Raheel Aslam | 0.33 | 66 |  |  |  | Complete | Wild Leaf Beverage | 6081 | 0.5 | 0.17 | 0.074206 | 3.7164
__export__.project_task_1581_ebf13508 | Customer Quotation Response | Sprint 2105 | 2021-01-25 | Development | Continuant: Quotation Management / Automation (P31) | Kaesi Lee | Danish Hassan | 17.83 | 92.22 |  |  |  | Complete | Continuant | 7417 | 19.3333 | 1.5033 | 0 | 446.0803
__export__.project_task_1426_5d61ca8c | iOS List View Display Issue | Sprint 2045 | 2020-11-02 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0 | 0 |  | 3.0.2 |  | Complete | Cellpoint Corporation | 8045 | 0 | 0 | 0.40491 | 177.3344
__export__.project_task_1109_d8415f40 | Synnex: Obtain Pricing and Availability | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9457 | 0 | 0 | 0 | 0
__export__.project_task_888_e903ce76 | Version update Android-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
Android
__export__.project_task_886_ef822e57 | Make an offer Android-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
Android
__export__.project_task_825_968350c9 | Tag list iOS-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_540_61ae106e | API:Select country | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 10.7308 | 0
__export__.project_task_359_3fff692b | Training: Prepare training materials | Sprint 32 | 2020-09-21 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 129.7145 | 425.7145
__export__.project_task_264_96e38a07 | Updated API Document | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10301 | 16 | 16 | 44.115 | 0
__export__.project_task_226_ced35fd4 | Webkul Meeting | Sprint 27 | 2020-08-17 | Development | Cellpoint: Odoo Back-End (P8) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10610 | 0 | 0 | 0 | 0
__export__.project_task_4569_188fb15f | Review the options on the Settings screen for Default taxes | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 799 | 0.16667 | 0.16667 | 0 | 40
__export__.project_task_4460_e18a1d5d | Parent Package and POS Label Scanning | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 5.08 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 967 | 4 | -1.08 | 0 | 93.4233
__export__.project_task_3245_87b37039 | Error on Payment (Pay to Card) | Sprint 2115 | 2021-04-05 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 6.83 | 97.57 |  |  | 4 | Complete | Mid-America Gardens, LLC | 4162 | 7 | 0.17 | 0 | 125.0854
__export__.project_task_2776_a7f251d0 | Continuant QM Deployment 2107 | Sprint 2109 | 2021-02-15 | Other | Continuant: Quotation Management / Automation (P31) | Nick Foy | Muzher Siddique | 0.42 | 42 |  |  |  | Complete | Continuant | 5048 | 1 | 0.58 | 0 | 0.042565
__export__.project_task_2315_930986a5 | facebook | Sprint 2105 | 2021-01-25 | Configuration | Mid-America: Help (P37) | Levi Barnes | Levi Barnes | 0.17 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 5861 | 0 | -0.17 | 0 | 270.7394
__export__.project_task_2288_8fa4497c | General 2102 |  |  | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 1.25 | 0 |  |  |  | Complete | EquityTeam | 5901 | 0 | -1.25 | 0 | 32
__export__.project_task_2114_d733a443 | Propertyworx Deployment 2053 | Sprint 2102 | 2021-01-04 | Configuration | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 1.17 | 58.5 |  |  |  | Complete | EquityTeam | 6081 | 2 | 0.83 | 0.037667 | 0.56794
__export__.project_task_1425_fb34dca7 | Priority 0: APPs are not updating | Sprint 2042 | 2020-10-12 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8053 | 0 | 0 | 0 | 55.522
__export__.project_task_1187_f7de3692 | Sales Order / Quotation: Change PDF Template | Sprint 30 | 2020-09-07 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 8932 | 0 | 0 | 0 | 0
__export__.project_task_1113_904b78ec | Synnex: Generate Shipping Quoatation | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9457 | 0 | 0 | 0 | 0
__export__.project_task_938_febcdaa7 | API:MyWatch Product List:Postman | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9894 | 1 | 1 | 0 | 0
Postman
__export__.project_task_918_87e7d573 | API:Change Password:Postman | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9927 | 0.5 | 0.5 | 0 | 0
Postman
__export__.project_task_842_83231376 | Get marketplace list iOS-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_591_cd36949e | API:Select state:APPMAVEN | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10070 | 3 | 3 | 0 | 0
Postman
__export__.project_task_562_511f93db | API:Set Batch Api | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 3 | 3 | 10.6517 | 0
__export__.project_task_291_9c2506be | Distributor: Research Distributor API | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 10250 | 8 | 8 | 56 | 0
__export__.project_task_200_7bc9e4eb | Allow bid from List view Web | Sprint 27 | 2020-08-17 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10783 | 16 | 16 | 98.5582 | 0
__export__.project_task_4568_dd41e7c9 | Review the options on the Settings screen for Cash Rounding | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.25 | 50 |  | SPLN |  | Complete | Zuma Sales LLC | 799 | 0.5 | 0.25 | 0 | 68.2244
__export__.project_task_4456_7305f06b | UEDF Activation | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 4.92 | 82 |  | SPLN |  | Complete | Cellpoint Corporation | 968 | 6 | 1.08 | 0 | 93.4233
__export__.project_task_3244_2536bed0 | Gift should be counted in the total count | Sprint 2114 | 2021-03-29 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 1.67 | 100 |  |  | 2 | Complete | Mid-America Gardens, LLC | 4163 | 1 | -0.67 | 0 | 125.5661
__export__.project_task_2768_3b4a96c7 | Continuant AV Warehouse Deployment 2107 | Sprint 2109 | 2021-02-15 | Other | Continuant: AV Warehouse (P34) | Nick Foy | Muzher Siddique | 1 | 100 |  |  |  | Complete | Continuant | 5071 | 1 | 0 | 0 | 3.0104
__export__.project_task_2281_f12dd62d | FW: You have been assigned to Deerfield Contacts Import (305): update invoices | Sprint 2103 | 2021-01-11 | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 0.5 | 0 |  |  |  | Complete | EquityTeam | 5909 | 0 | -0.5 | 0 | 118.8094
__export__.project_task_2113_b6da3bd4 | Deployment and Post QA on Production | Sprint 2102 | 2021-01-04 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 2.67 | 100 |  |  |  | Complete | Cellpoint Corporation | 6082 | 2.6667 | -0.0033333 | 0.014077 | 1.0974
__export__.project_task_1952_bfc1d310 | Import Products | Sprint 2053 | 2020-12-28 | Configuration | Mid-America: Help (P37) | Levi Barnes | Nick Foy | 0 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 6523 | 0 | 0 | 14.4119 | 80
__export__.project_task_1639_74968361 | Continuanat deployment | Sprint 2047 | 2020-11-16 | Configuration | Continuant: Power BI Integration (P30) | Muzher Siddique |  | 0.5 | 0 |  |  |  | Complete | Continuant | 7108 | 0 | -0.5 | 0 | 5.4422
__export__.project_task_1396_fb4a497a | Auto Update for iOS:APP MAVEN | Sprint 2042 | 2020-10-12 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8188 | 0 | 0 | 0 | 16
__export__.project_task_1083_64302271 | Product Mapping: GFK to Ingram Micro | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 9533 | 0 | 0 | 0 | 0
__export__.project_task_954_5c3cdf19 | Add Product Pricing Uplift | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9696 | 0 | 0 | 46.9594 | 0
__export__.project_task_926_1663553d | API:Lot view :Postman | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9926 | 1 | 1 | 0 | 0
Postman
__export__.project_task_911_e6eeb087 | Manifest API Android-Implementation | Sprint 27 | 2020-08-17 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 2 | 2 | 0.00016651 | 0
Android
__export__.project_task_897_015ebe45 | Product status Android-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
Android
__export__.project_task_813_a9894bd8 | Login API iOS-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
iOS
__export__.project_task_557_d7bba3fc | API:Logout | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 10.8092 | 0
__export__.project_task_546_b40fd201 | API:Location List | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 10.7622 | 0
__export__.project_task_4566_ce0d4d72 | Review the options on the Settings screen for Batch Payments | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.5 | 100 |  |  |  | Complete | Zuma Sales LLC | 799 | 0.5 | 0 | 0 | 40
__export__.project_task_4533_5e1968ce | On Delivery Order (stock.picking) changes | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 3.42 | 48.86 |  | SPLN |  | Complete | Cellpoint Corporation | 837 | 7 | 3.58 | 0 | 93.4244
__export__.project_task_3232_be66366f | Gifts in different section on delivery order | Sprint 2114 | 2021-03-29 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 4.17 | 92.67 |  |  | 2 | Complete | Mid-America Gardens, LLC | 4186 | 4.5 | 0.33 | 1.9563e-05 | 132.4492
__export__.project_task_2746_766308b6 | AV IQ Credentials |  |  | Other | Continuant: Quotation Management / Automation (P31) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Continuant | 5142 | 0 | 0 | 0 | 0
__export__.project_task_2707_14f74b7e | Set discussion for how to track credit card receipts and deal with expense reports. |  |  | Configuration | Wild Leaf: Accounting (P64) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 5324 | 0 | 0 | 160 | 527.5608
__export__.project_task_2643_ebc668fa | Mid America Deployment 2104 | Sprint 2107 | 2021-02-01 | Other | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 1.67 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 5411 | 1 | -0.67 | 0 | 1.899
__export__.project_task_2261_9774b946 | Deployment of Propertyworx 2101 | Sprint 2103 | 2021-01-11 | Configuration | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 0.25 | 100 |  |  |  | Complete | EquityTeam | 5913 | 0.25 | 0 | 0 | 0.18662
__export__.project_task_2103_7a204ac0 | Bank Details | Sprint 2102 | 2021-01-04 | Development | Silverdale: Help (P12) | Muhammad Afzaal | Kaleem Khan | 2.17 | 100 |  |  |  | Complete | Silverdale Technology LLC | 6104 | 2 | -0.17 | 0.058871 | 2.7203
__export__.project_task_1314_0c3c6ad1 | Mark Bids for Web/APP | Sprint 2041 | 2020-10-05 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 6 | 0 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 8429 | 0 | -6 | 0 | 45.1497
__export__.project_task_1164_d8d03cee | Check Out Process: Input Email | Sprint 30 | 2020-09-07 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9190 | 0 | 0 | 0 | 0
__export__.project_task_1159_119f7ec7 | All Buyers | Sprint 28 | 2020-08-24 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9201 | 0 | 0 | 0 | 0
__export__.project_task_1136_9625007a | Mail Server Issue | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9247 | 0 | 0 | 0 | 0
__export__.project_task_1100_ca13141f | Number of Views not populated | Sprint 28 | 2020-08-24 | Bug Fix | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9506 | 0 | 0 | 40 | 0
__export__.project_task_972_abf856f3 | Post and Rename Database Versions | Sprint 26 | 2020-08-10 | Configuration | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9604 | 0 | 0 | 0 | 0
__export__.project_task_843_144dc28b | Manifest API iOS-Implementation | Sprint 27 | 2020-08-17 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 2 | 2 | 0.00018745 | 0
iOS
__export__.project_task_836_1351c626 | Logout iOS-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_816_bb2db51c | Auction detail iOS-Implementation | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 2 | 2 | 0 | 0
iOS
__export__.project_task_599_32831466 | API:Update Terms and condition:APPMAVEN | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10070 | 3 | 3 | 0 | 0
Postman
__export__.project_task_4561_2fdb7086 | Review the options on the Settings screen for Online Payment of Invoices | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.25 | 50 |  | SPLN |  | Complete | Zuma Sales LLC | 799 | 0.5 | 0.25 | 0 | 68.0406
__export__.project_task_4444_15e19088 | For different products should export different UEDF ASN xml files | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 8.08 | 80.8 |  | SPLN |  | Complete | Cellpoint Corporation | 991 | 10 | 1.92 | 0 | 133.4244
__export__.project_task_3424_4a39f946 | Back-up existing odoo.sh install | Sprint 2123 | 2021-05-31 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.3447 | 284.8994
__export__.project_task_3229_4070d9f9 | In a single SO with multiple invoices showing extra Delivery charges | Sprint 2114 | 2021-03-29 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 7.33 | 100 |  |  | 2 | Complete | Mid-America Gardens, LLC | 4186 | 6.8333 | -0.49667 | 4.7506e-05 | 133.1478
__export__.project_task_2314_526eeb39 | paypal | Sprint 2105 | 2021-01-25 | Configuration | Mid-America: Help (P37) | Levi Barnes | Levi Barnes | 0 | 0 |  |  |  | Complete | Mid-America Gardens, LLC | 5861 | 0 | 0 | 0 | 270.7362
__export__.project_task_2256_29597099 | AV Warehouse Demo | Sprint 2103 | 2021-01-11 | Configuration | Continuant: AV Warehouse (P34) | Kaesi Lee |  | 0.75 | 0 |  |  |  | Complete | Continuant | 5926 | 0 | -0.75 | 0 | 0
__export__.project_task_304_3c8e4033 | Universal Appointments and Time Reservations |  |  | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 0 | 0 |  |  |  | Complete | EquityTeam | 5931 | 0 | 0 | 0 | 54.9253
__export__.project_task_2122_ff9c8a65 | General 2101 | Sprint 2102 | 2021-01-04 | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 1.5 | 0 |  |  |  | Complete | EquityTeam | 6079 | 0 | -1.5 | 0.010522 | 34.4536
__export__.project_task_1682_df715f9a | Deployment Continuant: Quotation Management / Automation | Sprint 2048 | 2020-11-23 | Configuration | Continuant: Quotation Management / Automation (P31) | Muzher Siddique |  | 1 | 100 |  |  |  | Complete | Continuant | 6921 | 0.5 | -0.5 | 0 | 0.083287
__export__.project_task_1114_456f3c64 | Ingram: Generate Shipping Quotation | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9457 | 0 | 0 | 0 | 0
__export__.project_task_1099_71998229 | Number of mywatch bidders not populated | Sprint 28 | 2020-08-24 | Bug Fix | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9506 | 0 | 0 | 76.465 | 0
__export__.project_task_941_4c019893 | Carrier: Test Dropship Functionality | Sprint 25 | 2020-08-03 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 9796 | 0 | 0 | 0 | 0
__export__.project_task_934_fa5366ff | API:Get Batch Api:Postman | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9894 | 1 | 1 | 0 | 0
Postman
__export__.project_task_881_efa022bf | Login API Android-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
Android
__export__.project_task_838_2247152a | Notification list iOS-Implementation | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_595_28c190a8 | API:Select City:APPMAVEN | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10070 | 3 | 3 | 0 | 0
Postman
__export__.project_task_539_7ecca02d | API:Version updation | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 24 | 0
__export__.project_task_246_9556444d | Signup all on staging AWS | Sprint 27 | 2020-08-17 | Development | Silverdale: Help (P12) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 10421 | 0 | 0 | 0 | 0
__export__.project_task_4556_aa5f93d2 | Set the clearing/suspense account on the Inventory Adjustment location so your summary suspense balance is cleared when the adjustment completes. | Sprint 2136 | 2021-08-30 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 799 | 0.16667 | 0.16667 | 0 | 104
__export__.project_task_4539_4421c10f | Package and Parent Package label numbers | Sprint 2134 | 2021-08-16 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 5.5 | 91.67 |  | SPLN |  | Complete | Cellpoint Corporation | 823 | 6 | 0.5 | 0 | 93.4244
__export__.project_task_3228_d9f62e8d | Gift prices reflect in delivery report | Sprint 2115 | 2021-04-05 | Development | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 2.42 | 80.67 |  |  | 3 | Complete | Mid-America Gardens, LLC | 4186 | 3 | 0.58 | 0 | 133.2604
__export__.project_task_2705_1d8e96db | Set bank connections for WildPack Beverage Inc. (CIBC - CDN bank) |  |  | Configuration | Wild Leaf: Accounting (P64) | Jeff Gross |  | 0 | 0 |  |  |  | Complete | Wild Leaf Beverage | 5324 | 0 | 0 | 160 | 685.6175
__export__.project_task_2317_0d34706a | shopping ux | Sprint 2105 | 2021-01-25 | Development | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 3.83 | 76.6 |  |  |  | Complete | Mid-America Gardens, LLC | 5861 | 5 | 1.17 | 0 | 270.6823
__export__.project_task_202_0343330d | Activity Bundle |  |  | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 0 | 0 |  |  |  | Complete | EquityTeam | 5931 | 0 | 0 | 0 | 54.9275
__export__.project_task_2137_7b136c11 | Consignment Receiving Training | Sprint 2102 | 2021-01-04 | Configuration | Wild Leaf: Help (P22) | Kaesi Lee |  | 0.5 | 0 |  |  |  | Complete | Wild Leaf Beverage | 6072 | 0 | -0.5 | 0 | 14.1469
__export__.project_task_2053_17cd0fa8 | Deployment of Continuant AV Warehouse | Sprint 2052 | 2020-12-21 | Configuration | Continuant: AV Warehouse (P34) | Kaesi Lee | Muzher Siddique | 0.5 | 50 |  |  |  | Complete | Continuant | 6248 | 1 | 0.5 | 0 | 0.25028
__export__.project_task_1120_d358bc20 | Ingram: Obtain Order Confirmation | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Gadha Continuant |  | 0 | 0 |  |  |  | Complete | Continuant | 9456 | 0 | 0 | 31.2225 | 0
__export__.project_task_1118_0fd66f4c | Synnex: Obtain Order Confirmation | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Gadha Continuant |  | 0 | 0 |  |  |  | Complete | Continuant | 9456 | 0 | 0 | 31.2325 | 0
__export__.project_task_1080_bb6aa0ff | Product Mapping: GFK to Tech Data | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 9533 | 0 | 0 | 0 | 0
__export__.project_task_922_7ecf0f1c | API:Get List of MarketPlaces:Postman | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9926 | 0.5 | 0.5 | 0 | 0
Postman
__export__.project_task_902_225ab054 | Change passord Android-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00016651 | 0
Android
__export__.project_task_832_48c02911 | My watch product list iOS-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 2 | 2 | 0.00018745 | 0
iOS
__export__.project_task_821_37e10709 | Select country iOS-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_561_b80eea6a | API:My Bids | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 6 | 6 | 10.6561 | 0
__export__.project_task_558_2ed97dad | API:Forcefully Update | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 10.8214 | 0
__export__.project_task_172_8f3780eb | Date and Time for Pictures | Sprint 27 | 2020-08-17 | Studio | Heronswood: Events (P3) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 11286 | 0 | 0 | 0 | 0
__export__.project_task_4554_bf3d6346 | Enter your default Terms & Conditions. | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.17 | 100 |  |  |  | Complete | Zuma Sales LLC | 799 | 0.16667 | -0.0033333 | 0 | 56
__export__.project_task_4528_e69c2856 | Phone check import successful message | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Kaleem Khan | 5.58 | 93 |  | SPLN |  | Complete | Cellpoint Corporation | 841 | 6 | 0.42 | 0 | 65.4233
__export__.project_task_3426_4d553775 | Configure the file system on the servers |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hussain Malik | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.3158 | 520.3435
__export__.project_task_3422_5d45b40c | Acquiring the Master Data as appropriate (I would make multiple tasks for each set of data) | Sprint 2126 | 2021-06-21 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.3401 | 336.3487
__export__.project_task_3222_7bf838e1 | Language switcher to Chinese not working for auction list |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 4.33 | 100 |  |  | 3 | Complete | Cellpoint Corporation | 4206 | 3 | -1.33 | 0 | 138.1019
__export__.project_task_2657_9c2831d4 | Deployment continuant Unit Test | Sprint 2107 | 2021-02-01 | Other | Continuant: Unit Testing (P51) | Kaesi Lee | Muzher Siddique | 2 | 0 |  |  |  | Complete | Continuant | 5378 | 0 | -2 | 0 | 12
__export__.project_task_2318_2188b37f | SO line item total count | Sprint 2105 | 2021-01-25 | Development | Mid-America: Help (P37) | Levi Barnes | Danish Hassan | 3.92 | 100 |  |  |  | Complete | Mid-America Gardens, LLC | 5861 | 3.5 | -0.42 | 0 | 270.6868
__export__.project_task_2164_0965579a | Belmont Azure Client Feedback:Export the invoices data,match column with schema | Sprint 2102 | 2021-01-04 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 4.5 | 0 |  |  |  | Complete | Cellpoint Corporation | 6033 | 0 | -4.5 | 9.6839e-05 | 96.232
__export__.project_task_2109_a0c784ac | Says "not connected" to employee profile (#40) |  |  | Bug Fix | PWX: Help (P23) | Levi Barnes | Danish Hassan | 0.75 | 75 |  | Difficulty 2 |  | Complete | EquityTeam | 6094 | 1 | 0.25 | 0 | 144
__export__.project_task_2025_1b35d0c6 | Deployment Continuant Power BI Integration 2051 | Sprint 2051 | 2020-12-14 | Configuration | Continuant: Power BI Integration (P30) | Kaesi Lee | Muzher Siddique | 0.28 | 0 |  |  |  | Complete | Continuant | 6416 | 0 | -0.28 | 4.1766e-05 | 7.2173
__export__.project_task_900_934de814 | My watch product list Android-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00016651 | 0
Android
__export__.project_task_556_690b3688 | API:Edit Profile | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 4 | 4 | 10.6658 | 0
__export__.project_task_554_ee9f13af | API:Add to watchlist | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 0 | 0 | 10.6706 | 0
__export__.project_task_553_da979c05 | API:MyWatch Product List | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 3 | 3 | 10.6758 | 0
__export__.project_task_543_1cc4bf4e | API:Download csv | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 10.7508 | 0
__export__.project_task_356_8de90f87 | Sponsor Meeting #6 | Sprint 28 | 2020-08-24 | Development | Continuant: eCommerce (P9) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 0.00032117 | 0
__export__.project_task_354_f87dba42 | Sponsor Meeting #4 | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 0.00032117 | 0
__export__.project_task_273_aa455370 | Group Sellers - Marketplace | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10260 | 12 | 12 | 1.2192 | 0
__export__.project_task_201_edb7ed7b | Marketplace for Web | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10783 | 16 | 16 | 125.0263 | 0
__export__.project_task_4552_e9dae999 | Define income, expense and cost of revenue accounts on your Product categories. | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  | SPLN |  | Complete | Zuma Sales LLC | 799 | 0.16667 | 0.16667 | 0 | 72
__export__.project_task_4527_7cb7813d | Done quantity should not be done on ASN Import | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 4.83 | 96.6 |  | SPLN |  | Complete | Cellpoint Corporation | 841 | 5 | 0.17 | 0 | 65.4233
__export__.project_task_3425_1052bca2 | Create user accounts on the servers |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3484 | 0 | 0 | 461.3223 | 440.3309
__export__.project_task_3421_68caa507 | Discussion and finalization on what do we do with historical data |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3485 | 0 | 0 | 461.3487 | 365.6117
__export__.project_task_3210_d3ab415d | Wildleaf: Add sale person as a follower in all invoices related to SO | Sprint 2114 | 2021-03-29 | Development | Wild Leaf: Help (P22) | Jeff Gross | Danish Hassan | 2.67 | 100 |  |  | 2 | Complete | Wild Leaf Beverage | 4232 | 2.3333 | -0.33667 | 0 | 148
__export__.project_task_2674_9c87d50f | Move from Constant Contact to Odoo Email Marketing |  |  | Configuration | Heronswood: Help (P54) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Port Gamble Sâ€™Klallam Foundation | 5352 | 0 | 0 | 168 | 406.3022
__export__.project_task_2121_ac9474f1 | Silverdale Deployment 2053 | Sprint 2102 | 2021-01-04 | Configuration | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 0.75 | 37.5 |  |  |  | Complete | Mid-America Gardens, LLC | 6079 | 2 | 1.25 | 0 | 1.5313
__export__.project_task_2072_c7b1a141 | FW: constantly being kicked out of odoo |  |  | Bug Fix | PWX: Help (P23) | Levi Barnes |  | 0.25 | 0 |  |  |  | Complete | EquityTeam | 6214 | 0 | -0.25 | 0 | 23.4342
__export__.project_task_1888_62c87d50 | Continuant AV Warehouse Deployment 2050 | Sprint 2050 | 2020-12-07 | Configuration | Continuant: AV Warehouse (P34) | Muzher Siddique | Muzher Siddique | 0.42 | 42 |  |  |  | Complete | Continuant | 6582 | 1 | 0.58 | 0 | 0.26317
__export__.project_task_1681_6f85573c | Deployment Continuant: Customer Portal AR | Sprint 2048 | 2020-11-23 | Development | Continuant: Customer Portal AR (P32) | Muzher Siddique |  | 0.17 | 34 |  |  |  | Complete | Continuant | 6921 | 0.5 | 0.33 | 0 | 0.12024
__export__.project_task_1652_0dc621f1 | Parameter mis match while adding product in watchlist if no bid is placed | Sprint 2048 | 2020-11-23 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Apps Maven | 1.5 | 0 |  | 3.0.5 |  | Complete | Cellpoint Corporation | 7066 | 0 | -1.5 | 0.40152 | 68.9168
__export__.project_task_1060_769bac42 | Seller Permissions Group: Action>Remove Duplicate Buyers | Sprint 28 | 2020-08-24 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9575 | 0 | 0 | 88.8572 | 0
__export__.project_task_951_07b72061 | Integration GFK Catalog: Replace default photo with GFK photo | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9723 | 0 | 0 | 0 | 0
__export__.project_task_935_4b783045 | API:Set Batch Api:Postman | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9894 | 1 | 1 | 0.0076269 | 0
Postman
__export__.project_task_905_fc899179 | Forcefully update Android-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00016651 | 0
Android
__export__.project_task_898_50dfbe4e | Bid history Android-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00016651 | 0
Android
__export__.project_task_548_fae73e2a | API:Product status | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 6 | 6 | 10.6858 | 0
__export__.project_task_537_8bf158a3 | API:Make an offer | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 10.6992 | 0
__export__.project_task_306_9c2e2097 | eCommerce: Release Module | Sprint 25 | 2020-08-03 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10247 | 0 | 0 | 6.2856 | 0
__export__.project_task_4551_dfef5a08 | Define your Inventory costing and valuation methods (if using the Inventory App) for your Product Categories. | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 799 | 0.16667 | 0.16667 | 0 | 32.7072
__export__.project_task_4440_2e9948be | Message for User for NMS has already been sent | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 3.83 | 95.75 |  | SPLN |  | Complete | Cellpoint Corporation | 1008 | 4 | 0.17 | 0 | 103.9606
__export__.project_task_3420_f5074a7b | Communicate go-live timeline to customers and vendors as appropriate |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3485 | 0 | 0 | 461.3609 | 454.1012
__export__.project_task_3209_5604db02 | Web Lot detail view in Chinese | Sprint 2115 | 2021-04-05 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 6.5 | 100 |  |  | 2 | Complete | Cellpoint Corporation | 4232 | 6.5 | 0 | 0 | 148
__export__.project_task_2672_7f4116b6 | Volunteer Shift Management |  |  | Configuration | Heronswood: Help (P54) | Jeff Gross |  | 0 | 0 |  |  |  | Cancelled | Port Gamble Sâ€™Klallam Foundation | 5352 | 0 | 0 | 168 | 406.3133
__export__.project_task_2669_95af32cf | Fw: Task Notification Alterations |  |  | Configuration | PWX: Help Desk (P65) | Levi Barnes |  | 0 | 0 |  |  |  | Cancelled | EquityTeam | 5353 | 0 | 0 | 0 | 922.8097
__export__.project_task_2119_dafb4cd1 | Continuant AV Warehouse Deployment 2053 | Sprint 2102 | 2021-01-04 | Configuration | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 0.2 | 20 |  |  |  | Complete | Mid-America Gardens, LLC | 6080 | 1 | 0.8 | 0 | 0.1173
__export__.project_task_2069_3c0b09ec | Consulting |  |  | Configuration | PWX: Help (P23) | Levi Barnes |  | 1.5 | 0 |  |  |  | Complete | EquityTeam | 6219 | 0 | -1.5 | 0 | 0
__export__.project_task_1858_ee42da84 | Option to add SSL Certificates to Encrypt Connections | Sprint 2051 | 2020-12-14 | Development | Continuant: Power BI Integration (P30) | Kaesi Lee | Fahad Hassan | 7.17 | 100 |  |  |  | Complete | Continuant | 6700 | 5 | -2.17 | 0 | 100
__export__.project_task_1506_0e69b0b5 | Scheduled Action |  |  | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Raheel Aslam | 11.33 | 100 |  | Odoo Migration |  | Complete | Cellpoint Corporation | 7685 | 13 | -15.41 | 0 | 216.9977
__export__.project_task_1180_bc8a8fe5 | API Configuration Form View | Sprint 30 | 2020-09-07 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9027 | 0 | 0 | 0 | 0
__export__.project_task_937_12feae8c | API:Add to watchlist : | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9894 | 1 | 1 | 0.021223 | 0
Postman
__export__.project_task_925_60a4f324 | API:Product status:Postman | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9926 | 1 | 1 | 0 | 0
Postman
__export__.project_task_920_ee3bf504 | API:Product List:Postman | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9926 | 0.5 | 0.5 | 0 | 0
Postman
__export__.project_task_835_23f18916 | Edit profile iOS-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_582_e29e1176 | Updated API Document:APPMAVEN | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Muhammad Afzaal |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10096 | 5 | 5 | 12 | 0
__export__.project_task_363_4e677992 | CPBids Website Status Page | Sprint 23 | 2020-07-20 | Development | Cellpoint CPBids: Help (P7) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10226 | 0 | 0 | 0 | 0
__export__.project_task_357_43b2ae09 | Sponsor Meeting #7 | Sprint 29 | 2020-08-31 | Development | Continuant: eCommerce (P9) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 0.00032117 | 0
__export__.project_task_275_7ba5dbb5 | Group Buyers: Super Selection | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10259 | 8 | 8 | 0.010754 | 0
__export__.project_task_268_bd91de66 | Share Github Account ID with Allison | Sprint 22 | 2020-07-12 | Development | Continuant: eCommerce (P9) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Continuant | 10274 | 0 | 0 | 14.2858 | 0
__export__.project_task_4547_1dbe91dc | Verify Fiscal Positions are setup and support your needs - potentially having a Tax Exempt position. | Sprint 2135 | 2021-08-23 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0.25 | 50 |  | SPLN |  | Complete | Zuma Sales LLC | 800 | 0.5 | 0.25 | 0 | 68.0739
__export__.project_task_4438_9151c699 | NMS Export file has imei's repeated and last space | Sprint 2133 | 2021-08-09 | Bug Fix | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 3.58 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 1008 | 2 | -1.58 | 0 | 104.1539
__export__.project_task_3419_662ca865 | Finalize cutover plan and checklists |  |  | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3485 | 0 | 0 | 461.3712 | 454.1145
__export__.project_task_3207_400ec443 | Deployment 2112:PWX | Sprint 2114 | 2021-03-29 | Configuration | PWX: Survey (P70) | Levi Barnes | Wajahat Ali | 1.58 | 0 |  |  |  | Complete | EquityTeam | 4233 | 0 | -1.58 | 0 | 148
__export__.project_task_2391_c67ec151 | Display Customer Statements in Customer Portal | Sprint 2109 | 2021-02-15 | Development | Continuant: Customer Portal AR (P32) | Nick Foy | Muhammad Bilal | 11.37 | 100 |  |  |  | Complete | Continuant | 5717 | 8 | -3.37 | 64.5432 | 239.0046
__export__.project_task_2118_0142a538 | Wild Leaf General Deployment 2053 | Sprint 2102 | 2021-01-04 | Configuration | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 0.97 | 48.5 |  |  |  | Complete | Mid-America Gardens, LLC | 6080 | 2 | 1.03 | 0 | 1.2569
__export__.project_task_2060_cc4b6a05 | New system@pwxusa.com credentials | Sprint 2052 | 2020-12-21 | Configuration | PWX: Help (P23) | Levi Barnes |  | 0.17 | 0 |  |  |  | Complete | EquityTeam | 6224 | 0 | -0.17 | 0 | 40.6223
__export__.project_task_1840_9a9ba1b0 | Send to Pick: Delivery Order Selection | Sprint 2052 | 2020-12-21 | Development | Continuant: AV Warehouse (P34) | Kaesi Lee | Danish Hassan | 13.17 | 100 |  |  |  | Complete | Continuant | 6743 | 6 | -23.09 | 0 | 164.8297
__export__.project_task_1354_6877ff2e | Beta Feedback Oct 1 | Sprint 2041 | 2020-10-05 | Development | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 31 | 0 |  |  |  | Complete | Cellpoint Corporation | 8379 | 0 | -31 | 0 | 63.9822
__export__.project_task_924_fae5c57f | API:Bid History:Postman | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9926 | 1 | 1 | 0 | 0
Postman
__export__.project_task_909_5318ee06 | Get batch API Android-Implementation | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00016651 | 0
Android
__export__.project_task_834_b4ff2226 | Change passord iOS-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_820_61edd43c | Version update iOS-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_607_8a075f4e | eCommerce: Add Customer Select Field | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9965 | 5 | 5 | 0.17582 | 0
__export__.project_task_580_a90438db | POPDM: Database Record Error | Sprint 24 | 2020-07-27 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10110 | 0 | 0 | 39.0483 | 0
__export__.project_task_345_b12a59c3 | Production Release #2 | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 0.00032117 | 0
__export__.project_task_271_21f74da7 | Marketplace- Backend | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10260 | 0 | 0 | 106.8069 | 0
__export__.project_task_4546_0d3904f0 | Define which accounts can be used to write Checks and modify your layout if needed. | Sprint 2137 | 2021-09-06 | Configuration | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 800 | 2 | 2 | 0 | 128
__export__.project_task_4407_bd48f06e | Deploy report_xml to the database | Sprint 2134 | 2021-08-16 | Configuration | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 0.42 | 0 |  | SPLN |  | Complete | Cellpoint Corporation | 1132 | 0 | -0.42 | 0 | 167.0585
__export__.project_task_3408_72c5c92a | A solution for saving credit card information |  |  | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Complete | Zuma Sales LLC | 3506 | 0 | 0 | 468.9914 | 528.0192
__export__.project_task_2653_7b461370 | Daily Meetings |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Nick Foy |  | 323.6 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 5402 | 0 | -323.6 | 0 | 420.4036
__export__.project_task_2117_7f7f95ca | Mid America Deployment 2053 | Sprint 2102 | 2021-01-04 | Configuration | Mid-America: Help (P37) | Levi Barnes | Muzher Siddique | 1.33 | 66.5 |  |  |  | Complete | Mid-America Gardens, LLC | 6081 | 2 | 0.67 | 0 | 0.67389
__export__.project_task_2051_81547b3d | How to set up task search to search for reference #'s (#44) |  |  | Configuration | PWX: Help (P23) | Levi Barnes |  | 0 | 0 |  |  |  | Complete | EquityTeam | 6260 | 0 | 0 | 0 | 52.8222
__export__.project_task_1828_78c708bd | Data Migration Module Documentation | Sprint 2050 | 2020-12-07 | Configuration | Continuant: Power BI Integration (P30) | Kaesi Lee |  | 1.5 | 0 |  |  |  | Complete | Continuant | 6750 | 0 | -1.5 | 0 | 88.4215
__export__.project_task_1680_107bb996 | Deployment Continuant: Customer Invoice Delivery Preferences | Sprint 2048 | 2020-11-23 | Development | Continuant: Customer Invoice Delivery Preferences (P33) | Muzher Siddique |  | 0.5 | 100 |  |  |  | Complete | Continuant | 6921 | 0.5 | 0 | 0 | 0.1401
__export__.project_task_1311_778fa696 | Unable to approve Buyer | Sprint 2041 | 2020-10-05 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8431 | 0 | 0 | 0 | 82.4268
__export__.project_task_956_d4bfc946 | Review Cart: Make Quantity Read Only | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9696 | 0 | 0 | 0 | 0
__export__.project_task_919_cf8da367 | API:Edit Profile:Postman | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9927 | 0.5 | 0.5 | 0 | 0
Postman
__export__.project_task_913_0bbf2d0a | Filter Screen fuctionality Android-Implementation | Sprint 28 | 2020-08-24 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 2 | 2 | 0.00016651 | 0
Android
__export__.project_task_889_4f04aef3 | Select country Android-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
Android
__export__.project_task_547_84e3927d | API:Category List | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 10.79 | 0
__export__.project_task_304_b4899f82 | Tax: Test Avalara Functionality: Obtain Credentials | Sprint 22 | 2020-07-12 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10247 | 0 | 0 | 6.2858 | 0
__export__.project_task_257_b9c039df | Manifest for web | Sprint 22 | 2020-07-12 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10382 | 24 | 24 | 0 | 0
__export__.project_task_4535_303cc771 | Planning New Go-Live Plan | Sprint 2133 | 2021-08-09 | Other | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 3 | 100 |  |  |  | Complete | Zuma Sales LLC | 826 | 3 | 0 | 0 | 0.0078762
__export__.project_task_4406_f56fba4b | Custom fields to add | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Kaleem Khan | 1.5 | 75 |  | SPLN | 1 | Complete | Cellpoint Corporation | 1137 | 2 | 0.5 | 0 | 133.4236
__export__.project_task_3407_6ecb3d86 | Customer Equipment Management |  |  | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0 | 0 |  |  |  | Cancelled | Zuma Sales LLC | 3506 | 0 | 0 | 468.9914 | 528.0192
__export__.project_task_3190_39a3eb7e | Need tech assistance to move Odoo instance |  |  | Development | MMH: Help (P83) | Jeff Gross | Levi Barnes | 3 | 0 |  |  | 4 | Complete | Mountain Meadow Herbs | 4328 | 0 | -3 | 0 | 164
__export__.project_task_2641_96a97384 | Create a list of Go-Live tasks for Wildleaf Las Vegas |  |  | Configuration | Wild Leaf: Las Vegas Go-Live (P57) | Jeff Gross | Fahad Hussain Malik | 0 | 0 |  |  |  | Cancelled | Wild Leaf Beverage | 5419 | 0 | 0 | 192 | 430.3181
__export__.project_task_2116_2a14f980 | Deployed tasks Meeting | Sprint 2102 | 2021-01-04 | Configuration | Mid-America: Help (P37) | Levi Barnes | Raheel Aslam | 0.33 | 66 |  |  |  | Complete | Mid-America Gardens, LLC | 6081 | 0.5 | 0.17 | 0.019178 | 2.4236
__export__.project_task_2022_a178d20b | Propertyworx Deployment 2051 | Sprint 2051 | 2020-12-14 | Configuration | PWX: Help (P23) | Levi Barnes | Muzher Siddique | 5.05 | 0 |  |  |  | Complete | EquityTeam | 6418 | 0 | -5.05 | 0.0077037 | 3.9213
__export__.project_task_1803_222bed44 | Project and AV Project List | Sprint 2050 | 2020-12-07 | Development | Continuant: AV Warehouse (P34) | Kaesi Lee | Danish Hassan | 5.42 | 100 |  |  |  | Complete | Continuant | 6773 | 4 | -1.42 | 0 | 95.3307
__export__.project_task_1231_5e9787c9 | Error 403 for Portal Users | Sprint 2042 | 2020-10-12 | Bug Fix | Silverdale: Help (P12) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Silverdale Technology LLC | 8736 | 0 | 0 | 30.6125 | 190.625
__export__.project_task_1175_c7c421dc | Splash Screen for Send Quotation | Sprint 30 | 2020-09-07 | Development | Continuant: eCommerce (P9) | Gadha Continuant |  | 0 | 0 |  |  |  | Complete | Continuant | 9047 | 0 | 0 | 0 | 0
__export__.project_task_940_b9d8e517 | Integrate GfK Etilize Catalog: Pull Tech Data U.S. and Ingram U.S. Product Codes | Sprint 25 | 2020-08-03 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 9891 | 0 | 0 | 55.8119 | 0
__export__.project_task_923_551bcfec | API:My Bids:Postman | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9926 | 1 | 1 | 0 | 0
Postman
__export__.project_task_907_f0877797 | My bids Android-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 2 | 2 | 0.00016651 | 0
Android
__export__.project_task_896_a0f87a5a | Category list Android-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
Android
__export__.project_task_839_0942fda6 | My bids iOS-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 2 | 2 | 0.00018745 | 0
iOS
__export__.project_task_833_6177f1fb | Add to watch list iOS-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_355_1b889e2b | Sponsor Meeting #5 | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 0.00032117 | 0
__export__.project_task_4534_cef3d137 | Revisiting the Project Requirements | Sprint 2133 | 2021-08-09 | Other | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Asfand Yaar | 6 | 60 |  |  |  | Complete | Zuma Sales LLC | 826 | 10 | 4 | 0 | 16.4082
__export__.project_task_4404_1fcdf732 | Split UEDF File that need activation (UEDF Activation File) | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 16.58 | 100 |  | SPLN | 2 | Complete | Cellpoint Corporation | 1138 | 15 | -6.5 | 0 | 133.4236
__export__.project_task_3406_f907c49e | Customer portals | Sprint 2126 | 2021-06-21 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik |  | 0.17 | 1.7 |  |  |  | Cancelled | Zuma Sales LLC | 3506 | 10 | 9.83 | 468.9914 | 329.3589
__export__.project_task_2036_db9f2b96 | Apply Filters to Transmitted Data |  |  | Development | Continuant: Power BI Integration (P30) | Kaesi Lee | Raheel Aslam | 0.33 | 11 |  | Difficulty 2 |  | Complete | Continuant | 6384 | 3 | 2.67 | 0 | 152
__export__.project_task_1890_3a7c515c | Fwd: Projects "tasks" not switching to different project after assignment (#37) | Sprint 2051 | 2020-12-14 | Configuration | PWX: Help (P23) | Levi Barnes | Nick Foy | 0 | 0 |  | Question |  | Complete | EquityTeam | 6582 | 0 | 0 | 0.038098 | 7.8445
__export__.project_task_1630_d95e6121 | Display Proposal Summary and Statement of Work | Sprint 2109 | 2021-02-15 | Development | Continuant: Quotation Management / Automation (P31) | Nick Foy | Muzher Siddique | 4.33 | 100 |  |  |  | Complete | Continuant | 7200 | 3.6667 | -0.66333 | 488 | 590.4811
__export__.project_task_908_60a373f0 | Set batch API Android-Implementation | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00016651 | 0
Android
__export__.project_task_903_ba76953d | Edit profile Android-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00016651 | 0
Android
__export__.project_task_891_5a5112a8 | Select city Android-Implementation | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
Android
__export__.project_task_552_2ef2bcd5 | API:Update Terms and condition | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 10.8272 | 0
__export__.project_task_353_44990b59 | Sponsor Meeting #3 | Sprint 25 | 2020-08-03 | Development | Continuant: eCommerce (P9) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 0.00032117 | 0
__export__.project_task_344_420650a6 | Production Release #1 | Sprint 25 | 2020-08-03 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 97.7145 | 0
__export__.project_task_209_56ac4364 | Webkul Document | Sprint 27 | 2020-08-17 | Development | Cellpoint: Odoo Back-End (P8) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10783 | 0 | 0 | 0 | 0
__export__.project_task_174_a0243bf8 | Tasks Outstanding and Past Due | Sprint 27 | 2020-08-17 | Studio | Heronswood: Events (P3) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Port Gamble Sâ€™Klallam Foundation | 11286 | 0 | 0 | 0 | 0
__export__.project_task_4501_abbe390a | Deploy to Deployment + Production 2132 | Sprint 2133 | 2021-08-09 | Development | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Fahad Hassan | 1.83 | 0 |  |  |  | Complete | Zuma Sales LLC | 872 | 0 | -1.83 | 0.019326 | 11.9229
__export__.project_task_4361_7a841c38 | NMS Bounce Utility (In Operations Tab) | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Danish Hassan | 3.42 | 76 |  | SPLN | 1 | Complete | Cellpoint Corporation | 1230 | 4.5 | 1.08 | 0 | 164.8985
__export__.project_task_2930_2ef96622 | Adding Role/Groups permission on accountability form | Sprint 2114 | 2021-03-29 | Development | PWX: Strategic Planning (P43) | Levi Barnes | Osama Khalid | 21.47 | 100 |  |  | 3 | Complete | EquityTeam | 4565 | 16 | -5.47 | 0 | 225.0768
__export__.project_task_2635_c104bb8f | Daily Breaks/Dinner/Prayers |  |  | Internal Time Tracking | Silverdale Time Tracking (P56) | Muhammad Afzaal |  | 468.42 | 0 |  |  |  | Cancelled | Silverdale Technology LLC | 5429 | 0 | -468.42 | 0.0078713 | 429.0843
__export__.project_task_1885_6ae317eb | Propertyworx Deployment 2050 | Sprint 2050 | 2020-12-07 | Configuration | PWX: Help (P23) | Muzher Siddique | Muzher Siddique | 0.83 | 83 |  |  |  | Complete | EquityTeam | 6584 | 1 | 0.17 | 0 | 1.9098
__export__.project_task_1679_ec41e622 | Development Continuant: AV Warehouse | Sprint 2048 | 2020-11-23 | Configuration | Continuant: AV Warehouse (P34) | Muzher Siddique |  | 0.33 | 66 |  |  |  | Complete | Continuant | 6921 | 0.5 | 0.17 | 0 | 0.24223
__export__.project_task_1664_c02ef44a | Schema for Belmont Integration | Sprint 2049 | 2020-11-30 | Configuration | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Kaleem Khan | 0.5 | 10 |  |  |  | Complete | Cellpoint Corporation | 7059 | 5 | 4.5 | 0 | 104
__export__.project_task_1515_09a31b5c | Test Connection from Power BI to Azure Server |  |  | Configuration | Continuant: Power BI Integration (P30) | Levi Barnes | Muzher Siddique | 0 | 0 |  |  |  | Complete | Continuant | 7680 | 1.5 | 1.5 | 0 | 32.7867
__export__.project_task_1205_95eb5c0f | Front End Fixes | Sprint 30 | 2020-09-07 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 8793 | 0 | 0 | 0 | 52
__export__.project_task_942_5c506571 | Integrate GfK Etilize Catalog: Import Shorter Product Description | Sprint 25 | 2020-08-03 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9790 | 0 | 0 | 0 | 0
__export__.project_task_827_d52925d6 | Location list iOS-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_826_f9317c2d | Seller list iOS-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_606_09b5330c | Test Ingram and Techdata Credentials | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 10031 | 4 | 4 | 0 | 0
__export__.project_task_549_4749478b | API:Bid History | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 4 | 4 | 10.6803 | 0
__export__.project_task_538_72d14c9e | API:Lot view | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 10.6922 | 0
__export__.project_task_4515_2e143b2c | Fields to add, remove and functionality | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Wajahat Ali | 2.42 | 100 |  | SPLN |  | Complete | Cellpoint Corporation | 860 | 2 | -0.42 | 0 | 69.4236
__export__.project_task_4461_5768a0dd | R&D Tax Cloud Calculation on Delivery Address | Sprint 2133 | 2021-08-09 | Research | Zuma: Odoo Implementation Phase 1 (P111) | Fahad Hussain Malik | Raheel Aslam | 1.5 | 18.75 |  |  |  | Complete | Zuma Sales LLC | 967 | 8 | 6.5 | 0 | 35.819
__export__.project_task_4369_ac882264 | NMS Bounce Form View (Import Utility) | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 13.33 | 100 |  | SPLN | 2 | Complete | Cellpoint Corporation | 1205 | 12 | -1.33 | 0 | 155.8046
__export__.project_task_1869_b91e24d9 | Recurring Scheduled Actions |  |  | Configuration | PWX: Help (P23) | Levi Barnes | Levi Barnes | 0.5 | 3.12 |  | 3rd Party App |  | Complete | EquityTeam | 6604 | 16 | 15.5 | 0.25731 | 215.1943
__export__.project_task_1839_50faaffe | User Group for Data Migration Module Access | Sprint 2051 | 2020-12-14 | Development | Continuant: Power BI Integration (P30) | Kaesi Lee | Danish Hassan | 2.77 | 92.33 |  | SPriority |  | Complete | Continuant | 6743 | 3 | 0.23 | 0 | 116
__export__.project_task_1658_fc856d53 | Auto Bids are not in order (Bid history) | Sprint 2048 | 2020-11-23 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Shajahan | 6 | 0 |  |  |  | Complete | Cellpoint Corporation | 7066 | 0 | -6 | 0 | 68.5442
__export__.project_task_1177_04213b2c | Product Details Page: Conditional Hide | Sprint 30 | 2020-09-07 | Development | Continuant: eCommerce (P9) | Gadha Continuant |  | 0 | 0 |  |  |  | Complete | Continuant | 9029 | 0 | 0 | 0 | 0
__export__.project_task_884_e2f027f7 | Auction detail Android-Implementation | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 2 | 2 | 0 | 0
Android
__export__.project_task_818_410dc2c2 | Make an offer iOS-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
iOS
__export__.project_task_602_a2af43d7 | Custom Module Dependencies List | Sprint 25 | 2020-08-03 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 10058 | 0 | 0 | 8 | 0
__export__.project_task_536_1b27acf6 | API:Place a Bid | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 8 | 8 | 10.7036 | 0
__export__.project_task_533_5437231f | API:Product List | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 4 | 4 | 10.7194 | 0
__export__.project_task_532_7d9ed12f | API:Login | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 10.715 | 0
__export__.project_task_337_44062e82 | Carrier: Create test labels | Sprint 24 | 2020-07-27 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 8 | 8 | 73.7145 | 0
__export__.project_task_335_e4e8b7a2 | Carrier: agree service levels to be offered | Sprint 24 | 2020-07-27 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 49.7145 | 0
__export__.project_task_302_33176a79 | Payment: Get Stripe credentials | Sprint 23 | 2020-07-20 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10247 | 0 | 0 | 6.2858 | 0
__export__.project_task_295_04ce3826 | Website: Install Module | Sprint 23 | 2020-07-20 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10248 | 0 | 0 | 6.2858 | 0
__export__.project_task_292_6a965156 | Hosting: Get Hosting Information | Sprint 22 | 2020-07-12 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10250 | 0 | 0 | 6.2856 | 0
__export__.project_task_272_e436a079 | Group Auctions - Marketplace | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10260 | 32 | 32 | 1.2571 | 0
__export__.project_task_223_89282658 | Create and send initial proposal | Sprint 21 | 2020-07-06 | Development | Continuant: eCommerce (P9) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Continuant | 10727 | 0 | 0 | 118.2856 | 0
__export__.project_task_222_c4f06cef | Prepare estimate | Sprint 21 | 2020-07-06 | Development | Continuant: eCommerce (P9) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Continuant | 10727 | 0 | 0 | 118.2858 | 0
__export__.project_task_4388_fb1d01aa | Scan POS Label | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Aleem khan | 7.92 | 99 |  | SPLN |  | Complete | Cellpoint Corporation | 1154 | 8 | 0.08 | 0 | 169.7643
__export__.project_task_4378_25b614d3 | Split UEDF File by SKU | Sprint 2134 | 2021-08-16 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Raheel Aslam | 18.42 | 100 |  | SPLN | 2 | Complete | Cellpoint Corporation | 1175 | 15 | -3.42 | 0 | 175.205
__export__.project_task_1825_4375fd75 | Propertyworx Deployment 2049 | Sprint 2049 | 2020-11-30 | Configuration | PWX: Help (P23) | Muzher Siddique |  | 2 | 100 |  |  |  | Complete | EquityTeam | 6752 | 2 | 0 | 0 | 15.7318
__export__.project_task_1643_2b6bbc33 | Continuant: Deploy AV Tracker Code 2047 | Sprint 2047 | 2020-11-16 | Configuration | Continuant: AV Warehouse (P34) | Muzher Siddique |  | 0.5 | 50 |  |  |  | Complete | Continuant | 7086 | 1 | 0.5 | 0 | 58.1749
__export__.project_task_1628_07cc45a3 | Wrong Winner Updated | Sprint 2047 | 2020-11-16 | Bug Fix | Cellpoint CPBids: Help (P7) | Muhammad Afzaal | Roshan Mecoth | 9.5 | 0 |  | P0 |  | Complete | Cellpoint Corporation | 7206 | 0 | -9.5 | 0 | 81.7249
__export__.project_task_906_8f50dbd6 | Notification list Android-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00016651 | 0
Android
__export__.project_task_597_ec67c3a9 | API:Category List :APPMAVEN | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10070 | 3 | 3 | 0 | 0
Postman
__export__.project_task_303_58c8e363 | Carrier: Get Credentials for FedEx and UPS | Sprint 22 | 2020-07-12 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10247 | 0 | 0 | 6.2856 | 0
__export__.project_task_296_07563dbc | Website: Configure Module | Sprint 23 | 2020-07-20 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10248 | 0 | 0 | 6.2858 | 0
__export__.project_task_290_33ed0d91 | Website: Create Website with Basic Functionality | Sprint 23 | 2020-07-20 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 10250 | 2 | 2 | 27.3097 | 0
__export__.project_task_267_755664e4 | Setup Continuant Project Access For Allison | Sprint 22 | 2020-07-12 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10274 | 0 | 0 | 14.2858 | 0
__export__.project_task_221_025e41b2 | Initial Review of Requirements | Sprint 21 | 2020-07-06 | Development | Continuant: eCommerce (P9) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Continuant | 10727 | 0 | 0 | 118.2856 | 0
__export__.project_task_204_aeb33e0e | Lot Extension | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10783 | 6 | 6 | 98.4796 | 0
__export__.project_task_199_25d4592a | Make an offer for Web | Sprint 22 | 2020-07-12 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10783 | 16 | 16 | 98.5646 | 0
__export__.project_task_4364_0051b8f4 | UEDF File Import Export Utility | Sprint 2133 | 2021-08-09 | Development | Cellpoint: Odoo for Boost Files (P165) | Farman Ahmad Cheema | Danish Hassan | 3.5 | 87.5 |  | SPLN | 1 | Complete | Cellpoint Corporation | 1225 | 4 | 0.5 | 0 | 160.8717
__export__.project_task_1720_7546b653 | activity view: Research Activity Access Rights | Sprint 2050 | 2020-12-07 | Configuration | PWX: Help (P23) | Levi Barnes | Fahad Hassan | 4 | 80 |  |  |  | Complete | EquityTeam | 6874 | 5 | 1 | 0 | 42.5138
__export__.project_task_1580_1c508c43 | Require Avalara Tax Calculation to Send Quotation | Sprint 2048 | 2020-11-23 | Development | Continuant: Quotation Management / Automation (P31) | Kaesi Lee | Raheel Aslam | 3.83 | 99.91 |  |  |  | Complete | Continuant | 7417 | 3.8333 | 0.0033333 | 0 | 152
__export__.project_task_1081_daa32d48 | Product Mapping: GFK to Synnex | Sprint 27 | 2020-08-17 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 9533 | 0 | 0 | 0 | 0
__export__.project_task_939_512e683c | Integrate GfK Etilize Catalog: Include Weight Unit Conversion | Sprint 24 | 2020-07-27 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9891 | 0 | 0 | 0 | 0
__export__.project_task_932_4b615bd8 | Create Clean Continuant Database | Sprint 24 | 2020-07-27 | Configuration | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 9916 | 0 | 0 | 0 | 0
__export__.project_task_921_b5752446 | API:Place a Bid:Postman | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9926 | 1 | 1 | 0 | 0
Postman
__export__.project_task_555_15a897d7 | API:Change Password | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 3 | 3 | 10.8153 | 0
__export__.project_task_274_1ba66ec2 | Group Buyers for Seller - Marketplace | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10260 | 24 | 24 | 1.2003 | 0
__export__.project_task_248_62d59120 | Project Plan - Post 20th July | Sprint 22 | 2020-07-12 | Development | Continuant: eCommerce (P9) | Muhammad Afzaal |  | 0 | 0 |  |  |  | Complete | Continuant | 10421 | 0 | 0 | 46.9476 | 0
__export__.project_task_1692_de752c7a | appraisals scorecard | Sprint 2050 | 2020-12-07 | Development | PWX: Help (P23) | Levi Barnes | Raheel Aslam | 12.75 | 100 |  |  |  | Complete | EquityTeam | 6915 | 12 | -0.75 | 0 | 126.5861
__export__.project_task_882_9bf691b9 | Product list Android-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 2 | 2 | 0 | 0
Android
__export__.project_task_829_7c1de471 | Product status iOS-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_594_e5222bd2 | API:Logout:APPMAVEN | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10070 | 4 | 4 | 0 | 0
Postman
__export__.project_task_340_da290258 | Carrier: Set-up service levels | Sprint 24 | 2020-07-27 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 73.7145 | 0
__export__.project_task_305_5e864ca3 | Website: Release Module | Sprint 23 | 2020-07-20 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10247 | 0 | 0 | 6.2858 | 0
__export__.project_task_289_f216b0dc | eCommerce: Develop a Product Template | Sprint 26 | 2020-08-10 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10250 | 0 | 0 | 144 | 0
__export__.project_task_266_d5a28454 | Setup Microsoft team for Continuent | Sprint 22 | 2020-07-12 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10276 | 0 | 0 | 14.2858 | 0
__export__.project_task_904_94c13af9 | Logout Android-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00016651 | 0
Android
__export__.project_task_814_a1669cd7 | Product list iOS-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 2 | 2 | 0 | 0
iOS
__export__.project_task_603_75589488 | Tax: Avalara: Review Current Configuration | Sprint 24 | 2020-07-27 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 10034 | 0 | 0 | 0 | 0
__export__.project_task_563_606674c9 | API:Get Batch Api | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 4 | 4 | 10.6478 | 0
__export__.project_task_366_b18f1fda | Integrate GfK Etilize Catalog | Sprint 25 | 2020-08-03 | Development | Continuant: eCommerce (P9) | Anusha |  | 4 | 25 |  |  |  | Complete | Continuant | 10204 | 16 | 12 | 40 | 0
__export__.project_task_247_7bc7af72 | List of Questions - Meeting | Sprint 21 | 2020-07-06 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10421 | 0 | 0 | 47.0251 | 0
__export__.project_task_883_3c4708d0 | Forgot password Android-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
Android
__export__.project_task_535_046adb83 | API:Auction detail | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 6 | 6 | 10.7089 | 0
__export__.project_task_301_38897f0a | Carrier: UPS and Fedex - check existing set-up | Sprint 23 | 2020-07-20 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 10247 | 1 | 1 | 27.4711 | 0
__export__.project_task_901_d6350b29 | Add to watch list Android-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00016651 | 0
Android
__export__.project_task_840_c684d457 | Set batch API iOS-Implementation | Sprint 26 | 2020-08-10 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00018745 | 0
iOS
__export__.project_task_351_0470d6ae | Sponsor Meeting #1 | Sprint 23 | 2020-07-20 | Development | Continuant: eCommerce (P9) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 0.00032117 | 0
__export__.project_task_815_3a018001 | Forgot password iOS-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
iOS
__export__.project_task_564_3a9185bb | API:Get List of MarketPlaces | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 10.6436 | 0
__export__.project_task_336_d44c5546 | Carrier: Agree shipping pricing uplifts | Sprint 24 | 2020-07-27 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 49.7145 | 0
__export__.project_task_944_cc3abc54 | List View for Buyers | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Deepak Krishnan |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 9786 | 2 | 2 | 0 | 0
__export__.project_task_910_aae19595 | Get marketplace list Android-Implementation | Sprint 25 | 2020-08-03 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0.00016651 | 0
Android
__export__.project_task_578_42291b10 | Delete Test Seller Accounts | Sprint 23 | 2020-07-20 | Development | Cellpoint CPBids: Help (P7) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Cellpoint Corporation | 10131 | 0 | 0 | 0 | 0
__export__.project_task_299_b1aa1799 | eCommerce: Test Module | Sprint 23 | 2020-07-20 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 10248 | 0 | 0 | 60.2783 | 0
__export__.project_task_895_161f8137 | Location list Android-Implementation | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9943 | 1 | 1 | 0 | 0
Android
__export__.project_task_601_d6256b0f | Test Connection to GfK Catalog | Sprint 24 | 2020-07-27 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 10060 | 0 | 0 | 0 | 0
__export__.project_task_593_91cda87a | API:Location List:APPMAVEN | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10070 | 3 | 3 | 0 | 0
Postman
__export__.project_task_916_971d5b2f | API:Seller List :Postman | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 9927 | 0 | 0 | 0 | 0
Postman
__export__.project_task_590_e380f9d2 | API:Select country:APPMAVEN | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10070 | 3 | 3 | 0 | 0
Postman
__export__.project_task_352_5265587f | Sponsor Meeting #2 | Sprint 24 | 2020-07-27 | Development | Continuant: eCommerce (P9) | Nick Foy |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 0 | 0 | 0.00032117 | 0
__export__.project_task_545_080f0ba7 | API:Seller List | Sprint 23 | 2020-07-20 | Development | Cellpoint: Odoo Back-End (P8) | Roshan Mecoth |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10147 | 2 | 2 | 10.7675 | 0
__export__.project_task_298_ba2eb05b | eCommerce: Install Module | Sprint 23 | 2020-07-20 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 10248 | 0.16667 | 0.16667 | 27.2972 | 0
__export__.project_task_589_175393ad | API:Forgot Password:APPMAVEN | Sprint 24 | 2020-07-27 | Development | Cellpoint: Odoo Back-End (P8) | Apps Maven |  | 0 | 0 |  | API-Odoo |  | Complete | Cellpoint Corporation | 10070 | 4 | 4 | 0 | 0
Postman
__export__.project_task_297_9ac4c2b0 | Website: Test Module | Sprint 23 | 2020-07-20 | Development | Continuant: eCommerce (P9) | Kaesi Lee |  | 0 | 0 |  |  |  | Complete | Continuant | 10248 | 0 | 0 | 6.2858 | 0
__export__.project_task_343_a6b77a32 | eCommerce: Configure Module | Sprint 23 | 2020-07-20 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 2 | 2 | 20.4364 | 0
__export__.project_task_341_40f0d6dd | Carrier: Set-up shipping pricing | Sprint 24 | 2020-07-27 | Development | Continuant: eCommerce (P9) | Anusha |  | 0 | 0 |  |  |  | Complete | Continuant | 10230 | 8 | 8 | 49.7145 | 0